## Page 1
Document Log Report
Contract Status : Active
Project : ZTK : Zawtika
Phase : 1F : Project Development Phase 1F (ZTK)
Contract : MMC25-5001 : ENGINEERING, PROCUREMENT, CONSTRUCTION, AND INSTALLATION OF WELLHEAD PLATFORMS, ASSOCIATED PIPELINES AND BROWNFIELD MODIFICATIONS FOR ZAWTIKA DEVELOPMENT PROJECT PHASE 1F (ZTK : 1F)
Asset Doctype : Engineering Document
Show Version :
Last Updated : 19-Oct-2026 07:48:55
Exported By : Jumpol Sudjitjul 19-Oct-2026 08:01:28
Submittal ID | Document No. | Document Title | Sht.No | Rev. | Creation Profile Type | Asset Doctype | Document Category | Area | Vendor Package Code | Vendor Package Name | Discipline Code | Discipline Name | Doc Type Code | Doc Type Name | Page Received | Status | Document Status Code | Document Status Name | Plan Submit In | Actual Submit In | Submitted By | Distribution Date | Distributed By | Reviewer Plan Finish | Reviewer Actual Finish | Focal Point | Focal Point Plan Finish | Focal Point Actual Finish | Approver | Approver Plan Finish | Approver Actual Finish | Return Status Code | Return Status Name | DC | DC Plan Validation | DC Actual Validation | Actual Submit Out | Page Return | Transmittal Out Date | Transmittal Out No. | Workflow | Open in D2
AO-001715 | INVOICE_Z1F-SSC-26-07-0003-SSC | INVOICE_Z1F-SSC-26-07-0003 (SERVICE WORK) & Z1F-SSC-26-07-0004 (SUPPLY WORK) FOR SO 3200045252 (SSC) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | INV | Invoice | 0 | Latest | IFI | Issued for Information |  | 26-Aug-2026 08:43:32 | 26002z1fdcc@thoresen-jutal.com | 26-Aug-2026 11:31:46 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 26-Aug-2026 13:38:21 | Prin Jitatisil |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-001715 | INVOICE_Z1F-TJE-26-07-0003-ALL | INVOICE_Z1F-TJE-26-07-0003 (SERVICE WORK) & Z1F-TJE-26-07-0004 (SUPPLY WORK) FOR SO 3200045251 (ALL) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | INV | Invoice | 0 | Latest | IFI | Issued for Information |  | 26-Aug-2026 08:44:00 | 26002z1fdcc@thoresen-jutal.com | 26-Aug-2026 11:32:05 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 26-Aug-2026 13:37:28 | Prin Jitatisil |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-001715 | INVOICE_Z1F-TJE-26-07-0003-TJE | INVOICE_Z1F-TJE-26-07-0003 (SERVICE WORK) & Z1F-TJE-26-07-0004 (SUPPLY WORK) FOR SO 3200045251 (TJE) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | INV | Invoice | 0 | Latest | IFI | Issued for Information |  | 26-Aug-2026 08:44:28 | 26002z1fdcc@thoresen-jutal.com | 26-Aug-2026 11:32:20 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 26-Aug-2026 12:51:32 | Prin Jitatisil |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-002304 | INVOICE_ZTK-SSC-26-0005-SSC | INVOICE_ZTK-SSC-26-0005 & SO 3200045252 (SSC) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | INV | Invoice | 0 | Submitted | IFI | Issued for Information |  | 29-Sep-2026 11:59:24 | 26002z1fdcc@thoresen-jutal.com | 29-Sep-2026 14:51:36 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 06-Oct-2026 15:55:46 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 06-Oct-2026 16:07:54 | 06-Oct-2026 09:26:41 | 0 |  |  | For Info | Locate
AO-001413 | INVOICE_ZTK-SSC-26-07-0001-SSC | INVOICE_ZTK-SSC-26-07-0001 & SO 3200045252 (SSC) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | INV | Invoice | 0 | Latest | IFI | Issued for Information |  | 04-Aug-2026 14:44:37 | 26002z1fdcc@thoresen-jutal.com | 04-Aug-2026 14:50:32 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 04-Aug-2026 17:06:15 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 04-Aug-2026 10:27:27 |  | 0 |  |  | For Info | Locate
AO-002304 | INVOICE_ZTK-TJE-26-0005-ALL | INVOICE_ZTK-TJE-26-0005 & SO 3200045251 (ALL) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | INV | Invoice | 0 | Submitted | IFI | Issued for Information |  | 29-Sep-2026 11:59:52 | 26002z1fdcc@thoresen-jutal.com | 29-Sep-2026 14:51:53 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 06-Oct-2026 16:09:06 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 06-Oct-2026 17:19:50 | 06-Oct-2026 10:53:18 | 0 |  |  | For Info | Locate
AO-002304 | INVOICE_ZTK-TJE-26-0005-TJE | INVOICE_ZTK-TJE-26-0005 & SO 3200045251 (TJE) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | INV | Invoice | 0 | Submitted | IFI | Issued for Information |  | 29-Sep-2026 12:00:19 | 26002z1fdcc@thoresen-jutal.com | 29-Sep-2026 14:52:08 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 06-Oct-2026 16:10:20 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 06-Oct-2026 17:20:43 | 06-Oct-2026 10:54:28 | 0 |  |  | For Info | Locate
AO-001412 | INVOICE_ZTK-TJE-26-07-0001-ALL | INVOICE_ZTK-TJE-26-07-0001 & SO 3200045251 (ALL) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | INV | Invoice | 0 | Latest | IFI | Issued for Information |  | 04-Aug-2026 14:45:06 | 26002z1fdcc@thoresen-jutal.com | 04-Aug-2026 14:50:53 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 04-Aug-2026 18:03:43 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 04-Aug-2026 10:28:46 |  | 0 |  |  | For Info | Locate
AO-001411 | INVOICE_ZTK-TJE-26-07-0001-TJE | INVOICE_ZTK-TJE-26-07-0001 & SO 3200045251 (TJE) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | INV | Invoice | 0 | Latest | IFI | Issued for Information |  | 04-Aug-2026 14:45:36 | 26002z1fdcc@thoresen-jutal.com | 04-Aug-2026 14:51:09 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 04-Aug-2026 18:04:45 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 04-Aug-2026 10:29:57 |  | 0 |  |  | For Info | Locate
AO-002315 | INVOICE_ZTK-TJE-CO-0002-01-TJE | INVOICE_ZTK-CO-0002 & SO 3200045444 (TJE) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | INV | Invoice | 0 | Submitted | IFI | Issued for Information |  | 30-Sep-2026 11:27:48 | 26002z1fdcc@thoresen-jutal.com | 30-Sep-2026 16:10:11 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 06-Oct-2026 16:19:05 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 06-Oct-2026 17:18:32 | 06-Oct-2026 10:50:55 | 0 |  |  | For Info | Locate
AO-002499 | MM-ZTK-1A-ZPQ-TEL-LAY-0002-002 | TELECOMMUNICATION RADIO ANTENNA LOCATION LAYOUT |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZPQ |  |  | TEL | Telecommunication | LAY | Layout Drawing | 0 | In Review | IFR | Issued for Review |  | 12-Oct-2026 17:06:05 | wisuda.c@jutal.com | 12-Oct-2026 17:18:17 | Jumpol Sudjitjul | 21-Oct-2026 |  |  | 26-Oct-2026 |  |  | 27-Oct-2026 |  |  |  |  | 28-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000855 | MM-ZTK-1B-WP4-INS-LIS-0003_A | WP4 ESD CAUSE & EFFECT MATRIX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP04 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 22:33:44 | wisuda.c@jutal.com | 22-Jun-2026 13:45:11 | Jumpol Sudjitjul | 29-Jun-2026 |  | Wichai Salee | 01-Jul-2026 | 03-Jul-2026 14:26:37 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 04-Jul-2026 19:07:23 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 03-Jul-2026 | 05-Jul-2026 10:35:19 | 05-Jul-2026 04:00:13 | 0 |  |  | Approver | Locate
AO-001777 | MM-ZTK-1B-WP4-INS-LIS-0003_A | WP4 ESD CAUSE & EFFECT MATRIX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP04 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:20:04 | wisuda.c@jutal.com | 31-Aug-2026 12:50:47 | Jumpol Sudjitjul | 07-Sep-2026 |  | Wichai Salee | 09-Sep-2026 | 09-Sep-2026 15:23:07 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 23:49:38 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 12-Sep-2026 20:38:06 | 12-Sep-2026 13:58:51 | 0 |  |  | Approver | Locate
AO-002272 | MM-ZTK-1B-WP4-INS-LIS-0003_A | WP4 ESD CAUSE & EFFECT MATRIX |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP04 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 25-Sep-2026 18:07:46 | wisuda.c@jutal.com | 26-Sep-2026 16:26:57 | Jumpol Sudjitjul | 02-Oct-2026 |  | Wichai Salee | 06-Oct-2026 | 30-Sep-2026 22:51:44 | Pornlert Wanaphattharaphan | 07-Oct-2026 | 01-Oct-2026 23:37:32 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 02-Oct-2026 11:25:49 | 02-Oct-2026 04:36:33 | 0 |  |  | Approver | Locate
AO-000860 | MM-ZTK-1B-WP4-PRO-ESD-0001 | WP4 ESD LOGIC DIAGRAM |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP04 |  |  | PRO | Process | ESD | Emergency Logic Diagram | 0 | Submitted | IFR | Issued for Review |  | 22-Jun-2026 13:23:13 | wisuda.c@jutal.com | 22-Jun-2026 14:15:17 | Jumpol Sudjitjul | 29-Jun-2026 |  |  | 01-Jul-2026 | 05-Jul-2026 16:58:31 |  | 02-Jul-2026 | 07-Jul-2026 00:49:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 07-Jul-2026 08:17:44 | 07-Jul-2026 01:49:11 | 0 |  |  | Approver | Locate
AO-001441 | MM-ZTK-1B-WP4-PRO-ESD-0001 | WP4 ESD LOGIC DIAGRAM |  | C1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP04 |  |  | PRO | Process | ESD | Emergency Logic Diagram | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 10:06:17 | wisuda.c@jutal.com | 07-Aug-2026 10:19:17 | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 23:43:38 |  | 19-Aug-2026 | 18-Aug-2026 09:10:41 |  | 20-Aug-2026 | 20-Aug-2026 23:41:49 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 10:16:47 | 21-Aug-2026 04:12:44 | 0 |  |  | Approver | Locate
AO-001002 | MM-ZTK-1B-WP4-PRO-LIS-0005_A | SAFETY ANALYSIS FUNCTION EVALUATION (SAFE CHARTS) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP04 |  |  | PRO | Process | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 16:17:04 | wisuda.c@jutal.com | 03-Jul-2026 16:36:06 | Jumpol Sudjitjul | 10-Jul-2026 | 13-Jul-2026 20:41:35 | Chananun Rojanarungruengporn | 14-Jul-2026 | 13-Jul-2026 20:56:45 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 23:39:01 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 10:11:16 | 15-Jul-2026 03:31:51 | 0 |  |  | Approver | Locate
AO-002388 | MM-ZTK-1B-WP4-PRO-LIS-0005_A | SAFETY ANALYSIS FUNCTION EVALUATION (SAFE CHARTS) |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP04 |  |  | PRO | Process | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 06-Oct-2026 08:33:01 | wisuda.c@jutal.com | 06-Oct-2026 08:53:07 | Jumpol Sudjitjul | 14-Oct-2026 |  | Chananun Rojanarungruengporn | 16-Oct-2026 | 08-Oct-2026 07:49:23 | Pornlert Wanaphattharaphan | 19-Oct-2026 | 11-Oct-2026 00:12:00 | APPR | Approved | Jumpol Sudjitjul | 20-Oct-2026 | 11-Oct-2026 09:55:24 | 11-Oct-2026 03:38:47 | 0 |  |  | Approver | Locate
AO-000928 | MM-ZTK-1B-WP7-INS-LIS-0003 | WP7 ESD CAUSE & EFFECT MATRIX |  | A1 | Project Working Copy | Engineering Document | Part B - Engineering Doc | ZWP07 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 18:57:08 | wisuda.c@jutal.com | 27-Jun-2026 19:07:03 | Jumpol Sudjitjul | 06-Jul-2026 |  |  | 08-Jul-2026 | 12-Jul-2026 23:52:19 |  | 09-Jul-2026 | 13-Jul-2026 23:14:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 14-Jul-2026 08:39:49 | 14-Jul-2026 02:25:47 | 0 |  |  | Approver | Locate
AO-001777 | MM-ZTK-1B-WP7-INS-LIS-0003 | WP7 ESD CAUSE & EFFECT MATRIX |  | B1 | Project Working Copy | Engineering Document | Part B - Engineering Doc | ZWP07 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:20:34 | wisuda.c@jutal.com | 31-Aug-2026 12:52:47 | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 23:23:05 |  | 09-Sep-2026 | 09-Sep-2026 15:23:33 |  | 10-Sep-2026 | 11-Sep-2026 23:51:13 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 12-Sep-2026 20:41:36 | 12-Sep-2026 14:00:06 | 0 |  |  | Approver | Locate
AO-002272 | MM-ZTK-1B-WP7-INS-LIS-0003 | WP7 ESD CAUSE & EFFECT MATRIX |  | C1 | Project Working Copy | Engineering Document | Part B - Engineering Doc | ZWP07 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 25-Sep-2026 18:37:46 | wisuda.c@jutal.com | 27-Sep-2026 13:03:31 | Jumpol Sudjitjul | 02-Oct-2026 |  |  | 06-Oct-2026 | 01-Oct-2026 11:36:58 |  | 07-Oct-2026 | 01-Oct-2026 23:36:53 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 02-Oct-2026 11:26:29 | 02-Oct-2026 04:37:45 | 0 |  |  | Approver | Locate
AO-000846 | MM-ZTK-1B-WP7-PRO-ESD-0001 | WP7 ESD LOGIC DIAGRAM |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP07 |  |  | PRO | Process | ESD | Emergency Logic Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 22:42:35 | wisuda.c@jutal.com | 22-Jun-2026 14:15:56 | Jumpol Sudjitjul | 29-Jun-2026 |  |  | 01-Jul-2026 | 05-Jul-2026 17:21:55 |  | 02-Jul-2026 | 07-Jul-2026 00:49:46 | APPR | Approved | Jumpol Sudjitjul | 03-Jul-2026 | 07-Jul-2026 08:20:15 | 07-Jul-2026 01:57:24 | 0 |  |  | Approver | Locate
AO-001441 | MM-ZTK-1B-WP7-PRO-ESD-0001 | WP7 ESD LOGIC DIAGRAM |  | C1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP07 |  |  | PRO | Process | ESD | Emergency Logic Diagram | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 10:06:47 | wisuda.c@jutal.com | 07-Aug-2026 10:19:24 | Jumpol Sudjitjul | 17-Aug-2026 |  |  | 19-Aug-2026 | 12-Aug-2026 08:34:12 |  | 20-Aug-2026 | 20-Aug-2026 23:29:42 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 10:18:58 | 21-Aug-2026 04:15:16 | 0 |  |  | Approver | Locate
AO-002440 | MM-ZTK-1C-WP11-ELE-CAL-0001-A | ELECTRICAL LOAD LIST AND LOAD ANALYSIS - WP11 PLATFORM |  | A1 | Project Working Copy | Engineering Document | Part B - Engineering Doc | ZWP11 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | In Review | IFR | Issued for Review |  | 08-Oct-2026 10:44:33 | wisuda.c@jutal.com | 08-Oct-2026 13:18:47 | Jumpol Sudjitjul | 16-Oct-2026 |  |  | 20-Oct-2026 |  |  | 21-Oct-2026 |  |  |  |  | 22-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-002480 | MM-ZTK-1C-WP11-TEL-LAY-0002 | WP11 TELECOMMUNICATION EQUIPMENT LAYOUT LOWER DECK PLAN |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP11 |  |  | TEL | Telecommunication | LAY | Layout Drawing | 0 | In Review | IFR | Issued for Review |  | 12-Oct-2026 12:07:48 | wisuda.c@jutal.com | 12-Oct-2026 13:38:38 | Jumpol Sudjitjul | 20-Oct-2026 |  |  | 22-Oct-2026 |  |  | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001003 | MM-ZTK-1C-WP7M-PRO-LIS-0005_A | SAFETY ANALYSIS FUNCTION EVALUATION (SAFE CHARTS) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP07 |  |  | PRO | Process | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 16:17:59 | wisuda.c@jutal.com | 03-Jul-2026 16:37:04 | Jumpol Sudjitjul | 10-Jul-2026 | 13-Jul-2026 20:41:52 | Chananun Rojanarungruengporn | 14-Jul-2026 | 13-Jul-2026 20:57:43 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 23:40:28 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 10:12:00 | 15-Jul-2026 03:33:05 | 0 |  |  | Approver | Locate
AO-002389 | MM-ZTK-1C-WP7M-PRO-LIS-0005_A | SAFETY ANALYSIS FUNCTION EVALUATION (SAFE CHARTS) |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP07 |  |  | PRO | Process | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 06-Oct-2026 08:33:33 | wisuda.c@jutal.com | 06-Oct-2026 08:53:25 | Jumpol Sudjitjul | 14-Oct-2026 |  | Chananun Rojanarungruengporn | 16-Oct-2026 | 08-Oct-2026 07:50:01 | Pornlert Wanaphattharaphan | 19-Oct-2026 | 11-Oct-2026 00:12:35 | APPR | Approved | Jumpol Sudjitjul | 20-Oct-2026 | 11-Oct-2026 09:56:05 | 11-Oct-2026 03:40:00 | 0 |  |  | Approver | Locate
AO-002408 | MM-ZTK-1C-WP8-ELE-BLD-0001 | ELECTRICAL POWER & CONTROL SYSTEM BLOCK DIAGRAM - WP8 PLATFORM |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | ELE | Electrical | BLD | Block Diagram | 0 | In Review | IFR | Issued for Review |  | 07-Oct-2026 11:49:54 | wisuda.c@jutal.com | 07-Oct-2026 13:39:37 | Jumpol Sudjitjul | 15-Oct-2026 |  |  | 19-Oct-2026 |  |  | 20-Oct-2026 |  |  |  |  | 21-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-002440 | MM-ZTK-1C-WP8-ELE-CAL-0001 | ELECTRICAL LOAD LIST AND LOAD ANALYSIS - WP8 PLATFORM |  | A1 | Project Working Copy | Engineering Document | Part B - Engineering Doc | ZWP08 |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | In Review | IFR | Issued for Review |  | 08-Oct-2026 10:45:03 | wisuda.c@jutal.com | 08-Oct-2026 13:19:06 | Jumpol Sudjitjul | 16-Oct-2026 |  |  | 20-Oct-2026 |  |  | 21-Oct-2026 |  |  |  |  | 22-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-002408 | MM-ZTK-1C-WP8-ELE-DWG-0001 | ELECTRICAL DRAWING INDEX |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Oct-2026 11:50:31 | wisuda.c@jutal.com | 07-Oct-2026 13:30:47 | Jumpol Sudjitjul | 15-Oct-2026 |  |  | 19-Oct-2026 | 15-Oct-2026 14:41:46 |  | 20-Oct-2026 | 15-Oct-2026 22:26:16 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Oct-2026 | 16-Oct-2026 13:30:41 | 16-Oct-2026 07:15:47 | 0 |  |  | Approver | Locate
AO-002408 | MM-ZTK-1C-WP8-ELE-DWG-0103 | ELECTRICAL CABLE ROUTING PLAN: E & I ROOM - WP8 PLATFORM |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | ELE | Electrical | DWG | General Drawing | 0 | In Review | IFR | Issued for Review |  | 07-Oct-2026 11:51:15 | wisuda.c@jutal.com | 07-Oct-2026 13:31:22 | Jumpol Sudjitjul | 15-Oct-2026 |  |  | 19-Oct-2026 |  |  | 20-Oct-2026 |  |  |  |  | 21-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-002408 | MM-ZTK-1C-WP8-ELE-DWG-0405 | ELECTRICAL EARTHING PLAN - E&I ROOM - WP8 PLATFORM |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | ELE | Electrical | DWG | General Drawing | 0 | In Review | IFR | Issued for Review |  | 07-Oct-2026 11:51:58 | wisuda.c@jutal.com | 07-Oct-2026 13:31:44 | Jumpol Sudjitjul | 15-Oct-2026 |  |  | 19-Oct-2026 |  |  | 20-Oct-2026 |  |  |  |  | 21-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-002408 | MM-ZTK-1C-WP8-ELE-LAY-0001 | E&I ROOM EQUIPMENT LAYOUT-WP8 PLATFORM |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | In Review | IFR | Issued for Review |  | 07-Oct-2026 11:52:34 | wisuda.c@jutal.com | 07-Oct-2026 13:36:03 | Jumpol Sudjitjul | 15-Oct-2026 |  |  | 19-Oct-2026 |  |  | 20-Oct-2026 |  |  |  |  | 21-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-002440 | MM-ZTK-1C-WP8-ELE-LIS-0004_A | ELECTRICAL CABLE SCHEDULE - WP8 PLATFORM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP08 |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | In Review | IFR | Issued for Review |  | 08-Oct-2026 10:45:32 | wisuda.c@jutal.com | 08-Oct-2026 13:21:02 | Jumpol Sudjitjul | 16-Oct-2026 |  | Wichai Salee | 20-Oct-2026 |  | Pornlert Wanaphattharaphan | 21-Oct-2026 |  |  |  |  | 22-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-002408 | MM-ZTK-1C-WP8-ELE-SLD-0001 | OVERALL SINGLE LINE DIAGRAM - WP8 PLATFORM |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | In Review | IFR | Issued for Review |  | 07-Oct-2026 11:53:14 | wisuda.c@jutal.com | 07-Oct-2026 13:34:13 | Jumpol Sudjitjul | 15-Oct-2026 |  |  | 19-Oct-2026 |  |  | 20-Oct-2026 |  |  |  |  | 21-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-002408 | MM-ZTK-1C-WP8-ELE-SLD-0003 | SINGLE LINE DIAGRAM 24 VDC DISTRIBUTION SYSTEM - WP8 PLATFORM |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | In Review | IFR | Issued for Review |  | 07-Oct-2026 11:54:06 | wisuda.c@jutal.com | 07-Oct-2026 13:34:35 | Jumpol Sudjitjul | 15-Oct-2026 |  |  | 19-Oct-2026 |  |  | 20-Oct-2026 |  |  |  |  | 21-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-002408 | MM-ZTK-1C-WP8-ELE-WIR-0004-01 | ELECTRICAL WIRING INTERCONNECTION - DISTRIBUTION BOARD FOR SCS/FGS & TELECOM - WP8 PLATFORM SHEET 1 OF 2 |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | In Review | IFR | Issued for Review |  | 07-Oct-2026 11:54:46 | wisuda.c@jutal.com | 07-Oct-2026 13:37:53 | Jumpol Sudjitjul | 15-Oct-2026 |  |  | 19-Oct-2026 |  |  | 20-Oct-2026 |  |  |  |  | 21-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001853 | MM-ZTK-1C-WP8-INS-BLD-0004_A | WP8 INSTRUMENT CABLE BLOCK DIAGRAM (ESD/FGS) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | BLD | Block Diagram | 0 | Submitted | IFR | Issued for Review |  | 03-Sep-2026 18:09:11 | wisuda.c@jutal.com | 04-Sep-2026 11:37:00 | Jumpol Sudjitjul | 11-Sep-2026 |  | Wichai Salee | 15-Sep-2026 | 10-Sep-2026 16:43:06 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 13-Sep-2026 17:05:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 22:46:10 | 13-Sep-2026 16:08:18 | 0 |  |  | Approver | Locate
AO-002244 | MM-ZTK-1C-WP8-INS-BLD-0004_A | WP8 INSTRUMENT CABLE BLOCK DIAGRAM (ESD/FGS) |  | X | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | BLD | Block Diagram | 0 | Submitted | VOID | Withdrawn or Superseded |  | 24-Sep-2026 10:49:16 | wisuda.c@jutal.com | 24-Sep-2026 13:57:52 | Jumpol Sudjitjul |  |  | Wichai Salee |  | 25-Sep-2026 12:11:36 | Pornlert Wanaphattharaphan |  | 26-Sep-2026 05:56:16 | REC | Received | Jumpol Sudjitjul |  | 26-Sep-2026 13:28:14 | 26-Sep-2026 06:57:35 | 0 |  |  | For Info | Locate
AO-002269 | MM-ZTK-1C-WP8-INS-BLD-0004-03 | WP8 INSTRUMENT CABLE BLOCK DIAGRAM - (ESD/FGS) |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | BLD | Block Diagram | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 18:08:13 | wisuda.c@jutal.com | 26-Sep-2026 16:28:18 | Jumpol Sudjitjul | 02-Oct-2026 |  |  | 06-Oct-2026 | 01-Oct-2026 11:34:42 |  | 07-Oct-2026 | 01-Oct-2026 23:38:30 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Oct-2026 | 02-Oct-2026 11:27:05 | 02-Oct-2026 04:38:50 | 0 |  |  | Approver | Locate
AO-001853 | MM-ZTK-1C-WP8-INS-DWG-0004_A | WP8 INSTRUMENT HOOK-UP DRAWINGS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Sep-2026 18:09:37 | wisuda.c@jutal.com | 04-Sep-2026 08:15:31 | Jumpol Sudjitjul | 11-Sep-2026 |  | Wichai Salee | 15-Sep-2026 | 10-Sep-2026 16:38:01 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 13-Sep-2026 17:03:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 22:46:50 | 13-Sep-2026 16:09:35 | 0 |  |  | Approver | Locate
AO-002244 | MM-ZTK-1C-WP8-INS-DWG-0004_A | WP8 INSTRUMENT HOOK-UP DRAWINGS |  | X | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | VOID | Withdrawn or Superseded |  | 24-Sep-2026 10:49:45 | wisuda.c@jutal.com | 24-Sep-2026 13:56:56 | Jumpol Sudjitjul |  |  | Wichai Salee |  | 25-Sep-2026 12:11:20 | Pornlert Wanaphattharaphan |  | 26-Sep-2026 05:56:34 | REC | Received | Jumpol Sudjitjul |  | 26-Sep-2026 13:28:48 | 26-Sep-2026 06:58:46 | 0 |  |  | For Info | Locate
AO-002269 | MM-ZTK-1C-WP8-INS-DWG-0004-02 | INDEX SHEET |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 18:08:39 | wisuda.c@jutal.com | 26-Sep-2026 16:24:28 | Jumpol Sudjitjul | 02-Oct-2026 |  |  | 06-Oct-2026 | 30-Sep-2026 23:06:56 |  | 07-Oct-2026 | 01-Oct-2026 23:39:03 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Oct-2026 | 02-Oct-2026 11:28:26 | 02-Oct-2026 04:39:54 | 0 |  |  | Approver | Locate
AO-002269 | MM-ZTK-1C-WP8-INS-DWG-0004-40 | ACTUATED BALL VALVE WITH TWO SOLENOID VALVES ON/OFF VALVE |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 18:09:04 | wisuda.c@jutal.com | 26-Sep-2026 16:24:43 | Jumpol Sudjitjul | 02-Oct-2026 |  |  | 06-Oct-2026 | 30-Sep-2026 23:06:44 |  | 07-Oct-2026 | 01-Oct-2026 23:40:31 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Oct-2026 | 02-Oct-2026 11:29:05 | 02-Oct-2026 04:41:04 | 0 |  |  | Approver | Locate
AO-001853 | MM-ZTK-1C-WP8-INS-LAY-0001_A | WP8 INSTRUMENT LOCATION PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Sep-2026 18:10:05 | wisuda.c@jutal.com | 04-Sep-2026 08:12:32 | Jumpol Sudjitjul | 11-Sep-2026 |  | Wichai Salee | 15-Sep-2026 | 10-Sep-2026 15:05:27 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 13-Sep-2026 12:02:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 22:59:17 | 13-Sep-2026 16:36:21 | 0 |  |  | Approver | Locate
AO-002244 | MM-ZTK-1C-WP8-INS-LAY-0001_A | WP8 INSTRUMENT LOCATION PLAN |  | X | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Latest | VOID | Withdrawn or Superseded |  | 24-Sep-2026 10:50:12 | wisuda.c@jutal.com | 24-Sep-2026 13:49:26 | Jumpol Sudjitjul |  |  | Wichai Salee |  | 25-Sep-2026 12:09:06 | Pornlert Wanaphattharaphan |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-002269 | MM-ZTK-1C-WP8-INS-LAY-0001-01 | WP8 INSTRUMENT LOCATION PLAN LAYOUT INDEX |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 18:09:31 | wisuda.c@jutal.com | 26-Sep-2026 11:40:14 | Jumpol Sudjitjul | 02-Oct-2026 |  |  | 06-Oct-2026 | 30-Sep-2026 08:32:54 |  | 07-Oct-2026 | 01-Oct-2026 23:39:58 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Oct-2026 | 02-Oct-2026 11:29:54 | 02-Oct-2026 05:21:58 | 0 |  |  | Approver | Locate
AO-002269 | MM-ZTK-1C-WP8-INS-LAY-0001-05 | WP8 INSTRUMENT LOCATION PLAN FOR SUMP DECK |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 18:09:56 | wisuda.c@jutal.com | 26-Sep-2026 11:40:14 | Jumpol Sudjitjul | 02-Oct-2026 |  |  | 06-Oct-2026 | 30-Sep-2026 08:41:29 |  | 07-Oct-2026 | 01-Oct-2026 23:41:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Oct-2026 | 02-Oct-2026 11:31:37 | 02-Oct-2026 05:23:13 | 0 |  |  | Approver | Locate
AO-002269 | MM-ZTK-1C-WP8-INS-LAY-0001-07 | WP8 INSTRUMENT LOCATION PLAN INSTRUMENT DETAILS |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 18:10:23 | wisuda.c@jutal.com | 26-Sep-2026 11:40:12 | Jumpol Sudjitjul | 02-Oct-2026 |  |  | 06-Oct-2026 | 30-Sep-2026 08:25:13 |  | 07-Oct-2026 | 01-Oct-2026 23:42:31 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Oct-2026 | 02-Oct-2026 11:37:16 | 02-Oct-2026 05:24:21 | 0 |  |  | Approver | Locate
AO-001853 | MM-ZTK-1C-WP8-INS-LAY-0006_A | WP8 INSTRUMENT MCT LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Sep-2026 18:10:32 | wisuda.c@jutal.com | 04-Sep-2026 08:12:53 | Jumpol Sudjitjul | 11-Sep-2026 |  | Wichai Salee | 15-Sep-2026 | 10-Sep-2026 15:06:06 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 23:31:32 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 17-Sep-2026 | 12-Sep-2026 23:37:51 | 12-Sep-2026 17:15:10 | 0 |  |  | Approver | Locate
AO-002244 | MM-ZTK-1C-WP8-INS-LAY-0006_A | WP8 INSTRUMENT MCT LAYOUT |  | X | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | VOID | Withdrawn or Superseded |  | 24-Sep-2026 10:50:41 | wisuda.c@jutal.com | 24-Sep-2026 13:49:53 | Jumpol Sudjitjul |  |  | Wichai Salee |  | 25-Sep-2026 12:09:38 | Pornlert Wanaphattharaphan |  | 26-Sep-2026 05:57:24 | REC | Received | Jumpol Sudjitjul |  | 26-Sep-2026 13:30:16 | 26-Sep-2026 06:59:58 | 0 |  |  | For Info | Locate
AO-002269 | MM-ZTK-1C-WP8-INS-LAY-0006-01 | WP8 INSTRUMENT MCT LAYOUT INDEX |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 18:10:48 | wisuda.c@jutal.com | 26-Sep-2026 11:40:14 | Jumpol Sudjitjul | 02-Oct-2026 |  |  | 06-Oct-2026 | 01-Oct-2026 11:33:22 |  | 07-Oct-2026 | 01-Oct-2026 23:43:32 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Oct-2026 | 02-Oct-2026 11:37:52 | 02-Oct-2026 05:25:23 | 0 |  |  | Approver | Locate
AO-002269 | MM-ZTK-1C-WP8-INS-LAY-0006-03 | WP8 INSTRUMENT MCT LAYOUT MCT-I-001 |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 18:11:14 | wisuda.c@jutal.com | 26-Sep-2026 11:40:12 | Jumpol Sudjitjul | 02-Oct-2026 |  |  | 06-Oct-2026 | 30-Sep-2026 08:26:56 |  | 07-Oct-2026 | 01-Oct-2026 23:29:40 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Oct-2026 | 02-Oct-2026 11:40:43 | 02-Oct-2026 05:26:27 | 0 |  |  | Approver | Locate
AO-002552 | MM-ZTK-1C-WP8-INS-LAY-0006-03-DE | WP8 INSTRUMENT MCT LAYOUT MCT-I-001 (DEMOLITION) SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | In Review | IFR | Issued for Review |  | 16-Oct-2026 17:34:52 | wisuda.c@jutal.com | 18-Oct-2026 16:38:15 | Jumpol Sudjitjul | 26-Oct-2026 |  | Wichai Salee | 28-Oct-2026 |  | Pornlert Wanaphattharaphan | 29-Oct-2026 |  |  |  |  | 30-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001853 | MM-ZTK-1C-WP8-INS-LAY-0008_A | WP8 INSTRUMENT MCT LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Sep-2026 18:11:00 | wisuda.c@jutal.com | 04-Sep-2026 08:13:08 | Jumpol Sudjitjul | 11-Sep-2026 |  | Wichai Salee | 15-Sep-2026 | 10-Sep-2026 16:22:12 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 13-Sep-2026 12:23:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 22:47:17 | 13-Sep-2026 16:10:49 | 0 |  |  | Approver | Locate
AO-002244 | MM-ZTK-1C-WP8-INS-LAY-0008_A | WP8 INSTRUMENT MCT LAYOUT |  | X | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | VOID | Withdrawn or Superseded |  | 24-Sep-2026 10:51:19 | wisuda.c@jutal.com | 24-Sep-2026 13:50:07 | Jumpol Sudjitjul |  |  | Wichai Salee |  | 25-Sep-2026 12:10:44 | Pornlert Wanaphattharaphan |  | 26-Sep-2026 05:57:51 | REC | Received | Jumpol Sudjitjul |  | 26-Sep-2026 13:30:48 | 26-Sep-2026 07:01:14 | 0 |  |  | For Info | Locate
AO-002269 | MM-ZTK-1C-WP8-INS-LAY-0008-01 | WP8 INSTRUMENT CABLE ROUTING PLAN INDEX |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 18:11:39 | wisuda.c@jutal.com | 26-Sep-2026 11:40:13 | Jumpol Sudjitjul | 02-Oct-2026 |  |  | 06-Oct-2026 | 30-Sep-2026 08:31:06 |  | 07-Oct-2026 | 01-Oct-2026 23:27:35 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Oct-2026 | 02-Oct-2026 11:42:24 | 02-Oct-2026 05:27:30 | 0 |  |  | Approver | Locate
AO-002269 | MM-ZTK-1C-WP8-INS-LAY-0008-06 | WP8 INSTRUMENT CABLE ROUTING PLAN - LOWER DECK (2/3) |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 18:12:05 | wisuda.c@jutal.com | 26-Sep-2026 11:40:13 | Jumpol Sudjitjul | 02-Oct-2026 |  |  | 06-Oct-2026 | 30-Sep-2026 08:29:14 |  | 07-Oct-2026 | 01-Oct-2026 23:27:08 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Oct-2026 | 02-Oct-2026 11:43:03 | 02-Oct-2026 05:28:35 | 0 |  |  | Approver | Locate
AO-002269 | MM-ZTK-1C-WP8-INS-LAY-0008-08 | WP8 INSTRUMENT CABLE ROUTING PLAN - SUMP DECK |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 18:12:31 | wisuda.c@jutal.com | 26-Sep-2026 11:40:18 | Jumpol Sudjitjul | 02-Oct-2026 |  |  | 06-Oct-2026 | 01-Oct-2026 11:33:40 |  | 07-Oct-2026 | 01-Oct-2026 23:26:39 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Oct-2026 | 02-Oct-2026 11:43:39 | 02-Oct-2026 05:29:49 | 0 |  |  | Approver | Locate
AO-002269 | MM-ZTK-1C-WP8-INS-LAY-0008-09 | WP8 INSTRUMENT CABLE ROUTING PLAN - E&I ROOM |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 18:12:56 | wisuda.c@jutal.com | 26-Sep-2026 11:40:17 | Jumpol Sudjitjul | 02-Oct-2026 |  |  | 06-Oct-2026 | 01-Oct-2026 11:33:04 |  | 07-Oct-2026 | 01-Oct-2026 23:25:22 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 02-Oct-2026 11:45:18 | 02-Oct-2026 05:30:56 | 0 |  |  | Approver | Locate
AO-001670 | MM-ZTK-1C-WP8-INS-LIS-0001_A | WP8 INSTRUMENT INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 09:38:31 | wisuda.c@jutal.com | 25-Aug-2026 08:31:55 | Jumpol Sudjitjul | 01-Sep-2026 |  | Wichai Salee | 03-Sep-2026 | 02-Sep-2026 10:30:49 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:09:28 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 11:13:59 | 07-Sep-2026 04:44:40 | 0 |  |  | Approver | Locate
AO-002346 | MM-ZTK-1C-WP8-INS-LIS-0001_A | WP8 INSTRUMENT INDEX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 02-Oct-2026 18:28:39 | wisuda.c@jutal.com | 03-Oct-2026 08:28:43 | Jumpol Sudjitjul | 09-Oct-2026 |  | Wichai Salee | 14-Oct-2026 | 14-Oct-2026 14:38:32 | Pornlert Wanaphattharaphan | 15-Oct-2026 | 15-Oct-2026 22:54:47 | APPR | Approved | Jumpol Sudjitjul | 16-Oct-2026 | 16-Oct-2026 13:41:17 | 16-Oct-2026 07:17:02 | 0 |  |  | Approver | Locate
AO-001718 | MM-ZTK-1C-WP8-INS-LIS-0002_A | WP8 INSTRUMENT I/O LIST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 26-Aug-2026 11:28:05 | wisuda.c@jutal.com | 26-Aug-2026 13:21:24 | Jumpol Sudjitjul | 02-Sep-2026 |  | Wichai Salee | 04-Sep-2026 | 08-Sep-2026 10:09:37 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 08-Sep-2026 23:04:01 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Sep-2026 | 09-Sep-2026 11:13:09 | 09-Sep-2026 05:38:08 | 0 |  |  | Approver | Locate
AO-002345 | MM-ZTK-1C-WP8-INS-LIS-0002_A | WP8 INSTRUMENT I/O LIST |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 02-Oct-2026 17:55:04 | wisuda.c@jutal.com | 02-Oct-2026 18:04:49 | Jumpol Sudjitjul | 12-Oct-2026 |  | Wichai Salee | 15-Oct-2026 | 14-Oct-2026 14:52:45 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 15-Oct-2026 23:06:02 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 16-Oct-2026 13:48:20 | 16-Oct-2026 07:30:31 | 0 |  |  | Approver | Locate
AO-000929 | MM-ZTK-1C-WP8-INS-LIS-0003 | WP8 ESD CAUSE & EFFECT DIAGRAMS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP08 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 18:58:26 | wisuda.c@jutal.com | 27-Jun-2026 19:07:18 | Jumpol Sudjitjul | 06-Jul-2026 |  | Wichai Salee | 08-Jul-2026 | 13-Jul-2026 00:03:06 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 13-Jul-2026 23:15:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 14-Jul-2026 08:41:15 | 14-Jul-2026 02:27:08 | 0 |  |  | Approver | Locate
AO-001777 | MM-ZTK-1C-WP8-INS-LIS-0003 | WP8 ESD CAUSE & EFFECT DIAGRAMS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP08 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:21:03 | wisuda.c@jutal.com | 31-Aug-2026 12:53:05 | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 23:23:40 | Wichai Salee | 09-Sep-2026 | 09-Sep-2026 15:23:47 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 23:52:00 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 12-Sep-2026 20:44:13 | 12-Sep-2026 14:01:20 | 0 |  |  | Approver | Locate
AO-002272 | MM-ZTK-1C-WP8-INS-LIS-0003 | WP8 ESD CAUSE & EFFECT DIAGRAMS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP08 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 25-Sep-2026 18:38:13 | wisuda.c@jutal.com | 27-Sep-2026 13:03:49 | Jumpol Sudjitjul | 02-Oct-2026 |  | Wichai Salee | 06-Oct-2026 | 01-Oct-2026 11:37:56 | Pornlert Wanaphattharaphan | 07-Oct-2026 | 01-Oct-2026 23:24:38 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 02-Oct-2026 11:47:36 | 02-Oct-2026 05:32:14 | 0 |  |  | Approver | Locate
AO-001670 | MM-ZTK-1C-WP8-INS-LIS-0004_A | WP8 INSTRUMENT CABLE SCHEDULE |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 09:39:08 | wisuda.c@jutal.com | 25-Aug-2026 08:32:14 | Jumpol Sudjitjul | 01-Sep-2026 |  | Wichai Salee | 03-Sep-2026 | 02-Sep-2026 10:31:07 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:09:58 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 11:30:18 | 07-Sep-2026 04:45:47 | 0 |  |  | Approver | Locate
AO-002345 | MM-ZTK-1C-WP8-INS-LIS-0004_A | WP8 INSTRUMENT CABLE SCHEDULE |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 02-Oct-2026 17:55:30 | wisuda.c@jutal.com | 02-Oct-2026 18:05:01 | Jumpol Sudjitjul | 12-Oct-2026 |  | Wichai Salee | 15-Oct-2026 | 14-Oct-2026 14:53:45 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 15-Oct-2026 23:06:28 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 16-Oct-2026 13:52:30 | 16-Oct-2026 07:31:49 | 0 |  |  | Approver | Locate
AO-001670 | MM-ZTK-1C-WP8-INS-LIS-0005_A | WP8 INSTRUMENT TUBE SCHEDULE |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 09:39:43 | wisuda.c@jutal.com | 25-Aug-2026 08:32:35 | Jumpol Sudjitjul | 01-Sep-2026 |  | Wichai Salee | 03-Sep-2026 | 02-Sep-2026 10:31:20 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:10:17 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 11:31:05 | 07-Sep-2026 04:46:51 | 0 |  |  | Approver | Locate
AO-002345 | MM-ZTK-1C-WP8-INS-LIS-0005_A | WP8 INSTRUMENT TUBE SCHEDULE |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 02-Oct-2026 17:55:55 | wisuda.c@jutal.com | 02-Oct-2026 18:05:15 | Jumpol Sudjitjul | 12-Oct-2026 |  | Wichai Salee | 15-Oct-2026 | 14-Oct-2026 14:55:19 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 15-Oct-2026 23:07:03 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 16-Oct-2026 13:56:02 | 16-Oct-2026 07:32:59 | 0 |  |  | Approver | Locate
AO-001853 | MM-ZTK-1C-WP8-INS-WIR-0001_A | WP8 INSTRUMENT WIRING DIAGRAMS (PCS & SIS/FGS) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 03-Sep-2026 18:11:29 | wisuda.c@jutal.com | 04-Sep-2026 08:14:18 | Jumpol Sudjitjul | 11-Sep-2026 |  | Wichai Salee | 15-Sep-2026 | 10-Sep-2026 16:25:11 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 13-Sep-2026 12:28:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 23:00:06 | 13-Sep-2026 16:37:39 | 0 |  |  | Approver | Locate
AO-002244 | MM-ZTK-1C-WP8-INS-WIR-0001_A | WP8 INSTRUMENT WIRING DIAGRAMS (PCS & SIS/FGS) |  | X | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | VOID | Withdrawn or Superseded |  | 24-Sep-2026 10:51:48 | wisuda.c@jutal.com | 24-Sep-2026 13:54:49 | Jumpol Sudjitjul |  |  | Wichai Salee |  | 25-Sep-2026 12:11:02 | Pornlert Wanaphattharaphan |  | 26-Sep-2026 05:56:50 | REC | Received | Jumpol Sudjitjul |  | 26-Sep-2026 13:31:32 | 26-Sep-2026 07:02:24 | 0 |  |  | For Info | Locate
AO-002269 | MM-ZTK-1C-WP8-INS-WIR-0001-02 | INDEX SHEET |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 18:13:22 | wisuda.c@jutal.com | 26-Sep-2026 16:23:01 | Jumpol Sudjitjul | 02-Oct-2026 |  |  | 06-Oct-2026 | 30-Sep-2026 22:42:56 |  | 07-Oct-2026 | 01-Oct-2026 23:24:02 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Oct-2026 | 02-Oct-2026 11:49:02 | 02-Oct-2026 05:33:19 | 0 |  |  | Approver | Locate
AO-002269 | MM-ZTK-1C-WP8-INS-WIR-0001-20 | SIS/FGS-WP08-001 - PLC CABINET |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 18:13:47 | wisuda.c@jutal.com | 26-Sep-2026 16:23:21 | Jumpol Sudjitjul | 02-Oct-2026 |  |  | 06-Oct-2026 | 30-Sep-2026 22:41:40 |  | 07-Oct-2026 | 01-Oct-2026 23:23:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Oct-2026 | 02-Oct-2026 11:51:54 | 02-Oct-2026 05:35:37 | 0 |  |  | Approver | Locate
AO-002269 | MM-ZTK-1C-WP8-INS-WIR-0001-21 | SIS/FGS-WP08-001 - PLC CABINET |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 18:14:12 | wisuda.c@jutal.com | 26-Sep-2026 16:23:37 | Jumpol Sudjitjul | 02-Oct-2026 |  |  | 06-Oct-2026 | 30-Sep-2026 22:42:43 |  | 07-Oct-2026 | 01-Oct-2026 23:22:45 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 02-Oct-2026 11:51:04 | 02-Oct-2026 05:34:25 | 0 |  |  | Approver | Locate
AO-002269 | MM-ZTK-1C-WP8-INS-WIR-0001-24 | SBN-WP08-015 - INTERFACE JUNCTION BOX |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 16:10:40 | wisuda.c@jutal.com | 25-Sep-2026 17:18:18 | Jumpol Sudjitjul | 05-Oct-2026 |  |  | 07-Oct-2026 | 01-Oct-2026 11:48:03 |  | 08-Oct-2026 | 01-Oct-2026 23:22:03 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 09-Oct-2026 | 02-Oct-2026 11:53:34 | 02-Oct-2026 05:39:07 | 0 |  |  | Approver | Locate
AO-001853 | MM-ZTK-1C-WP8-INS-WIR-0002 | WP8 INSTRUMENT LOOP DIAGRAM |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 03-Sep-2026 18:11:56 | wisuda.c@jutal.com | 04-Sep-2026 08:14:40 | Jumpol Sudjitjul | 11-Sep-2026 |  |  | 15-Sep-2026 | 10-Sep-2026 16:27:53 |  | 16-Sep-2026 | 13-Sep-2026 17:00:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 23:00:11 | 13-Sep-2026 16:38:52 | 0 |  |  | Approver | Locate
AO-000846 | MM-ZTK-1C-WP8-PRO-ESD-0001 | WP8 ESD LOGIC DIAGRAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | PRO | Process | ESD | Emergency Logic Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 22:42:59 | wisuda.c@jutal.com | 22-Jun-2026 14:16:13 | Jumpol Sudjitjul | 29-Jun-2026 |  | Chananun Rojanarungruengporn | 01-Jul-2026 | 05-Jul-2026 17:17:28 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 07-Jul-2026 00:49:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 07-Jul-2026 08:22:59 | 07-Jul-2026 02:01:04 | 0 |  |  | Approver | Locate
AO-001441 | MM-ZTK-1C-WP8-PRO-ESD-0001 | WP8 ESD LOGIC DIAGRAM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | PRO | Process | ESD | Emergency Logic Diagram | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 10:07:20 | wisuda.c@jutal.com | 07-Aug-2026 10:19:13 | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 23:58:21 | Chananun Rojanarungruengporn | 19-Aug-2026 | 18-Aug-2026 09:11:38 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:42:21 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 10:20:58 | 21-Aug-2026 04:17:47 | 0 |  |  | Approver | Locate
AO-001383 | MM-ZTK-1C-WP8-PRO-LIS-0005_A | SAFETY ANALYSIS FUNCTION EVALUATION (SAFE CHARTS) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | PRO | Process | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 11:00:46 | wisuda.c@jutal.com | 03-Aug-2026 14:18:30 | Jumpol Sudjitjul | 10-Aug-2026 | 09-Aug-2026 23:59:43 | Chananun Rojanarungruengporn | 13-Aug-2026 | 17-Aug-2026 12:22:53 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 20-Aug-2026 22:54:53 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 21-Aug-2026 10:21:43 | 21-Aug-2026 03:58:12 | 0 |  |  | Approver | Locate
AO-002390 | MM-ZTK-1C-WP8-PRO-LIS-0005_A | SAFETY ANALYSIS FUNCTION EVALUATION (SAFE CHARTS) |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | PRO | Process | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 06-Oct-2026 08:34:10 | wisuda.c@jutal.com | 06-Oct-2026 08:53:45 | Jumpol Sudjitjul | 14-Oct-2026 |  | Chananun Rojanarungruengporn | 16-Oct-2026 | 08-Oct-2026 07:50:34 | Pornlert Wanaphattharaphan | 19-Oct-2026 | 11-Oct-2026 00:12:58 | APPR | Approved | Jumpol Sudjitjul | 20-Oct-2026 | 11-Oct-2026 09:56:40 | 11-Oct-2026 03:41:12 | 0 |  |  | Approver | Locate
AO-000872 | MM-ZTK-1C-WP8-PRO-PFD-0001 | PROCESS FLOW DIAGRAM WELLHEAD PLATFORM |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | PRO | Process | PFD | Process Flow Diagram | 0 | Submitted | IFR | Issued for Review |  | 23-Jun-2026 11:32:40 | wisuda.c@jutal.com | 23-Jun-2026 12:48:14 | Jumpol Sudjitjul | 30-Jun-2026 |  |  | 02-Jul-2026 | 01-Jul-2026 22:55:47 |  | 03-Jul-2026 | 03-Jul-2026 00:49:51 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 06-Jul-2026 | 03-Jul-2026 11:07:16 | 03-Jul-2026 04:54:01 | 0 |  |  | Approver | Locate
AO-001790 | MM-ZTK-1C-WP8-PRO-PFD-0001 | PROCESS FLOW DIAGRAM WELLHEAD PLATFORM |  | C1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | PRO | Process | PFD | Process Flow Diagram | 0 | Submitted | AFC | Approved for Construction |  | 31-Aug-2026 08:43:02 | wisuda.c@jutal.com | 31-Aug-2026 12:58:19 | Jumpol Sudjitjul | 07-Sep-2026 |  |  | 09-Sep-2026 | 01-Sep-2026 08:13:05 |  | 10-Sep-2026 | 07-Sep-2026 00:10:40 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 07-Sep-2026 11:32:29 | 07-Sep-2026 05:15:13 | 0 |  |  | Approver | Locate
AO-000872 | MM-ZTK-1C-WP8-PRO-PID-0014 | PIPING & INSTRUMENTATION DIAGRAM HORIZONTAL PIG LAUNCHER & EXPORT LINE |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 23-Jun-2026 11:33:07 | wisuda.c@jutal.com | 23-Jun-2026 12:39:04 | Jumpol Sudjitjul | 30-Jun-2026 |  |  | 02-Jul-2026 | 05-Jul-2026 17:15:33 |  | 03-Jul-2026 | 07-Jul-2026 00:52:39 | APPR | Approved | Jumpol Sudjitjul | 06-Jul-2026 | 07-Jul-2026 08:28:07 | 07-Jul-2026 02:03:24 | 0 |  |  | Approver | Locate
AO-001757 | MM-ZTK-1C-WP8-PRO-PID-0014 | PIPING & INSTRUMENTATION DIAGRAM HORIZONTAL PIG LAUNCHER & EXPORT LINE |  | C1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 16:51:27 | wisuda.c@jutal.com | 29-Aug-2026 13:39:00 | Jumpol Sudjitjul | 04-Sep-2026 | 04-Sep-2026 15:24:04 |  | 08-Sep-2026 | 08-Sep-2026 09:53:07 |  | 09-Sep-2026 | 10-Sep-2026 22:47:21 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 11-Sep-2026 08:17:02 | 11-Sep-2026 02:00:37 | 0 |  |  | Approver | Locate
AO-000872 | MM-ZTK-1C-WP8-PRO-PID-0017 | PIPING & INSTRUMENTATION DIAGRAM PIG RECEIVER |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 23-Jun-2026 11:33:38 | wisuda.c@jutal.com | 23-Jun-2026 12:39:35 | Jumpol Sudjitjul | 30-Jun-2026 |  |  | 02-Jul-2026 | 05-Jul-2026 17:14:20 |  | 03-Jul-2026 | 07-Jul-2026 00:51:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Jul-2026 | 07-Jul-2026 08:29:34 | 07-Jul-2026 02:04:58 | 0 |  |  | Approver | Locate
AO-001747 | MM-ZTK-1C-WP8-PRO-PID-0017 | PIPING & INSTRUMENTATION DIAGRAM PIG RECEIVER |  | C1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 10:32:16 | wisuda.c@jutal.com | 28-Aug-2026 14:04:48 | Jumpol Sudjitjul | 04-Sep-2026 |  |  | 08-Sep-2026 | 03-Sep-2026 08:08:34 |  | 09-Sep-2026 | 07-Sep-2026 00:11:05 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 11:34:51 | 07-Sep-2026 04:47:57 | 0 |  |  | Approver | Locate
AO-002479 | MM-ZTK-1C-WP8-TEL-LAY-0002 | WP8 TELECOMMUNICATION EQUIPMENT LAYOUT LOWER DECK PLAN |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | TEL | Telecommunication | LAY | Layout Drawing | 0 | In Review | IFR | Issued for Review |  | 12-Oct-2026 12:08:15 | wisuda.c@jutal.com | 12-Oct-2026 13:39:02 | Jumpol Sudjitjul | 20-Oct-2026 |  |  | 22-Oct-2026 |  |  | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-002440 | MM-ZTK-1C-WPX-ELE-CAL-0001-A | ELECTRICAL EQUIPMENT SIZING AND CALCULATION FOR WP 8,9, 10 AND 11 |  | A1 | Project Working Copy | Engineering Document | Part B - Engineering Doc | ZWPX |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | In Review | IFR | Issued for Review |  | 08-Oct-2026 10:46:00 | wisuda.c@jutal.com | 08-Oct-2026 13:19:28 | Jumpol Sudjitjul | 16-Oct-2026 |  |  | 20-Oct-2026 |  |  | 21-Oct-2026 |  |  |  |  | 22-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001007 | MM-ZTK-1C-WPX-PRO-LIS-0005_A | SAFETY ANALYSIS FUNCTION EVALUATION (SAFE CHARTS) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 20:33:44 | wisuda.c@jutal.com | 04-Jul-2026 15:00:21 | Jumpol Sudjitjul | 10-Jul-2026 |  | Chananun Rojanarungruengporn | 14-Jul-2026 | 14-Jul-2026 13:48:35 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 23:39:22 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 10:14:26 | 15-Jul-2026 04:07:45 | 0 |  |  | Approver | Locate
AO-001691 | MM-ZTK-1C-WPX-PRO-LIS-0005_A | SAFETY ANALYSIS FUNCTION EVALUATION (SAFE CHARTS) |  | X | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | LIS | List, Index, Schedule, Listing | 0 | In Review | VOID | Withdrawn or Superseded |  | 24-Aug-2026 17:16:30 | wisuda.c@jutal.com | 25-Aug-2026 14:54:25 | Jumpol Sudjitjul |  | 01-Sep-2026 11:51:29 | Chananun Rojanarungruengporn |  |  | Pornlert Wanaphattharaphan | [8 empty] | 0 |  |  | For Info | Locate
AO-001008 | MM-ZTK-1C-ZPQM-PRO-DWG-0001_A | SAFETY ANALYSIS FUNCTION EVALUATION [SAFE] CHART FOR ZPQ (BROWNFIELD MODIFICATION) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZPQ |  |  | PRO | Process | DWG |  | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 20:34:10 | wisuda.c@jutal.com | 04-Jul-2026 14:58:35 | Jumpol Sudjitjul | 10-Jul-2026 | 13-Jul-2026 20:52:09 | Chananun Rojanarungruengporn | 14-Jul-2026 | 13-Jul-2026 21:01:06 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 16-Jul-2026 23:09:37 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:26:11 | 17-Jul-2026 03:39:58 | 0 |  |  | Approver | Locate
AO-002387 | MM-ZTK-1C-ZPQM-PRO-DWG-0001_A | SAFETY ANALYSIS FUNCTION EVALUATION [SAFE] CHART FOR ZPQ (BROWNFIELD MODIFICATION) |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZPQ |  |  | PRO | Process | DWG |  | 0 | Submitted | AFC | Approved for Construction |  | 06-Oct-2026 08:34:45 | wisuda.c@jutal.com | 06-Oct-2026 09:28:58 | Jumpol Sudjitjul | 14-Oct-2026 |  | Chananun Rojanarungruengporn | 16-Oct-2026 | 07-Oct-2026 08:48:32 | Pornlert Wanaphattharaphan | 19-Oct-2026 | 11-Oct-2026 00:11:22 | APPR | Approved | Jumpol Sudjitjul | 20-Oct-2026 | 11-Oct-2026 09:57:13 | 11-Oct-2026 03:42:26 | 0 |  |  | Approver | Locate
AO-002494 | MM-ZTK-1C-ZPQM-TEL-BLD-0001_A | TELECOMMUNICATION BLOCK DIAGRAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZPQ |  |  | TEL | Telecommunication | BLD | Block Diagram | 0 | In Review | IFR | Issued for Review |  | 12-Oct-2026 12:08:43 | wisuda.c@jutal.com | 12-Oct-2026 13:40:22 | Jumpol Sudjitjul | 20-Oct-2026 |  | Wichai Salee | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000855 | MM-ZTK-1D-ZPQ-INS-LIS-0001_A | ZAWTIKA PLC GATEWAY CAUSE & EFFECT DIAGRAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZPQ |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 22:34:07 | wisuda.c@jutal.com | 22-Jun-2026 13:45:31 | Jumpol Sudjitjul | 29-Jun-2026 |  | Wichai Salee | 01-Jul-2026 | 03-Jul-2026 14:38:34 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 04-Jul-2026 19:11:34 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 03-Jul-2026 | 05-Jul-2026 10:36:12 | 05-Jul-2026 04:01:23 | 0 |  |  | Approver | Locate
AO-001760 | MM-ZTK-1D-ZPQ-INS-LIS-0001_A | ZAWTIKA PLC GATEWAY CAUSE & EFFECT DIAGRAM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZPQ |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 28-Aug-2026 18:09:28 | wisuda.c@jutal.com | 29-Aug-2026 13:31:54 | Jumpol Sudjitjul | 04-Sep-2026 |  | Wichai Salee | 08-Sep-2026 | 08-Sep-2026 16:19:18 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 11-Sep-2026 22:27:03 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 12-Sep-2026 20:46:13 | 12-Sep-2026 14:02:36 | 0 |  |  | Approver | Locate
AO-002272 | MM-ZTK-1D-ZPQ-INS-LIS-0001_A | ZAWTIKA PLC GATEWAY CAUSE & EFFECT DIAGRAM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZPQ |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 25-Sep-2026 18:14:37 | wisuda.c@jutal.com | 26-Sep-2026 16:27:08 | Jumpol Sudjitjul | 02-Oct-2026 |  | Wichai Salee | 06-Oct-2026 | 01-Oct-2026 11:26:27 | Pornlert Wanaphattharaphan | 07-Oct-2026 | 01-Oct-2026 23:21:42 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 02-Oct-2026 11:54:17 | 02-Oct-2026 05:36:49 | 0 |  |  | Approver | Locate
AO-000846 | MM-ZTK-1D-ZPQ-PRO-ESD-0002_A | ZPQ PLC GATEWAY ESD LOGIC DIAGRAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZPQ |  |  | PRO | Process | ESD | Emergency Logic Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 22:43:23 | wisuda.c@jutal.com | 22-Jun-2026 14:16:32 | Jumpol Sudjitjul | 29-Jun-2026 |  | Chananun Rojanarungruengporn | 01-Jul-2026 | 05-Jul-2026 16:57:21 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 07-Jul-2026 00:48:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 07-Jul-2026 09:00:47 | 07-Jul-2026 02:56:20 | 0 |  |  | Approver | Locate
AO-001479 | MM-ZTK-1D-ZPQ-PRO-ESD-0002_A | ZPQ PLC GATEWAY ESD LOGIC DIAGRAM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZPQ |  |  | PRO | Process | ESD | Emergency Logic Diagram | 0 | Submitted | AFC | Approved for Construction |  | 10-Aug-2026 12:02:20 | wisuda.c@jutal.com | 10-Aug-2026 15:15:03 | Jumpol Sudjitjul | 18-Aug-2026 | 18-Aug-2026 23:53:42 | Chananun Rojanarungruengporn | 20-Aug-2026 | 19-Aug-2026 09:35:26 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:45:32 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 17:36:44 | 24-Aug-2026 11:14:57 | 0 |  |  | Approver | Locate
AO-000855 | MM-ZTK-1D-ZWP14-INS-LIS-0006_A | ZWP14 ESD CAUSE & EFFECT DIAGRAMS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP14 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 22:34:31 | wisuda.c@jutal.com | 22-Jun-2026 13:45:54 | Jumpol Sudjitjul | 29-Jun-2026 |  | Wichai Salee | 01-Jul-2026 | 12-Jul-2026 22:27:46 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 12-Jul-2026 23:59:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 13-Jul-2026 08:04:32 | 13-Jul-2026 01:24:14 | 0 |  |  | Approver | Locate
AO-001777 | MM-ZTK-1D-ZWP14-INS-LIS-0006_A | ZWP14 ESD CAUSE & EFFECT DIAGRAMS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP14 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:21:33 | wisuda.c@jutal.com | 31-Aug-2026 12:51:05 | Jumpol Sudjitjul | 07-Sep-2026 |  | Wichai Salee | 09-Sep-2026 | 09-Sep-2026 15:23:20 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 23:50:13 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 12-Sep-2026 20:46:55 | 12-Sep-2026 14:03:55 | 0 |  |  | Approver | Locate
AO-002272 | MM-ZTK-1D-ZWP14-INS-LIS-0006_A | ZWP14 ESD CAUSE & EFFECT DIAGRAMS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP14 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 25-Sep-2026 18:15:03 | wisuda.c@jutal.com | 26-Sep-2026 16:27:25 | Jumpol Sudjitjul | 02-Oct-2026 |  | Wichai Salee | 06-Oct-2026 | 01-Oct-2026 11:27:25 | Pornlert Wanaphattharaphan | 07-Oct-2026 | 01-Oct-2026 23:21:14 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 02-Oct-2026 11:56:28 | 02-Oct-2026 05:38:03 | 0 |  |  | Approver | Locate
AO-000846 | MM-ZTK-1D-ZWP14-PRO-ESD-0001_A | ESD LOGIC DIAGRAM (ZWP14) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP14 |  |  | PRO | Process | ESD | Emergency Logic Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 22:43:47 | wisuda.c@jutal.com | 22-Jun-2026 14:17:42 | Jumpol Sudjitjul | 29-Jun-2026 |  | Chananun Rojanarungruengporn | 01-Jul-2026 | 05-Jul-2026 16:55:50 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 07-Jul-2026 00:48:19 | APPR | Approved | Jumpol Sudjitjul | 03-Jul-2026 | 07-Jul-2026 09:02:26 | 07-Jul-2026 02:58:28 | 0 |  |  | Approver | Locate
AO-001442 | MM-ZTK-1D-ZWP14-PRO-ESD-0001_A | ESD LOGIC DIAGRAM (ZWP14) |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP14 |  |  | PRO | Process | ESD | Emergency Logic Diagram | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 10:59:49 | wisuda.c@jutal.com | 07-Aug-2026 14:32:37 | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 23:50:06 | Chananun Rojanarungruengporn | 19-Aug-2026 | 18-Aug-2026 09:12:27 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:42:50 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 10:34:59 | 21-Aug-2026 04:21:47 | 0 |  |  | Approver | Locate
AO-000855 | MM-ZTK-1E-ZWP16-INS-ESD-0001 | ZWP16 CAUSE AND EFFECT DIAGRAM |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP16 |  |  | INS | Instrumentation and Control | ESD | Emergency Logic Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 22:34:58 | wisuda.c@jutal.com | 22-Jun-2026 13:47:52 | Jumpol Sudjitjul | 29-Jun-2026 |  |  | 01-Jul-2026 | 12-Jul-2026 22:28:38 |  | 02-Jul-2026 | 13-Jul-2026 00:10:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 13-Jul-2026 08:11:27 | 13-Jul-2026 01:29:17 | 0 |  |  | Approver | Locate
AO-001777 | MM-ZTK-1E-ZWP16-INS-ESD-0001 | ZWP16 CAUSE AND EFFECT DIAGRAM |  | B1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP16 |  |  | INS | Instrumentation and Control | ESD | Emergency Logic Diagram | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:22:00 | wisuda.c@jutal.com | 31-Aug-2026 11:49:13 | Jumpol Sudjitjul | 07-Sep-2026 |  |  | 09-Sep-2026 | 04-Sep-2026 10:58:53 |  | 10-Sep-2026 | 07-Sep-2026 00:11:26 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 07-Sep-2026 11:35:55 | 07-Sep-2026 05:07:26 | 0 |  |  | Approver | Locate
AO-002272 | MM-ZTK-1E-ZWP16-INS-ESD-0001 | ZWP16 CAUSE AND EFFECT DIAGRAM |  | C1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP16 |  |  | INS | Instrumentation and Control | ESD | Emergency Logic Diagram | 0 | Submitted | AFC | Approved for Construction |  | 25-Sep-2026 18:15:35 | wisuda.c@jutal.com | 26-Sep-2026 16:25:36 | Jumpol Sudjitjul | 02-Oct-2026 |  |  | 06-Oct-2026 | 30-Sep-2026 22:54:31 |  | 07-Oct-2026 | 01-Oct-2026 23:20:29 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 02-Oct-2026 13:06:34 | 02-Oct-2026 06:18:02 | 0 |  |  | Approver | Locate
AO-000846 | MM-ZTK-1E-ZWP16-PRO-ESD-0002 | ESD LOGIC DIAGRAM |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP16 |  |  | PRO | Process | ESD | Emergency Logic Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 22:44:11 | wisuda.c@jutal.com | 22-Jun-2026 14:18:11 | Jumpol Sudjitjul | 29-Jun-2026 |  |  | 01-Jul-2026 | 05-Jul-2026 16:55:01 |  | 02-Jul-2026 | 07-Jul-2026 00:48:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 07-Jul-2026 09:04:44 | 07-Jul-2026 03:00:52 | 0 |  |  | Approver | Locate
AO-001441 | MM-ZTK-1E-ZWP16-PRO-ESD-0002 | ESD LOGIC DIAGRAM |  | C1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP16 |  |  | PRO | Process | ESD | Emergency Logic Diagram | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 10:07:52 | wisuda.c@jutal.com | 07-Aug-2026 10:19:24 | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 23:37:32 |  | 19-Aug-2026 | 18-Aug-2026 09:15:10 |  | 20-Aug-2026 | 20-Aug-2026 23:43:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 10:36:09 | 21-Aug-2026 04:23:05 | 0 |  |  | Approver | Locate
AO-000872 | MM-ZTK-1E-ZWP16-PRO-PID-0014 | PIPING AND INSTRUMENTATION DIAGRAM - PIG RECEIVER |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP16 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 23-Jun-2026 11:34:07 | wisuda.c@jutal.com | 23-Jun-2026 12:39:52 | Jumpol Sudjitjul | 30-Jun-2026 |  |  | 02-Jul-2026 | 05-Jul-2026 17:15:08 |  | 03-Jul-2026 | 07-Jul-2026 00:52:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Jul-2026 | 07-Jul-2026 09:07:40 | 07-Jul-2026 02:38:30 | 0 |  |  | Approver | Locate
AO-001749 | MM-ZTK-1E-ZWP16-PRO-PID-0014 | PIPING AND INSTRUMENTATION DIAGRAM - PIG RECEIVER |  | C1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP16 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 10:32:48 | wisuda.c@jutal.com | 28-Aug-2026 14:05:13 | Jumpol Sudjitjul | 04-Sep-2026 |  |  | 08-Sep-2026 | 08-Sep-2026 10:33:53 |  | 09-Sep-2026 | 10-Sep-2026 22:50:12 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 11-Sep-2026 08:15:23 | 11-Sep-2026 01:51:11 | 0 |  |  | Approver | Locate
AO-000855 | MM-ZTK-1E-ZWP18-INS-ESD-0001 | ZWP18 CAUSE AND EFFECT DIAGRAM |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP18 |  |  | INS | Instrumentation and Control | ESD | Emergency Logic Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 22:35:22 | wisuda.c@jutal.com | 22-Jun-2026 13:48:11 | Jumpol Sudjitjul | 29-Jun-2026 |  |  | 01-Jul-2026 | 12-Jul-2026 22:29:43 |  | 02-Jul-2026 | 13-Jul-2026 00:14:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 13-Jul-2026 08:05:09 | 13-Jul-2026 01:25:38 | 0 |  |  | Approver | Locate
AO-001777 | MM-ZTK-1E-ZWP18-INS-ESD-0001 | ZWP18 CAUSE AND EFFECT DIAGRAM |  | B1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP18 |  |  | INS | Instrumentation and Control | ESD | Emergency Logic Diagram | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:22:29 | wisuda.c@jutal.com | 31-Aug-2026 11:49:41 | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 16:41:09 |  | 09-Sep-2026 | 09-Sep-2026 15:22:38 |  | 10-Sep-2026 | 11-Sep-2026 23:46:56 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 12-Sep-2026 20:48:35 | 12-Sep-2026 14:05:20 | 0 |  |  | Approver | Locate
AO-002272 | MM-ZTK-1E-ZWP18-INS-ESD-0001 | ZWP18 CAUSE AND EFFECT DIAGRAM |  | C1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP18 |  |  | INS | Instrumentation and Control | ESD | Emergency Logic Diagram | 0 | Submitted | AFC | Approved for Construction |  | 25-Sep-2026 18:16:04 | wisuda.c@jutal.com | 26-Sep-2026 16:25:54 | Jumpol Sudjitjul | 02-Oct-2026 |  |  | 06-Oct-2026 | 30-Sep-2026 22:58:00 |  | 07-Oct-2026 | 01-Oct-2026 23:20:06 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 02-Oct-2026 13:07:01 | 02-Oct-2026 06:19:14 | 0 |  |  | Approver | Locate
AO-000846 | MM-ZTK-1E-ZWP18-PRO-ESD-0002 | ESD LOGIC DIAGRAM |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP18 |  |  | PRO | Process | ESD | Emergency Logic Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 22:44:35 | wisuda.c@jutal.com | 22-Jun-2026 14:18:55 | Jumpol Sudjitjul | 29-Jun-2026 |  |  | 01-Jul-2026 | 05-Jul-2026 16:56:15 |  | 02-Jul-2026 | 07-Jul-2026 00:48:37 | APPR | Approved | Jumpol Sudjitjul | 03-Jul-2026 | 07-Jul-2026 09:10:13 | 07-Jul-2026 03:06:16 | 0 |  |  | Approver | Locate
AO-001441 | MM-ZTK-1E-ZWP18-PRO-ESD-0002 | ESD LOGIC DIAGRAM |  | C1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP18 |  |  | PRO | Process | ESD | Emergency Logic Diagram | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 10:08:30 | wisuda.c@jutal.com | 07-Aug-2026 10:19:23 | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 23:39:08 |  | 19-Aug-2026 | 18-Aug-2026 09:18:22 |  | 20-Aug-2026 | 20-Aug-2026 23:44:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 10:36:34 | 21-Aug-2026 04:24:22 | 0 |  |  | Approver | Locate
AO-000855 | MM-ZTK-1E-ZWP19-INS-ESD-0001 | ZWP19 CAUSE AND EFFECT DIAGRAM |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP19 |  |  | INS | Instrumentation and Control | ESD | Emergency Logic Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 22:35:46 | wisuda.c@jutal.com | 22-Jun-2026 13:48:28 | Jumpol Sudjitjul | 29-Jun-2026 |  |  | 01-Jul-2026 | 12-Jul-2026 22:30:24 |  | 02-Jul-2026 | 13-Jul-2026 00:14:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 13-Jul-2026 08:05:47 | 13-Jul-2026 01:26:55 | 0 |  |  | Approver | Locate
AO-001777 | MM-ZTK-1E-ZWP19-INS-ESD-0001 | ZWP19 CAUSE AND EFFECT DIAGRAM |  | B1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP19 |  |  | INS | Instrumentation and Control | ESD | Emergency Logic Diagram | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:22:59 | wisuda.c@jutal.com | 31-Aug-2026 11:49:59 | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 16:48:44 |  | 09-Sep-2026 | 09-Sep-2026 15:22:51 |  | 10-Sep-2026 | 11-Sep-2026 23:47:34 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 12-Sep-2026 20:51:37 | 12-Sep-2026 14:27:16 | 0 |  |  | Approver | Locate
AO-002272 | MM-ZTK-1E-ZWP19-INS-ESD-0001 | ZWP19 CAUSE AND EFFECT DIAGRAM |  | C1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP19 |  |  | INS | Instrumentation and Control | ESD | Emergency Logic Diagram | 0 | Submitted | AFC | Approved for Construction |  | 25-Sep-2026 18:16:30 | wisuda.c@jutal.com | 26-Sep-2026 16:26:09 | Jumpol Sudjitjul | 02-Oct-2026 |  |  | 06-Oct-2026 | 30-Sep-2026 23:00:07 |  | 07-Oct-2026 | 01-Oct-2026 23:19:31 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 02-Oct-2026 13:08:04 | 02-Oct-2026 06:20:27 | 0 |  |  | Approver | Locate
AO-000846 | MM-ZTK-1E-ZWP19-PRO-ESD-0002 | ESD LOGIC DIAGRAM |  | A1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP19 |  |  | PRO | Process | ESD | Emergency Logic Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 22:44:59 | wisuda.c@jutal.com | 22-Jun-2026 14:19:48 | Jumpol Sudjitjul | 29-Jun-2026 |  |  | 01-Jul-2026 | 05-Jul-2026 17:22:38 |  | 02-Jul-2026 | 07-Jul-2026 00:50:03 | APPR | Approved | Jumpol Sudjitjul | 03-Jul-2026 | 07-Jul-2026 09:12:05 | 07-Jul-2026 03:07:27 | 0 |  |  | Approver | Locate
AO-001441 | MM-ZTK-1E-ZWP19-PRO-ESD-0002 | ESD LOGIC DIAGRAM |  | C1 | Project Working Copy | Engineering Document | Part C - Engineering Dwg | ZWP19 |  |  | PRO | Process | ESD | Emergency Logic Diagram | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 10:09:04 | wisuda.c@jutal.com | 07-Aug-2026 10:19:17 | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 23:05:32 |  | 19-Aug-2026 | 18-Aug-2026 09:21:35 |  | 20-Aug-2026 | 20-Aug-2026 23:44:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 10:37:06 | 21-Aug-2026 04:25:45 | 0 |  |  | Approver | Locate
AO-000343 | MM-ZTK-1F-GEN-CON-MOM-0001 | CONSTRUCTABILITY WORKSHOP FOR ZAWTIKA 1F |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 08-May-2026 13:36:06 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000731 | MM-ZTK-1F-GEN-CON-MOM-0002 | CONSTRUCTABILITY AND CONSTRUCTION KICK-OFF MEETING FOR ZAWTIKA 1F |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 10-Jun-2026 14:41:55 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000874 | MM-ZTK-1F-GEN-CON-MOM-5001 | CONSTRUCTION PROGRESS WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 23-Jun-2026 11:30:54 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000875 | MM-ZTK-1F-GEN-CON-MOM-5002 | CONSTRUCTION PROGRESS WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 23-Jun-2026 11:31:27 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001030 | MM-ZTK-1F-GEN-CON-MOM-5003 | CONSTRUCTION PROGRESS WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 07-Jul-2026 18:07:02 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001121 | MM-ZTK-1F-GEN-CON-MOM-5004 | CONSTRUCTION PROGRESS WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 16-Jul-2026 09:17:20 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001224 | MM-ZTK-1F-GEN-CON-MOM-5005 | CONSTRUCTION PROGRESS WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 22-Jul-2026 17:24:59 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001332 | MM-ZTK-1F-GEN-CON-MOM-5006 | CONSTRUCTION PROGRESS WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 30-Jul-2026 09:52:43 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001639 | MM-ZTK-1F-GEN-CON-MOM-5007 | CONSTRUCTION PROGRESS WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 21-Aug-2026 10:27:19 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001639 | MM-ZTK-1F-GEN-CON-MOM-5008 | CONSTRUCTION PROGRESS WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 21-Aug-2026 09:41:55 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001639 | MM-ZTK-1F-GEN-CON-MOM-5009 | CONSTRUCTION PROGRESS WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 21-Aug-2026 09:42:21 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001695 | MM-ZTK-1F-GEN-CON-MOM-5010 | CONSTRUCTION PROGRESS WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 24-Aug-2026 17:15:59 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001924 | MM-ZTK-1F-GEN-CON-MOM-5011 | CONSTRUCTION PROGRESS WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 08-Sep-2026 12:35:30 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000536 | MM-ZTK-1F-GEN-CON-PDR-5001 | JACKET CONSTRUCTION PROCEDURE |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 18:41:53 | zm169dc@jutal.com | 20-May-2026 18:53:53 | Jumpol Sudjitjul | 28-May-2026 | 29-May-2026 08:02:53 | Poramate Kamlangkeng | 02-Jun-2026 | 01-Jun-2026 15:25:21 | Prin Jitatisil | 04-Jun-2026 | 04-Jun-2026 16:57:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 04-Jun-2026 17:02:41 | 04-Jun-2026 15:05:07 | 0 |  |  | Approver | Locate
AO-000960 | MM-ZTK-1F-GEN-CON-PDR-5001 | JACKET CONSTRUCTION PROCEDURE |  | B1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 30-Jun-2026 18:39:44 | zm169dc@jutal.com | 01-Jul-2026 10:06:24 | Jumpol Sudjitjul | 08-Jul-2026 | 07-Jul-2026 16:36:18 | Poramate Kamlangkeng | 10-Jul-2026 | 10-Jul-2026 07:48:09 | Prin Jitatisil | 13-Jul-2026 | 11-Jul-2026 12:12:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Jul-2026 | 12-Jul-2026 11:28:17 | 12-Jul-2026 04:46:40 | 0 |  |  | Approver | Locate
AO-001650 | MM-ZTK-1F-GEN-CON-PDR-5001 | JACKET CONSTRUCTION PROCEDURE |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 14:53:12 | zm169dc@jutal.com | 21-Aug-2026 15:05:37 | Jumpol Sudjitjul | 28-Aug-2026 | 22-Aug-2026 07:24:46 | Poramate Kamlangkeng | 01-Sep-2026 | 24-Aug-2026 12:45:38 | Prin Jitatisil | 02-Sep-2026 | 24-Aug-2026 15:09:13 | APPR | Approved | Jumpol Sudjitjul | 03-Sep-2026 | 24-Aug-2026 17:37:48 | 24-Aug-2026 11:33:24 | 0 |  |  | Approver | Locate
AO-001438 | MM-ZTK-1F-GEN-CON-PDR-5002 | WEIGHTING CONTROL PROCEDURE |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 06-Aug-2026 17:36:54 | zm169dc@jutal.com | 07-Aug-2026 16:19:39 | Jumpol Sudjitjul | 17-Aug-2026 | 08-Aug-2026 06:46:16 | Poramate Kamlangkeng | 19-Aug-2026 | 15-Aug-2026 08:51:38 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 15-Aug-2026 14:36:22 | 15-Aug-2026 08:33:16 | 0 |  |  | Focal Point | Locate
AO-001622 | MM-ZTK-1F-GEN-CON-PDR-5002 | WEIGHTING CONTROL PROCEDURE |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 12:11:10 | zm169dc@jutal.com | 20-Aug-2026 13:49:06 | Jumpol Sudjitjul | 27-Aug-2026 | 20-Aug-2026 14:26:20 | Poramate Kamlangkeng | 31-Aug-2026 | 21-Aug-2026 09:49:12 | Prin Jitatisil | 01-Sep-2026 | 21-Aug-2026 15:31:40 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 21-Aug-2026 15:49:29 | 21-Aug-2026 09:30:08 | 0 |  |  | Approver | Locate
AO-001046 | MM-ZTK-1F-GEN-CON-PDR-5004 | HANDLING AND LIFTING PROCEDURE |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 09-Jul-2026 18:43:51 | zm169dc@jutal.com | 09-Jul-2026 21:03:56 | Jumpol Sudjitjul | 17-Jul-2026 | 11-Jul-2026 06:22:25 | Poramate Kamlangkeng | 21-Jul-2026 | 14-Jul-2026 08:31:18 | Prin Jitatisil | 22-Jul-2026 | 14-Jul-2026 08:56:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 14-Jul-2026 09:00:14 | 14-Jul-2026 03:18:25 | 0 |  |  | Approver | Locate
AO-001423 | MM-ZTK-1F-GEN-CON-PDR-5004 | HANDLING AND LIFTING PROCEDURE |  | B1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 05-Aug-2026 16:08:59 | zm169dc@jutal.com | 05-Aug-2026 16:15:39 | Jumpol Sudjitjul | 13-Aug-2026 | 08-Aug-2026 06:46:55 | Poramate Kamlangkeng | 17-Aug-2026 | 14-Aug-2026 15:53:17 | Prin Jitatisil | 18-Aug-2026 | 14-Aug-2026 15:56:30 | APPR | Approved | Jumpol Sudjitjul | 19-Aug-2026 | 14-Aug-2026 16:15:22 | 14-Aug-2026 09:34:59 | 0 |  |  | Approver | Locate
AO-001609 | MM-ZTK-1F-GEN-CON-PDR-5004 | HANDLING AND LIFTING PROCEDURE |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 10:07:28 | zm169dc@jutal.com | 19-Aug-2026 15:11:55 | Jumpol Sudjitjul | 26-Aug-2026 | 20-Aug-2026 14:26:47 | Poramate Kamlangkeng | 28-Aug-2026 | 21-Aug-2026 09:51:43 | Prin Jitatisil | 31-Aug-2026 | 21-Aug-2026 15:32:02 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 21-Aug-2026 15:49:56 | 21-Aug-2026 09:31:19 | 0 |  |  | Approver | Locate
AO-001263 | MM-ZTK-1F-GEN-CON-PDR-5006 | STRUCTURE FABRICATION PROCEDURE |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 12:06:33 | zm169dc@jutal.com | 26-Jul-2026 23:43:46 | Jumpol Sudjitjul | 05-Aug-2026 | 29-Jul-2026 06:53:51 | Poramate Kamlangkeng | 07-Aug-2026 | 30-Jul-2026 11:08:48 | Prin Jitatisil | 10-Aug-2026 | 30-Jul-2026 12:24:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 30-Jul-2026 14:05:55 | 30-Jul-2026 07:41:43 | 0 |  |  | Approver | Locate
AO-001999 | MM-ZTK-1F-GEN-CON-PDR-5006 | STRUCTURE FABRICATION PROCEDURE |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 09:15:54 | zhaoli@jutal.com | 11-Sep-2026 19:37:33 | Jumpol Sudjitjul | 21-Sep-2026 | 14-Sep-2026 17:35:19 | Poramate Kamlangkeng | 23-Sep-2026 | 18-Sep-2026 09:29:04 | Prin Jitatisil | 24-Sep-2026 | 18-Sep-2026 09:43:59 | APPR | Approved | Jumpol Sudjitjul | 25-Sep-2026 | 18-Sep-2026 10:14:12 | 18-Sep-2026 03:53:30 | 0 |  |  | Approver | Locate
AO-001587 | MM-ZTK-1F-GEN-CON-PDR-5007 | PIPING FABRICATION PROCEDURE |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 18-Aug-2026 13:57:01 | zm169dc@jutal.com | 18-Aug-2026 14:09:14 | Jumpol Sudjitjul | 25-Aug-2026 | 19-Aug-2026 13:44:19 | Poramate Kamlangkeng | 27-Aug-2026 | 24-Aug-2026 13:03:25 | Prin Jitatisil | 28-Aug-2026 | 24-Aug-2026 15:09:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Aug-2026 | 24-Aug-2026 17:38:47 | 24-Aug-2026 11:16:11 | 0 |  |  | Approver | Locate
AO-002000 | MM-ZTK-1F-GEN-CON-PDR-5007 | PIPING FABRICATION PROCEDURE |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 09:16:27 | zhaoli@jutal.com | 11-Sep-2026 19:37:46 | Jumpol Sudjitjul | 21-Sep-2026 | 17-Sep-2026 14:23:00 | Poramate Kamlangkeng | 23-Sep-2026 | 18-Sep-2026 09:29:50 | Prin Jitatisil | 24-Sep-2026 | 18-Sep-2026 09:44:36 | APPR | Approved | Jumpol Sudjitjul | 25-Sep-2026 | 18-Sep-2026 09:55:19 | 18-Sep-2026 03:45:12 | 0 |  |  | Approver | Locate
AO-001588 | MM-ZTK-1F-GEN-CON-PDR-5009 | BOLT TIGHTENING AND FLANGE MANAGEMENT PROCEDURE |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 18-Aug-2026 13:57:44 | zm169dc@jutal.com | 18-Aug-2026 14:11:21 | Jumpol Sudjitjul | 25-Aug-2026 | 20-Aug-2026 09:53:18 | Poramate Kamlangkeng | 27-Aug-2026 | 24-Aug-2026 13:08:54 | Prin Jitatisil | 28-Aug-2026 | 24-Aug-2026 15:10:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Aug-2026 | 24-Aug-2026 17:40:31 | 24-Aug-2026 11:34:40 | 0 |  |  | Approver | Locate
AO-001429 | MM-ZTK-1F-GEN-CON-PDR-5013 | LEVELING AND DIMENSIONAL CONTROL PROCEDURE |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 06-Aug-2026 10:51:58 | zm169dc@jutal.com | 06-Aug-2026 14:40:47 | Jumpol Sudjitjul | 14-Aug-2026 |  | Poramate Kamlangkeng | 18-Aug-2026 | 14-Aug-2026 16:01:05 | Prin Jitatisil | 19-Aug-2026 | 15-Aug-2026 11:20:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 15-Aug-2026 14:37:19 | 15-Aug-2026 09:03:39 | 0 |  |  | Approver | Locate
AO-001598 | MM-ZTK-1F-GEN-CON-PDR-5013 | LEVELING AND DIMENSIONAL CONTROL PROCEDURE |  | B1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 18-Aug-2026 17:32:21 | zm169dc@jutal.com | 19-Aug-2026 15:12:21 | Jumpol Sudjitjul | 26-Aug-2026 | 20-Aug-2026 16:26:08 | Poramate Kamlangkeng | 28-Aug-2026 | 24-Aug-2026 12:49:51 | Prin Jitatisil | 31-Aug-2026 | 24-Aug-2026 15:11:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Sep-2026 | 25-Aug-2026 13:21:32 | 25-Aug-2026 07:26:10 | 0 |  |  | Approver | Locate
AO-001818 | MM-ZTK-1F-GEN-CON-PDR-5013 | LEVELING AND DIMENSIONAL CONTROL PROCEDURE |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 18:22:14 | zm169dc@jutal.com | 03-Sep-2026 11:30:32 | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 09:11:22 | Poramate Kamlangkeng | 14-Sep-2026 | 08-Sep-2026 09:32:09 | Prin Jitatisil | 15-Sep-2026 | 08-Sep-2026 09:37:32 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 08-Sep-2026 13:18:17 | 08-Sep-2026 07:36:58 | 0 |  |  | Approver | Locate
AO-000951 | MM-ZTK-1F-GEN-CON-PDR-5015 | TOPSIDE ERECTION PEOCEDURE |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 30-Jun-2026 08:33:43 | zm169dc@jutal.com | 30-Jun-2026 11:13:43 | Jumpol Sudjitjul | 07-Jul-2026 | 07-Jul-2026 16:33:10 | Poramate Kamlangkeng | 09-Jul-2026 | 10-Jul-2026 07:43:52 | Prin Jitatisil | 10-Jul-2026 | 11-Jul-2026 12:12:49 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 13-Jul-2026 | 12-Jul-2026 11:28:49 | 12-Jul-2026 05:33:29 | 0 |  |  | Approver | Locate
AO-000600 | MM-ZTK-1F-GEN-CON-PDR-5016 | JACKET CONSTRUCTION PROCEDURE |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 25-May-2026 21:28:16 | zm169dc@jutal.com | 25-May-2026 22:19:27 | Jumpol Sudjitjul | 04-Jun-2026 | 04-Jun-2026 15:44:39 | Poramate Kamlangkeng | 08-Jun-2026 | 05-Jun-2026 09:32:55 | Prin Jitatisil | 09-Jun-2026 | 06-Jun-2026 10:55:05 | NA | Not Approved | Jumpol Sudjitjul | 10-Jun-2026 | 07-Jun-2026 17:21:24 | 07-Jun-2026 11:31:45 | 0 |  |  | Approver | Locate
AO-001698 | MM-ZTK-1F-GEN-CON-PDR-5018 | ONSHORE SKID BEAM ARRANGEMENT PROCEDURE |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 25-Aug-2026 11:02:18 | zm169dc@jutal.com | 25-Aug-2026 15:39:22 | Jumpol Sudjitjul | 01-Sep-2026 |  | Poramate Kamlangkeng | 03-Sep-2026 | 31-Aug-2026 13:08:33 | Prin Jitatisil | 04-Sep-2026 | 31-Aug-2026 14:29:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 15:43:50 | 31-Aug-2026 10:18:21 | 0 |  |  | Approver | Locate
AO-002378 | MM-ZTK-1F-GEN-CON-PDR-5018 | ONSHORE SKID BEAM ARRANGEMENT PROCEDURE |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 18:04:38 | zhaoli@jutal.com | 06-Oct-2026 08:59:44 | Jumpol Sudjitjul | 14-Oct-2026 |  | Poramate Kamlangkeng | 16-Oct-2026 | 17-Oct-2026 12:04:35 | Prin Jitatisil | 19-Oct-2026 | 17-Oct-2026 13:15:03 | APPR | Approved | Jumpol Sudjitjul | 20-Oct-2026 | 18-Oct-2026 09:05:08 | 18-Oct-2026 02:22:55 | 0 |  |  | Approver | Locate
AO-001228 | MM-ZTK-1F-GEN-CON-PDR-5021 | LAUNCH CRADLE CONSTRUCTION PROCEDURE |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 23-Jul-2026 18:13:21 | zm169dc@jutal.com | 24-Jul-2026 10:45:42 | Jumpol Sudjitjul | 04-Aug-2026 |  | Poramate Kamlangkeng | 06-Aug-2026 | 30-Jul-2026 11:00:04 | Prin Jitatisil | 07-Aug-2026 | 30-Jul-2026 12:24:20 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 10-Aug-2026 | 30-Jul-2026 14:06:59 | 30-Jul-2026 07:43:05 | 0 |  |  | Approver | Locate
AO-001515 | MM-ZTK-1F-GEN-CON-PDR-5021 | LAUNCH CRADLE CONSTRUCTION PROCEDURE |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 13-Aug-2026 15:25:42 | zm169dc@jutal.com | 13-Aug-2026 16:40:53 | Jumpol Sudjitjul | 20-Aug-2026 |  | Poramate Kamlangkeng | 24-Aug-2026 | 15-Aug-2026 09:35:51 | Prin Jitatisil | 25-Aug-2026 | 15-Aug-2026 11:22:23 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 15-Aug-2026 14:38:17 | 15-Aug-2026 08:12:40 | 0 |  |  | Approver | Locate
AO-001621 | MM-ZTK-1F-GEN-CON-PDR-5029 | SCAFFOLD ERECTION PROCEDURE |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 20-Aug-2026 07:52:10 | zm169dc@jutal.com | 20-Aug-2026 09:31:52 | Jumpol Sudjitjul | 27-Aug-2026 | 22-Aug-2026 07:25:21 | Poramate Kamlangkeng | 31-Aug-2026 | 24-Aug-2026 13:17:34 | Prin Jitatisil | 01-Sep-2026 | 24-Aug-2026 15:11:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Sep-2026 | 24-Aug-2026 17:44:51 | 24-Aug-2026 11:25:37 | 0 |  |  | Approver | Locate
AO-001998 | MM-ZTK-1F-GEN-CON-PDR-5029 | SCAFFOLD ERECTION PROCEDURE |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 09:17:01 | zhaoli@jutal.com | 11-Sep-2026 19:38:03 | Jumpol Sudjitjul | 21-Sep-2026 | 14-Sep-2026 12:54:53 | Poramate Kamlangkeng | 23-Sep-2026 | 18-Sep-2026 09:31:03 | Prin Jitatisil | 24-Sep-2026 | 18-Sep-2026 10:05:11 | APPR | Approved | Jumpol Sudjitjul | 25-Sep-2026 | 18-Sep-2026 18:59:40 | 18-Sep-2026 13:26:43 | 0 |  |  | Approver | Locate
AO-001932 | MM-ZTK-1F-GEN-CON-PDR-5033 | GALVANIZING CONTROL PROCEDURE |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PDR | Procedure | 0 | In Review | AFC | Approved for Construction |  | 08-Sep-2026 14:14:31 | zhaoli@jutal.com | 08-Sep-2026 15:10:53 | Jumpol Sudjitjul | 15-Sep-2026 | 17-Oct-2026 09:04:52 | Pornlert Wanaphattharaphan | 17-Sep-2026 |  | Prin Jitatisil | 18-Sep-2026 |  |  |  |  | 21-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001355 | MM-ZTK-1F-GEN-CON-PLN-5001 | CONSTRUCTION EXECUTION PLAN |  | A1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 31-Jul-2026 16:24:05 | zm169dc@jutal.com | 31-Jul-2026 17:15:35 | Jumpol Sudjitjul | 10-Aug-2026 |  | Poramate Kamlangkeng | 13-Aug-2026 | 14-Aug-2026 15:24:57 | Prin Jitatisil | 14-Aug-2026 | 14-Aug-2026 15:56:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 14-Aug-2026 16:16:56 | 14-Aug-2026 09:28:44 | 0 |  |  | Approver | Locate
AO-001894 | MM-ZTK-1F-GEN-CON-PLN-5001 | CONSTRUCTION EXECUTION PLAN |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | CON | Construction | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 09:36:51 | zhaoli@jutal.com | 08-Sep-2026 09:15:57 | Jumpol Sudjitjul | 15-Sep-2026 |  | Poramate Kamlangkeng | 17-Sep-2026 | 18-Sep-2026 09:17:13 | Prin Jitatisil | 18-Sep-2026 | 18-Sep-2026 09:49:46 | APPR | Approved | Jumpol Sudjitjul | 21-Sep-2026 | 18-Sep-2026 19:04:29 | 18-Sep-2026 12:51:19 | 0 |  |  | Approver | Locate
AO-000388 | MM-ZTK-1F-GEN-COR-RPT-0001 | TOPSIDE FACILITY AND PIPELINE CORROSION ASSESSMENT AND MATERIAL SELECTION STUDY REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | COR | Corrosion | RPT | Report | 0 | In Review | IFI | Issued for Information |  | 13-May-2026 15:28:43 | wisuda.c@jutal.com | 14-May-2026 09:43:04 | Jumpol Sudjitjul |  |  | Pornlert Wanaphattharaphan | [11 empty] | 0 |  |  | For Info | Locate
AO-000110 | MM-ZTK-1F-GEN-ELE-BOD-0001 | ELECTRICAL BASIS OF DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | BOD | Basis of Design | 0 | Submitted | IFR | Issued for Review |  | 10-Apr-2026 14:15:29 | zm169dc@jutal.com | 10-Apr-2026 15:29:56 | Jumpol Sudjitjul | 22-Apr-2026 |  | Wichai Salee | 24-Apr-2026 | 28-Apr-2026 16:05:22 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 29-Apr-2026 00:27:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 29-Apr-2026 08:32:04 | 30-Apr-2026 11:49:43 | 0 |  |  | Approver | Locate
AO-000604 | MM-ZTK-1F-GEN-ELE-BOD-0001 | ELECTRICAL BASIS OF DESIGN |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 26-May-2026 16:47:53 | wisuda.c@jutal.com | 27-May-2026 09:15:14 | Jumpol Sudjitjul | 05-Jun-2026 |  | Wichai Salee | 09-Jun-2026 | 22-Jun-2026 16:16:01 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 22-Jun-2026 22:13:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Jun-2026 | 23-Jun-2026 09:31:44 | 23-Jun-2026 02:59:32 | 0 |  |  | Approver | Locate
AO-001729 | MM-ZTK-1F-GEN-ELE-BOD-0001 | ELECTRICAL BASIS OF DESIGN |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 26-Aug-2026 19:20:51 | wisuda.c@jutal.com | 27-Aug-2026 11:23:44 | Jumpol Sudjitjul | 03-Sep-2026 |  | Wichai Salee | 07-Sep-2026 | 08-Sep-2026 10:06:01 | Pornlert Wanaphattharaphan | 08-Sep-2026 | 08-Sep-2026 23:18:42 | APPR | Approved | Jumpol Sudjitjul | 09-Sep-2026 | 09-Sep-2026 10:40:14 | 09-Sep-2026 04:10:14 | 0 |  |  | Approver | Locate
AO-000348 | MM-ZTK-1F-GEN-ELE-CAL-0001 | ELECTRICAL LOAD LIST AND LOAD ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:56:34 | wisuda.c@jutal.com | 11-May-2026 11:36:04 | Jumpol Sudjitjul | 18-May-2026 |  | Wichai Salee | 20-May-2026 | 15-Jun-2026 09:24:59 | Pornlert Wanaphattharaphan | 21-May-2026 | 15-Jun-2026 22:50:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 16-Jun-2026 09:40:48 | 16-Jun-2026 03:37:29 | 0 |  |  | Approver | Locate
AO-001726 | MM-ZTK-1F-GEN-ELE-CAL-0001 | ELECTRICAL LOAD LIST AND LOAD ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 26-Aug-2026 18:36:26 | wisuda.c@jutal.com | 27-Aug-2026 09:06:26 | Jumpol Sudjitjul | 03-Sep-2026 |  | Wichai Salee | 07-Sep-2026 | 08-Sep-2026 09:59:13 | Pornlert Wanaphattharaphan | 08-Sep-2026 | 08-Sep-2026 23:17:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Sep-2026 | 09-Sep-2026 11:05:10 | 09-Sep-2026 05:14:23 | 0 |  |  | Approver | Locate
AO-000542 | MM-ZTK-1F-GEN-ELE-CAL-0002 | ELECTRICAL EQUIPMENT SIZING CALCULATIONS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 13:36:39 | wisuda.c@jutal.com | 21-May-2026 14:20:19 | Jumpol Sudjitjul | 28-May-2026 |  | Wichai Salee | 02-Jun-2026 | 22-Jun-2026 16:08:34 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 22-Jun-2026 22:13:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 23-Jun-2026 09:45:18 | 23-Jun-2026 03:06:27 | 0 |  |  | Approver | Locate
AO-002348 | MM-ZTK-1F-GEN-ELE-CAL-0002 | ELECTRICAL EQUIPMENT SIZING CALCULATIONS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 02-Oct-2026 18:29:34 | wisuda.c@jutal.com | 03-Oct-2026 08:35:49 | Jumpol Sudjitjul | 09-Oct-2026 |  | Wichai Salee | 14-Oct-2026 | 14-Oct-2026 15:18:03 | Pornlert Wanaphattharaphan | 15-Oct-2026 | 15-Oct-2026 23:07:59 | APPR | Approved | Jumpol Sudjitjul | 16-Oct-2026 | 16-Oct-2026 13:59:52 | 16-Oct-2026 07:34:11 | 0 |  |  | Approver | Locate
AO-001128 | MM-ZTK-1F-GEN-ELE-CAL-0003 | ELECTRICAL CABLE SIZING CALCULATIONS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 16-Jul-2026 12:39:44 | wisuda.c@jutal.com | 16-Jul-2026 14:07:11 | Jumpol Sudjitjul | 23-Jul-2026 |  | Wichai Salee | 27-Jul-2026 | 24-Jul-2026 18:26:44 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 26-Jul-2026 10:03:17 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 31-Jul-2026 | 27-Jul-2026 14:46:30 | 27-Jul-2026 08:45:16 | 0 |  |  | Approver | Locate
AO-002134 | MM-ZTK-1F-GEN-ELE-CAL-0003 | ELECTRICAL CABLE SIZING CALCULATIONS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 17-Sep-2026 16:07:55 | wisuda.c@jutal.com | 17-Sep-2026 16:14:12 | Jumpol Sudjitjul | 24-Sep-2026 |  | Wichai Salee | 28-Sep-2026 | 24-Sep-2026 11:09:54 | Pornlert Wanaphattharaphan | 29-Sep-2026 | 26-Sep-2026 05:50:56 | APPR | Approved | Jumpol Sudjitjul | 30-Sep-2026 | 26-Sep-2026 13:51:43 | 26-Sep-2026 07:43:45 | 0 |  |  | Approver | Locate
AO-000876 | MM-ZTK-1F-GEN-ELE-CAL-0004 | SHORT CIRCUIT CALCULATIONS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 23-Jun-2026 16:43:47 | wisuda.c@jutal.com | 23-Jun-2026 17:31:32 | Jumpol Sudjitjul | 01-Jul-2026 |  | Wichai Salee | 03-Jul-2026 | 12-Jul-2026 23:40:27 | Pornlert Wanaphattharaphan | 06-Jul-2026 | 13-Jul-2026 00:15:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Jul-2026 | 13-Jul-2026 08:07:22 | 13-Jul-2026 01:19:18 | 0 |  |  | Approver | Locate
AO-002337 | MM-ZTK-1F-GEN-ELE-CAL-0004 | SHORT CIRCUIT CALCULATIONS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 02-Oct-2026 11:59:49 | wisuda.c@jutal.com | 02-Oct-2026 17:33:52 | Jumpol Sudjitjul | 12-Oct-2026 |  | Wichai Salee | 15-Oct-2026 | 14-Oct-2026 15:10:21 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 15-Oct-2026 23:07:31 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 16-Oct-2026 13:57:54 | 16-Oct-2026 07:39:25 | 0 |  |  | Approver | Locate
AO-001408 | MM-ZTK-1F-GEN-ELE-CAL-0005 | ILLUMINATION CALCULATIONS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 04-Aug-2026 10:01:55 | wisuda.c@jutal.com | 04-Aug-2026 10:39:52 | Jumpol Sudjitjul | 11-Aug-2026 |  | Wichai Salee | 14-Aug-2026 | 24-Aug-2026 15:37:25 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 25-Aug-2026 22:23:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 26-Aug-2026 08:31:24 | 26-Aug-2026 02:00:30 | 0 |  |  | Approver | Locate
AO-002349 | MM-ZTK-1F-GEN-ELE-CAL-0005 | ILLUMINATION CALCULATIONS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | CAL | Calculation Note, Calculation Report | 0 | In Review | AFC | Approved for Construction |  | 05-Oct-2026 09:38:53 | wisuda.c@jutal.com | 05-Oct-2026 10:58:21 | Jumpol Sudjitjul | 12-Oct-2026 |  | Wichai Salee | 15-Oct-2026 |  | Pornlert Wanaphattharaphan | 16-Oct-2026 |  |  |  |  | 19-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000222 | MM-ZTK-1F-GEN-ELE-DTS-0001 | DATASHEET FOR SOLAR POWER SYSTEM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 15:28:11 | wisuda.c@jutal.com | 24-Apr-2026 15:46:39 | Jumpol Sudjitjul | 05-May-2026 |  | Wichai Salee | 07-May-2026 | 11-May-2026 23:13:24 | Pornlert Wanaphattharaphan | 08-May-2026 | 11-May-2026 23:53:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 10:20:06 | 12-May-2026 03:41:12 | 0 |  |  | Approver | Locate
AO-001171 | MM-ZTK-1F-GEN-ELE-DTS-0001 | DATASHEET FOR SOLAR POWER SYSTEM |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 10:38:48 | wisuda.c@jutal.com | 20-Jul-2026 15:02:47 | Jumpol Sudjitjul | 27-Jul-2026 |  | Wichai Salee | 31-Jul-2026 | 06-Aug-2026 17:54:21 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 07-Aug-2026 05:32:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 07-Aug-2026 08:52:12 | 07-Aug-2026 02:04:30 | 0 |  |  | Approver | Locate
AO-002168 | MM-ZTK-1F-GEN-ELE-DTS-0001 | DATASHEET FOR SOLAR POWER SYSTEM |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 19:02:08 | wisuda.c@jutal.com | 20-Sep-2026 12:42:19 | Jumpol Sudjitjul | 25-Sep-2026 |  | Wichai Salee | 29-Sep-2026 | 24-Sep-2026 11:03:35 | Pornlert Wanaphattharaphan | 30-Sep-2026 | 26-Sep-2026 05:49:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Oct-2026 | 26-Sep-2026 13:55:01 | 26-Sep-2026 07:30:32 | 0 |  |  | Approver | Locate
AO-000233 | MM-ZTK-1F-GEN-ELE-DTS-0002 | DATASHEET FOR DC DISTRIBUTION BOARDS/PANELS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 16:35:50 | wisuda.c@jutal.com | 28-Apr-2026 08:36:03 | Jumpol Sudjitjul | 07-May-2026 |  | Wichai Salee | 11-May-2026 | 11-May-2026 23:16:45 | Pornlert Wanaphattharaphan | 12-May-2026 | 15-May-2026 00:51:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-May-2026 | 15-May-2026 08:16:02 | 15-May-2026 03:39:20 | 0 |  |  | Approver | Locate
AO-001178 | MM-ZTK-1F-GEN-ELE-DTS-0002 | DATASHEET FOR DC DISTRIBUTION BOARDS/PANELS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 10:39:14 | wisuda.c@jutal.com | 20-Jul-2026 15:03:02 | Jumpol Sudjitjul | 27-Jul-2026 |  | Wichai Salee | 31-Jul-2026 | 06-Aug-2026 21:58:35 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 07-Aug-2026 05:33:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 07-Aug-2026 08:52:50 | 07-Aug-2026 02:06:03 | 0 |  |  | Approver | Locate
AO-002169 | MM-ZTK-1F-GEN-ELE-DTS-0002 | DATASHEET FOR DC DISTRIBUTION BOARDS/PANELS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 19:02:35 | wisuda.c@jutal.com | 20-Sep-2026 12:42:30 | Jumpol Sudjitjul | 25-Sep-2026 |  | Wichai Salee | 29-Sep-2026 | 24-Sep-2026 11:04:32 | Pornlert Wanaphattharaphan | 30-Sep-2026 | 26-Sep-2026 05:49:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Oct-2026 | 26-Sep-2026 13:55:45 | 26-Sep-2026 07:31:51 | 0 |  |  | Approver | Locate
AO-000237 | MM-ZTK-1F-GEN-ELE-DTS-0003 | DATASHEET FOR AC DISTRIBUTION BOARDS/PANELS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 16:36:31 | wisuda.c@jutal.com | 28-Apr-2026 08:36:30 | Jumpol Sudjitjul | 07-May-2026 |  | Wichai Salee | 11-May-2026 | 11-May-2026 23:15:59 | Pornlert Wanaphattharaphan | 12-May-2026 | 15-May-2026 00:47:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-May-2026 | 15-May-2026 10:31:16 | 15-May-2026 03:44:15 | 0 |  |  | Approver | Locate
AO-001222 | MM-ZTK-1F-GEN-ELE-DTS-0003 | DATASHEET FOR AC DISTRIBUTION BOARDS/PANELS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 22-Jul-2026 08:37:40 | wisuda.c@jutal.com | 22-Jul-2026 08:49:03 | Jumpol Sudjitjul | 31-Jul-2026 |  | Wichai Salee | 04-Aug-2026 | 07-Aug-2026 15:09:37 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 07-Aug-2026 21:52:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 08-Aug-2026 10:25:29 | 08-Aug-2026 04:38:07 | 0 |  |  | Approver | Locate
AO-002170 | MM-ZTK-1F-GEN-ELE-DTS-0003 | DATASHEET FOR AC DISTRIBUTION BOARDS/PANELS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 19:03:04 | wisuda.c@jutal.com | 20-Sep-2026 12:42:42 | Jumpol Sudjitjul | 25-Sep-2026 |  | Wichai Salee | 29-Sep-2026 | 24-Sep-2026 11:05:39 | Pornlert Wanaphattharaphan | 30-Sep-2026 | 26-Sep-2026 05:48:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Oct-2026 | 26-Sep-2026 13:56:41 | 26-Sep-2026 07:33:05 | 0 |  |  | Approver | Locate
AO-000258 | MM-ZTK-1F-GEN-ELE-DTS-0004 | DATASHEET FOR NAVIGATION AID, RED LANTERN, FLASHING BEACON AND WARNING SIREN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Review |  | 29-Apr-2026 13:04:51 | wisuda.c@jutal.com | 29-Apr-2026 13:25:26 | Jumpol Sudjitjul | 08-May-2026 |  | Wichai Salee | 12-May-2026 | 14-May-2026 15:20:15 | Pornlert Wanaphattharaphan | 13-May-2026 | 15-May-2026 23:39:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 17-May-2026 08:17:32 | 17-May-2026 01:32:00 | 0 |  |  | Approver | Locate
AO-001251 | MM-ZTK-1F-GEN-ELE-DTS-0004 | DATASHEET FOR NAVIGATION AID, RED LANTERN, FLASHING BEACON AND WARNING SIREN |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 10:48:15 | wisuda.c@jutal.com | 24-Jul-2026 11:29:38 | Jumpol Sudjitjul | 04-Aug-2026 |  | Wichai Salee | 06-Aug-2026 | 07-Aug-2026 15:14:22 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 07-Aug-2026 21:54:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Aug-2026 | 08-Aug-2026 10:24:01 | 08-Aug-2026 03:57:50 | 0 |  |  | Approver | Locate
AO-002180 | MM-ZTK-1F-GEN-ELE-DTS-0004 | DATASHEET FOR NAVIGATION AID, RED LANTERN, FLASHING BEACON AND WARNING SIREN |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 11:11:33 | wisuda.c@jutal.com | 21-Sep-2026 14:23:00 | Jumpol Sudjitjul | 28-Sep-2026 |  | Wichai Salee | 30-Sep-2026 | 24-Sep-2026 16:05:33 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 26-Sep-2026 05:45:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Oct-2026 | 26-Sep-2026 13:57:06 | 26-Sep-2026 07:44:58 | 0 |  |  | Approver | Locate
AO-000495 | MM-ZTK-1F-GEN-ELE-DTS-0005 | DATASHEET FOR ELECTRICAL CABLES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 18-May-2026 08:13:33 | wisuda.c@jutal.com | 18-May-2026 19:45:54 | Jumpol Sudjitjul | 26-May-2026 |  | Wichai Salee | 28-May-2026 | 17-Jun-2026 11:46:50 | Pornlert Wanaphattharaphan | 29-May-2026 | 17-Jun-2026 15:26:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 17-Jun-2026 15:30:52 | 17-Jun-2026 09:08:19 | 0 |  |  | Approver | Locate
AO-001292 | MM-ZTK-1F-GEN-ELE-DTS-0005 | DATASHEET FOR ELECTRICAL CABLES |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:37:50 | wisuda.c@jutal.com | 27-Jul-2026 15:56:50 | Jumpol Sudjitjul | 05-Aug-2026 |  | Wichai Salee | 07-Aug-2026 | 08-Aug-2026 09:18:44 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:48:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 10:52:04 | 13-Aug-2026 04:49:54 | 0 |  |  | Approver | Locate
AO-002355 | MM-ZTK-1F-GEN-ELE-DTS-0005 | DATASHEET FOR ELECTRICAL CABLES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 05-Oct-2026 09:39:22 | wisuda.c@jutal.com | 05-Oct-2026 11:09:06 | Jumpol Sudjitjul | 12-Oct-2026 |  | Wichai Salee | 15-Oct-2026 |  | Pornlert Wanaphattharaphan | 16-Oct-2026 |  |  |  |  | 19-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000280 | MM-ZTK-1F-GEN-ELE-DTS-0006 | DATASHEET FOR ELECTRICAL LIGHTING FIXTURES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 30-Apr-2026 13:21:18 | wisuda.c@jutal.com | 30-Apr-2026 13:56:11 | Jumpol Sudjitjul | 11-May-2026 |  | Wichai Salee | 13-May-2026 | 14-May-2026 11:08:50 | Pornlert Wanaphattharaphan | 14-May-2026 | 20-May-2026 00:47:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 10:49:34 | 20-May-2026 11:19:37 | 0 |  |  | Approver | Locate
AO-001253 | MM-ZTK-1F-GEN-ELE-DTS-0006 | DATASHEET FOR ELECTRICAL LIGHTING FIXTURES |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 10:48:44 | wisuda.c@jutal.com | 24-Jul-2026 11:29:53 | Jumpol Sudjitjul | 04-Aug-2026 |  | Wichai Salee | 06-Aug-2026 | 07-Aug-2026 15:15:35 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 07-Aug-2026 21:55:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Aug-2026 | 08-Aug-2026 10:24:08 | 08-Aug-2026 03:59:09 | 0 |  |  | Approver | Locate
AO-002356 | MM-ZTK-1F-GEN-ELE-DTS-0006 | DATASHEET FOR ELECTRICAL LIGHTING FIXTURES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 05-Oct-2026 09:39:53 | wisuda.c@jutal.com | 05-Oct-2026 11:09:25 | Jumpol Sudjitjul | 12-Oct-2026 |  | Wichai Salee | 15-Oct-2026 |  | Pornlert Wanaphattharaphan | 16-Oct-2026 |  |  |  |  | 19-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000652 | MM-ZTK-1F-GEN-ELE-DTS-0007 | DATASHEET FOR ELECTRICAL BULK MATERIALS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 02-Jun-2026 16:25:54 | wisuda.c@jutal.com | 02-Jun-2026 16:32:21 | Jumpol Sudjitjul | 10-Jun-2026 |  | Wichai Salee | 12-Jun-2026 | 23-Jun-2026 11:16:53 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 23-Jun-2026 23:03:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 24-Jun-2026 13:32:26 | 24-Jun-2026 06:57:29 | 0 |  |  | Approver | Locate
AO-002265 | MM-ZTK-1F-GEN-ELE-DTS-0007 | DATASHEET FOR ELECTRICAL BULK MATERIALS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 25-Sep-2026 16:13:06 | wisuda.c@jutal.com | 25-Sep-2026 17:23:57 | Jumpol Sudjitjul | 05-Oct-2026 |  | Wichai Salee | 07-Oct-2026 | 01-Oct-2026 13:32:10 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 01-Oct-2026 23:19:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 02-Oct-2026 13:15:27 | 02-Oct-2026 06:31:54 | 0 |  |  | Approver | Locate
AO-000496 | MM-ZTK-1F-GEN-ELE-LIS-0001 | ELECTRICAL EQUIPMENT AND CERTIFICATES LIST |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 18-May-2026 08:14:02 | wisuda.c@jutal.com | 18-May-2026 19:48:24 | Jumpol Sudjitjul | 26-May-2026 |  | Wichai Salee | 28-May-2026 | 17-Jun-2026 09:53:56 | Pornlert Wanaphattharaphan | 29-May-2026 | 17-Jun-2026 15:23:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 17-Jun-2026 15:36:27 | 17-Jun-2026 09:09:39 | 0 |  |  | Approver | Locate
AO-002539 | MM-ZTK-1F-GEN-ELE-LIS-0001 | ELECTRICAL EQUIPMENT AND CERTIFICATES LIST |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | In Review | AFC | Approved for Construction |  | 16-Oct-2026 10:52:22 | wisuda.c@jutal.com | 16-Oct-2026 16:56:29 | Jumpol Sudjitjul | 26-Oct-2026 |  | Wichai Salee | 28-Oct-2026 |  | Pornlert Wanaphattharaphan | 29-Oct-2026 |  |  |  |  | 30-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001386 | MM-ZTK-1F-GEN-ELE-LIS-0002 | ELECTRICAL CABLE SCHEDULE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 11:30:17 | wisuda.c@jutal.com | 03-Aug-2026 13:32:44 | Jumpol Sudjitjul | 10-Aug-2026 |  | Wichai Salee | 13-Aug-2026 | 17-Aug-2026 10:53:48 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 20-Aug-2026 22:53:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 21-Aug-2026 10:23:46 | 21-Aug-2026 03:59:29 | 0 |  |  | Approver | Locate
AO-002136 | MM-ZTK-1F-GEN-ELE-LIS-0002 | ELECTRICAL CABLE SCHEDULE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 17-Sep-2026 16:08:34 | wisuda.c@jutal.com | 17-Sep-2026 16:13:52 | Jumpol Sudjitjul | 24-Sep-2026 |  | Wichai Salee | 28-Sep-2026 | 25-Sep-2026 14:45:25 | Pornlert Wanaphattharaphan | 29-Sep-2026 | 26-Sep-2026 05:50:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 30-Sep-2026 | 26-Sep-2026 13:57:40 | 26-Sep-2026 07:46:12 | 0 |  |  | Approver | Locate
AO-001252 | MM-ZTK-1F-GEN-ELE-LIS-0003 | ELECTRICAL CONTROL & INDICATION SCHEDULE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 09:58:59 | wisuda.c@jutal.com | 24-Jul-2026 11:16:42 | Jumpol Sudjitjul | 04-Aug-2026 |  | Wichai Salee | 06-Aug-2026 | 07-Aug-2026 15:13:20 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 07-Aug-2026 21:53:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Aug-2026 | 08-Aug-2026 10:26:13 | 08-Aug-2026 04:23:42 | 0 |  |  | Approver | Locate
AO-002334 | MM-ZTK-1F-GEN-ELE-LIS-0003 | ELECTRICAL CONTROL & INDICATION SCHEDULE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | LIS | List, Index, Schedule, Listing | 0 | In Review | AFC | Approved for Construction |  | 02-Oct-2026 08:39:50 | wisuda.c@jutal.com | 02-Oct-2026 17:44:12 | Jumpol Sudjitjul | 12-Oct-2026 |  | Wichai Salee | 15-Oct-2026 |  | Pornlert Wanaphattharaphan | 16-Oct-2026 |  |  |  |  | 19-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000088 | MM-ZTK-1F-GEN-ELE-MOM-0001 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 08-Apr-2026 15:00:13 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000089 | MM-ZTK-1F-GEN-ELE-MOM-0002 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 08-Apr-2026 13:39:29 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000378 | MM-ZTK-1F-GEN-ELE-MOM-0003 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 12-May-2026 14:17:09 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000378 | MM-ZTK-1F-GEN-ELE-MOM-0004 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 12-May-2026 14:17:42 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000378 | MM-ZTK-1F-GEN-ELE-MOM-0005 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 12-May-2026 14:50:55 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000378 | MM-ZTK-1F-GEN-ELE-MOM-0006 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 12-May-2026 14:51:26 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000407 | MM-ZTK-1F-GEN-ELE-MOM-0007 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 15-May-2026 10:50:43 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000678 | MM-ZTK-1F-GEN-ELE-MOM-0008 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 05-Jun-2026 08:59:31 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000678 | MM-ZTK-1F-GEN-ELE-MOM-0009 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 05-Jun-2026 09:00:10 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000865 | MM-ZTK-1F-GEN-ELE-MOM-0010 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 22-Jun-2026 13:17:34 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000865 | MM-ZTK-1F-GEN-ELE-MOM-0011 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 22-Jun-2026 13:18:19 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001592 | MM-ZTK-1F-GEN-ELE-MOM-0012 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 18-Aug-2026 15:21:43 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001592 | MM-ZTK-1F-GEN-ELE-MOM-0013 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 18-Aug-2026 16:32:39 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001592 | MM-ZTK-1F-GEN-ELE-MOM-0014 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 18-Aug-2026 16:34:58 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001592 | MM-ZTK-1F-GEN-ELE-MOM-0015 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 18-Aug-2026 16:36:41 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002066 | MM-ZTK-1F-GEN-ELE-MOM-0016 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Sep-2026 19:31:12 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002066 | MM-ZTK-1F-GEN-ELE-MOM-0017 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Sep-2026 19:31:42 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002066 | MM-ZTK-1F-GEN-ELE-MOM-0018 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Sep-2026 19:32:09 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002039 | MM-ZTK-1F-GEN-ELE-MOM-0019 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Sep-2026 09:51:13 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002248 | MM-ZTK-1F-GEN-ELE-MOM-0020 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 24-Sep-2026 14:59:50 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002248 | MM-ZTK-1F-GEN-ELE-MOM-0021 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 24-Sep-2026 15:00:30 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002397 | MM-ZTK-1F-GEN-ELE-MOM-0022 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Oct-2026 14:56:18 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000224 | MM-ZTK-1F-GEN-ELE-MR-0001 | MATERIAL REQUISITION FOR SOLAR POWER SYSTEM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 15:28:42 | wisuda.c@jutal.com | 24-Apr-2026 15:49:26 | Jumpol Sudjitjul | 05-May-2026 |  | Wichai Salee | 07-May-2026 | 11-May-2026 16:25:34 | Pornlert Wanaphattharaphan | 08-May-2026 | 11-May-2026 21:12:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 10:21:36 | 12-May-2026 03:42:37 | 0 |  |  | Approver | Locate
AO-001387 | MM-ZTK-1F-GEN-ELE-MR-0001 | MATERIAL REQUISITION FOR SOLAR POWER SYSTEM |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 10:58:21 | wisuda.c@jutal.com | 03-Aug-2026 13:31:11 | Jumpol Sudjitjul | 10-Aug-2026 |  | Wichai Salee | 13-Aug-2026 | 08-Aug-2026 18:56:35 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 10-Aug-2026 00:32:57 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 17:43:15 | 10-Aug-2026 11:03:08 | 0 |  |  | Approver | Locate
AO-000234 | MM-ZTK-1F-GEN-ELE-MR-0002 | MATERIAL REQUISITION FOR DC DISTRIBUTION BOARDS/PANELS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 16:37:09 | wisuda.c@jutal.com | 28-Apr-2026 08:39:18 | Jumpol Sudjitjul | 07-May-2026 |  | Wichai Salee | 11-May-2026 | 11-May-2026 16:26:46 | Pornlert Wanaphattharaphan | 12-May-2026 | 11-May-2026 23:50:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-May-2026 | 12-May-2026 10:25:36 | 12-May-2026 03:43:53 | 0 |  |  | Approver | Locate
AO-001387 | MM-ZTK-1F-GEN-ELE-MR-0002 | MATERIAL REQUISITION FOR DC DISTRIBUTION BOARDS/PANELS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 11:30:47 | wisuda.c@jutal.com | 03-Aug-2026 13:31:29 | Jumpol Sudjitjul | 10-Aug-2026 |  | Wichai Salee | 13-Aug-2026 | 08-Aug-2026 18:56:52 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 12-Aug-2026 21:11:52 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 13-Aug-2026 10:51:27 | 13-Aug-2026 04:48:40 | 0 |  |  | Approver | Locate
AO-000238 | MM-ZTK-1F-GEN-ELE-MR-0003 | MATERIAL REQUISITION FOR AC DISTRIBUTION BOARDS/PANELS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 16:37:54 | wisuda.c@jutal.com | 28-Apr-2026 08:40:00 | Jumpol Sudjitjul | 07-May-2026 |  | Wichai Salee | 11-May-2026 | 11-May-2026 16:27:49 | Pornlert Wanaphattharaphan | 12-May-2026 | 11-May-2026 23:51:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-May-2026 | 12-May-2026 10:27:04 | 12-May-2026 03:45:08 | 0 |  |  | Approver | Locate
AO-001387 | MM-ZTK-1F-GEN-ELE-MR-0003 | MATERIAL REQUISITION FOR AC DISTRIBUTION BOARDS/PANELS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 10:58:48 | wisuda.c@jutal.com | 03-Aug-2026 13:31:52 | Jumpol Sudjitjul | 10-Aug-2026 |  | Wichai Salee | 13-Aug-2026 | 08-Aug-2026 18:57:12 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 12-Aug-2026 21:12:12 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 13-Aug-2026 10:54:44 | 13-Aug-2026 04:52:17 | 0 |  |  | Approver | Locate
AO-000259 | MM-ZTK-1F-GEN-ELE-MR-0004 | MATERIAL REQUISITION FOR NAVIGATION AID, RED LANTERN, FLASHING BEACON, WARNING SIREN AND FOG HORN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 18:30:31 | wisuda.c@jutal.com | 30-Apr-2026 10:14:28 | Jumpol Sudjitjul | 11-May-2026 |  | Wichai Salee | 13-May-2026 | 13-May-2026 10:59:06 | Pornlert Wanaphattharaphan | 14-May-2026 | 15-May-2026 22:29:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 17-May-2026 08:20:04 | 17-May-2026 01:33:17 | 0 |  |  | Approver | Locate
AO-001410 | MM-ZTK-1F-GEN-ELE-MR-0004 | MATERIAL REQUISITION FOR NAVIGATION AID, RED LANTERN, FLASHING BEACON, WARNING SIREN AND FOG HORN |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 04-Aug-2026 10:53:36 | wisuda.c@jutal.com | 04-Aug-2026 11:35:46 | Jumpol Sudjitjul | 11-Aug-2026 |  | Wichai Salee | 14-Aug-2026 | 17-Aug-2026 10:32:26 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 17-Aug-2026 21:09:12 | APPR | Approved | Jumpol Sudjitjul | 18-Aug-2026 | 18-Aug-2026 08:17:39 | 18-Aug-2026 01:35:27 | 0 |  |  | Approver | Locate
AO-000497 | MM-ZTK-1F-GEN-ELE-MR-0005 | MATERIAL REQUISITION FOR ELECTRICAL CABLES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 18-May-2026 08:14:41 | wisuda.c@jutal.com | 18-May-2026 19:49:28 | Jumpol Sudjitjul | 26-May-2026 |  | Wichai Salee | 28-May-2026 | 15-Jun-2026 10:54:22 | Pornlert Wanaphattharaphan | 29-May-2026 | 15-Jun-2026 22:15:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 16-Jun-2026 09:40:41 | 16-Jun-2026 03:44:20 | 0 |  |  | Approver | Locate
AO-002266 | MM-ZTK-1F-GEN-ELE-MR-0005 | MATERIAL REQUISITION FOR ELECTRICAL CABLES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 25-Sep-2026 16:13:34 | wisuda.c@jutal.com | 25-Sep-2026 16:25:14 | Jumpol Sudjitjul | 02-Oct-2026 |  | Wichai Salee | 06-Oct-2026 | 26-Sep-2026 14:56:29 | Pornlert Wanaphattharaphan | 07-Oct-2026 | 28-Sep-2026 22:59:08 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 29-Sep-2026 13:46:03 | 29-Sep-2026 07:00:29 | 0 |  |  | Approver | Locate
AO-000281 | MM-ZTK-1F-GEN-ELE-MR-0006 | MATERIAL REQUISITION FOR ELECTRICAL LIGHTING FIXTURES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 30-Apr-2026 13:21:43 | wisuda.c@jutal.com | 30-Apr-2026 13:58:32 | Jumpol Sudjitjul | 11-May-2026 |  | Wichai Salee | 13-May-2026 | 14-May-2026 11:08:01 | Pornlert Wanaphattharaphan | 14-May-2026 | 15-May-2026 22:30:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 17-May-2026 08:22:10 | 17-May-2026 01:35:49 | 0 |  |  | Approver | Locate
AO-001446 | MM-ZTK-1F-GEN-ELE-MR-0006 | MATERIAL REQUISITION FOR ELECTRICAL LIGHTING FIXTURES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 14:09:10 | wisuda.c@jutal.com | 07-Aug-2026 14:29:54 | Jumpol Sudjitjul | 17-Aug-2026 |  | Wichai Salee | 19-Aug-2026 | 09-Aug-2026 18:53:06 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 17-Aug-2026 00:06:03 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 17-Aug-2026 09:51:40 | 17-Aug-2026 03:23:58 | 0 |  |  | Approver | Locate
AO-000839 | MM-ZTK-1F-GEN-ELE-MR-0007 | MATERIAL REQUISITION FOR CABLE LADDER/TRAY |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 22:41:13 | wisuda.c@jutal.com | 22-Jun-2026 14:03:49 | Jumpol Sudjitjul | 29-Jun-2026 |  | Wichai Salee | 01-Jul-2026 | 07-Jul-2026 11:32:36 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 07-Jul-2026 23:54:33 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 03-Jul-2026 | 08-Jul-2026 09:40:31 | 08-Jul-2026 03:30:59 | 0 |  |  | Approver | Locate
AO-002266 | MM-ZTK-1F-GEN-ELE-MR-0007 | MATERIAL REQUISITION FOR CABLE LADDER/TRAY |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 25-Sep-2026 16:14:03 | wisuda.c@jutal.com | 25-Sep-2026 16:25:35 | Jumpol Sudjitjul | 02-Oct-2026 |  | Wichai Salee | 06-Oct-2026 | 26-Sep-2026 14:59:42 | Pornlert Wanaphattharaphan | 07-Oct-2026 | 28-Sep-2026 22:59:34 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 29-Sep-2026 13:47:02 | 29-Sep-2026 07:01:46 | 0 |  |  | Approver | Locate
AO-000749 | MM-ZTK-1F-GEN-ELE-MR-0008 | MATERIAL REQUISITION FOR MULTI-CABLE TRANSITS (MCT) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 12-Jun-2026 08:40:46 | wisuda.c@jutal.com | 12-Jun-2026 14:47:34 | Jumpol Sudjitjul | 19-Jun-2026 |  | Wichai Salee | 23-Jun-2026 | 26-Jun-2026 15:42:56 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 28-Jun-2026 08:46:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 28-Jun-2026 08:50:25 | 28-Jun-2026 02:16:11 | 0 |  |  | Approver | Locate
AO-002266 | MM-ZTK-1F-GEN-ELE-MR-0008 | MATERIAL REQUISITION FOR MULTI-CABLE TRANSITS (MCT) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 25-Sep-2026 16:14:45 | wisuda.c@jutal.com | 25-Sep-2026 16:25:54 | Jumpol Sudjitjul | 02-Oct-2026 |  | Wichai Salee | 06-Oct-2026 | 26-Sep-2026 15:02:35 | Pornlert Wanaphattharaphan | 07-Oct-2026 | 28-Sep-2026 23:00:05 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 29-Sep-2026 13:55:41 | 29-Sep-2026 08:19:24 | 0 |  |  | Approver | Locate
AO-000831 | MM-ZTK-1F-GEN-ELE-MR-0009 | MATERIAL REQUISITION FOR POWER SOCKET/PLUG, JUNCTION BOXES, EARH BAR AND CABLE GLAND |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 15:58:44 | wisuda.c@jutal.com | 18-Jun-2026 17:33:15 | Jumpol Sudjitjul | 26-Jun-2026 |  | Wichai Salee | 30-Jun-2026 | 03-Jul-2026 14:20:24 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 04-Jul-2026 15:58:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 05-Jul-2026 10:37:20 | 05-Jul-2026 03:56:28 | 0 |  |  | Approver | Locate
AO-002279 | MM-ZTK-1F-GEN-ELE-MR-0009 | MATERIAL REQUISITION FOR POWER SOCKET/PLUG, JUNCTION BOXES, EARH BAR AND CABLE GLAND |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 09:52:45 | wisuda.c@jutal.com | 28-Sep-2026 11:25:04 | Jumpol Sudjitjul | 05-Oct-2026 |  | Wichai Salee | 07-Oct-2026 | 01-Oct-2026 12:57:58 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 01-Oct-2026 23:18:44 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 02-Oct-2026 13:16:57 | 02-Oct-2026 06:57:49 | 0 |  |  | Approver | Locate
AO-002179 | MM-ZTK-1F-GEN-ELE-MTO-0001 | ELECTRICAL BULK MATERIAL TAKE-OFF |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 21-Sep-2026 11:12:00 | wisuda.c@jutal.com | 21-Sep-2026 14:27:38 | Jumpol Sudjitjul | 28-Sep-2026 | 24-Sep-2026 15:53:34 | Wichai Salee | 30-Sep-2026 | 28-Sep-2026 20:25:41 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 28-Sep-2026 22:51:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Oct-2026 | 29-Sep-2026 14:00:48 | 29-Sep-2026 08:11:07 | 0 |  |  | Approver | Locate
AO-002556 | MM-ZTK-1F-GEN-ELE-MTO-0001 | ELECTRICAL BULK MATERIAL TAKE-OFF |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | MTO | Material Take Off | 0 | In Review | IFA | Issued for Approval |  | 16-Oct-2026 17:36:44 | wisuda.c@jutal.com | 18-Oct-2026 16:40:11 | Jumpol Sudjitjul | 26-Oct-2026 |  | Wichai Salee | 28-Oct-2026 |  | Pornlert Wanaphattharaphan | 29-Oct-2026 |  |  |  |  | 30-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000248 | MM-ZTK-1F-GEN-ELE-RPT-0001 | SOLAR POWER SYSTEM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:46:11 | zm169dc@jutal.com | 29-Apr-2026 09:34:32 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 18:21:30 |  |  | 06-May-2026 16:42:58 |  |  | Jumpol Sudjitjul |  | 06-May-2026 17:40:27 | 27-Apr-2026 15:10:42 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-ELE-RPT-0002 | DC DISTRIBUTION BOARDS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:46:40 | zm169dc@jutal.com | 29-Apr-2026 09:34:44 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 18:20:29 |  |  | 06-May-2026 16:42:34 |  |  | Jumpol Sudjitjul |  | 07-May-2026 08:09:49 | 27-Apr-2026 15:11:07 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-ELE-RPT-0003 | AC DISTRIBUTION BOARDS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:47:05 | zm169dc@jutal.com | 29-Apr-2026 09:35:01 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 18:18:31 |  |  | 06-May-2026 16:41:06 |  |  | Jumpol Sudjitjul |  | 07-May-2026 08:10:43 | 27-Apr-2026 15:11:30 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-ELE-RPT-0004 | NAVIGATION AID, RED LANTERN, FLASHING BEACON, WARNING SIREN AND FOG HORN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:47:31 | zm169dc@jutal.com | 29-Apr-2026 09:35:12 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 18:17:34 |  |  | 06-May-2026 16:40:38 |  |  | Jumpol Sudjitjul |  | 07-May-2026 08:14:59 | 27-Apr-2026 15:11:55 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-ELE-RPT-0005 | EL CABLE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:47:57 | zm169dc@jutal.com | 29-Apr-2026 09:37:28 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 18:16:37 |  |  | 06-May-2026 16:39:20 |  |  | Jumpol Sudjitjul |  | 07-May-2026 08:14:24 | 27-Apr-2026 15:12:20 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-ELE-RPT-0006 | CABLE GLAND |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:48:26 | zm169dc@jutal.com | 29-Apr-2026 09:37:42 | Jumpol Sudjitjul |  |  |  |  | 30-Apr-2026 14:58:20 |  |  | 06-May-2026 16:35:33 |  |  | Jumpol Sudjitjul |  | 06-May-2026 16:38:14 | 27-Apr-2026 15:12:43 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-ELE-RPT-0007 | ELECTRICAL LIGHTING FIXTURES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:48:55 | zm169dc@jutal.com | 29-Apr-2026 09:38:04 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 18:14:13 |  |  | 06-May-2026 16:37:45 |  |  | Jumpol Sudjitjul |  | 06-May-2026 16:39:11 | 27-Apr-2026 15:13:09 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-ELE-RPT-0008 | EL CABLE TRAY |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:49:21 | zm169dc@jutal.com | 29-Apr-2026 09:37:41 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 18:15:22 |  |  | 06-May-2026 16:38:32 |  |  | Jumpol Sudjitjul |  | 06-May-2026 16:41:32 | 27-Apr-2026 15:13:32 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-ELE-RPT-0009 | MULTI-CABLE TRANSITS (MCT) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:49:47 | zm169dc@jutal.com | 29-Apr-2026 09:38:04 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 18:06:33 |  |  | 06-May-2026 16:37:03 |  |  | Jumpol Sudjitjul |  | 07-May-2026 08:13:18 | 27-Apr-2026 15:13:55 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-ELE-RPT-0010 | POWER SOCKET/PLUG, JUNCTION BOXES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:50:15 | zm169dc@jutal.com | 29-Apr-2026 09:38:30 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 18:05:01 |  |  | 06-May-2026 16:36:31 |  |  | Jumpol Sudjitjul |  | 07-May-2026 08:12:37 | 27-Apr-2026 15:14:19 | 0 |  |  |  | Locate
AO-000529 | MM-ZTK-1F-GEN-ELE-RPT-0100 | CRITICALITY RATING ANALYSIS (ELECTRICAL) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 15:08:05 | zm169dc@jutal.com | 20-May-2026 16:16:16 | Jumpol Sudjitjul | 27-May-2026 |  | Wichai Salee | 29-May-2026 | 15-Jun-2026 09:48:55 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 15-Jun-2026 22:51:57 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 04-Jun-2026 | 16-Jun-2026 09:39:21 | 16-Jun-2026 03:35:14 | 0 |  |  | Approver | Locate
AO-001209 | MM-ZTK-1F-GEN-ELE-RPT-0100 | CRITICALITY RATING ANALYSIS (ELECTRICAL) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 17:39:19 | zm169dc@jutal.com | 21-Jul-2026 07:46:00 | Jumpol Sudjitjul | 30-Jul-2026 |  | Wichai Salee | 03-Aug-2026 | 07-Aug-2026 13:59:49 | Pornlert Wanaphattharaphan | 04-Aug-2026 | 07-Aug-2026 21:52:06 | APPR | Approved | Jumpol Sudjitjul | 05-Aug-2026 | 08-Aug-2026 10:16:00 | 08-Aug-2026 03:27:59 | 0 |  |  | Approver | Locate
AO-000225 | MM-ZTK-1F-GEN-ELE-SPE-0001 | PROJECT SPECIFICATION FOR SOLAR POWER SYSTEM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 15:29:12 | wisuda.c@jutal.com | 24-Apr-2026 15:47:40 | Jumpol Sudjitjul | 05-May-2026 |  | Wichai Salee | 07-May-2026 | 11-May-2026 23:17:32 | Pornlert Wanaphattharaphan | 08-May-2026 | 11-May-2026 23:52:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 10:27:57 | 12-May-2026 03:46:24 | 0 |  |  | Approver | Locate
AO-001372 | MM-ZTK-1F-GEN-ELE-SPE-0001 | PROJECT SPECIFICATION FOR SOLAR POWER SYSTEM |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 10:19:28 | wisuda.c@jutal.com | 03-Aug-2026 13:29:01 | Jumpol Sudjitjul | 10-Aug-2026 |  | Wichai Salee | 13-Aug-2026 | 07-Aug-2026 18:02:12 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 23:05:43 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 09:52:07 | 17-Aug-2026 03:42:10 | 0 |  |  | Approver | Locate
AO-000232 | MM-ZTK-1F-GEN-ELE-SPE-0002 | PROJECT SPECIFICATION FOR DC DISTRIBUTION BOARDS/PANELS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 16:38:36 | wisuda.c@jutal.com | 28-Apr-2026 08:43:11 | Jumpol Sudjitjul | 07-May-2026 |  | Wichai Salee | 11-May-2026 | 11-May-2026 23:15:10 | Pornlert Wanaphattharaphan | 12-May-2026 | 15-May-2026 00:43:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-May-2026 | 15-May-2026 10:33:17 | 15-May-2026 04:18:52 | 0 |  |  | Approver | Locate
AO-001372 | MM-ZTK-1F-GEN-ELE-SPE-0002 | PROJECT SPECIFICATION FOR DC DISTRIBUTION BOARDS/PANELS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 10:20:19 | wisuda.c@jutal.com | 03-Aug-2026 13:29:16 | Jumpol Sudjitjul | 10-Aug-2026 |  | Wichai Salee | 13-Aug-2026 | 07-Aug-2026 18:03:10 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 23:06:11 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 11:06:10 | 17-Aug-2026 05:14:22 | 0 |  |  | Approver | Locate
AO-000240 | MM-ZTK-1F-GEN-ELE-SPE-0003 | PROJECT SPECIFICATION FOR AC DISTRIBUTION BOARDS/PANELS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 17:17:29 | wisuda.c@jutal.com | 28-Apr-2026 08:43:44 | Jumpol Sudjitjul | 07-May-2026 |  | Wichai Salee | 11-May-2026 | 11-May-2026 23:14:14 | Pornlert Wanaphattharaphan | 12-May-2026 | 15-May-2026 00:42:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-May-2026 | 15-May-2026 10:35:14 | 15-May-2026 04:20:06 | 0 |  |  | Approver | Locate
AO-001372 | MM-ZTK-1F-GEN-ELE-SPE-0003 | PROJECT SPECIFICATION FOR AC DISTRIBUTION BOARDS/PANELS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 10:59:24 | wisuda.c@jutal.com | 03-Aug-2026 13:29:30 | Jumpol Sudjitjul | 10-Aug-2026 |  | Wichai Salee | 13-Aug-2026 | 07-Aug-2026 18:03:26 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 23:06:48 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 10:53:43 | 17-Aug-2026 04:19:43 | 0 |  |  | Approver | Locate
AO-000260 | MM-ZTK-1F-GEN-ELE-SPE-0004 | PROJECT SPECIFICATION FOR NAVIGATION AID, RED LANTERN, FLASHING BEACON, WARNING SIREN AND FOG HORN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 18:31:01 | wisuda.c@jutal.com | 30-Apr-2026 10:13:19 | Jumpol Sudjitjul | 11-May-2026 |  | Wichai Salee | 13-May-2026 | 16-May-2026 01:17:19 | Pornlert Wanaphattharaphan | 14-May-2026 | 20-May-2026 00:46:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 10:59:46 | 20-May-2026 04:28:03 | 0 |  |  | Approver | Locate
AO-001372 | MM-ZTK-1F-GEN-ELE-SPE-0004 | PROJECT SPECIFICATION FOR NAVIGATION AID, RED LANTERN, FLASHING BEACON, WARNING SIREN AND FOG HORN |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 10:59:51 | wisuda.c@jutal.com | 03-Aug-2026 13:29:43 | Jumpol Sudjitjul | 10-Aug-2026 |  | Wichai Salee | 13-Aug-2026 | 08-Aug-2026 22:05:12 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 23:07:17 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 11:06:58 | 17-Aug-2026 05:15:34 | 0 |  |  | Approver | Locate
AO-000282 | MM-ZTK-1F-GEN-ELE-SPE-0005 | PROJECT SPECIFICATION FOR ELECTRICAL BULK MATERIALS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 30-Apr-2026 13:22:10 | wisuda.c@jutal.com | 30-Apr-2026 13:57:20 | Jumpol Sudjitjul | 11-May-2026 |  | Wichai Salee | 13-May-2026 | 16-May-2026 20:40:12 | Pornlert Wanaphattharaphan | 14-May-2026 | 20-May-2026 00:47:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 11:03:28 | 20-May-2026 04:20:49 | 0 |  |  | Approver | Locate
AO-001677 | MM-ZTK-1F-GEN-ELE-SPE-0005 | PROJECT SPECIFICATION FOR ELECTRICAL BULK MATERIALS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 10:02:20 | wisuda.c@jutal.com | 25-Aug-2026 13:03:10 | Jumpol Sudjitjul | 01-Sep-2026 |  | Wichai Salee | 03-Sep-2026 | 28-Aug-2026 13:50:35 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 23:00:51 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 15:42:29 | 31-Aug-2026 09:50:59 | 0 |  |  | Approver | Locate
AO-000975 | MM-ZTK-1F-GEN-ELE-TBE-0001 | TECHNICAL BID EVALUATION FOR SOLAR POWER SYSTEM |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 02-Jul-2026 09:55:45 | wisuda.c@jutal.com | 02-Jul-2026 14:02:13 | Jumpol Sudjitjul | 09-Jul-2026 |  | Wichai Salee | 13-Jul-2026 | 03-Jul-2026 14:04:14 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 04-Jul-2026 20:50:13 | APPR | Approved | Jumpol Sudjitjul | 15-Jul-2026 | 05-Jul-2026 10:38:17 | 05-Jul-2026 04:19:12 | 0 |  |  | Approver | Locate
AO-001028 | MM-ZTK-1F-GEN-ELE-TBE-0002 | TECHNICAL BID EVALUATION FOR DC DISTRIBUTION BOARDS/ PANELS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 07-Jul-2026 11:34:55 | wisuda.c@jutal.com | 07-Jul-2026 11:55:23 | Jumpol Sudjitjul | 14-Jul-2026 |  | Wichai Salee | 16-Jul-2026 | 08-Jul-2026 13:18:37 | Pornlert Wanaphattharaphan | 17-Jul-2026 | 08-Jul-2026 17:26:01 | APPR | Approved | Jumpol Sudjitjul | 20-Jul-2026 | 08-Jul-2026 19:43:56 | 08-Jul-2026 13:26:21 | 0 |  |  | Approver | Locate
AO-001029 | MM-ZTK-1F-GEN-ELE-TBE-0003 | TECHNICAL BID EVALUATION FOR AC DISTRIBUTION BOARDS/ PANELS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 07-Jul-2026 11:35:32 | wisuda.c@jutal.com | 10-Jul-2026 20:36:03 | Jumpol Sudjitjul | 20-Jul-2026 |  | Wichai Salee | 22-Jul-2026 | 12-Jul-2026 22:36:07 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 12-Jul-2026 23:22:49 | APPR | Approved | Jumpol Sudjitjul | 24-Jul-2026 | 13-Jul-2026 08:09:22 | 13-Jul-2026 01:28:03 | 0 |  |  | Approver | Locate
AO-001072 | MM-ZTK-1F-GEN-ELE-TBE-0004 | TECHNICAL BID EVALUATION FOR NAVIGATION AID, RED LANTERN, FLASHING BEACON, WARNING SIREN AND FOG HORN |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 10-Jul-2026 18:46:29 | wisuda.c@jutal.com | 10-Jul-2026 20:35:47 | Jumpol Sudjitjul | 20-Jul-2026 |  | Wichai Salee | 22-Jul-2026 | 12-Jul-2026 22:34:58 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 12-Jul-2026 23:14:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 13-Jul-2026 08:10:09 | 13-Jul-2026 01:20:42 | 0 |  |  | Approver | Locate
AO-001270 | MM-ZTK-1F-GEN-ELE-TBE-0004 | TECHNICAL BID EVALUATION FOR NAVIGATION AID, RED LANTERN, FLASHING BEACON, WARNING SIREN AND FOG HORN |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 24-Jul-2026 17:37:11 | wisuda.c@jutal.com | 26-Jul-2026 23:49:46 | Jumpol Sudjitjul | 05-Aug-2026 |  | Wichai Salee | 07-Aug-2026 | 01-Aug-2026 22:00:48 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 02-Aug-2026 16:29:07 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 02-Aug-2026 21:13:09 | 02-Aug-2026 14:53:13 | 0 |  |  | Approver | Locate
AO-002289 | MM-ZTK-1F-GEN-ELE-TBE-0005 | TECHNICAL BID EVALUATION FOR ELECTRICAL CABLES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 28-Sep-2026 08:37:00 | wisuda.c@jutal.com | 28-Sep-2026 13:22:06 | Jumpol Sudjitjul | 05-Oct-2026 |  | Wichai Salee | 07-Oct-2026 | 06-Oct-2026 12:09:52 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 07-Oct-2026 00:44:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 07-Oct-2026 08:14:01 | 07-Oct-2026 01:48:29 | 0 |  |  | Approver | Locate
AO-001424 | MM-ZTK-1F-GEN-ELE-TBE-0006 | TECHNICAL BID EVALUATION FOR ELECTRICAL LIGHTING FIXTURES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | ELE | Electrical | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 05-Aug-2026 16:09:35 | wisuda.c@jutal.com | 05-Aug-2026 16:13:08 | Jumpol Sudjitjul | 13-Aug-2026 |  | Wichai Salee | 17-Aug-2026 | 07-Aug-2026 18:01:32 | Pornlert Wanaphattharaphan | 18-Aug-2026 | 07-Aug-2026 20:50:49 | APPR | Approved | Jumpol Sudjitjul | 19-Aug-2026 | 08-Aug-2026 10:16:42 | 08-Aug-2026 03:55:22 | 0 |  |  | Approver | Locate
AO-000635 | MM-ZTK-1F-GEN-ENG-BOD-0001 | PROJECT BASIS OF DESIGN |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | BOD | Basis of Design | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 20:51:12 | wisuda.c@jutal.com | 31-May-2026 21:00:58 | Jumpol Sudjitjul | 10-Jun-2026 | 11-Jun-2026 08:18:38 | Prin Jitatisil | 12-Jun-2026 | 15-Jun-2026 14:09:53 |  |  |  | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 16-Jun-2026 | 15-Jun-2026 14:11:37 | 15-Jun-2026 07:51:52 | 0 |  |  | Focal Point | Locate
AO-001873 | MM-ZTK-1F-GEN-ENG-BOD-0001 | PROJECT BASIS OF DESIGN |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 04-Sep-2026 12:41:09 | wisuda.c@jutal.com | 05-Sep-2026 19:49:24 | Jumpol Sudjitjul | 14-Sep-2026 | 16-Sep-2026 13:48:00 | Prin Jitatisil | 16-Sep-2026 | 18-Sep-2026 10:07:13 |  |  |  | APPR | Approved | Jumpol Sudjitjul | 18-Sep-2026 | 18-Sep-2026 19:00:11 | 18-Sep-2026 13:00:49 | 0 |  |  | Focal Point | Locate
AO-000057 | MM-ZTK-1F-GEN-ENG-MOM-0001 | WHP TOPSIDE DETAIL ENGINEERING DESIGN WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 31-Mar-2026 16:50:43 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000058 | MM-ZTK-1F-GEN-ENG-MOM-0002 | WHP TOPSIDE DETAIL ENGINEERING DESIGN 2ND WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 31-Mar-2026 16:51:08 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000062 | MM-ZTK-1F-GEN-ENG-MOM-0003 | WHP TOPSIDE DETAIL ENGINEERING DESIGN 3RD WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 02-Apr-2026 12:54:04 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000145 | MM-ZTK-1F-GEN-ENG-MOM-0004 | WHP TOPSIDE DETAIL ENGINEERING DESIGN 4TH WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 17-Apr-2026 15:28:04 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000228 | MM-ZTK-1F-GEN-ENG-MOM-0005 | WHP TOPSIDE DETAIL ENGINEERING DESIGN 5TH WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 27-Apr-2026 10:32:39 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000334 | MM-ZTK-1F-GEN-ENG-MOM-0006 | WHP TOPSIDE DETAILED ENGINEERING DESIGN: 6TH WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-May-2026 16:37:01 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000337 | MM-ZTK-1F-GEN-ENG-MOM-0007 | WHP TOPSIDE DETAILED ENGINEERING DESIGN: 7TH WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 07-May-2026 10:37:40 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000505 | MM-ZTK-1F-GEN-ENG-MOM-0008 | WHP TOPSIDE DETAILED ENGINEERING DESIGN: 8TH WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 19-May-2026 10:11:37 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000603 | MM-ZTK-1F-GEN-ENG-MOM-0009 | WHP TOPSIDE DETAILED ENGINEERING DESIGN: 9TH WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 26-May-2026 14:14:56 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000642 | MM-ZTK-1F-GEN-ENG-MOM-0010 | WHP TOPSIDE DETAILED ENGINEERING DESIGN: 10TH WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 01-Jun-2026 22:33:16 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000730 | MM-ZTK-1F-GEN-ENG-MOM-0011 | WHP TOPSIDE DETAILED ENGINEERING DESIGN: 11TH WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 10-Jun-2026 09:23:14 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000865 | MM-ZTK-1F-GEN-ENG-MOM-0012 | WHP TOPSIDE DETAILED ENGINEERING DESIGN: 12TH WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 22-Jun-2026 13:19:19 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000865 | MM-ZTK-1F-GEN-ENG-MOM-0013 | WHP TOPSIDE DETAILED ENGINEERING DESIGN: 13TH WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 22-Jun-2026 13:20:21 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000958 | MM-ZTK-1F-GEN-ENG-MOM-0014 | WHP TOPSIDE DETAILED ENGINEERING DESIGN: 14TH WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 30-Jun-2026 15:58:54 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001100 | MM-ZTK-1F-GEN-ENG-MOM-0015 | WHP TOPSIDE DETAILED ENGINEERING DESIGN: 15TH WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Jul-2026 09:48:42 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001211 | MM-ZTK-1F-GEN-ENG-MOM-0016 | WHP TOPSIDE DETAILED ENGINEERING DESIGN: 16TH WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 21-Jul-2026 08:37:12 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001504 | MM-ZTK-1F-GEN-ENG-MOM-0017 | WHP TOPSIDE DETAILED ENGINEERING DESIGN: 17TH WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 11-Aug-2026 10:45:15 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001511 | MM-ZTK-1F-GEN-ENG-MOM-0018 | WHP TOPSIDE DETAILED ENGINEERING DESIGN: 18TH WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 13-Aug-2026 08:57:28 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001574 | MM-ZTK-1F-GEN-ENG-MOM-0019 | WHP TOPSIDE DETAILED ENGINEERING DESIGN: 19TH WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 17-Aug-2026 17:18:06 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001744 | MM-ZTK-1F-GEN-ENG-MOM-0020 | WHP TOPSIDE DETAILED ENGINEERING DESIGN: 19TH WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 27-Aug-2026 19:05:18 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001805 | MM-ZTK-1F-GEN-ENG-MOM-0021 | WHP TOPSIDE DETAILED ENGINEERING DESIGN: 19TH WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 01-Sep-2026 10:15:14 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002109 | MM-ZTK-1F-GEN-ENG-MOM-0022 | WHP TOPSIDE DETAILED ENGINEERING DESIGN: 22TH WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 17-Sep-2026 10:38:40 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002109 | MM-ZTK-1F-GEN-ENG-MOM-0023 | WHP TOPSIDE DETAILED ENGINEERING DESIGN: 23TH WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 17-Sep-2026 10:39:24 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002123 | MM-ZTK-1F-GEN-ENG-MOM-0024 | WHP TOPSIDE DETAILED ENGINEERING DESIGN: 24TH WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 17-Sep-2026 13:35:03 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002402 | MM-ZTK-1F-GEN-ENG-MOM-0101 | WHP TOPSIDE DETAILED ENGINEERING DESIGN: 30% 3D MODEL REVIEW WORKSHOP |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Oct-2026 17:55:06 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001511 | MM-ZTK-1F-GEN-ENG-MOM-0102 | WHP TOPSIDE DETAILED ENGINEERING DESIGN: 60% 3D MODEL REVIEW WORKSHOP |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 13-Aug-2026 08:58:06 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002403 | MM-ZTK-1F-GEN-ENG-MOM-0103 | WHP TOPSIDE DETAILED ENGINEERING DESIGN: 90% 3D MODEL REVIEW WORKSHOP |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Oct-2026 17:55:36 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000024 | MM-ZTK-1F-GEN-ENG-MOM-5001 | WHP TOPSIDE DETAIL ENGINEERING DESIGN WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 19-Mar-2026 09:55:46 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000044 | MM-ZTK-1F-GEN-ENG-MOM-5002 | WHP TOPSIDE DETAIL ENGINEERING DESIGN 2ND WEEKLY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 26-Mar-2026 15:14:39 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000047 | MM-ZTK-1F-GEN-ENG-PLN-0001 | ENGINEERING EXECUTION PLAN |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 26-Mar-2026 16:29:41 | zm169dc@jutal.com | 26-Mar-2026 16:59:22 | Jumpol Sudjitjul | 02-Apr-2026 | 02-Apr-2026 10:37:44 | Pornlert Wanaphattharaphan | 07-Apr-2026 | 05-Apr-2026 18:37:26 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Apr-2026 | 06-Apr-2026 06:57:46 | 06-Apr-2026 07:06:54 | 0 |  |  | Focal Point | Locate
AO-000718 | MM-ZTK-1F-GEN-ENG-PLN-0001 | ENGINEERING EXECUTION PLAN |  | X | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | PLN | Plan | 0 | In Review | VOID | Withdrawn or Superseded |  | 09-Jun-2026 13:12:56 | zm169dc@jutal.com | 09-Jun-2026 13:36:38 | Jumpol Sudjitjul |  | 17-Oct-2026 17:52:13 | Pornlert Wanaphattharaphan | [11 empty] | 0 |  |  | For Info | Locate
AO-000410 | MM-ZTK-1F-GEN-ENG-PLN-0010 | ENGINEERING EXECUTION PLAN (WORK PACKAGE 1) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 10:52:11 | wisuda.c@jutal.com | 15-May-2026 18:13:34 | Jumpol Sudjitjul | 25-May-2026 | 04-Jun-2026 07:06:52 | Pornlert Wanaphattharaphan | 27-May-2026 | 04-Jun-2026 23:03:22 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 05-Jun-2026 07:39:58 | 05-Jun-2026 00:51:01 | 0 |  |  | Focal Point | Locate
AO-000870 | MM-ZTK-1F-GEN-ENG-PLN-0010 | ENGINEERING EXECUTION PLAN (WORK PACKAGE 1) |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | PLN | Plan | 0 | Submitted | IFA | Issued for Approval |  | 23-Jun-2026 11:32:03 | wisuda.c@jutal.com | 23-Jun-2026 12:41:18 | Jumpol Sudjitjul | 30-Jun-2026 | 06-Jul-2026 22:12:16 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 08-Jul-2026 00:12:58 |  |  |  | APPR | Approved | Jumpol Sudjitjul | 06-Jul-2026 | 08-Jul-2026 09:41:25 | 08-Jul-2026 03:18:19 | 0 |  |  | Focal Point | Locate
AO-001069 | MM-ZTK-1F-GEN-ENG-PLN-0010 | ENGINEERING EXECUTION PLAN (WORK PACKAGE 1) |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 18:46:56 | wisuda.c@jutal.com | 10-Jul-2026 20:28:39 | Jumpol Sudjitjul | 20-Jul-2026 | 15-Jul-2026 17:53:30 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 16-Jul-2026 10:07:15 |  |  |  | APPR | Approved | Jumpol Sudjitjul | 24-Jul-2026 | 16-Jul-2026 11:03:34 | 16-Jul-2026 04:20:11 | 0 |  |  | Focal Point | Locate
AO-000007 | MM-ZTK-1F-GEN-ENG-PLN-3001 | ENGINEERING EXECUTION PLAN (PIPELINE) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 04-Mar-2026 12:01:10 | 26002z1fdcc@thoresen-jutal.com | 04-Mar-2026 13:09:37 | Jumpol Sudjitjul | 11-Mar-2026 | 10-Mar-2026 13:22:15 | Pornlert Wanaphattharaphan | 13-Mar-2026 | 11-Mar-2026 13:32:26 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Mar-2026 | 25-Mar-2026 08:32:15 | 25-Mar-2026 01:49:59 | 0 |  |  | Focal Point | Locate
AO-000052 | MM-ZTK-1F-GEN-ENG-PLN-8001 | ENGINEERING EXECUTION PLAN (T&I PLATFORMS) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 31-Mar-2026 08:55:44 | kjb@coes.cn | 31-Mar-2026 09:55:47 | Jumpol Sudjitjul | 08-Apr-2026 | 03-Apr-2026 09:53:12 | Sukit Nualchanchai | 10-Apr-2026 | 03-Apr-2026 17:50:10 | Prin Jitatisil | 16-Apr-2026 | 06-Apr-2026 17:34:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Apr-2026 | 06-Apr-2026 21:35:11 | 06-Apr-2026 21:56:17 | 0 |  |  | Approver | Locate
AO-000499 | MM-ZTK-1F-GEN-ENG-PLN-8001 | ENGINEERING EXECUTION PLAN (T&I PLATFORMS) |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | PLN | Plan | 0 | Submitted | IFA | Issued for Approval | 23-Apr-2026 | 18-May-2026 19:37:25 | kjb@coes.cn | 18-May-2026 20:14:49 | Jumpol Sudjitjul | 26-May-2026 |  | Sukit Nualchanchai | 28-May-2026 | 19-May-2026 13:48:13 | Prin Jitatisil | 29-May-2026 | 27-May-2026 08:59:56 | APPR | Approved | Jumpol Sudjitjul | 02-Jun-2026 | 27-May-2026 10:36:51 | 27-May-2026 11:05:28 | 0 |  |  | Approver | Locate
AO-000813 | MM-ZTK-1F-GEN-ENG-PLN-8001 | ENGINEERING EXECUTION PLAN (T&I PLATFORMS) |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 16-Jun-2026 10:09:49 | kjb@coes.cn | 16-Jun-2026 11:03:49 | Jumpol Sudjitjul | 23-Jun-2026 | 16-Jun-2026 11:23:03 | Sukit Nualchanchai | 25-Jun-2026 | 17-Jun-2026 16:11:03 | Jumpol Sudjitjul | 26-Jun-2026 | 18-Jun-2026 09:35:22 | APPR | Approved | Jumpol Sudjitjul | 29-Jun-2026 | 18-Jun-2026 09:37:17 | 18-Jun-2026 02:45:52 | 0 |  |  | Approver | Locate
AO-000112 | MM-ZTK-1F-GEN-ENG-PLN-9001 | ENGINEERING EXECUTION PLAN (PIPELINE) |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | PLN | Plan | 0 | Submitted | IFA | Issued for Approval |  | 10-Apr-2026 16:35:00 | 26002z1fdcc@thoresen-jutal.com | 10-Apr-2026 17:07:46 | Jumpol Sudjitjul | 23-Apr-2026 | 07-May-2026 15:00:27 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 09-May-2026 00:25:37 |  |  |  | APPR | Approved | Jumpol Sudjitjul | 29-Apr-2026 | 09-May-2026 08:06:15 | 09-May-2026 08:32:51 | 0 |  |  | Focal Point | Locate
AO-000566 | MM-ZTK-1F-GEN-ENG-PLN-9001 | ENGINEERING EXECUTION PLAN (PIPELINE) |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 21-May-2026 23:39:29 | 26002z1fdcc@thoresen-jutal.com | 22-May-2026 14:36:23 | Jumpol Sudjitjul | 29-May-2026 | 29-May-2026 14:05:25 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 09-Jun-2026 00:47:22 |  |  |  | APPR | Approved | Jumpol Sudjitjul | 08-Jun-2026 | 09-Jun-2026 07:45:25 | 09-Jun-2026 01:24:19 | 0 |  |  | Focal Point | Locate
AO-002042 | MM-ZTK-1F-GEN-ENG-RPT-0001 | SITE SURVEY REPORT |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | RPT | Report | 0 | In Review | IFR | Issued for Review |  | 14-Sep-2026 09:52:21 | wisuda.c@jutal.com | 15-Sep-2026 16:19:38 | Jumpol Sudjitjul | 22-Sep-2026 | 17-Oct-2026 09:12:49 | Pornlert Wanaphattharaphan | 24-Sep-2026 | [7 empty] | 28-Sep-2026 |  |  | 0 |  |  | Focal Point | Locate
AO-000010 | MM-ZTK-1F-GEN-ENG-TBE-3001 | TECHNICAL BID EVALUATION FOR PIPELINE DETAIL DESIGN ENGINEERING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | TBE | Technical Bid Evaluation | 0 | Submitted | IFR | Issued for Review |  | 05-Mar-2026 16:48:40 | 26002z1fdcc@thoresen-jutal.com | 06-Mar-2026 13:57:28 | Jumpol Sudjitjul | 13-Mar-2026 |  | Akkarapat Suntornsuttiwat | 17-Mar-2026 | 06-Mar-2026 14:47:56 | Pornlert Wanaphattharaphan | 18-Mar-2026 | 11-Mar-2026 08:27:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Mar-2026 | 11-Mar-2026 08:41:20 | 11-Mar-2026 08:48:43 | 0 |  |  | Approver | Locate
AO-000016 | MM-ZTK-1F-GEN-ENG-TBE-9001 | TECHNICAL BID EVALUATION FOR PIPELINE DETAIL DESIGN ENGINEERING |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | TBE | Technical Bid Evaluation | 0 | Submitted | IFA | Issued for Approval |  | 17-Mar-2026 09:27:44 | 26002z1fdcc@thoresen-jutal.com | 17-Mar-2026 09:39:22 | Jumpol Sudjitjul | 24-Mar-2026 |  | Akkarapat Suntornsuttiwat | 26-Mar-2026 | 23-Mar-2026 08:57:52 | Pornlert Wanaphattharaphan | 27-Mar-2026 | 27-Mar-2026 16:28:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 30-Mar-2026 | 27-Mar-2026 16:43:28 | 27-Mar-2026 17:30:48 | 0 |  |  | Approver | Locate
AO-000230 | MM-ZTK-1F-GEN-ENG-TBE-9001 | TECHNICAL BID EVALUATION FOR PIPELINE DETAIL DESIGN ENGINEERING |  | B2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | TBE | Technical Bid Evaluation | 0 | Submitted | IFA | Issued for Approval | 16-Apr-2026 | 27-Apr-2026 13:48:40 | 26002z1fdcc@thoresen-jutal.com | 27-Apr-2026 14:16:26 | Jumpol Sudjitjul | 06-May-2026 |  | Akkarapat Suntornsuttiwat | 08-May-2026 | 28-Apr-2026 08:48:20 | Pornlert Wanaphattharaphan | 11-May-2026 | 09-May-2026 22:39:46 | APPR | Approved | Jumpol Sudjitjul | 12-May-2026 | 10-May-2026 23:21:15 | 11-May-2026 00:13:00 | 0 |  |  | Approver | Locate
AO-000565 | MM-ZTK-1F-GEN-ENG-TBE-9001 | TECHNICAL BID EVALUATION FOR PIPELINE DETAIL DESIGN ENGINEERING |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 21-May-2026 22:37:15 | 26002z1fdcc@thoresen-jutal.com | 22-May-2026 12:37:38 | Jumpol Sudjitjul | 29-May-2026 |  | Akkarapat Suntornsuttiwat | 04-Jun-2026 | 04-Jun-2026 11:00:27 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 09-Jun-2026 00:48:41 | APPR | Approved | Jumpol Sudjitjul | 08-Jun-2026 | 09-Jun-2026 07:47:36 | 09-Jun-2026 01:25:27 | 0 |  |  | Approver | Locate
AO-000059 | MM-ZTK-1F-GEN-ENG-WPR-0001 | DETAIL DESIGN AND ENGINEERING WEEKLY PROGRESS REPORT NO.0001 CUT-OFF DATE: 27 MAR 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 01-Apr-2026 08:59:00 | zm169dc@jutal.com | 01-Apr-2026 09:00:22 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 17-Apr-2026 11:25:53 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000086 | MM-ZTK-1F-GEN-ENG-WPR-0002 | DETAIL DESIGN AND ENGINEERING WEEKLY PROGRESS REPORT NO.0002 CUT-OFF DATE: 03 APR 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 08-Apr-2026 10:19:32 | zm169dc@jutal.com | 10-Apr-2026 14:38:46 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 17-Apr-2026 11:29:40 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000206 | MM-ZTK-1F-GEN-ENG-WPR-0003 | DETAIL DESIGN AND ENGINEERING WEEKLY PROGRESS REPORT NO.0002 CUT-OFF DATE: 17 APR 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | WPR | Weekly Progress Report | 0 | In Review | IFI | Issued for Information |  | 22-Apr-2026 08:58:59 | zm169dc@jutal.com | 22-Apr-2026 13:17:54 | Jumpol Sudjitjul |  |  | Pornlert Wanaphattharaphan | [11 empty] | 0 |  |  | For Info | Locate
AO-000254 | MM-ZTK-1F-GEN-ENG-WPR-0004 | DETAIL DESIGN AND ENGINEERING WEEKLY PROGRESS REPORT NO. 0004 CUT-OFF DATE: 24 APR 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | WPR | Weekly Progress Report | 0 | In Review | IFI | Issued for Information |  | 29-Apr-2026 09:50:24 | zm169dc@jutal.com | 29-Apr-2026 10:44:45 | Jumpol Sudjitjul |  |  | Pornlert Wanaphattharaphan | [11 empty] | 0 |  |  | For Info | Locate
AO-000333 | MM-ZTK-1F-GEN-ENG-WPR-0005 | DETAIL DESIGN AND ENGINEERING WEEKLY PROGRESS REPORT NO. 0005 CUT-OFF DATE: 01 MAY 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | ENG | Engineering | WPR | Weekly Progress Report | 0 | In Review | IFI | Issued for Information |  | 06-May-2026 16:37:29 | zm169dc@jutal.com | 06-May-2026 17:11:37 | Jumpol Sudjitjul |  |  | Pornlert Wanaphattharaphan | [11 empty] | 0 |  |  | For Info | Locate
AO-000078 | MM-ZTK-1F-GEN-INS-BOD-0001 | INSTRUMENT BASIS OF DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | BOD | Basis of Design | 0 | Submitted | IFR | Issued for Review |  | 03-Apr-2026 15:45:50 | zm169dc@jutal.com | 05-Apr-2026 07:31:51 | Jumpol Sudjitjul | 16-Apr-2026 |  | Wichai Salee | 20-Apr-2026 | 22-Apr-2026 10:15:48 | Pornlert Wanaphattharaphan | 21-Apr-2026 | 27-Apr-2026 22:19:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Apr-2026 | 28-Apr-2026 10:15:26 | 28-Apr-2026 11:05:29 | 0 |  |  | Approver | Locate
AO-000586 | MM-ZTK-1F-GEN-INS-BOD-0001 | INSTRUMENT BASIS OF DESIGN |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 24-May-2026 15:28:49 | wisuda.c@jutal.com | 24-May-2026 20:47:21 | Jumpol Sudjitjul | 02-Jun-2026 | 29-May-2026 14:01:51 | Wichai Salee | 05-Jun-2026 | 17-Jun-2026 15:10:01 | Pornlert Wanaphattharaphan | 08-Jun-2026 | 18-Jun-2026 08:15:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jun-2026 | 18-Jun-2026 08:24:39 | 18-Jun-2026 01:48:33 | 0 |  |  | Approver | Locate
AO-001785 | MM-ZTK-1F-GEN-INS-BOD-0001 | INSTRUMENT BASIS OF DESIGN |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 31-Aug-2026 08:35:17 | wisuda.c@jutal.com | 31-Aug-2026 11:46:24 | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 10:45:42 | Wichai Salee | 09-Sep-2026 | 08-Sep-2026 16:24:22 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 23:04:55 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 12-Sep-2026 20:55:59 | 12-Sep-2026 14:33:40 | 0 |  |  | Approver | Locate
AO-000095 | MM-ZTK-1F-GEN-INS-DTS-0001 | DATASHEET FOR ACTUATED CHOKE VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 08-Apr-2026 15:41:17 | zm169dc@jutal.com | 10-Apr-2026 15:05:57 | Jumpol Sudjitjul | 22-Apr-2026 | 17-Apr-2026 16:04:16 | Wichai Salee | 24-Apr-2026 | 28-Apr-2026 10:36:31 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 29-Apr-2026 00:28:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 29-Apr-2026 08:30:54 | 30-Apr-2026 11:02:23 | 0 |  |  | Approver | Locate
AO-000779 | MM-ZTK-1F-GEN-INS-DTS-0001 | DATASHEET FOR ACTUATED CHOKE VALVES |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 14-Jun-2026 22:03:50 | wisuda.c@jutal.com | 15-Jun-2026 09:06:44 | Jumpol Sudjitjul | 22-Jun-2026 | 22-Jun-2026 22:35:33 | Wichai Salee | 24-Jun-2026 | 30-Jun-2026 16:32:12 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 30-Jun-2026 18:53:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Jun-2026 | 01-Jul-2026 08:34:42 | 01-Jul-2026 01:50:37 | 0 |  |  | Approver | Locate
AO-001669 | MM-ZTK-1F-GEN-INS-DTS-0001 | DATASHEET FOR ACTUATED CHOKE VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 10:46:02 | wisuda.c@jutal.com | 25-Aug-2026 09:38:00 | Jumpol Sudjitjul | 01-Sep-2026 | 31-Aug-2026 23:27:39 | Wichai Salee | 03-Sep-2026 | 02-Sep-2026 10:41:59 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:11:47 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 11:38:34 | 07-Sep-2026 04:53:38 | 0 |  |  | Approver | Locate
AO-002249 | MM-ZTK-1F-GEN-INS-DTS-0001 | DATASHEET FOR ACTUATED CHOKE VALVES |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 15:42:59 | wisuda.c@jutal.com | 24-Sep-2026 16:46:00 | Jumpol Sudjitjul | 01-Oct-2026 |  | Wichai Salee | 05-Oct-2026 | 25-Sep-2026 23:29:01 | Pornlert Wanaphattharaphan | 06-Oct-2026 | 26-Sep-2026 05:18:03 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 26-Sep-2026 14:06:39 | 26-Sep-2026 07:23:35 | 0 |  |  | Approver | Locate
AO-000185 | MM-ZTK-1F-GEN-INS-DTS-0002 | DATASHEET FOR ACTUATED BALL VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 13:09:14 | wisuda.c@jutal.com | 21-Apr-2026 15:38:52 | Jumpol Sudjitjul | 28-Apr-2026 | 29-Apr-2026 11:23:56 | Wichai Salee | 30-Apr-2026 | 07-May-2026 17:29:09 | Pornlert Wanaphattharaphan | 05-May-2026 | 07-May-2026 20:56:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 08-May-2026 08:21:37 | 08-May-2026 01:50:58 | 0 |  |  | Approver | Locate
AO-001021 | MM-ZTK-1F-GEN-INS-DTS-0002 | DATASHEET FOR ACTUATED BALL VALVES |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 23:30:51 | wisuda.c@jutal.com | 04-Jul-2026 14:47:02 | Jumpol Sudjitjul | 10-Jul-2026 | 09-Jul-2026 20:39:25 | Wichai Salee | 14-Jul-2026 | 22-Jul-2026 11:40:42 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 22-Jul-2026 22:52:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 23-Jul-2026 08:23:51 | 23-Jul-2026 02:10:05 | 0 |  |  | Approver | Locate
AO-002277 | MM-ZTK-1F-GEN-INS-DTS-0002 | DATASHEET FOR ACTUATED BALL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 09:36:12 | wisuda.c@jutal.com | 28-Sep-2026 12:54:52 | Jumpol Sudjitjul | 05-Oct-2026 |  | Wichai Salee | 07-Oct-2026 | 01-Oct-2026 15:33:54 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 01-Oct-2026 23:17:58 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 02-Oct-2026 13:17:57 | 02-Oct-2026 07:06:46 | 0 |  |  | Approver | Locate
AO-000168 | MM-ZTK-1F-GEN-INS-DTS-0003 | DATASHEET FOR ACTUATED COMPACT BALL VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 17:26:02 | wisuda.c@jutal.com | 21-Apr-2026 09:32:13 | Jumpol Sudjitjul | 28-Apr-2026 | 23-Apr-2026 10:26:39 | Wichai Salee | 30-Apr-2026 | 06-May-2026 14:48:17 | Pornlert Wanaphattharaphan | 05-May-2026 | 06-May-2026 16:22:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 06-May-2026 16:24:41 | 06-May-2026 10:26:08 | 0 |  |  | Approver | Locate
AO-000924 | MM-ZTK-1F-GEN-INS-DTS-0003 | DATASHEET FOR ACTUATED COMPACT BALL VALVES |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 27-Jun-2026 19:24:12 | wisuda.c@jutal.com | 27-Jun-2026 19:32:33 | Jumpol Sudjitjul | 06-Jul-2026 | 04-Jul-2026 23:13:26 | Wichai Salee | 08-Jul-2026 | 12-Jul-2026 22:49:05 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 13-Jul-2026 23:11:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 14-Jul-2026 08:40:30 | 14-Jul-2026 02:04:26 | 0 |  |  | Approver | Locate
AO-001669 | MM-ZTK-1F-GEN-INS-DTS-0003 | DATASHEET FOR ACTUATED COMPACT BALL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 09:40:32 | wisuda.c@jutal.com | 25-Aug-2026 09:38:31 | Jumpol Sudjitjul | 01-Sep-2026 | 01-Sep-2026 11:50:50 | Wichai Salee | 03-Sep-2026 | 02-Sep-2026 10:49:09 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:12:44 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 11:39:11 | 07-Sep-2026 04:49:04 | 0 |  |  | Approver | Locate
AO-002249 | MM-ZTK-1F-GEN-INS-DTS-0003 | DATASHEET FOR ACTUATED COMPACT BALL VALVES |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 15:43:35 | wisuda.c@jutal.com | 24-Sep-2026 16:46:19 | Jumpol Sudjitjul | 01-Oct-2026 |  | Wichai Salee | 05-Oct-2026 | 26-Sep-2026 14:43:06 | Pornlert Wanaphattharaphan | 06-Oct-2026 | 28-Sep-2026 22:55:40 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 29-Sep-2026 14:05:15 | 29-Sep-2026 08:20:39 | 0 |  |  | Approver | Locate
AO-000118 | MM-ZTK-1F-GEN-INS-DTS-0004 | DATASHEET FOR PRESSURE RELIEF VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 13-Apr-2026 10:13:12 | zm169dc@jutal.com | 13-Apr-2026 11:14:17 | Jumpol Sudjitjul | 22-Apr-2026 | 17-Apr-2026 13:08:26 | Wichai Salee | 24-Apr-2026 | 04-May-2026 11:26:56 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 05-May-2026 22:05:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 06-May-2026 09:11:56 | 06-May-2026 02:51:34 | 0 |  |  | Approver | Locate
AO-000925 | MM-ZTK-1F-GEN-INS-DTS-0004 | DATASHEET FOR PRESSURE RELIEF VALVES |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 27-Jun-2026 18:59:01 | wisuda.c@jutal.com | 27-Jun-2026 19:05:49 | Jumpol Sudjitjul | 06-Jul-2026 | 06-Jul-2026 10:14:17 | Wichai Salee | 08-Jul-2026 | 13-Jul-2026 15:06:24 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 13-Jul-2026 23:20:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 14-Jul-2026 08:45:36 | 14-Jul-2026 02:28:37 | 0 |  |  | Approver | Locate
AO-001789 | MM-ZTK-1F-GEN-INS-DTS-0004 | DATASHEET FOR PRESSURE RELIEF VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 31-Aug-2026 08:35:45 | wisuda.c@jutal.com | 31-Aug-2026 11:45:33 | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 23:27:35 | Wichai Salee | 09-Sep-2026 | 08-Sep-2026 16:22:04 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 23:02:42 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 12-Sep-2026 20:49:50 | 12-Sep-2026 13:57:32 | 0 |  |  | Approver | Locate
AO-000349 | MM-ZTK-1F-GEN-INS-DTS-0005 | DATASHEET FOR CORIOLIS FLOW METERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:45:34 | wisuda.c@jutal.com | 11-May-2026 10:48:43 | Jumpol Sudjitjul | 18-May-2026 | 14-May-2026 13:31:15 | Wichai Salee | 20-May-2026 | 23-May-2026 16:13:08 | Pornlert Wanaphattharaphan | 21-May-2026 | 29-May-2026 00:23:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 29-May-2026 09:38:24 | 29-May-2026 03:31:39 | 0 |  |  | Approver | Locate
AO-001057 | MM-ZTK-1F-GEN-INS-DTS-0005 | DATASHEET FOR CORIOLIS FLOW METERS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 10-Jul-2026 12:17:35 | wisuda.c@jutal.com | 10-Jul-2026 13:08:11 | Jumpol Sudjitjul | 17-Jul-2026 | 13-Jul-2026 21:11:30 | Wichai Salee | 21-Jul-2026 | 23-Jul-2026 20:07:16 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 26-Jul-2026 01:43:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 27-Jul-2026 14:45:41 | 27-Jul-2026 09:32:46 | 0 |  |  | Approver | Locate
AO-002478 | MM-ZTK-1F-GEN-INS-DTS-0005 | DATASHEET FOR CORIOLIS FLOW METERS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 11:36:49 | wisuda.c@jutal.com | 12-Oct-2026 11:44:53 | Jumpol Sudjitjul | 20-Oct-2026 | 15-Oct-2026 12:43:42 | Wichai Salee | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001051 | MM-ZTK-1F-GEN-INS-DTS-0006 | DATASHEET FOR WELLHEAD CONTROL PANEL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Revised | IFR | Issued for Review |  | 10-Jul-2026 12:17:59 | wisuda.c@jutal.com | 21-Apr-2026 09:32:30 | Jumpol Sudjitjul |  | 23-Apr-2026 22:41:40 | Wichai Salee |  | 07-May-2026 11:08:21 | Pornlert Wanaphattharaphan |  | 07-May-2026 14:57:33 |  |  | Jumpol Sudjitjul |  | 07-May-2026 15:00:00 |  | 0 |  |  |  | Locate
AO-001060 | MM-ZTK-1F-GEN-INS-DTS-0006 | DATASHEET FOR WELLHEAD CONTROL PANEL |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  |  | wisuda.c@jutal.com | 10-Jul-2026 18:15:27 | Jumpol Sudjitjul | 20-Jul-2026 |  | Wichai Salee | 22-Jul-2026 | 24-Jul-2026 11:52:27 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 26-Jul-2026 03:23:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 27-Jul-2026 14:47:54 | 27-Jul-2026 09:34:07 | 0 |  |  | Approver | Locate
AO-000199 | MM-ZTK-1F-GEN-INS-DTS-0009 | DATASHEET FOR CONTROL VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:34:04 | wisuda.c@jutal.com | 22-Apr-2026 10:28:01 | Jumpol Sudjitjul | 29-Apr-2026 | 30-Apr-2026 14:38:03 | Wichai Salee | 05-May-2026 | 13-May-2026 11:05:46 | Pornlert Wanaphattharaphan | 06-May-2026 | 13-May-2026 21:13:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 14-May-2026 08:42:31 | 14-May-2026 02:37:18 | 0 |  |  | Approver | Locate
AO-000926 | MM-ZTK-1F-GEN-INS-DTS-0009 | DATASHEET FOR CONTROL VALVES |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 27-Jun-2026 18:59:40 | wisuda.c@jutal.com | 27-Jun-2026 19:06:42 | Jumpol Sudjitjul | 06-Jul-2026 | 06-Jul-2026 17:16:36 | Wichai Salee | 08-Jul-2026 | 13-Jul-2026 15:07:54 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 13-Jul-2026 23:21:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 14-Jul-2026 08:47:26 | 14-Jul-2026 02:30:01 | 0 |  |  | Approver | Locate
AO-001961 | MM-ZTK-1F-GEN-INS-DTS-0009 | DATASHEET FOR CONTROL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 09-Sep-2026 18:06:52 | wisuda.c@jutal.com | 10-Sep-2026 10:22:11 | Jumpol Sudjitjul | 17-Sep-2026 |  | Wichai Salee | 21-Sep-2026 | 15-Sep-2026 09:23:36 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 21:00:51 | APPR | Approved | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 17:07:51 | 20-Sep-2026 11:51:17 | 0 |  |  | Approver | Locate
AO-000166 | MM-ZTK-1F-GEN-INS-DTS-0010 | DATASHEET FOR SELF-ACTUATED PRESSURE CONTROL VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 17:26:51 | wisuda.c@jutal.com | 21-Apr-2026 09:32:42 | Jumpol Sudjitjul | 28-Apr-2026 | 29-Apr-2026 14:36:49 | Wichai Salee | 30-Apr-2026 | 07-May-2026 11:11:09 | Pornlert Wanaphattharaphan | 05-May-2026 | 07-May-2026 15:34:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 07-May-2026 16:23:20 | 07-May-2026 09:52:13 | 0 |  |  | Approver | Locate
AO-001000 | MM-ZTK-1F-GEN-INS-DTS-0010 | DATASHEET FOR SELF-ACTUATED PRESSURE CONTROL VALVES |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 16:15:39 | wisuda.c@jutal.com | 03-Jul-2026 16:31:23 | Jumpol Sudjitjul | 10-Jul-2026 | 12-Jul-2026 09:31:34 | Wichai Salee | 14-Jul-2026 | 22-Jul-2026 10:05:37 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 22-Jul-2026 22:47:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 23-Jul-2026 08:24:29 | 23-Jul-2026 02:12:55 | 0 |  |  | Approver | Locate
AO-001829 | MM-ZTK-1F-GEN-INS-DTS-0010 | DATASHEET FOR SELF-ACTUATED PRESSURE CONTROL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 18:41:49 | wisuda.c@jutal.com | 03-Sep-2026 11:22:42 | Jumpol Sudjitjul | 10-Sep-2026 | 08-Sep-2026 13:35:13 | Wichai Salee | 14-Sep-2026 | 10-Sep-2026 13:02:04 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 16:44:05 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 20:53:17 | 12-Sep-2026 14:31:15 | 0 |  |  | Approver | Locate
AO-000356 | MM-ZTK-1F-GEN-INS-DTS-0011 | DATASHEET FOR FIRE & GAS DETECTORS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:46:14 | wisuda.c@jutal.com | 11-May-2026 10:48:59 | Jumpol Sudjitjul | 18-May-2026 | 18-May-2026 15:00:22 | Wichai Salee | 20-May-2026 | 23-May-2026 16:13:57 | Pornlert Wanaphattharaphan | 21-May-2026 | 29-May-2026 00:27:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 29-May-2026 09:39:31 | 29-May-2026 03:32:57 | 0 |  |  | Approver | Locate
AO-001084 | MM-ZTK-1F-GEN-INS-DTS-0011 | DATASHEET FOR FIRE & GAS DETECTORS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:39:07 | wisuda.c@jutal.com | 12-Jul-2026 12:24:42 | Jumpol Sudjitjul | 17-Jul-2026 | 13-Jul-2026 21:48:50 | Wichai Salee | 21-Jul-2026 | 24-Jul-2026 11:51:33 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 26-Jul-2026 02:35:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 27-Jul-2026 14:49:41 | 27-Jul-2026 09:35:28 | 0 |  |  | Approver | Locate
AO-002478 | MM-ZTK-1F-GEN-INS-DTS-0011 | DATASHEET FOR FIRE & GAS DETECTORS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 11:37:19 | wisuda.c@jutal.com | 12-Oct-2026 11:44:51 | Jumpol Sudjitjul | 20-Oct-2026 | 15-Oct-2026 12:53:39 | Wichai Salee | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001462 | MM-ZTK-1F-GEN-INS-DTS-0012 | DATASHEET FOR INSTRUMENT BULK MATERIAL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 10-Aug-2026 11:39:40 | wisuda.c@jutal.com | 10-Aug-2026 15:00:01 | Jumpol Sudjitjul | 18-Aug-2026 | 18-Aug-2026 10:13:19 | Wichai Salee | 20-Aug-2026 | 24-Aug-2026 16:10:55 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 27-Aug-2026 14:36:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 27-Aug-2026 16:36:21 | 27-Aug-2026 10:53:29 | 0 |  |  | Approver | Locate
AO-002174 | MM-ZTK-1F-GEN-INS-DTS-0012 | DATASHEET FOR INSTRUMENT BULK MATERIAL |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 21-Sep-2026 11:03:37 | wisuda.c@jutal.com | 21-Sep-2026 11:58:23 | Jumpol Sudjitjul | 28-Sep-2026 | 23-Sep-2026 13:09:22 | Wichai Salee | 30-Sep-2026 | 27-Sep-2026 21:14:21 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 28-Sep-2026 22:19:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Oct-2026 | 29-Sep-2026 14:06:49 | 29-Sep-2026 07:54:13 | 0 |  |  | Approver | Locate
AO-002478 | MM-ZTK-1F-GEN-INS-DTS-0012 | DATASHEET FOR INSTRUMENT BULK MATERIAL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 11:37:47 | wisuda.c@jutal.com | 12-Oct-2026 11:44:53 | Jumpol Sudjitjul | 20-Oct-2026 |  | Wichai Salee | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000349 | MM-ZTK-1F-GEN-INS-DTS-0013 | DATASHEET FOR POSITION LIMIT SWITCH |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:46:38 | wisuda.c@jutal.com | 11-May-2026 10:49:15 | Jumpol Sudjitjul | 18-May-2026 | 14-May-2026 13:40:30 | Wichai Salee | 20-May-2026 | 23-May-2026 16:12:20 | Pornlert Wanaphattharaphan | 21-May-2026 | 29-May-2026 00:16:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 29-May-2026 09:41:26 | 29-May-2026 03:34:09 | 0 |  |  | Approver | Locate
AO-001001 | MM-ZTK-1F-GEN-INS-DTS-0013 | DATASHEET FOR POSITION LIMIT SWITCH |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 16:16:14 | wisuda.c@jutal.com | 03-Jul-2026 16:32:29 | Jumpol Sudjitjul | 10-Jul-2026 | 12-Jul-2026 09:33:50 | Wichai Salee | 14-Jul-2026 | 21-Jul-2026 11:32:42 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 22-Jul-2026 22:47:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 23-Jul-2026 08:25:09 | 23-Jul-2026 02:15:47 | 0 |  |  | Approver | Locate
AO-002478 | MM-ZTK-1F-GEN-INS-DTS-0013 | DATASHEET FOR POSITION LIMIT SWITCH |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 11:38:22 | wisuda.c@jutal.com | 12-Oct-2026 11:44:55 | Jumpol Sudjitjul | 20-Oct-2026 | 15-Oct-2026 12:50:40 | Wichai Salee | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000349 | MM-ZTK-1F-GEN-INS-DTS-0014 | DATASHEET FOR PRESSURE GAUGES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:47:02 | wisuda.c@jutal.com | 11-May-2026 10:51:43 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 12:03:18 | Wichai Salee | 20-May-2026 | 24-May-2026 00:24:14 | Pornlert Wanaphattharaphan | 21-May-2026 | 29-May-2026 14:23:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 29-May-2026 15:15:20 | 29-May-2026 08:24:42 | 0 |  |  | Approver | Locate
AO-001298 | MM-ZTK-1F-GEN-INS-DTS-0014 | DATASHEET FOR PRESSURE GAUGES |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 08:37:01 | wisuda.c@jutal.com | 27-Jul-2026 16:26:10 | Jumpol Sudjitjul | 05-Aug-2026 | 05-Aug-2026 23:57:41 | Wichai Salee | 07-Aug-2026 | 08-Aug-2026 09:20:00 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:48:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 10:53:20 | 13-Aug-2026 04:51:12 | 0 |  |  | Approver | Locate
AO-002478 | MM-ZTK-1F-GEN-INS-DTS-0014 | DATASHEET FOR PRESSURE GAUGES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 11:38:52 | wisuda.c@jutal.com | 12-Oct-2026 11:45:02 | Jumpol Sudjitjul | 20-Oct-2026 | 15-Oct-2026 13:10:20 | Wichai Salee | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000349 | MM-ZTK-1F-GEN-INS-DTS-0015 | DATASHEET FOR PRESSURE GAUGES WIRELESS TYPE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:47:26 | wisuda.c@jutal.com | 11-May-2026 10:51:56 | Jumpol Sudjitjul | 18-May-2026 | 18-May-2026 23:54:03 | Wichai Salee | 20-May-2026 | 24-May-2026 00:23:19 | Pornlert Wanaphattharaphan | 21-May-2026 | 29-May-2026 19:30:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 29-May-2026 19:35:06 | 29-May-2026 12:55:53 | 0 |  |  | Approver | Locate
AO-001184 | MM-ZTK-1F-GEN-INS-DTS-0015 | DATASHEET FOR PRESSURE GAUGES WIRELESS TYPE |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 08:43:50 | wisuda.c@jutal.com | 20-Jul-2026 14:08:08 | Jumpol Sudjitjul | 27-Jul-2026 | 31-Jul-2026 13:19:58 | Wichai Salee | 31-Jul-2026 | 01-Aug-2026 22:20:20 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 01:11:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:04:32 | 03-Aug-2026 02:23:45 | 0 |  |  | Approver | Locate
AO-002478 | MM-ZTK-1F-GEN-INS-DTS-0015 | DATASHEET FOR PRESSURE GAUGES WIRELESS TYPE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 11:39:25 | wisuda.c@jutal.com | 12-Oct-2026 11:44:51 | Jumpol Sudjitjul | 20-Oct-2026 | 14-Oct-2026 08:31:04 | Wichai Salee | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000356 | MM-ZTK-1F-GEN-INS-DTS-0016 | DATASHEET FOR TEMPERATURE GAUGES AND THERMOWELLS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:01:45 | wisuda.c@jutal.com | 11-May-2026 10:52:09 | Jumpol Sudjitjul | 18-May-2026 | 18-May-2026 23:59:13 | Wichai Salee | 20-May-2026 | 27-May-2026 09:34:00 | Pornlert Wanaphattharaphan | 21-May-2026 | 30-May-2026 23:40:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 31-May-2026 20:39:39 | 31-May-2026 14:04:29 | 0 |  |  | Approver | Locate
AO-001180 | MM-ZTK-1F-GEN-INS-DTS-0016 | DATASHEET FOR TEMPERATURE GAUGES AND THERMOWELLS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 10:28:41 | wisuda.c@jutal.com | 20-Jul-2026 14:08:27 | Jumpol Sudjitjul | 27-Jul-2026 | 20-Jul-2026 16:25:12 | Wichai Salee | 31-Jul-2026 | 01-Aug-2026 23:32:50 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 01:11:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:05:02 | 03-Aug-2026 02:26:14 | 0 |  |  | Approver | Locate
AO-002478 | MM-ZTK-1F-GEN-INS-DTS-0016 | DATASHEET FOR TEMPERATURE GAUGES AND THERMOWELLS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 11:39:53 | wisuda.c@jutal.com | 12-Oct-2026 11:44:52 | Jumpol Sudjitjul | 20-Oct-2026 | 14-Oct-2026 08:34:08 | Wichai Salee | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000356 | MM-ZTK-1F-GEN-INS-DTS-0017 | DATASHEET FOR TEMPERATURE TRANSMITTERS AND THERMOWELLS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:02:11 | wisuda.c@jutal.com | 11-May-2026 10:52:22 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 00:02:54 | Wichai Salee | 20-May-2026 | 27-May-2026 09:53:40 | Pornlert Wanaphattharaphan | 21-May-2026 | 30-May-2026 23:38:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 31-May-2026 20:40:10 | 31-May-2026 14:05:47 | 0 |  |  | Approver | Locate
AO-001298 | MM-ZTK-1F-GEN-INS-DTS-0017 | DATASHEET FOR TEMPERATURE TRANSMITTERS AND THERMOWELLS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 08:37:32 | wisuda.c@jutal.com | 27-Jul-2026 16:26:23 | Jumpol Sudjitjul | 05-Aug-2026 | 06-Aug-2026 16:33:23 | Wichai Salee | 07-Aug-2026 | 08-Aug-2026 09:25:13 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:48:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 10:55:25 | 13-Aug-2026 04:53:31 | 0 |  |  | Approver | Locate
AO-002557 | MM-ZTK-1F-GEN-INS-DTS-0017 | DATASHEET FOR TEMPERATURE TRANSMITTERS AND THERMOWELLS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 16-Oct-2026 17:35:21 | wisuda.c@jutal.com | 18-Oct-2026 16:38:57 | Jumpol Sudjitjul | 26-Oct-2026 |  | Wichai Salee | 28-Oct-2026 |  | Pornlert Wanaphattharaphan | 29-Oct-2026 |  |  |  |  | 30-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000374 | MM-ZTK-1F-GEN-INS-DTS-0018 | DATASHEET FOR TEMPERATURE TRANSMITTERS WIRELESS TYPE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 12-May-2026 10:09:01 | wisuda.c@jutal.com | 12-May-2026 11:23:07 | Jumpol Sudjitjul | 19-May-2026 | 19-May-2026 23:02:21 | Wichai Salee | 21-May-2026 | 02-Jun-2026 16:40:51 | Pornlert Wanaphattharaphan | 22-May-2026 | 05-Jun-2026 23:57:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-May-2026 | 07-Jun-2026 17:21:55 | 07-Jun-2026 10:50:19 | 0 |  |  | Approver | Locate
AO-001373 | MM-ZTK-1F-GEN-INS-DTS-0018 | DATASHEET FOR TEMPERATURE TRANSMITTERS WIRELESS TYPE |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 03-Aug-2026 10:51:47 | wisuda.c@jutal.com | 03-Aug-2026 13:37:10 | Jumpol Sudjitjul | 10-Aug-2026 | 05-Aug-2026 23:57:20 | Wichai Salee | 13-Aug-2026 | 09-Aug-2026 18:23:11 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 23:10:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 11:09:25 | 17-Aug-2026 05:16:51 | 0 |  |  | Approver | Locate
AO-000356 | MM-ZTK-1F-GEN-INS-DTS-0019 | DATASHEET FOR PRESSURE TRANSMITTERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:02:34 | wisuda.c@jutal.com | 11-May-2026 10:53:08 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 13:54:31 | Wichai Salee | 20-May-2026 | 27-May-2026 10:37:45 | Pornlert Wanaphattharaphan | 21-May-2026 | 30-May-2026 23:32:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 31-May-2026 20:40:36 | 31-May-2026 14:07:04 | 0 |  |  | Approver | Locate
AO-001298 | MM-ZTK-1F-GEN-INS-DTS-0019 | DATASHEET FOR PRESSURE TRANSMITTERS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 08:38:07 | wisuda.c@jutal.com | 27-Jul-2026 16:26:38 | Jumpol Sudjitjul | 05-Aug-2026 | 06-Aug-2026 16:36:21 | Wichai Salee | 07-Aug-2026 | 08-Aug-2026 09:27:04 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:49:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 10:56:01 | 13-Aug-2026 04:54:46 | 0 |  |  | Approver | Locate
AO-002478 | MM-ZTK-1F-GEN-INS-DTS-0019 | DATASHEET FOR PRESSURE TRANSMITTERS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 11:40:21 | wisuda.c@jutal.com | 12-Oct-2026 11:44:51 | Jumpol Sudjitjul | 20-Oct-2026 | 14-Oct-2026 08:38:48 | Wichai Salee | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000356 | MM-ZTK-1F-GEN-INS-DTS-0020 | DATASHEET FOR PRESSURE TRANSMITTERS WIRELESS TYPE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:47:51 | wisuda.c@jutal.com | 11-May-2026 10:52:55 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 13:35:33 | Wichai Salee | 20-May-2026 | 27-May-2026 10:46:43 | Pornlert Wanaphattharaphan | 21-May-2026 | 30-May-2026 23:28:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 31-May-2026 20:41:51 | 31-May-2026 13:54:30 | 0 |  |  | Approver | Locate
AO-001298 | MM-ZTK-1F-GEN-INS-DTS-0020 | DATASHEET FOR PRESSURE TRANSMITTERS WIRELESS TYPE |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 08:38:33 | wisuda.c@jutal.com | 27-Jul-2026 16:26:56 | Jumpol Sudjitjul | 05-Aug-2026 | 05-Aug-2026 23:59:02 | Wichai Salee | 07-Aug-2026 | 08-Aug-2026 09:30:07 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:49:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 10:56:36 | 13-Aug-2026 04:56:02 | 0 |  |  | Approver | Locate
AO-002478 | MM-ZTK-1F-GEN-INS-DTS-0020 | DATASHEET FOR PRESSURE TRANSMITTERS WIRELESS TYPE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 11:40:47 | wisuda.c@jutal.com | 12-Oct-2026 11:44:51 | Jumpol Sudjitjul | 20-Oct-2026 | 14-Oct-2026 12:29:12 | Wichai Salee | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000170 | MM-ZTK-1F-GEN-INS-DTS-0021 | DATASHEET FOR MAGNETIC LEVEL GAUGES AND TRANSMITTERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 17:27:19 | wisuda.c@jutal.com | 21-Apr-2026 09:32:55 | Jumpol Sudjitjul | 28-Apr-2026 | 24-Apr-2026 12:29:27 | Wichai Salee | 30-Apr-2026 | 30-Apr-2026 16:10:45 | Pornlert Wanaphattharaphan | 05-May-2026 | 01-May-2026 20:19:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 03-May-2026 16:15:15 | 03-May-2026 10:10:53 | 0 |  |  | Approver | Locate
AO-001180 | MM-ZTK-1F-GEN-INS-DTS-0021 | DATASHEET FOR MAGNETIC LEVEL GAUGES AND TRANSMITTERS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 10:29:09 | wisuda.c@jutal.com | 20-Jul-2026 14:08:51 | Jumpol Sudjitjul | 27-Jul-2026 |  | Wichai Salee | 31-Jul-2026 | 06-Aug-2026 17:44:36 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 07-Aug-2026 05:31:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 07-Aug-2026 08:53:29 | 07-Aug-2026 02:09:04 | 0 |  |  | Approver | Locate
AO-002478 | MM-ZTK-1F-GEN-INS-DTS-0021 | DATASHEET FOR MAGNETIC LEVEL GAUGES AND TRANSMITTERS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 11:41:13 | wisuda.c@jutal.com | 12-Oct-2026 11:44:52 | Jumpol Sudjitjul | 20-Oct-2026 | 14-Oct-2026 13:26:23 | Wichai Salee | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000356 | MM-ZTK-1F-GEN-INS-DTS-0023 | DATASHEET FOR D/P LEVEL TRANSMITTERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:02:59 | wisuda.c@jutal.com | 11-May-2026 10:52:43 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 13:28:14 | Wichai Salee | 20-May-2026 | 27-May-2026 11:50:59 | Pornlert Wanaphattharaphan | 21-May-2026 | 30-May-2026 23:25:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 31-May-2026 20:42:29 | 31-May-2026 14:08:20 | 0 |  |  | Approver | Locate
AO-001374 | MM-ZTK-1F-GEN-INS-DTS-0023 | DATASHEET FOR D/P LEVEL TRANSMITTERS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 10:52:13 | wisuda.c@jutal.com | 03-Aug-2026 13:37:27 | Jumpol Sudjitjul | 10-Aug-2026 |  | Wichai Salee | 13-Aug-2026 | 09-Aug-2026 18:17:35 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 23:07:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 11:10:07 | 17-Aug-2026 05:18:15 | 0 |  |  | Approver | Locate
AO-002478 | MM-ZTK-1F-GEN-INS-DTS-0023 | DATASHEET FOR D/P LEVEL TRANSMITTERS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 11:41:41 | wisuda.c@jutal.com | 12-Oct-2026 11:44:51 | Jumpol Sudjitjul | 20-Oct-2026 |  | Wichai Salee | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000356 | MM-ZTK-1F-GEN-INS-DTS-0024 | DATASHEET FOR RESTRICTION ORIFICE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:03:24 | wisuda.c@jutal.com | 11-May-2026 10:50:29 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 11:40:34 | Wichai Salee | 20-May-2026 | 24-May-2026 00:25:10 | Pornlert Wanaphattharaphan | 21-May-2026 | 29-May-2026 19:30:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 29-May-2026 19:35:59 | 29-May-2026 12:50:49 | 0 |  |  | Approver | Locate
AO-001180 | MM-ZTK-1F-GEN-INS-DTS-0024 | DATASHEET FOR RESTRICTION ORIFICE |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 10:29:39 | wisuda.c@jutal.com | 20-Jul-2026 14:09:18 | Jumpol Sudjitjul | 27-Jul-2026 |  | Wichai Salee | 31-Jul-2026 | 06-Aug-2026 17:47:36 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 07-Aug-2026 05:32:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 07-Aug-2026 08:54:08 | 07-Aug-2026 02:12:03 | 0 |  |  | Approver | Locate
AO-002478 | MM-ZTK-1F-GEN-INS-DTS-0024 | DATASHEET FOR RESTRICTION ORIFICE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 11:42:08 | wisuda.c@jutal.com | 12-Oct-2026 11:44:59 | Jumpol Sudjitjul | 20-Oct-2026 | 16-Oct-2026 11:01:25 | Wichai Salee | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000349 | MM-ZTK-1F-GEN-INS-DTS-0025 | DATASHEET FOR VORTEX FLOW METERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:48:15 | wisuda.c@jutal.com | 11-May-2026 10:50:16 | Jumpol Sudjitjul | 18-May-2026 | 18-May-2026 23:34:45 | Wichai Salee | 20-May-2026 | 02-Jun-2026 16:22:52 | Pornlert Wanaphattharaphan | 21-May-2026 | 05-Jun-2026 23:43:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 07-Jun-2026 17:22:26 | 07-Jun-2026 11:25:23 | 0 |  |  | Approver | Locate
AO-001056 | MM-ZTK-1F-GEN-INS-DTS-0025 | DATASHEET FOR VORTEX FLOW METERS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 10-Jul-2026 12:18:25 | wisuda.c@jutal.com | 10-Jul-2026 13:08:26 | Jumpol Sudjitjul | 17-Jul-2026 | 13-Jul-2026 14:36:51 | Wichai Salee | 21-Jul-2026 | 23-Jul-2026 20:08:26 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 26-Jul-2026 01:43:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 27-Jul-2026 14:51:02 | 27-Jul-2026 09:36:45 | 0 |  |  | Approver | Locate
AO-002478 | MM-ZTK-1F-GEN-INS-DTS-0025 | DATASHEET FOR VORTEX FLOW METERS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 11:42:35 | wisuda.c@jutal.com | 12-Oct-2026 11:48:59 | Jumpol Sudjitjul | 20-Oct-2026 | 15-Oct-2026 13:13:32 | Wichai Salee | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000351 | MM-ZTK-1F-GEN-INS-DTS-0026 | DATASHEET FOR NON-INTRUSIVE SAND MONITORING SYSTEM (ACOUSTIC TYPE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:48:43 | wisuda.c@jutal.com | 11-May-2026 10:50:03 | Jumpol Sudjitjul | 18-May-2026 | 18-May-2026 23:34:00 | Wichai Salee | 20-May-2026 | 24-May-2026 00:27:51 | Pornlert Wanaphattharaphan | 21-May-2026 | 29-May-2026 19:31:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 29-May-2026 19:33:09 | 29-May-2026 12:52:05 | 0 |  |  | Approver | Locate
AO-001409 | MM-ZTK-1F-GEN-INS-DTS-0026 | DATASHEET FOR NON-INTRUSIVE SAND MONITORING SYSTEM (ACOUSTIC TYPE) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 04-Aug-2026 10:53:07 | wisuda.c@jutal.com | 04-Aug-2026 11:36:52 | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 00:39:13 | Wichai Salee | 14-Aug-2026 | 17-Aug-2026 11:25:21 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 20-Aug-2026 22:57:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 21-Aug-2026 10:35:14 | 21-Aug-2026 04:00:51 | 0 |  |  | Approver | Locate
AO-002478 | MM-ZTK-1F-GEN-INS-DTS-0026 | DATASHEET FOR NON-INTRUSIVE SAND MONITORING SYSTEM (ACOUSTIC TYPE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 11:43:03 | wisuda.c@jutal.com | 12-Oct-2026 11:49:19 | Jumpol Sudjitjul | 20-Oct-2026 |  | Wichai Salee | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000351 | MM-ZTK-1F-GEN-INS-DTS-0027 | DATASHEET FOR NON-INTRUSIVE SAND MONITORING SYSTEM (ULTRASONIC TYPE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:49:08 | wisuda.c@jutal.com | 11-May-2026 10:49:50 | Jumpol Sudjitjul | 18-May-2026 | 18-May-2026 23:33:11 | Wichai Salee | 20-May-2026 | 23-May-2026 16:18:39 | Pornlert Wanaphattharaphan | 21-May-2026 | 29-May-2026 00:31:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 29-May-2026 09:42:45 | 29-May-2026 03:35:25 | 0 |  |  | Approver | Locate
AO-001787 | MM-ZTK-1F-GEN-INS-DTS-0027 | DATASHEET FOR NON-INTRUSIVE SAND MONITORING SYSTEM (ULTRASONIC TYPE) |  | X | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | VOID | Withdrawn or Superseded |  | 31-Aug-2026 08:36:14 | wisuda.c@jutal.com | 31-Aug-2026 11:45:14 | Jumpol Sudjitjul |  |  | Wichai Salee |  | 31-Aug-2026 15:12:06 | Pornlert Wanaphattharaphan |  | 02-Sep-2026 23:34:50 | REC | Received | Jumpol Sudjitjul |  | 03-Sep-2026 09:38:51 | 03-Sep-2026 03:08:03 | 0 |  |  | For Info | Locate
AO-001906 | MM-ZTK-1F-GEN-INS-LIS-0001 | INSTRUMENT DOCUMENT INDEX |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 07-Sep-2026 10:03:52 | wisuda.c@jutal.com | 08-Sep-2026 09:21:58 | Jumpol Sudjitjul | 15-Sep-2026 |  | Wichai Salee | 17-Sep-2026 | 14-Sep-2026 16:40:51 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 00:21:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 16:53:51 | 20-Sep-2026 10:44:32 | 0 |  |  | Approver | Locate
AO-002347 | MM-ZTK-1F-GEN-INS-LIS-0001 | INSTRUMENT DOCUMENT INDEX |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 02-Oct-2026 18:29:05 | wisuda.c@jutal.com | 03-Oct-2026 08:29:32 | Jumpol Sudjitjul | 09-Oct-2026 |  | Wichai Salee | 14-Oct-2026 | 14-Oct-2026 15:30:50 | Pornlert Wanaphattharaphan | 15-Oct-2026 | 15-Oct-2026 22:56:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Oct-2026 | 16-Oct-2026 14:01:08 | 16-Oct-2026 07:35:34 | 0 |  |  | Approver | Locate
AO-000576 | MM-ZTK-1F-GEN-INS-LIS-0002 | INSTRUMENT INDEX |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 23-May-2026 08:51:16 | wisuda.c@jutal.com | 23-May-2026 09:32:48 | Jumpol Sudjitjul | 29-May-2026 |  | Wichai Salee | 04-Jun-2026 | 22-Jun-2026 15:52:49 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 22-Jun-2026 22:13:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 23-Jun-2026 09:44:57 | 23-Jun-2026 03:05:10 | 0 |  |  | Approver | Locate
AO-001021 | MM-ZTK-1F-GEN-INS-LIS-0002 | INSTRUMENT INDEX |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 23:31:24 | wisuda.c@jutal.com | 04-Jul-2026 14:45:40 | Jumpol Sudjitjul | 10-Jul-2026 |  | Wichai Salee | 14-Jul-2026 | 22-Jul-2026 11:34:16 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 22-Jul-2026 22:51:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 23-Jul-2026 08:24:57 | 23-Jul-2026 02:14:16 | 0 |  |  | Approver | Locate
AO-001961 | MM-ZTK-1F-GEN-INS-LIS-0002 | INSTRUMENT INDEX |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 09-Sep-2026 18:07:20 | wisuda.c@jutal.com | 10-Sep-2026 10:20:30 | Jumpol Sudjitjul | 17-Sep-2026 |  | Wichai Salee | 21-Sep-2026 | 15-Sep-2026 09:20:18 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 23:27:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 16:46:36 | 20-Sep-2026 11:06:50 | 0 |  |  | Approver | Locate
AO-000998 | MM-ZTK-1F-GEN-INS-LIS-0003 | INSTRUMENT CABLE SCHEDULE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 13:23:17 | wisuda.c@jutal.com | 03-Jul-2026 14:26:06 | Jumpol Sudjitjul | 10-Jul-2026 |  | Wichai Salee | 14-Jul-2026 | 21-Jul-2026 10:59:31 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 22-Jul-2026 22:46:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 23-Jul-2026 08:24:33 | 23-Jul-2026 01:56:21 | 0 |  |  | Approver | Locate
AO-001473 | MM-ZTK-1F-GEN-INS-LIS-0004 | INSTRUMENT TUBING SCHEDULE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 10-Aug-2026 11:40:22 | wisuda.c@jutal.com | 10-Aug-2026 14:58:32 | Jumpol Sudjitjul | 18-Aug-2026 |  | Wichai Salee | 20-Aug-2026 | 28-Aug-2026 15:59:38 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 29-Aug-2026 00:37:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 29-Aug-2026 13:56:50 | 29-Aug-2026 07:10:42 | 0 |  |  | Approver | Locate
AO-000637 | MM-ZTK-1F-GEN-INS-LIS-0005 | INSTRUMENT EQUIPMENT AND EX-CERTIFICATES LIST |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 20:50:36 | wisuda.c@jutal.com | 31-May-2026 21:03:43 | Jumpol Sudjitjul | 10-Jun-2026 |  | Wichai Salee | 12-Jun-2026 | 22-Jun-2026 18:37:56 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 23-Jun-2026 00:38:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 23-Jun-2026 09:44:32 | 23-Jun-2026 03:03:48 | 0 |  |  | Approver | Locate
AO-001985 | MM-ZTK-1F-GEN-INS-LIS-0005 | INSTRUMENT EQUIPMENT AND EX-CERTIFICATES LIST |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 19:55:04 | wisuda.c@jutal.com | 10-Sep-2026 20:12:59 | Jumpol Sudjitjul | 18-Sep-2026 |  | Wichai Salee | 22-Sep-2026 | 16-Sep-2026 09:37:32 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 19-Sep-2026 23:23:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Sep-2026 | 20-Sep-2026 17:08:25 | 20-Sep-2026 11:06:56 | 0 |  |  | Approver | Locate
AO-000641 | MM-ZTK-1F-GEN-INS-LIS-0006 | PLC INPUT/OUTPUT LIST |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 01-Jun-2026 10:02:42 | wisuda.c@jutal.com | 01-Jun-2026 12:31:55 | Jumpol Sudjitjul | 09-Jun-2026 |  | Wichai Salee | 11-Jun-2026 | 22-Jun-2026 17:42:44 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 22-Jun-2026 23:49:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 23-Jun-2026 09:43:56 | 23-Jun-2026 03:02:33 | 0 |  |  | Approver | Locate
AO-001021 | MM-ZTK-1F-GEN-INS-LIS-0006 | PLC INPUT/OUTPUT LIST |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 23:31:58 | wisuda.c@jutal.com | 04-Jul-2026 14:45:53 | Jumpol Sudjitjul | 10-Jul-2026 |  | Wichai Salee | 14-Jul-2026 | 22-Jul-2026 11:35:29 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 22-Jul-2026 22:51:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 23-Jul-2026 08:24:00 | 23-Jul-2026 02:11:30 | 0 |  |  | Approver | Locate
AO-001961 | MM-ZTK-1F-GEN-INS-LIS-0006 | PLC INPUT/OUTPUT LIST |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 09-Sep-2026 18:07:47 | wisuda.c@jutal.com | 10-Sep-2026 10:20:50 | Jumpol Sudjitjul | 17-Sep-2026 |  | Wichai Salee | 21-Sep-2026 | 15-Sep-2026 09:21:31 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 22:42:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 17:08:59 | 20-Sep-2026 11:52:41 | 0 |  |  | Approver | Locate
AO-000091 | MM-ZTK-1F-GEN-INS-MOM-0001 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 08-Apr-2026 15:41:53 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000092 | MM-ZTK-1F-GEN-INS-MOM-0002 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 08-Apr-2026 15:42:26 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000378 | MM-ZTK-1F-GEN-INS-MOM-0003 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 12-May-2026 14:48:36 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000378 | MM-ZTK-1F-GEN-INS-MOM-0004 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 12-May-2026 14:49:11 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000378 | MM-ZTK-1F-GEN-INS-MOM-0005 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 12-May-2026 14:49:43 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000378 | MM-ZTK-1F-GEN-INS-MOM-0006 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 12-May-2026 14:50:17 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000408 | MM-ZTK-1F-GEN-INS-MOM-0007 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 15-May-2026 10:47:16 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000678 | MM-ZTK-1F-GEN-INS-MOM-0008 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 05-Jun-2026 08:58:15 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000678 | MM-ZTK-1F-GEN-INS-MOM-0009 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 05-Jun-2026 08:58:53 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000865 | MM-ZTK-1F-GEN-INS-MOM-0010 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 22-Jun-2026 13:15:14 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000865 | MM-ZTK-1F-GEN-INS-MOM-0011 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 22-Jun-2026 13:16:01 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001592 | MM-ZTK-1F-GEN-INS-MOM-0012 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 18-Aug-2026 15:20:00 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001592 | MM-ZTK-1F-GEN-INS-MOM-0013 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 18-Aug-2026 16:26:55 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001592 | MM-ZTK-1F-GEN-INS-MOM-0014 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 18-Aug-2026 15:20:38 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001592 | MM-ZTK-1F-GEN-INS-MOM-0015 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 18-Aug-2026 16:28:37 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002066 | MM-ZTK-1F-GEN-INS-MOM-0016 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Sep-2026 19:22:53 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002066 | MM-ZTK-1F-GEN-INS-MOM-0017 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Sep-2026 19:23:24 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002066 | MM-ZTK-1F-GEN-INS-MOM-0018 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Sep-2026 19:23:55 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002039 | MM-ZTK-1F-GEN-INS-MOM-0019 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Sep-2026 09:27:11 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002248 | MM-ZTK-1F-GEN-INS-MOM-0020 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 24-Sep-2026 14:58:43 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002248 | MM-ZTK-1F-GEN-INS-MOM-0021 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 24-Sep-2026 14:59:17 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002398 | MM-ZTK-1F-GEN-INS-MOM-0022 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Oct-2026 15:30:05 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000096 | MM-ZTK-1F-GEN-INS-MR-0001 | MATERIAL REQUISITION FOR ACTUATED CHOKE VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 08-Apr-2026 15:42:53 | zm169dc@jutal.com | 10-Apr-2026 15:05:14 | Jumpol Sudjitjul | 22-Apr-2026 | 22-Apr-2026 14:14:35 | Wichai Salee | 24-Apr-2026 | 27-Apr-2026 09:12:51 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 27-Apr-2026 22:30:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 28-Apr-2026 10:28:06 | 28-Apr-2026 11:02:03 | 0 |  |  | Approver | Locate
AO-000772 | MM-ZTK-1F-GEN-INS-MR-0001 | MATERIAL REQUISITION FOR ACTUATED CHOKE VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 14-Jun-2026 22:04:18 | wisuda.c@jutal.com | 15-Jun-2026 09:07:29 | Jumpol Sudjitjul | 22-Jun-2026 |  | Wichai Salee | 24-Jun-2026 | 30-Jun-2026 16:01:14 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 30-Jun-2026 18:46:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Jun-2026 | 01-Jul-2026 08:33:41 | 01-Jul-2026 01:49:12 | 0 |  |  | Approver | Locate
AO-001010 | MM-ZTK-1F-GEN-INS-MR-0001 | MATERIAL REQUISITION FOR ACTUATED CHOKE VALVES |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 20:32:21 | wisuda.c@jutal.com | 04-Jul-2026 15:04:33 | Jumpol Sudjitjul | 10-Jul-2026 |  | Wichai Salee | 14-Jul-2026 | 22-Jul-2026 11:45:48 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 22-Jul-2026 22:52:46 | APPR | Approved | Jumpol Sudjitjul | 16-Jul-2026 | 23-Jul-2026 08:18:34 | 23-Jul-2026 02:08:32 | 0 |  |  | Approver | Locate
AO-001669 | MM-ZTK-1F-GEN-INS-MR-0001 | MATERIAL REQUISITION FOR ACTUATED CHOKE VALVES |  | C3 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 10:46:32 | wisuda.c@jutal.com | 25-Aug-2026 13:06:17 | Jumpol Sudjitjul | 01-Sep-2026 |  | Wichai Salee | 03-Sep-2026 | 26-Aug-2026 14:53:58 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 00:07:31 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 16:23:18 | 30-Aug-2026 10:58:43 | 0 |  |  | Approver | Locate
AO-002249 | MM-ZTK-1F-GEN-INS-MR-0001 | MATERIAL REQUISITION FOR ACTUATED CHOKE VALVES |  | C4 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 15:44:22 | wisuda.c@jutal.com | 24-Sep-2026 16:41:45 | Jumpol Sudjitjul | 01-Oct-2026 | 25-Sep-2026 15:17:26 | Wichai Salee | 05-Oct-2026 | 25-Sep-2026 22:39:03 | Pornlert Wanaphattharaphan | 06-Oct-2026 | 26-Sep-2026 05:19:57 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 26-Sep-2026 14:07:42 | 26-Sep-2026 07:24:46 | 0 |  |  | Approver | Locate
AO-000187 | MM-ZTK-1F-GEN-INS-MR-0002 | MATERIAL REQUISITION FOR ACTUATED BALL VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 14:50:34 | wisuda.c@jutal.com | 21-Apr-2026 15:43:25 | Jumpol Sudjitjul | 28-Apr-2026 |  | Wichai Salee | 30-Apr-2026 | 10-May-2026 18:58:01 | Pornlert Wanaphattharaphan | 05-May-2026 | 11-May-2026 09:35:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 11-May-2026 10:34:00 | 11-May-2026 03:44:27 | 0 |  |  | Approver | Locate
AO-001379 | MM-ZTK-1F-GEN-INS-MR-0002 | MATERIAL REQUISITION FOR ACTUATED BALL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 10:52:48 | wisuda.c@jutal.com | 03-Aug-2026 13:38:55 | Jumpol Sudjitjul | 10-Aug-2026 |  | Wichai Salee | 13-Aug-2026 | 09-Aug-2026 18:16:23 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 12-Aug-2026 21:12:47 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 13-Aug-2026 10:57:31 | 13-Aug-2026 04:57:08 | 0 |  |  | Approver | Locate
AO-000171 | MM-ZTK-1F-GEN-INS-MR-0003 | MATERIAL REQUISITION FOR ACTUATED COMPACT BALL VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 17:27:51 | wisuda.c@jutal.com | 21-Apr-2026 09:39:05 | Jumpol Sudjitjul | 28-Apr-2026 | 24-Apr-2026 12:36:14 | Wichai Salee | 30-Apr-2026 | 11-May-2026 10:05:41 | Pornlert Wanaphattharaphan | 05-May-2026 | 11-May-2026 14:57:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 11-May-2026 15:11:50 | 11-May-2026 11:05:20 | 0 |  |  | Approver | Locate
AO-001223 | MM-ZTK-1F-GEN-INS-MR-0003 | MATERIAL REQUISITION FOR ACTUATED COMPACT BALL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 22-Jul-2026 16:43:12 | wisuda.c@jutal.com | 22-Jul-2026 17:11:01 | Jumpol Sudjitjul | 03-Aug-2026 | 24-Jul-2026 09:15:56 | Wichai Salee | 05-Aug-2026 | 07-Aug-2026 15:10:59 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 07-Aug-2026 21:52:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 08-Aug-2026 10:28:39 | 08-Aug-2026 04:03:09 | 0 |  |  | Approver | Locate
AO-001669 | MM-ZTK-1F-GEN-INS-MR-0003 | MATERIAL REQUISITION FOR ACTUATED COMPACT BALL VALVES |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 10:47:00 | wisuda.c@jutal.com | 25-Aug-2026 13:06:34 | Jumpol Sudjitjul | 01-Sep-2026 | 02-Sep-2026 10:39:56 | Wichai Salee | 03-Sep-2026 | 02-Sep-2026 10:52:17 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 02-Sep-2026 23:53:14 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 03-Sep-2026 09:43:47 | 03-Sep-2026 03:23:05 | 0 |  |  | Approver | Locate
AO-002249 | MM-ZTK-1F-GEN-INS-MR-0003 | MATERIAL REQUISITION FOR ACTUATED COMPACT BALL VALVES |  | C3 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 15:45:03 | wisuda.c@jutal.com | 24-Sep-2026 16:41:45 | Jumpol Sudjitjul | 01-Oct-2026 | 25-Sep-2026 15:17:20 | Wichai Salee | 05-Oct-2026 | 25-Sep-2026 22:25:33 | Pornlert Wanaphattharaphan | 06-Oct-2026 | 26-Sep-2026 05:20:21 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 26-Sep-2026 14:08:29 | 26-Sep-2026 07:25:55 | 0 |  |  | Approver | Locate
AO-000119 | MM-ZTK-1F-GEN-INS-MR-0004 | MATERIAL REQUISITION FOR PRESSURE RELIEF VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 13-Apr-2026 10:13:35 | zm169dc@jutal.com | 13-Apr-2026 11:15:48 | Jumpol Sudjitjul | 22-Apr-2026 | 22-Apr-2026 13:22:58 | Wichai Salee | 24-Apr-2026 | 05-May-2026 11:11:56 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 05-May-2026 22:09:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 06-May-2026 09:17:57 | 06-May-2026 02:52:50 | 0 |  |  | Approver | Locate
AO-001347 | MM-ZTK-1F-GEN-INS-MR-0004 | MATERIAL REQUISITION FOR PRESSURE RELIEF VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 09:28:25 | wisuda.c@jutal.com | 31-Jul-2026 09:33:42 | Jumpol Sudjitjul | 07-Aug-2026 | 05-Aug-2026 14:00:23 | Wichai Salee | 11-Aug-2026 | 08-Aug-2026 10:08:16 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 10:04:14 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 11:02:47 | 13-Aug-2026 05:19:30 | 0 |  |  | Approver | Locate
AO-000349 | MM-ZTK-1F-GEN-INS-MR-0005 | MATERIAL REQUISITION FOR CORIOLIS FLOW METERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:49:33 | wisuda.c@jutal.com | 11-May-2026 11:02:39 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 10:08:33 | Wichai Salee | 20-May-2026 | 30-May-2026 10:02:51 | Pornlert Wanaphattharaphan | 21-May-2026 | 30-May-2026 23:05:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 31-May-2026 20:42:59 | 31-May-2026 13:55:47 | 0 |  |  | Approver | Locate
AO-002249 | MM-ZTK-1F-GEN-INS-MR-0005 | MATERIAL REQUISITION FOR CORIOLIS FLOW METERS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 15:45:37 | wisuda.c@jutal.com | 24-Sep-2026 16:41:51 | Jumpol Sudjitjul | 01-Oct-2026 | 25-Sep-2026 15:19:39 | Wichai Salee | 05-Oct-2026 | 26-Sep-2026 14:05:19 | Pornlert Wanaphattharaphan | 06-Oct-2026 | 28-Sep-2026 22:54:59 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 29-Sep-2026 14:07:26 | 29-Sep-2026 08:21:53 | 0 |  |  | Approver | Locate
AO-000172 | MM-ZTK-1F-GEN-INS-MR-0006 | MATERIAL REQUISITION FOR WELLHEAD CONTROL PANEL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 17:28:19 | wisuda.c@jutal.com | 21-Apr-2026 09:39:18 | Jumpol Sudjitjul | 28-Apr-2026 | 24-Apr-2026 12:36:54 | Wichai Salee | 30-Apr-2026 | 10-May-2026 17:28:19 | Pornlert Wanaphattharaphan | 05-May-2026 | 11-May-2026 08:52:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 11-May-2026 08:54:37 | 11-May-2026 02:17:20 | 0 |  |  | Approver | Locate
AO-001169 | MM-ZTK-1F-GEN-INS-MR-0006 | MATERIAL REQUISITION FOR WELLHEAD CONTROL PANEL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:30:18 | wisuda.c@jutal.com | 20-Jul-2026 14:39:39 | Jumpol Sudjitjul | 27-Jul-2026 |  | Wichai Salee | 31-Jul-2026 | 01-Aug-2026 23:22:59 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 00:17:35 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:05:10 | 03-Aug-2026 02:24:56 | 0 |  |  | Approver | Locate
AO-000207 | MM-ZTK-1F-GEN-INS-MR-0008 | MATERIAL REQUISITION FOR PLC SYSTEM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 22-Apr-2026 11:00:53 | wisuda.c@jutal.com | 22-Apr-2026 13:20:25 | Jumpol Sudjitjul | 29-Apr-2026 | 24-Apr-2026 12:37:17 | Wichai Salee | 05-May-2026 | 13-May-2026 10:54:25 | Pornlert Wanaphattharaphan | 06-May-2026 | 13-May-2026 16:41:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 13-May-2026 17:17:29 | 13-May-2026 11:19:38 | 0 |  |  | Approver | Locate
AO-001961 | MM-ZTK-1F-GEN-INS-MR-0008 | MATERIAL REQUISITION FOR PLC SYSTEM |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 09-Sep-2026 18:08:24 | wisuda.c@jutal.com | 10-Sep-2026 10:24:24 | Jumpol Sudjitjul | 17-Sep-2026 | 16-Sep-2026 14:05:52 | Wichai Salee | 21-Sep-2026 | 17-Sep-2026 16:05:55 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 21:56:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 17:09:36 | 20-Sep-2026 11:53:58 | 0 |  |  | Approver | Locate
AO-002392 | MM-ZTK-1F-GEN-INS-MR-0008 | MATERIAL REQUISITION FOR PLC SYSTEM |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 06-Oct-2026 08:31:54 | wisuda.c@jutal.com | 06-Oct-2026 08:50:54 | Jumpol Sudjitjul | 14-Oct-2026 | 06-Oct-2026 13:02:56 | Wichai Salee | 16-Oct-2026 | 09-Oct-2026 07:46:01 | Pornlert Wanaphattharaphan | 19-Oct-2026 | 11-Oct-2026 00:13:45 | APPR | Approved | Jumpol Sudjitjul | 20-Oct-2026 | 11-Oct-2026 09:57:45 | 11-Oct-2026 03:43:34 | 0 |  |  | Approver | Locate
AO-000200 | MM-ZTK-1F-GEN-INS-MR-0009 | MATERIAL REQUISITION FOR CONTROL VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:34:36 | wisuda.c@jutal.com | 22-Apr-2026 10:31:06 | Jumpol Sudjitjul | 29-Apr-2026 | 24-Apr-2026 12:37:38 | Wichai Salee | 05-May-2026 | 13-May-2026 10:55:57 | Pornlert Wanaphattharaphan | 06-May-2026 | 13-May-2026 16:44:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 13-May-2026 17:16:41 | 13-May-2026 11:22:05 | 0 |  |  | Approver | Locate
AO-001439 | MM-ZTK-1F-GEN-INS-MR-0009 | MATERIAL REQUISITION FOR CONTROL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 10:05:38 | wisuda.c@jutal.com | 07-Aug-2026 14:38:17 | Jumpol Sudjitjul | 17-Aug-2026 |  | Wichai Salee | 19-Aug-2026 | 08-Aug-2026 22:14:26 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 12-Aug-2026 21:10:28 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 13-Aug-2026 11:03:41 | 13-Aug-2026 05:47:20 | 0 |  |  | Approver | Locate
AO-000167 | MM-ZTK-1F-GEN-INS-MR-0010 | MATERIAL REQUISITION FOR SELF-ACTUATED PRESSURE CONTROL VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 17:29:01 | wisuda.c@jutal.com | 21-Apr-2026 09:35:59 | Jumpol Sudjitjul | 28-Apr-2026 | 24-Apr-2026 12:35:28 | Wichai Salee | 30-Apr-2026 | 10-May-2026 17:25:10 | Pornlert Wanaphattharaphan | 05-May-2026 | 11-May-2026 08:44:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 11-May-2026 08:53:11 | 11-May-2026 02:16:04 | 0 |  |  | Approver | Locate
AO-001380 | MM-ZTK-1F-GEN-INS-MR-0010 | MATERIAL REQUISITION FOR SELF-ACTUATED PRESSURE CONTROL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 10:53:20 | wisuda.c@jutal.com | 03-Aug-2026 13:39:25 | Jumpol Sudjitjul | 10-Aug-2026 | 05-Aug-2026 14:04:35 | Wichai Salee | 13-Aug-2026 | 08-Aug-2026 21:50:24 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 12-Aug-2026 21:12:30 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 13-Aug-2026 11:09:45 | 13-Aug-2026 05:04:50 | 0 |  |  | Approver | Locate
AO-000356 | MM-ZTK-1F-GEN-INS-MR-0011 | MATERIAL REQUISITION FOR FIRE & GAS DETECTORS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:03:48 | wisuda.c@jutal.com | 11-May-2026 11:08:13 | Jumpol Sudjitjul | 18-May-2026 |  | Wichai Salee | 20-May-2026 | 16-May-2026 01:19:13 | Pornlert Wanaphattharaphan | 21-May-2026 | 24-May-2026 22:34:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 25-May-2026 08:44:53 | 25-May-2026 02:09:12 | 0 |  |  | Approver | Locate
AO-001669 | MM-ZTK-1F-GEN-INS-MR-0011 | MATERIAL REQUISITION FOR FIRE & GAS DETECTORS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 10:47:27 | wisuda.c@jutal.com | 25-Aug-2026 13:06:54 | Jumpol Sudjitjul | 01-Sep-2026 | 02-Sep-2026 10:36:59 | Wichai Salee | 03-Sep-2026 | 02-Sep-2026 11:15:23 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 02-Sep-2026 23:52:46 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 03-Sep-2026 09:45:11 | 03-Sep-2026 03:24:15 | 0 |  |  | Approver | Locate
AO-001463 | MM-ZTK-1F-GEN-INS-MR-0012 | MATERIAL REQUISITION FOR INSTRUMENT JUNCTION BOXES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 10-Aug-2026 11:40:48 | wisuda.c@jutal.com | 10-Aug-2026 14:57:13 | Jumpol Sudjitjul | 18-Aug-2026 |  | Wichai Salee | 20-Aug-2026 | 18-Aug-2026 10:23:37 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:28:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 19:58:37 | 24-Aug-2026 13:32:55 | 0 |  |  | Approver | Locate
AO-002175 | MM-ZTK-1F-GEN-INS-MR-0012 | MATERIAL REQUISITION FOR INSTRUMENT JUNCTION BOXES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 11:04:10 | wisuda.c@jutal.com | 21-Sep-2026 11:59:41 | Jumpol Sudjitjul | 28-Sep-2026 |  | Wichai Salee | 30-Sep-2026 | 23-Sep-2026 23:15:34 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 26-Sep-2026 05:46:07 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 26-Sep-2026 14:09:19 | 26-Sep-2026 07:40:15 | 0 |  |  | Approver | Locate
AO-000349 | MM-ZTK-1F-GEN-INS-MR-0013 | MATERIAL REQUISITION FOR POSITION LIMIT SWITCH |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:49:58 | wisuda.c@jutal.com | 11-May-2026 11:08:28 | Jumpol Sudjitjul | 18-May-2026 |  | Wichai Salee | 20-May-2026 | 16-May-2026 01:21:05 | Pornlert Wanaphattharaphan | 21-May-2026 | 24-May-2026 22:35:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 25-May-2026 08:40:19 | 25-May-2026 02:01:15 | 0 |  |  | Approver | Locate
AO-001643 | MM-ZTK-1F-GEN-INS-MR-0013 | MATERIAL REQUISITION FOR POSITION LIMIT SWITCH |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 09:39:29 | wisuda.c@jutal.com | 21-Aug-2026 10:55:02 | Jumpol Sudjitjul | 28-Aug-2026 |  | Wichai Salee | 01-Sep-2026 | 24-Aug-2026 11:17:09 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 29-Aug-2026 23:55:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Sep-2026 | 30-Aug-2026 16:31:08 | 30-Aug-2026 10:45:23 | 0 |  |  | Approver | Locate
AO-002249 | MM-ZTK-1F-GEN-INS-MR-0013 | MATERIAL REQUISITION FOR POSITION LIMIT SWITCH |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 15:46:10 | wisuda.c@jutal.com | 24-Sep-2026 16:41:49 | Jumpol Sudjitjul | 01-Oct-2026 | 25-Sep-2026 15:18:00 | Wichai Salee | 05-Oct-2026 | 27-Sep-2026 21:30:28 | Pornlert Wanaphattharaphan | 06-Oct-2026 | 28-Sep-2026 22:56:34 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 29-Sep-2026 14:10:29 | 29-Sep-2026 08:23:08 | 0 |  |  | Approver | Locate
AO-000349 | MM-ZTK-1F-GEN-INS-MR-0014 | MATERIAL REQUISITION FOR PRESSURE GAUGES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:50:25 | wisuda.c@jutal.com | 11-May-2026 11:08:42 | Jumpol Sudjitjul | 18-May-2026 |  | Wichai Salee | 20-May-2026 | 16-May-2026 20:42:42 | Pornlert Wanaphattharaphan | 21-May-2026 | 24-May-2026 23:10:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 25-May-2026 08:23:35 | 25-May-2026 01:27:59 | 0 |  |  | Approver | Locate
AO-001780 | MM-ZTK-1F-GEN-INS-MR-0014 | MATERIAL REQUISITION FOR PRESSURE GAUGES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 31-Aug-2026 08:36:42 | wisuda.c@jutal.com | 31-Aug-2026 11:41:31 | Jumpol Sudjitjul | 07-Sep-2026 | 01-Sep-2026 13:53:37 | Wichai Salee | 09-Sep-2026 | 03-Sep-2026 08:24:34 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 04-Sep-2026 23:52:04 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 05-Sep-2026 18:00:27 | 05-Sep-2026 11:31:32 | 0 |  |  | Approver | Locate
AO-000349 | MM-ZTK-1F-GEN-INS-MR-0015 | MATERIAL REQUISITION FOR PRESSURE GAUGES WIRELESS TYPE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:51:04 | wisuda.c@jutal.com | 11-May-2026 11:08:56 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 13:36:46 | Wichai Salee | 20-May-2026 | 30-May-2026 17:20:07 | Pornlert Wanaphattharaphan | 21-May-2026 | 30-May-2026 23:01:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 31-May-2026 20:44:01 | 31-May-2026 14:01:45 | 0 |  |  | Approver | Locate
AO-001780 | MM-ZTK-1F-GEN-INS-MR-0015 | MATERIAL REQUISITION FOR PRESSURE GAUGES WIRELESS TYPE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 31-Aug-2026 08:37:11 | wisuda.c@jutal.com | 31-Aug-2026 11:41:55 | Jumpol Sudjitjul | 07-Sep-2026 | 01-Sep-2026 13:56:32 | Wichai Salee | 09-Sep-2026 | 03-Sep-2026 08:29:38 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 04-Sep-2026 23:50:43 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 05-Sep-2026 18:00:52 | 05-Sep-2026 11:32:49 | 0 |  |  | Approver | Locate
AO-002249 | MM-ZTK-1F-GEN-INS-MR-0015 | MATERIAL REQUISITION FOR PRESSURE GAUGES WIRELESS TYPE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 15:46:40 | wisuda.c@jutal.com | 24-Sep-2026 16:41:49 | Jumpol Sudjitjul | 01-Oct-2026 | 25-Sep-2026 15:18:38 | Wichai Salee | 05-Oct-2026 | 25-Sep-2026 23:17:12 | Pornlert Wanaphattharaphan | 06-Oct-2026 | 26-Sep-2026 05:19:13 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 26-Sep-2026 14:09:44 | 26-Sep-2026 07:27:04 | 0 |  |  | Approver | Locate
AO-000356 | MM-ZTK-1F-GEN-INS-MR-0016 | MATERIAL REQUISITION FOR TEMPERATURE GAUGES AND THERMOWELLS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:04:11 | wisuda.c@jutal.com | 11-May-2026 11:10:07 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 13:37:49 | Wichai Salee | 20-May-2026 | 30-May-2026 17:25:06 | Pornlert Wanaphattharaphan | 21-May-2026 | 30-May-2026 22:59:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 31-May-2026 20:43:31 | 31-May-2026 14:09:38 | 0 |  |  | Approver | Locate
AO-001643 | MM-ZTK-1F-GEN-INS-MR-0016 | MATERIAL REQUISITION FOR TEMPERATURE GAUGES AND THERMOWELLS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 09:39:59 | wisuda.c@jutal.com | 21-Aug-2026 10:55:25 | Jumpol Sudjitjul | 28-Aug-2026 |  | Wichai Salee | 01-Sep-2026 | 24-Aug-2026 11:15:37 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 29-Aug-2026 23:55:39 | APPR | Approved | Jumpol Sudjitjul | 03-Sep-2026 | 30-Aug-2026 16:24:23 | 30-Aug-2026 10:42:53 | 0 |  |  | Approver | Locate
AO-000356 | MM-ZTK-1F-GEN-INS-MR-0017 | MATERIAL REQUISITION FOR TEMPERATURE TRANSMITTERS AND THERMOWELLS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:04:34 | wisuda.c@jutal.com | 11-May-2026 11:10:23 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 13:38:48 | Wichai Salee | 20-May-2026 | 30-May-2026 17:28:12 | Pornlert Wanaphattharaphan | 21-May-2026 | 30-May-2026 22:55:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 31-May-2026 20:44:34 | 31-May-2026 14:11:10 | 0 |  |  | Approver | Locate
AO-001643 | MM-ZTK-1F-GEN-INS-MR-0017 | MATERIAL REQUISITION FOR TEMPERATURE TRANSMITTERS AND THERMOWELLS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 09:40:24 | wisuda.c@jutal.com | 21-Aug-2026 10:55:49 | Jumpol Sudjitjul | 28-Aug-2026 |  | Wichai Salee | 01-Sep-2026 | 24-Aug-2026 11:15:26 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 29-Aug-2026 23:55:08 | APPR | Approved | Jumpol Sudjitjul | 03-Sep-2026 | 30-Aug-2026 16:40:08 | 30-Aug-2026 10:50:20 | 0 |  |  | Approver | Locate
AO-000375 | MM-ZTK-1F-GEN-INS-MR-0018 | MATERIAL REQUISITION FOR TEMPERATURE TRANSMITTERS WIRELESS TYPE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 12-May-2026 10:09:27 | wisuda.c@jutal.com | 12-May-2026 11:22:10 | Jumpol Sudjitjul | 19-May-2026 | 19-May-2026 16:24:19 | Wichai Salee | 21-May-2026 | 08-Jun-2026 16:24:53 | Pornlert Wanaphattharaphan | 22-May-2026 | 09-Jun-2026 00:56:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-May-2026 | 09-Jun-2026 07:46:57 | 09-Jun-2026 01:13:43 | 0 |  |  | Approver | Locate
AO-002345 | MM-ZTK-1F-GEN-INS-MR-0018 | MATERIAL REQUISITION FOR TEMPERATURE TRANSMITTERS WIRELESS TYPE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 02-Oct-2026 17:56:22 | wisuda.c@jutal.com | 03-Oct-2026 08:30:35 | Jumpol Sudjitjul | 09-Oct-2026 | 08-Oct-2026 09:11:15 | Wichai Salee | 14-Oct-2026 | 09-Oct-2026 07:41:46 | Pornlert Wanaphattharaphan | 15-Oct-2026 | 10-Oct-2026 01:54:26 | APPR | Approved | Jumpol Sudjitjul | 16-Oct-2026 | 10-Oct-2026 17:24:00 | 10-Oct-2026 11:22:42 | 0 |  |  | Approver | Locate
AO-000356 | MM-ZTK-1F-GEN-INS-MR-0019 | MATERIAL REQUISITION FOR PRESSURE TRANSMITTERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:05:01 | wisuda.c@jutal.com | 11-May-2026 11:10:38 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 13:40:56 | Wichai Salee | 20-May-2026 | 30-May-2026 17:30:53 | Pornlert Wanaphattharaphan | 21-May-2026 | 30-May-2026 22:50:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 31-May-2026 20:45:02 | 31-May-2026 14:12:29 | 0 |  |  | Approver | Locate
AO-002478 | MM-ZTK-1F-GEN-INS-MR-0019 | MATERIAL REQUISITION FOR PRESSURE TRANSMITTERS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 11:43:36 | wisuda.c@jutal.com | 12-Oct-2026 11:47:05 | Jumpol Sudjitjul | 20-Oct-2026 |  | Wichai Salee | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000356 | MM-ZTK-1F-GEN-INS-MR-0020 | MATERIAL REQUISITION FOR PRESSURE TRANSMITTERS WIRELESS TYPE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:05:24 | wisuda.c@jutal.com | 11-May-2026 11:10:53 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 13:41:50 | Wichai Salee | 20-May-2026 | 30-May-2026 17:34:10 | Pornlert Wanaphattharaphan | 21-May-2026 | 30-May-2026 22:49:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 31-May-2026 20:45:33 | 31-May-2026 14:15:53 | 0 |  |  | Approver | Locate
AO-001780 | MM-ZTK-1F-GEN-INS-MR-0020 | MATERIAL REQUISITION FOR PRESSURE TRANSMITTERS WIRELESS TYPE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 31-Aug-2026 08:37:37 | wisuda.c@jutal.com | 31-Aug-2026 11:42:10 | Jumpol Sudjitjul | 07-Sep-2026 | 01-Sep-2026 13:58:02 | Wichai Salee | 09-Sep-2026 | 04-Sep-2026 10:58:14 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 07-Sep-2026 00:13:55 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 07-Sep-2026 11:43:36 | 07-Sep-2026 05:29:35 | 0 |  |  | Approver | Locate
AO-002249 | MM-ZTK-1F-GEN-INS-MR-0020 | MATERIAL REQUISITION FOR PRESSURE TRANSMITTERS WIRELESS TYPE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 15:47:12 | wisuda.c@jutal.com | 24-Sep-2026 16:41:50 | Jumpol Sudjitjul | 01-Oct-2026 | 25-Sep-2026 15:20:13 | Wichai Salee | 05-Oct-2026 | 25-Sep-2026 22:40:38 | Pornlert Wanaphattharaphan | 06-Oct-2026 | 26-Sep-2026 05:19:31 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 26-Sep-2026 14:10:10 | 26-Sep-2026 07:28:10 | 0 |  |  | Approver | Locate
AO-000173 | MM-ZTK-1F-GEN-INS-MR-0021 | MATERIAL REQUISITION FOR MAGNETIC LEVEL GAUGES AND TRANSMITTERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 17:29:31 | wisuda.c@jutal.com | 21-Apr-2026 09:35:38 | Jumpol Sudjitjul | 28-Apr-2026 | 24-Apr-2026 12:34:54 | Wichai Salee | 30-Apr-2026 | 10-May-2026 17:23:01 | Pornlert Wanaphattharaphan | 05-May-2026 | 11-May-2026 08:44:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 11-May-2026 08:56:11 | 11-May-2026 02:20:16 | 0 |  |  | Approver | Locate
AO-001761 | MM-ZTK-1F-GEN-INS-MR-0021 | MATERIAL REQUISITION FOR MAGNETIC LEVEL GAUGES AND TRANSMITTERS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 18:09:56 | wisuda.c@jutal.com | 29-Aug-2026 13:30:48 | Jumpol Sudjitjul | 04-Sep-2026 | 07-Sep-2026 15:12:52 | Wichai Salee | 08-Sep-2026 |  | Pornlert Wanaphattharaphan | 09-Sep-2026 |  | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 11-Sep-2026 08:17:07 | 11-Sep-2026 02:32:47 | 0 |  |  | Approver | Locate
AO-000356 | MM-ZTK-1F-GEN-INS-MR-0023 | MATERIAL REQUISITION FOR D/P LEVEL TRANSMITTERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:05:50 | wisuda.c@jutal.com | 11-May-2026 11:02:25 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 10:06:32 | Wichai Salee | 20-May-2026 | 30-May-2026 10:01:29 | Pornlert Wanaphattharaphan | 21-May-2026 | 30-May-2026 23:07:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 31-May-2026 20:46:15 | 31-May-2026 14:17:10 | 0 |  |  | Approver | Locate
AO-001830 | MM-ZTK-1F-GEN-INS-MR-0023 | MATERIAL REQUISITION FOR D/P LEVEL TRANSMITTERS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 18:42:27 | wisuda.c@jutal.com | 03-Sep-2026 11:23:03 | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 08:56:47 | Wichai Salee | 14-Sep-2026 | 09-Sep-2026 15:35:48 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 16:43:12 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 20:58:55 | 12-Sep-2026 14:34:50 | 0 |  |  | Approver | Locate
AO-000356 | MM-ZTK-1F-GEN-INS-MR-0024 | MATERIAL REQUISITION FOR RESTRICTION ORIFICES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:06:19 | wisuda.c@jutal.com | 11-May-2026 10:58:51 | Jumpol Sudjitjul | 18-May-2026 |  | Wichai Salee | 20-May-2026 | 14-May-2026 11:17:54 | Pornlert Wanaphattharaphan | 21-May-2026 | 15-May-2026 23:37:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 17-May-2026 09:57:01 | 17-May-2026 03:04:47 | 0 |  |  | Approver | Locate
AO-001762 | MM-ZTK-1F-GEN-INS-MR-0024 | MATERIAL REQUISITION FOR RESTRICTION ORIFICES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 18:10:24 | wisuda.c@jutal.com | 29-Aug-2026 13:31:07 | Jumpol Sudjitjul | 04-Sep-2026 | 07-Sep-2026 15:14:58 | Wichai Salee | 08-Sep-2026 | 08-Sep-2026 13:02:22 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 10-Sep-2026 22:48:59 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 11-Sep-2026 08:16:31 | 11-Sep-2026 02:29:32 | 0 |  |  | Approver | Locate
AO-000349 | MM-ZTK-1F-GEN-INS-MR-0025 | MATERIAL REQUISITION FOR VORTEX FLOW METERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:51:30 | wisuda.c@jutal.com | 11-May-2026 10:59:11 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 10:09:18 | Wichai Salee | 20-May-2026 | 30-May-2026 09:40:38 | Pornlert Wanaphattharaphan | 21-May-2026 | 30-May-2026 23:14:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 31-May-2026 20:46:45 | 31-May-2026 14:03:10 | 0 |  |  | Approver | Locate
AO-002249 | MM-ZTK-1F-GEN-INS-MR-0025 | MATERIAL REQUISITION FOR VORTEX FLOW METERS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 15:47:50 | wisuda.c@jutal.com | 24-Sep-2026 16:41:49 | Jumpol Sudjitjul | 01-Oct-2026 | 25-Sep-2026 15:18:45 | Wichai Salee | 05-Oct-2026 | 26-Sep-2026 14:00:57 | Pornlert Wanaphattharaphan | 06-Oct-2026 | 28-Sep-2026 22:54:20 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 29-Sep-2026 14:13:18 | 29-Sep-2026 08:25:38 | 0 |  |  | Approver | Locate
AO-000351 | MM-ZTK-1F-GEN-INS-MR-0026 | MATERIAL REQUISITION FOR NON-INTRUSIVE SAND MONITORING SYSTEM (NON-INTRUSIVE PASSIVE ACOUSTICS TYPE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:51:55 | wisuda.c@jutal.com | 11-May-2026 10:59:45 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 09:56:45 | Wichai Salee | 20-May-2026 | 30-May-2026 09:45:39 | Pornlert Wanaphattharaphan | 21-May-2026 | 30-May-2026 23:11:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 31-May-2026 20:47:34 | 31-May-2026 14:35:30 | 0 |  |  | Approver | Locate
AO-002176 | MM-ZTK-1F-GEN-INS-MR-0026 | MATERIAL REQUISITION FOR NON-INTRUSIVE SAND MONITORING SYSTEM (NON-INTRUSIVE PASSIVE ACOUSTICS TYPE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 11:04:40 | wisuda.c@jutal.com | 21-Sep-2026 12:00:04 | Jumpol Sudjitjul | 28-Sep-2026 | 25-Sep-2026 10:38:58 | Wichai Salee | 30-Sep-2026 | 25-Sep-2026 14:07:28 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 26-Sep-2026 05:37:52 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 26-Sep-2026 14:10:43 | 26-Sep-2026 07:41:23 | 0 |  |  | Approver | Locate
AO-000351 | MM-ZTK-1F-GEN-INS-MR-0033 | MATERIAL REQUISITION FOR NON-INTRUSIVE SAND MONITORING SYSTEM (ULTRASONIC TYPE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:52:22 | wisuda.c@jutal.com | 11-May-2026 10:59:26 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 10:09:53 | Wichai Salee | 20-May-2026 | 30-May-2026 09:42:18 | Pornlert Wanaphattharaphan | 21-May-2026 | 30-May-2026 23:13:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 31-May-2026 20:48:04 | 31-May-2026 14:36:46 | 0 |  |  | Approver | Locate
AO-001786 | MM-ZTK-1F-GEN-INS-MR-0033 | MATERIAL REQUISITION FOR NON-INTRUSIVE SAND MONITORING SYSTEM (ULTRASONIC TYPE) |  | X | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | VOID | Withdrawn or Superseded |  | 31-Aug-2026 08:38:03 | wisuda.c@jutal.com | 31-Aug-2026 11:42:33 | Jumpol Sudjitjul |  |  | Wichai Salee |  | 31-Aug-2026 15:11:23 | Pornlert Wanaphattharaphan |  | 02-Sep-2026 23:34:40 | REC | Received | Jumpol Sudjitjul |  | 03-Sep-2026 09:46:50 | 03-Sep-2026 03:09:14 | 0 |  |  | For Info | Locate
AO-001464 | MM-ZTK-1F-GEN-INS-MR-0034 | MATERIAL REQUISITION FOR INSTRUMENT BULK MATERIALS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 10-Aug-2026 11:41:16 | wisuda.c@jutal.com | 10-Aug-2026 14:57:28 | Jumpol Sudjitjul | 18-Aug-2026 |  | Wichai Salee | 20-Aug-2026 | 18-Aug-2026 10:36:04 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:29:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 19:59:11 | 24-Aug-2026 13:35:33 | 0 |  |  | Approver | Locate
AO-002249 | MM-ZTK-1F-GEN-INS-MR-0034 | MATERIAL REQUISITION FOR INSTRUMENT BULK MATERIALS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 16:28:52 | wisuda.c@jutal.com | 24-Sep-2026 16:41:49 | Jumpol Sudjitjul | 01-Oct-2026 |  | Wichai Salee | 05-Oct-2026 | 25-Sep-2026 23:22:30 | Pornlert Wanaphattharaphan | 06-Oct-2026 | 26-Sep-2026 05:18:23 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 26-Sep-2026 14:11:09 | 26-Sep-2026 07:49:44 | 0 |  |  | Approver | Locate
AO-001908 | MM-ZTK-1F-GEN-INS-MTO-0001 | INSTRUMENT BULK MATERIAL TAKE OFF |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 07-Sep-2026 10:04:39 | wisuda.c@jutal.com | 08-Sep-2026 09:21:22 | Jumpol Sudjitjul | 15-Sep-2026 |  | Wichai Salee | 17-Sep-2026 | 14-Sep-2026 10:56:51 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 00:19:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 16:54:39 | 20-Sep-2026 10:45:46 | 0 |  |  | Approver | Locate
AO-002354 | MM-ZTK-1F-GEN-INS-MTO-0001 | INSTRUMENT BULK MATERIAL TAKE OFF |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | MTO | Material Take Off | 0 | In Review | IFA | Issued for Approval |  | 05-Oct-2026 09:12:22 | wisuda.c@jutal.com | 05-Oct-2026 10:44:07 | Jumpol Sudjitjul | 12-Oct-2026 |  | Wichai Salee | 15-Oct-2026 |  | Pornlert Wanaphattharaphan | 16-Oct-2026 |  |  |  |  | 19-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000376 | MM-ZTK-1F-GEN-INS-PHI-0001 | INSTRUMENT AND CONTROL PHILOSOPHY |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | PHI | Philosophy | 0 | Submitted | IFR | Issued for Review |  | 12-May-2026 10:09:53 | wisuda.c@jutal.com | 12-May-2026 11:19:18 | Jumpol Sudjitjul | 19-May-2026 |  | Wichai Salee | 21-May-2026 | 17-Jun-2026 09:45:38 | Pornlert Wanaphattharaphan | 22-May-2026 | 17-Jun-2026 15:19:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-May-2026 | 17-Jun-2026 15:20:48 | 17-Jun-2026 09:16:29 | 0 |  |  | Approver | Locate
AO-001678 | MM-ZTK-1F-GEN-INS-PHI-0001 | INSTRUMENT AND CONTROL PHILOSOPHY |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | PHI | Philosophy | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 09:41:11 | wisuda.c@jutal.com | 25-Aug-2026 09:35:57 | Jumpol Sudjitjul | 01-Sep-2026 |  | Wichai Salee | 03-Sep-2026 | 26-Aug-2026 14:57:46 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 23:03:39 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 15:44:20 | 31-Aug-2026 10:19:34 | 0 |  |  | Approver | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0001 | ACTUATED CHOKE VALVE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:32:08 | zm169dc@jutal.com | 29-Apr-2026 09:19:43 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 19:19:10 |  |  | 08-May-2026 23:24:33 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:08:07 | 27-Apr-2026 15:15:20 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0002 | ACTUATED BALL VALVE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:32:38 | zm169dc@jutal.com | 29-Apr-2026 09:20:01 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 19:18:17 |  |  | 08-May-2026 23:25:25 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:08:50 | 27-Apr-2026 15:15:52 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0003 | ACTUATED COMPACT BALL VALVE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:33:06 | zm169dc@jutal.com | 29-Apr-2026 09:20:15 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 19:17:21 |  |  | 09-May-2026 00:17:33 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:09:13 | 27-Apr-2026 15:16:25 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0004 | PRESSURE RELIEF VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:33:32 | zm169dc@jutal.com | 29-Apr-2026 09:20:28 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 19:16:34 |  |  | 09-May-2026 00:16:19 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:09:39 | 27-Apr-2026 15:16:58 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0005 | CORIOLIS FLOW METERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:33:58 | zm169dc@jutal.com | 29-Apr-2026 09:26:23 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 19:15:27 |  |  | 09-May-2026 00:14:34 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:10:02 | 27-Apr-2026 15:17:30 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0006 | WELLHEAD CONTROL PANEL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:34:25 | zm169dc@jutal.com | 29-Apr-2026 09:26:38 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 19:14:14 |  |  | 09-May-2026 00:12:50 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:10:35 | 27-Apr-2026 15:18:03 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0007 | PLC SYSTEM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:34:54 | zm169dc@jutal.com | 29-Apr-2026 09:26:54 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 19:13:02 |  |  | 09-May-2026 00:09:43 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:10:55 | 27-Apr-2026 15:18:39 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0008 | CONTROL VALVE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:35:21 | zm169dc@jutal.com | 29-Apr-2026 09:27:12 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 19:09:38 |  |  | 09-May-2026 00:04:17 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:11:16 | 27-Apr-2026 15:19:10 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0009 | SELF-ACTUATED PRESSURE CONTROL VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:35:59 | zm169dc@jutal.com | 29-Apr-2026 09:29:19 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 19:04:06 |  |  | 08-May-2026 23:52:17 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:11:39 | 27-Apr-2026 15:19:41 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0010 | FIRE & GAS DETECTORS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:36:24 | zm169dc@jutal.com | 29-Apr-2026 09:29:31 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 19:02:16 |  |  | 08-May-2026 23:51:01 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:12:03 | 27-Apr-2026 15:20:14 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0011 | IN JUNCTION BOX |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:36:51 | zm169dc@jutal.com | 29-Apr-2026 09:29:49 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 19:00:57 |  |  | 08-May-2026 23:50:06 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:12:27 | 27-Apr-2026 15:20:48 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0012 | POSITION LIMIT SWITCH |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:37:17 | zm169dc@jutal.com | 29-Apr-2026 09:30:01 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 18:54:10 |  |  | 08-May-2026 23:49:02 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:12:55 | 27-Apr-2026 15:21:20 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0013 | PRESSURE GAUGES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:37:44 | zm169dc@jutal.com | 29-Apr-2026 09:31:13 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 18:47:58 |  |  | 08-May-2026 23:38:04 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:07:00 | 27-Apr-2026 15:21:49 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0014 | PRESSURE GAUGES (WIRELESS TYPE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:38:11 | zm169dc@jutal.com | 29-Apr-2026 09:31:26 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 18:42:26 |  |  | 08-May-2026 23:30:32 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:08:02 | 27-Apr-2026 15:22:20 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0015 | TEMPERATURE GAUGES AND THERMOWELLS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:38:40 | zm169dc@jutal.com | 29-Apr-2026 09:31:38 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 18:36:10 |  |  | 08-May-2026 23:29:29 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:13:13 | 27-Apr-2026 15:22:52 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0016 | TEMPERATURE TRANSMITTERS AND THERMOWELLS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:39:08 | zm169dc@jutal.com | 29-Apr-2026 09:31:54 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 18:30:41 |  |  | 08-May-2026 23:26:56 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:13:20 | 27-Apr-2026 15:23:21 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0017 | TEMPERATURE TRANSMITTERS (PIPE CLAMP) WIRELESS TYPE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:39:33 | zm169dc@jutal.com | 29-Apr-2026 09:33:18 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 18:26:38 |  |  | 08-May-2026 23:27:53 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:13:35 | 27-Apr-2026 15:23:56 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0018 | PRESSURE TRANSMITTERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:39:58 | zm169dc@jutal.com | 29-Apr-2026 09:33:29 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 18:25:04 |  |  | 08-May-2026 23:26:22 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:13:40 | 27-Apr-2026 15:24:29 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0019 | PRESSURE TRANSMITTERS (WIRELESS TYPE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:40:31 | zm169dc@jutal.com | 29-Apr-2026 09:33:42 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 18:23:53 |  |  | 06-May-2026 16:48:13 |  |  | Jumpol Sudjitjul |  | 07-May-2026 08:12:01 | 27-Apr-2026 15:25:01 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0020 | MAGNETIC LEVEL GAUGES AND TRANSMITTERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:41:02 | zm169dc@jutal.com | 29-Apr-2026 09:33:54 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 18:22:56 |  |  | 06-May-2026 16:45:57 |  |  | Jumpol Sudjitjul |  | 07-May-2026 08:13:43 | 27-Apr-2026 15:25:40 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0021 | DP LEVEL TRANSMITTERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:41:29 | zm169dc@jutal.com | 29-Apr-2026 09:34:46 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 18:19:26 |  |  | 06-May-2026 16:42:00 |  |  | Jumpol Sudjitjul |  | 07-May-2026 08:15:20 | 27-Apr-2026 15:26:11 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0022 | RESTRICTION ORIFICES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:42:12 | zm169dc@jutal.com | 29-Apr-2026 09:30:58 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 18:52:42 |  |  | 08-May-2026 23:40:21 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:13:57 | 27-Apr-2026 15:26:45 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0023 | VORTEX FLOW METERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:42:51 | zm169dc@jutal.com | 29-Apr-2026 09:31:15 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 18:43:55 |  |  | 08-May-2026 23:37:27 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:14:00 | 27-Apr-2026 15:27:15 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0024 | NON-INTRUSIVE SAND MONITORING SYSTEM (ACOUSTIC TYPE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:43:15 | zm169dc@jutal.com | 29-Apr-2026 09:31:29 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 18:39:50 |  |  | 08-May-2026 23:30:00 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:14:19 | 27-Apr-2026 15:27:45 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0025 | NON-INTRUSIVE WIRELESS SAND MONITORING SYSTEM (ULTRASONIC TYPE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:43:43 | zm169dc@jutal.com | 29-Apr-2026 09:31:42 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 18:34:12 |  |  | 08-May-2026 23:28:37 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:14:22 | 27-Apr-2026 15:28:21 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0026 | IN CABLE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:44:10 | zm169dc@jutal.com | 29-Apr-2026 09:27:14 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 19:11:21 |  |  | 09-May-2026 00:05:56 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:14:45 | 27-Apr-2026 15:28:54 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0027 | IN CABLE TRAY |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:44:42 | zm169dc@jutal.com | 29-Apr-2026 09:27:28 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 19:07:44 |  |  | 08-May-2026 23:59:00 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:15:03 | 27-Apr-2026 15:29:27 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0028 | IN CABLE GLAND |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:45:13 | zm169dc@jutal.com | 29-Apr-2026 09:27:45 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 19:06:27 |  |  | 08-May-2026 23:55:52 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:15:23 | 27-Apr-2026 15:29:56 | 0 |  |  |  | Locate
AO-000248 | MM-ZTK-1F-GEN-INS-RPT-0029 | IN FITTING AND TUBING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 28-Apr-2026 16:45:39 | zm169dc@jutal.com | 29-Apr-2026 09:27:59 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 19:05:18 |  |  | 08-May-2026 23:54:18 |  |  | Jumpol Sudjitjul |  | 09-May-2026 08:15:42 | 27-Apr-2026 15:30:27 | 0 |  |  |  | Locate
AO-000530 | MM-ZTK-1F-GEN-INS-RPT-0100 | CRITICALITY RATING ANALYSIS (INSTRUMENT) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 15:07:31 | zm169dc@jutal.com | 20-May-2026 16:27:16 | Jumpol Sudjitjul | 27-May-2026 |  | Wichai Salee | 29-May-2026 | 15-Jun-2026 09:48:35 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 15-Jun-2026 22:51:23 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 04-Jun-2026 | 16-Jun-2026 09:38:44 | 16-Jun-2026 03:34:04 | 0 |  |  | Approver | Locate
AO-001207 | MM-ZTK-1F-GEN-INS-RPT-0100 | CRITICALITY RATING ANALYSIS (INSTRUMENT) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 17:38:37 | zm169dc@jutal.com | 21-Jul-2026 07:46:46 | Jumpol Sudjitjul | 30-Jul-2026 |  | Wichai Salee | 03-Aug-2026 | 07-Aug-2026 13:57:53 | Pornlert Wanaphattharaphan | 04-Aug-2026 | 07-Aug-2026 21:51:47 | APPR | Approved | Jumpol Sudjitjul | 05-Aug-2026 | 08-Aug-2026 10:17:22 | 08-Aug-2026 04:34:14 | 0 |  |  | Approver | Locate
AO-000773 | MM-ZTK-1F-GEN-INS-SPE-0001 | PROJECT SPECIFICATION FOR ACTUATED CHOKE VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Revised | IFR | Issued for Review | 14-May-2026 | 14-Jun-2026 22:04:44 | wisuda.c@jutal.com | 10-Apr-2026 15:04:15 | Jumpol Sudjitjul |  | 22-Apr-2026 13:24:24 | Wichai Salee |  | 23-Apr-2026 17:07:35 | Pornlert Wanaphattharaphan |  | 27-Apr-2026 22:25:27 |  |  | Jumpol Sudjitjul |  | 28-Apr-2026 10:36:16 |  | 0 |  |  |  | Locate
AO-000797 | MM-ZTK-1F-GEN-INS-SPE-0001 | PROJECT SPECIFICATION FOR ACTUATED CHOKE VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  |  | wisuda.c@jutal.com | 15-Jun-2026 16:29:18 | Jumpol Sudjitjul | 22-Jun-2026 |  | Wichai Salee | 24-Jun-2026 | 30-Jun-2026 16:33:56 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 30-Jun-2026 22:03:35 | APPR | Approved | Jumpol Sudjitjul | 26-Jun-2026 | 01-Jul-2026 08:33:12 | 01-Jul-2026 01:47:52 | 0 |  |  | Approver | Locate
AO-000174 | MM-ZTK-1F-GEN-INS-SPE-0002 | PROJECT SPECIFICATION FOR ACTUATED BALL VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 17:30:01 | wisuda.c@jutal.com | 21-Apr-2026 09:40:37 | Jumpol Sudjitjul | 28-Apr-2026 |  | Wichai Salee | 30-Apr-2026 | 11-May-2026 10:13:21 | Pornlert Wanaphattharaphan | 05-May-2026 | 11-May-2026 16:29:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 11-May-2026 17:42:40 | 11-May-2026 11:07:52 | 0 |  |  | Approver | Locate
AO-000921 | MM-ZTK-1F-GEN-INS-SPE-0002 | PROJECT SPECIFICATION FOR ACTUATED BALL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 27-Jun-2026 19:24:49 | wisuda.c@jutal.com | 27-Jun-2026 19:31:49 | Jumpol Sudjitjul | 06-Jul-2026 |  | Wichai Salee | 08-Jul-2026 | 13-Jul-2026 15:56:07 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 13-Jul-2026 23:21:57 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 14-Jul-2026 08:48:24 | 14-Jul-2026 02:08:17 | 0 |  |  | Approver | Locate
AO-000116 | MM-ZTK-1F-GEN-INS-SPE-0004 | PROJECT SPECIFICATION FOR PRESSURE RELIEF VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 13-Apr-2026 10:13:57 | zm169dc@jutal.com | 13-Apr-2026 11:17:47 | Jumpol Sudjitjul | 22-Apr-2026 |  | Wichai Salee | 24-Apr-2026 | 05-May-2026 11:28:14 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 05-May-2026 22:10:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 06-May-2026 09:19:06 | 06-May-2026 02:54:10 | 0 |  |  | Approver | Locate
AO-000922 | MM-ZTK-1F-GEN-INS-SPE-0004 | PROJECT SPECIFICATION FOR PRESSURE RELIEF VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 27-Jun-2026 19:25:40 | wisuda.c@jutal.com | 27-Jun-2026 19:32:26 | Jumpol Sudjitjul | 06-Jul-2026 |  | Wichai Salee | 08-Jul-2026 | 13-Jul-2026 15:56:21 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 13-Jul-2026 23:22:20 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 14-Jul-2026 08:49:41 | 14-Jul-2026 02:09:40 | 0 |  |  | Approver | Locate
AO-000349 | MM-ZTK-1F-GEN-INS-SPE-0005 | PROJECT SPECIFICATION FOR CORIOLIS FLOW METERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:52:49 | wisuda.c@jutal.com | 11-May-2026 11:11:45 | Jumpol Sudjitjul | 18-May-2026 |  | Wichai Salee | 20-May-2026 | 02-Jun-2026 16:11:02 | Pornlert Wanaphattharaphan | 21-May-2026 | 05-Jun-2026 23:27:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 07-Jun-2026 17:22:56 | 07-Jun-2026 11:35:31 | 0 |  |  | Approver | Locate
AO-001181 | MM-ZTK-1F-GEN-INS-SPE-0005 | PROJECT SPECIFICATION FOR CORIOLIS FLOW METERS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 08:44:16 | wisuda.c@jutal.com | 20-Jul-2026 16:17:57 | Jumpol Sudjitjul | 27-Jul-2026 |  | Wichai Salee | 31-Jul-2026 | 06-Aug-2026 16:38:04 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 07-Aug-2026 05:31:45 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 07-Aug-2026 08:54:38 | 07-Aug-2026 02:26:51 | 0 |  |  | Approver | Locate
AO-000175 | MM-ZTK-1F-GEN-INS-SPE-0006 | PROJECT SPECIFICATION FOR WELLHEAD CONTROL PANEL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 17:30:35 | wisuda.c@jutal.com | 21-Apr-2026 09:40:50 | Jumpol Sudjitjul | 28-Apr-2026 |  | Wichai Salee | 30-Apr-2026 | 11-May-2026 14:12:05 | Pornlert Wanaphattharaphan | 05-May-2026 | 11-May-2026 20:17:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 12-May-2026 10:27:32 | 12-May-2026 03:38:23 | 0 |  |  | Approver | Locate
AO-001170 | MM-ZTK-1F-GEN-INS-SPE-0006 | PROJECT SPECIFICATION FOR WELLHEAD CONTROL PANEL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:30:54 | wisuda.c@jutal.com | 20-Jul-2026 14:06:03 | Jumpol Sudjitjul | 27-Jul-2026 |  | Wichai Salee | 31-Jul-2026 | 01-Aug-2026 22:02:50 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 01:10:48 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:04:28 | 03-Aug-2026 02:22:24 | 0 |  |  | Approver | Locate
AO-000351 | MM-ZTK-1F-GEN-INS-SPE-0007 | PROJECT SPECIFICATION FOR SAND MONITORING SYSTEM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:53:19 | wisuda.c@jutal.com | 11-May-2026 11:11:57 | Jumpol Sudjitjul | 18-May-2026 |  | Wichai Salee | 20-May-2026 | 02-Jun-2026 16:12:29 | Pornlert Wanaphattharaphan | 21-May-2026 | 05-Jun-2026 23:27:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 07-Jun-2026 17:23:43 | 07-Jun-2026 11:36:45 | 0 |  |  | Approver | Locate
AO-001754 | MM-ZTK-1F-GEN-INS-SPE-0007 | PROJECT SPECIFICATION FOR SAND MONITORING SYSTEM |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 11:37:07 | wisuda.c@jutal.com | 28-Aug-2026 14:18:46 | Jumpol Sudjitjul | 04-Sep-2026 |  | Wichai Salee | 08-Sep-2026 | 09-Sep-2026 12:05:46 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 11-Sep-2026 22:28:15 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 12-Sep-2026 20:38:02 | 12-Sep-2026 14:16:58 | 0 |  |  | Approver | Locate
AO-000208 | MM-ZTK-1F-GEN-INS-SPE-0008 | PROJECT SPECIFICATION FOR PLC SYSTEM (PCS/SIS/FGS FUNCTIONS) AND SCADA SYSTEM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 22-Apr-2026 11:01:19 | wisuda.c@jutal.com | 22-Apr-2026 13:22:06 | Jumpol Sudjitjul | 29-Apr-2026 |  | Wichai Salee | 05-May-2026 | 14-May-2026 16:24:38 | Pornlert Wanaphattharaphan | 06-May-2026 | 14-May-2026 22:38:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 15-May-2026 10:36:04 | 15-May-2026 04:13:42 | 0 |  |  | Approver | Locate
AO-001474 | MM-ZTK-1F-GEN-INS-SPE-0008 | PROJECT SPECIFICATION FOR PLC SYSTEM (PCS/SIS/FGS FUNCTIONS) AND SCADA SYSTEM |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 10-Aug-2026 11:41:46 | wisuda.c@jutal.com | 10-Aug-2026 14:53:59 | Jumpol Sudjitjul | 18-Aug-2026 |  | Wichai Salee | 20-Aug-2026 | 24-Aug-2026 15:39:37 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 27-Aug-2026 14:35:52 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 27-Aug-2026 16:41:26 | 27-Aug-2026 10:54:42 | 0 |  |  | Approver | Locate
AO-000176 | MM-ZTK-1F-GEN-INS-SPE-0009 | PROJECT SPECIFICATION FOR CONTROL VALVES AND SELF-ACTUATED PRESSURE CONTROL VALVE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 17:31:03 | wisuda.c@jutal.com | 21-Apr-2026 09:41:03 | Jumpol Sudjitjul | 28-Apr-2026 |  | Wichai Salee | 30-Apr-2026 | 11-May-2026 14:12:56 | Pornlert Wanaphattharaphan | 05-May-2026 | 11-May-2026 20:28:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 12-May-2026 10:26:02 | 12-May-2026 03:37:08 | 0 |  |  | Approver | Locate
AO-000923 | MM-ZTK-1F-GEN-INS-SPE-0009 | PROJECT SPECIFICATION FOR CONTROL VALVES AND SELF-ACTUATED PRESSURE CONTROL VALVE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 27-Jun-2026 19:00:47 | wisuda.c@jutal.com | 27-Jun-2026 19:07:55 | Jumpol Sudjitjul | 06-Jul-2026 |  | Wichai Salee | 08-Jul-2026 | 03-Jul-2026 14:02:41 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 11-Jul-2026 13:55:47 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 12-Jul-2026 11:29:17 | 12-Jul-2026 04:39:56 | 0 |  |  | Approver | Locate
AO-000356 | MM-ZTK-1F-GEN-INS-SPE-0011 | PROJECT SPECIFICATION FOR FIRE & GAS DETECTORS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:06:47 | wisuda.c@jutal.com | 11-May-2026 11:12:10 | Jumpol Sudjitjul | 18-May-2026 |  | Wichai Salee | 20-May-2026 | 02-Jun-2026 16:13:42 | Pornlert Wanaphattharaphan | 21-May-2026 | 05-Jun-2026 23:30:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 07-Jun-2026 17:24:14 | 07-Jun-2026 11:32:59 | 0 |  |  | Approver | Locate
AO-001085 | MM-ZTK-1F-GEN-INS-SPE-0011 | PROJECT SPECIFICATION FOR FIRE & GAS DETECTORS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 12-Jul-2026 11:39:32 | wisuda.c@jutal.com | 12-Jul-2026 12:01:12 | Jumpol Sudjitjul | 17-Jul-2026 |  | Wichai Salee | 21-Jul-2026 | 23-Jul-2026 20:08:48 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 26-Jul-2026 01:44:11 | APPR | Approved | Jumpol Sudjitjul | 23-Jul-2026 | 27-Jul-2026 14:53:08 | 27-Jul-2026 09:37:55 | 0 |  |  | Approver | Locate
AO-000177 | MM-ZTK-1F-GEN-INS-SPE-0012 | PROJECT SPECIFICATION FOR INSTRUMENT BULK MATERIAL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 17:31:38 | wisuda.c@jutal.com | 21-Apr-2026 09:41:18 | Jumpol Sudjitjul | 28-Apr-2026 |  | Wichai Salee | 30-Apr-2026 | 11-May-2026 10:10:20 | Pornlert Wanaphattharaphan | 05-May-2026 | 11-May-2026 15:29:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 11-May-2026 17:41:02 | 11-May-2026 18:06:37 | 0 |  |  | Approver | Locate
AO-000748 | MM-ZTK-1F-GEN-INS-SPE-0012 | PROJECT SPECIFICATION FOR INSTRUMENT BULK MATERIAL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 08:37:46 | wisuda.c@jutal.com | 12-Jun-2026 15:11:12 | Jumpol Sudjitjul | 19-Jun-2026 |  | Wichai Salee | 23-Jun-2026 | 02-Jul-2026 17:38:38 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 02-Jul-2026 22:06:27 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 03-Jul-2026 11:07:54 | 03-Jul-2026 04:17:34 | 0 |  |  | Approver | Locate
AO-000561 | MM-ZTK-1F-GEN-INS-SPE-0013 | PROJECT SPECIFICATION FOR INSTALLATION OF INSTRUMENTATION AND CONTROL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 17:49:35 | wisuda.c@jutal.com | 21-May-2026 18:00:04 | Jumpol Sudjitjul | 29-May-2026 |  | Wichai Salee | 04-Jun-2026 | 17-Jun-2026 11:41:35 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 17-Jun-2026 15:33:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 17-Jun-2026 15:37:27 | 17-Jun-2026 09:32:20 | 0 |  |  | Approver | Locate
AO-001256 | MM-ZTK-1F-GEN-INS-SPE-0013 | PROJECT SPECIFICATION FOR INSTALLATION OF INSTRUMENTATION AND CONTROL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 09:57:52 | wisuda.c@jutal.com | 24-Jul-2026 11:15:05 | Jumpol Sudjitjul | 04-Aug-2026 |  | Wichai Salee | 06-Aug-2026 | 07-Aug-2026 15:12:24 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 07-Aug-2026 21:53:18 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 08-Aug-2026 10:18:16 | 08-Aug-2026 04:14:57 | 0 |  |  | Approver | Locate
AO-000117 | MM-ZTK-1F-GEN-INS-SPE-0014 | PROJECT SPECIFICATION FOR GENERAL FIELD INSTRUMENTS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 13-Apr-2026 10:14:21 | zm169dc@jutal.com | 13-Apr-2026 11:18:42 | Jumpol Sudjitjul | 22-Apr-2026 |  | Wichai Salee | 24-Apr-2026 | 06-May-2026 13:59:19 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 06-May-2026 16:21:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 06-May-2026 16:26:54 | 06-May-2026 10:16:55 | 0 |  |  | Approver | Locate
AO-001551 | MM-ZTK-1F-GEN-INS-SPE-0014 | PROJECT SPECIFICATION FOR GENERAL FIELD INSTRUMENTS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 14:17:05 | wisuda.c@jutal.com | 17-Aug-2026 16:09:30 | Jumpol Sudjitjul | 24-Aug-2026 |  | Wichai Salee | 26-Aug-2026 | 24-Aug-2026 16:13:13 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 21:51:32 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 16:41:33 | 30-Aug-2026 10:28:29 | 0 |  |  | Approver | Locate
AO-000349 | MM-ZTK-1F-GEN-INS-SPE-0025 | PROJECT SPECIFICATION FOR VORTEX FLOW METERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:53:50 | wisuda.c@jutal.com | 11-May-2026 11:12:22 | Jumpol Sudjitjul | 18-May-2026 |  | Wichai Salee | 20-May-2026 | 02-Jun-2026 16:15:06 | Pornlert Wanaphattharaphan | 21-May-2026 | 05-Jun-2026 23:33:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 07-Jun-2026 17:24:45 | 07-Jun-2026 11:37:57 | 0 |  |  | Approver | Locate
AO-001183 | MM-ZTK-1F-GEN-INS-SPE-0025 | PROJECT SPECIFICATION FOR VORTEX FLOW METERS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 08:44:53 | wisuda.c@jutal.com | 20-Jul-2026 14:06:29 | Jumpol Sudjitjul | 27-Jul-2026 |  | Wichai Salee | 31-Jul-2026 | 01-Aug-2026 22:04:04 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 03-Aug-2026 01:11:02 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 03-Aug-2026 09:04:00 | 03-Aug-2026 02:21:13 | 0 |  |  | Approver | Locate
AO-000803 | MM-ZTK-1F-GEN-INS-TBE-0001 | TECHNICAL BID EVALUATION FOR ACTUATED CHOKE VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 12-Jun-2026 19:51:33 | wisuda.c@jutal.com | 15-Jun-2026 21:18:16 | Jumpol Sudjitjul | 23-Jun-2026 |  | Wichai Salee | 25-Jun-2026 | 16-Jun-2026 12:50:56 | Pornlert Wanaphattharaphan | 26-Jun-2026 | 17-Jun-2026 11:46:35 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 29-Jun-2026 | 17-Jun-2026 13:09:05 | 17-Jun-2026 07:01:23 | 0 |  |  | Approver | Locate
AO-000940 | MM-ZTK-1F-GEN-INS-TBE-0001 | TECHNICAL BID EVALUATION FOR ACTUATED CHOKE VALVES |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 29-Jun-2026 08:39:41 | wisuda.c@jutal.com | 30-Jun-2026 08:38:07 | Jumpol Sudjitjul | 07-Jul-2026 |  | Wichai Salee | 09-Jul-2026 | 30-Jun-2026 11:38:20 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 30-Jun-2026 16:39:05 | APPR | Approved | Jumpol Sudjitjul | 13-Jul-2026 | 30-Jun-2026 16:50:32 | 30-Jun-2026 10:05:15 | 0 |  |  | Approver | Locate
AO-001296 | MM-ZTK-1F-GEN-INS-TBE-0002 | TECHNICAL BID EVALUATION FOR ACTUATED BALL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 27-Jul-2026 08:39:14 | wisuda.c@jutal.com | 27-Jul-2026 16:24:31 | Jumpol Sudjitjul | 05-Aug-2026 |  | Wichai Salee | 07-Aug-2026 | 01-Aug-2026 22:23:20 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 02-Aug-2026 16:26:55 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-Aug-2026 | 02-Aug-2026 21:13:49 | 02-Aug-2026 14:43:40 | 0 |  |  | Approver | Locate
AO-001673 | MM-ZTK-1F-GEN-INS-TBE-0002 | TECHNICAL BID EVALUATION FOR ACTUATED BALL VALVES |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 24-Aug-2026 09:41:59 | wisuda.c@jutal.com | 25-Aug-2026 08:57:00 | Jumpol Sudjitjul | 01-Sep-2026 |  | Wichai Salee | 03-Sep-2026 | 02-Sep-2026 08:58:45 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 02-Sep-2026 23:56:06 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 03-Sep-2026 09:48:26 | 03-Sep-2026 03:02:57 | 0 |  |  | Approver | Locate
AO-001112 | MM-ZTK-1F-GEN-INS-TBE-0003 | TECHNICAL BID EVALUATION FOR ACTUATED COMPACT BALL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 14-Jul-2026 17:32:48 | wisuda.c@jutal.com | 14-Jul-2026 20:01:07 | Jumpol Sudjitjul | 22-Jul-2026 |  | Wichai Salee | 24-Jul-2026 | 15-Jul-2026 11:43:54 | Pornlert Wanaphattharaphan | 27-Jul-2026 | 16-Jul-2026 17:29:56 | APPR | Approved | Jumpol Sudjitjul | 30-Jul-2026 | 16-Jul-2026 17:53:59 | 16-Jul-2026 10:57:54 | 0 |  |  | Approver | Locate
AO-001299 | MM-ZTK-1F-GEN-INS-TBE-0004 | TECHNICAL BID EVALUATION FOR PRESSURE RELIEF VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 27-Jul-2026 08:39:55 | wisuda.c@jutal.com | 27-Jul-2026 16:24:48 | Jumpol Sudjitjul | 05-Aug-2026 |  | Wichai Salee | 07-Aug-2026 | 01-Aug-2026 23:42:07 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 02-Aug-2026 13:16:33 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 02-Aug-2026 21:14:49 | 02-Aug-2026 14:46:28 | 0 |  |  | Approver | Locate
AO-001115 | MM-ZTK-1F-GEN-INS-TBE-0006 | TECHNICAL BID EVALUATION FOR WELLHEAD CONTROL PANEL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 14-Jul-2026 17:33:22 | wisuda.c@jutal.com | 14-Jul-2026 20:01:28 | Jumpol Sudjitjul | 22-Jul-2026 |  | Wichai Salee | 24-Jul-2026 | 15-Jul-2026 11:44:05 | Pornlert Wanaphattharaphan | 27-Jul-2026 | 16-Jul-2026 13:14:56 | APPR | Approved | Jumpol Sudjitjul | 30-Jul-2026 | 16-Jul-2026 14:03:06 | 16-Jul-2026 07:31:49 | 0 |  |  | Approver | Locate
AO-001381 | MM-ZTK-1F-GEN-INS-TBE-0008 | TECHNICAL BID EVALUATION FOR PLC SYSTEM |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 03-Aug-2026 11:26:49 | wisuda.c@jutal.com | 03-Aug-2026 13:41:04 | Jumpol Sudjitjul | 10-Aug-2026 |  | Wichai Salee | 13-Aug-2026 | 03-Aug-2026 19:59:11 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 03-Aug-2026 23:35:09 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 04-Aug-2026 08:49:12 | 04-Aug-2026 02:18:48 | 0 |  |  | Approver | Locate
AO-001382 | MM-ZTK-1F-GEN-INS-TBE-0009 | TECHNICAL BID EVALUATION FOR CONTROL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 03-Aug-2026 11:27:33 | wisuda.c@jutal.com | 03-Aug-2026 13:41:21 | Jumpol Sudjitjul | 10-Aug-2026 |  | Wichai Salee | 13-Aug-2026 | 03-Aug-2026 20:07:23 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 06-Aug-2026 20:08:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 07-Aug-2026 08:54:01 | 07-Aug-2026 02:10:36 | 0 |  |  | Approver | Locate
AO-001546 | MM-ZTK-1F-GEN-INS-TBE-0009 | TECHNICAL BID EVALUATION FOR CONTROL VALVES |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 17-Aug-2026 14:17:46 | wisuda.c@jutal.com | 17-Aug-2026 16:07:53 | Jumpol Sudjitjul | 24-Aug-2026 |  | Wichai Salee | 26-Aug-2026 | 24-Aug-2026 16:11:14 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 26-Aug-2026 00:27:46 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 26-Aug-2026 08:30:37 | 26-Aug-2026 01:56:55 | 0 |  |  | Approver | Locate
AO-001297 | MM-ZTK-1F-GEN-INS-TBE-0010 | TECHNICAL BID EVALUATION FOR SELF-ACTUATED PRESSURE CONTROL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 27-Jul-2026 08:40:20 | wisuda.c@jutal.com | 27-Jul-2026 16:25:07 | Jumpol Sudjitjul | 05-Aug-2026 |  | Wichai Salee | 07-Aug-2026 | 01-Aug-2026 22:37:25 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 02-Aug-2026 13:20:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 02-Aug-2026 21:15:04 | 02-Aug-2026 14:47:45 | 0 |  |  | Approver | Locate
AO-001475 | MM-ZTK-1F-GEN-INS-TBE-0010 | TECHNICAL BID EVALUATION FOR SELF-ACTUATED PRESSURE CONTROL VALVES |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 10-Aug-2026 11:42:21 | wisuda.c@jutal.com | 10-Aug-2026 14:52:59 | Jumpol Sudjitjul | 18-Aug-2026 |  | Wichai Salee | 20-Aug-2026 | 17-Aug-2026 10:55:53 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 17-Aug-2026 16:31:44 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 17-Aug-2026 17:06:29 | 17-Aug-2026 10:54:09 | 0 |  |  | Approver | Locate
AO-002445 | MM-ZTK-1F-GEN-INS-TBE-0013 | TECHNICAL BID EVALUATION FOR POSITION LIMIT SWITCHES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 08-Oct-2026 15:37:36 | wisuda.c@jutal.com | 08-Oct-2026 15:52:00 | Jumpol Sudjitjul | 16-Oct-2026 |  | Wichai Salee | 20-Oct-2026 | 15-Oct-2026 14:31:34 | Pornlert Wanaphattharaphan | 21-Oct-2026 | 15-Oct-2026 22:31:44 | APPR | Approved | Jumpol Sudjitjul | 22-Oct-2026 | 16-Oct-2026 14:01:40 | 16-Oct-2026 07:48:49 | 0 |  |  | Approver | Locate
AO-002559 | MM-ZTK-1F-GEN-INS-TBE-0017 | TECHNICAL BID EVALUATION FOR TEMPERATURE TRANSMITTERS AND THERMOWELLS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | In Review | IFP | Issued for Purchase |  | 16-Oct-2026 19:13:50 | wisuda.c@jutal.com | 18-Oct-2026 16:41:23 | Jumpol Sudjitjul | 26-Oct-2026 |  | Wichai Salee | 28-Oct-2026 |  | Pornlert Wanaphattharaphan | 29-Oct-2026 |  |  |  |  | 30-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-002352 | MM-ZTK-1F-GEN-INS-TBE-0021 | TECHNICAL BID EVALUATION FOR MAGNETIC LEVEL GAUGES AND TRANSMITTERS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 05-Oct-2026 09:13:04 | wisuda.c@jutal.com | 05-Oct-2026 10:53:36 | Jumpol Sudjitjul | 12-Oct-2026 |  | Wichai Salee | 15-Oct-2026 | 14-Oct-2026 14:45:33 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 15-Oct-2026 22:30:27 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 16-Oct-2026 14:02:42 | 16-Oct-2026 07:36:53 | 0 |  |  | Approver | Locate
AO-002278 | MM-ZTK-1F-GEN-INS-TBE-0024 | TECHNICAL BID EVALUATION FOR RESTRICTION ORIFICES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 28-Sep-2026 09:37:01 | wisuda.c@jutal.com | 28-Sep-2026 12:52:31 | Jumpol Sudjitjul | 05-Oct-2026 |  | Wichai Salee | 07-Oct-2026 | 29-Sep-2026 20:11:26 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:46:25 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 11:48:01 | 30-Sep-2026 05:26:23 | 0 |  |  | Approver | Locate
AO-002442 | MM-ZTK-1F-GEN-INS-TBE-0026 | TECHNICAL BID EVALUATION FOR SAND MONITORING SYSTEM (NON-INTRUSIVE PASSIVE ACOUSTICS TYPE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 08-Oct-2026 14:05:19 | wisuda.c@jutal.com | 08-Oct-2026 15:15:31 | Jumpol Sudjitjul | 16-Oct-2026 |  | Wichai Salee | 20-Oct-2026 | 15-Oct-2026 14:55:25 | Pornlert Wanaphattharaphan | 21-Oct-2026 | 15-Oct-2026 22:33:07 | APPR | Approved | Jumpol Sudjitjul | 22-Oct-2026 | 16-Oct-2026 14:03:33 | 16-Oct-2026 07:57:54 | 0 |  |  | Approver | Locate
AO-000111 | MM-ZTK-1F-GEN-MEC-BOD-0001 | MECHANICAL DESIGN BASIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | BOD | Basis of Design | 0 | Submitted | IFR | Issued for Review |  | 10-Apr-2026 14:15:04 | zm169dc@jutal.com | 10-Apr-2026 15:29:19 | Jumpol Sudjitjul | 22-Apr-2026 | 22-Apr-2026 13:31:54 | Aphisit Pinkaew | 24-Apr-2026 | 22-Apr-2026 15:42:55 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 26-Apr-2026 01:22:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 27-Apr-2026 16:15:26 | 27-Apr-2026 10:27:40 | 0 |  |  | Approver | Locate
AO-001079 | MM-ZTK-1F-GEN-MEC-BOD-0001 | MECHANICAL DESIGN BASIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 12-Jul-2026 11:38:04 | wisuda.c@jutal.com | 12-Jul-2026 11:59:16 | Jumpol Sudjitjul | 17-Jul-2026 | 16-Jul-2026 09:46:46 | Aphisit Pinkaew | 21-Jul-2026 | 28-Jul-2026 19:39:38 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 28-Jul-2026 22:31:39 | APPR | Approved | Jumpol Sudjitjul | 23-Jul-2026 | 30-Jul-2026 09:29:01 | 30-Jul-2026 03:28:47 | 0 |  |  | Approver | Locate
AO-000120 | MM-ZTK-1F-GEN-MEC-DTS-0001 | DATASHEET FOR OFFSHORE PEDESTAL CRANE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 13-Apr-2026 10:12:04 | zm169dc@jutal.com | 13-Apr-2026 11:06:56 | Jumpol Sudjitjul | 22-Apr-2026 | 14-Apr-2026 08:14:19 | Aphisit Pinkaew | 24-Apr-2026 | 23-Apr-2026 16:44:56 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 29-Apr-2026 00:22:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 29-Apr-2026 08:33:11 | 30-Apr-2026 04:49:54 | 0 |  |  | Approver | Locate
AO-001151 | MM-ZTK-1F-GEN-MEC-DTS-0001 | DATASHEET FOR OFFSHORE PEDESTAL CRANE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 21:10:11 | wisuda.c@jutal.com | 17-Jul-2026 10:38:13 | Jumpol Sudjitjul | 24-Jul-2026 | 18-Jul-2026 08:12:18 | Aphisit Pinkaew | 30-Jul-2026 | 29-Jul-2026 09:39:24 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 30-Jul-2026 18:11:58 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 30-Jul-2026 19:09:51 | 30-Jul-2026 12:41:37 | 0 |  |  | Approver | Locate
AO-000149 | MM-ZTK-1F-GEN-MEC-DTS-0002 | DATASHEET FOR TEST SEPARATOR |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 17-Apr-2026 23:39:03 | wisuda.c@jutal.com | 19-Apr-2026 21:48:41 | Jumpol Sudjitjul | 27-Apr-2026 | 22-Apr-2026 17:23:14 | Aphisit Pinkaew | 29-Apr-2026 | 03-May-2026 20:24:37 | Pornlert Wanaphattharaphan | 30-Apr-2026 | 05-May-2026 23:41:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-May-2026 | 06-May-2026 09:20:13 | 06-May-2026 02:55:29 | 0 |  |  | Approver | Locate
AO-001168 | MM-ZTK-1F-GEN-MEC-DTS-0002 | DATASHEET FOR TEST SEPARATOR |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:25:16 | wisuda.c@jutal.com | 20-Jul-2026 14:14:21 | Jumpol Sudjitjul | 27-Jul-2026 | 24-Jul-2026 14:13:32 | Aphisit Pinkaew | 31-Jul-2026 | 04-Aug-2026 18:53:17 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 05-Aug-2026 20:42:53 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 06-Aug-2026 09:16:27 | 06-Aug-2026 03:16:57 | 0 |  |  | Approver | Locate
AO-000287 | MM-ZTK-1F-GEN-MEC-DTS-0003 | DATASHEET FOR INSTRUMENT GAS FILTER COALESCER |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 11:02:52 | wisuda.c@jutal.com | 04-May-2026 13:18:47 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 18:44:30 | Aphisit Pinkaew | 13-May-2026 | 11-May-2026 19:13:41 | Pornlert Wanaphattharaphan | 14-May-2026 | 12-May-2026 00:00:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 12-May-2026 10:23:16 | 12-May-2026 03:39:45 | 0 |  |  | Approver | Locate
AO-001168 | MM-ZTK-1F-GEN-MEC-DTS-0003 | DATASHEET FOR INSTRUMENT GAS FILTER COALESCER |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:25:45 | wisuda.c@jutal.com | 20-Jul-2026 14:15:04 | Jumpol Sudjitjul | 27-Jul-2026 | 24-Jul-2026 14:17:02 | Aphisit Pinkaew | 31-Jul-2026 | 04-Aug-2026 18:55:19 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 05-Aug-2026 20:45:35 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 06-Aug-2026 09:17:50 | 06-Aug-2026 03:18:18 | 0 |  |  | Approver | Locate
AO-000150 | MM-ZTK-1F-GEN-MEC-DTS-0004 | DATASHEET FOR CLOSED DRAIN SUMP VESSEL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 17-Apr-2026 23:39:38 | wisuda.c@jutal.com | 19-Apr-2026 21:50:54 | Jumpol Sudjitjul | 27-Apr-2026 | 24-Apr-2026 12:55:16 | Aphisit Pinkaew | 29-Apr-2026 | 04-May-2026 11:21:34 | Pornlert Wanaphattharaphan | 30-Apr-2026 | 05-May-2026 23:54:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-May-2026 | 06-May-2026 09:30:44 | 06-May-2026 02:56:48 | 0 |  |  | Approver | Locate
AO-001168 | MM-ZTK-1F-GEN-MEC-DTS-0004 | DATASHEET FOR CLOSED DRAIN SUMP VESSEL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:26:14 | wisuda.c@jutal.com | 20-Jul-2026 14:15:31 | Jumpol Sudjitjul | 27-Jul-2026 | 24-Jul-2026 14:19:15 | Aphisit Pinkaew | 31-Jul-2026 | 04-Aug-2026 19:09:44 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 05-Aug-2026 20:46:50 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 06-Aug-2026 09:32:07 | 06-Aug-2026 04:00:38 | 0 |  |  | Approver | Locate
AO-000155 | MM-ZTK-1F-GEN-MEC-DTS-0005 | DATASHEET FOR CLOSED DRAIN SUMP PUMP SKID |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 18-Apr-2026 19:32:53 | wisuda.c@jutal.com | 19-Apr-2026 21:53:28 | Jumpol Sudjitjul | 27-Apr-2026 | 22-Apr-2026 17:59:28 | Aphisit Pinkaew | 29-Apr-2026 | 07-May-2026 11:53:15 | Pornlert Wanaphattharaphan | 30-Apr-2026 | 07-May-2026 15:31:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-May-2026 | 07-May-2026 16:22:14 | 07-May-2026 09:47:11 | 0 |  |  | Approver | Locate
AO-001606 | MM-ZTK-1F-GEN-MEC-DTS-0005 | DATASHEET FOR CLOSED DRAIN SUMP PUMP SKID |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 10:44:18 | wisuda.c@jutal.com | 19-Aug-2026 11:06:40 | Jumpol Sudjitjul | 26-Aug-2026 | 26-Aug-2026 23:10:37 | Aphisit Pinkaew | 28-Aug-2026 | 30-Aug-2026 08:46:33 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 30-Aug-2026 12:10:35 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 30-Aug-2026 16:42:32 | 30-Aug-2026 11:02:20 | 0 |  |  | Approver | Locate
AO-000158 | MM-ZTK-1F-GEN-MEC-DTS-0006 | DATASHEET FOR CHEMICAL INJECTION PUMP SKID |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 18-Apr-2026 19:33:24 | wisuda.c@jutal.com | 19-Apr-2026 21:53:42 | Jumpol Sudjitjul | 27-Apr-2026 |  | Aphisit Pinkaew | 29-Apr-2026 | 08-May-2026 10:03:44 | Pornlert Wanaphattharaphan | 30-Apr-2026 | 08-May-2026 22:29:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-May-2026 | 08-May-2026 22:41:22 | 08-May-2026 15:46:45 | 0 |  |  | Approver | Locate
AO-001606 | MM-ZTK-1F-GEN-MEC-DTS-0006 | DATASHEET FOR CHEMICAL INJECTION PUMP SKID |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 10:44:59 | wisuda.c@jutal.com | 19-Aug-2026 11:07:25 | Jumpol Sudjitjul | 26-Aug-2026 | 26-Aug-2026 23:10:14 | Aphisit Pinkaew | 28-Aug-2026 | 30-Aug-2026 08:52:24 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 30-Aug-2026 12:23:39 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 30-Aug-2026 16:44:01 | 30-Aug-2026 11:03:29 | 0 |  |  | Approver | Locate
AO-000163 | MM-ZTK-1F-GEN-MEC-DTS-0007 | DATASHEET FOR CHEMICAL STORAGE TANKS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 17:24:42 | wisuda.c@jutal.com | 21-Apr-2026 09:13:04 | Jumpol Sudjitjul | 28-Apr-2026 | 23-Apr-2026 18:27:56 | Aphisit Pinkaew | 30-Apr-2026 | 08-May-2026 15:48:48 | Pornlert Wanaphattharaphan | 05-May-2026 | 08-May-2026 22:54:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 09-May-2026 08:17:04 | 09-May-2026 02:18:45 | 0 |  |  | Approver | Locate
AO-001606 | MM-ZTK-1F-GEN-MEC-DTS-0007 | DATASHEET FOR CHEMICAL STORAGE TANKS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 09:54:38 | wisuda.c@jutal.com | 19-Aug-2026 11:07:59 | Jumpol Sudjitjul | 26-Aug-2026 | 26-Aug-2026 22:49:01 | Aphisit Pinkaew | 28-Aug-2026 | 30-Aug-2026 08:54:42 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 30-Aug-2026 12:26:26 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 30-Aug-2026 16:45:29 | 30-Aug-2026 10:13:34 | 0 |  |  | Approver | Locate
AO-000373 | MM-ZTK-1F-GEN-MEC-DTS-0008 | DATASHEET FOR MATERIAL HANDLING EQUIPMENT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 12-May-2026 10:08:04 | wisuda.c@jutal.com | 12-May-2026 11:25:59 | Jumpol Sudjitjul | 19-May-2026 | 13-May-2026 07:21:39 | Aphisit Pinkaew | 21-May-2026 | 26-May-2026 20:48:21 | Pornlert Wanaphattharaphan | 22-May-2026 | 31-May-2026 00:59:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-May-2026 | 31-May-2026 20:48:34 | 31-May-2026 14:20:16 | 0 |  |  | Approver | Locate
AO-002335 | MM-ZTK-1F-GEN-MEC-DTS-0008 | DATASHEET FOR MATERIAL HANDLING EQUIPMENT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 02-Oct-2026 11:58:18 | wisuda.c@jutal.com | 02-Oct-2026 17:57:49 | Jumpol Sudjitjul | 12-Oct-2026 | 07-Oct-2026 13:25:59 | Aphisit Pinkaew | 15-Oct-2026 | 11-Oct-2026 13:28:26 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 12-Oct-2026 01:48:14 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 12-Oct-2026 11:33:17 | 12-Oct-2026 05:47:23 | 0 |  |  | Approver | Locate
AO-000283 | MM-ZTK-1F-GEN-MEC-LIS-0001 | MECHANICAL EQUIPMENT LIST |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 30-Apr-2026 16:08:08 | wisuda.c@jutal.com | 30-Apr-2026 16:23:26 | Jumpol Sudjitjul | 11-May-2026 | 04-May-2026 16:04:30 | Aphisit Pinkaew | 13-May-2026 | 11-May-2026 20:17:07 | Pornlert Wanaphattharaphan | 14-May-2026 | 20-May-2026 00:45:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 11:05:09 | 20-May-2026 04:25:31 | 0 |  |  | Approver | Locate
AO-001151 | MM-ZTK-1F-GEN-MEC-LIS-0001 | MECHANICAL EQUIPMENT LIST |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 21:10:41 | wisuda.c@jutal.com | 17-Jul-2026 10:39:15 | Jumpol Sudjitjul | 24-Jul-2026 | 18-Jul-2026 08:20:42 | Aphisit Pinkaew | 30-Jul-2026 | 04-Aug-2026 19:17:49 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 05-Aug-2026 20:37:09 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 06-Aug-2026 09:32:49 | 06-Aug-2026 03:31:45 | 0 |  |  | Approver | Locate
AO-000607 | MM-ZTK-1F-GEN-MEC-MOM-0001 | MECHANICAL DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 27-May-2026 10:08:51 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000607 | MM-ZTK-1F-GEN-MEC-MOM-0002 | MECHANICAL DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 27-May-2026 10:09:15 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000607 | MM-ZTK-1F-GEN-MEC-MOM-0003 | MECHANICAL DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 27-May-2026 10:09:38 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000607 | MM-ZTK-1F-GEN-MEC-MOM-0004 | MECHANICAL DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 27-May-2026 10:10:01 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000607 | MM-ZTK-1F-GEN-MEC-MOM-0005 | MECHANICAL DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 27-May-2026 10:10:24 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000607 | MM-ZTK-1F-GEN-MEC-MOM-0006 | MECHANICAL DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 27-May-2026 10:10:46 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000607 | MM-ZTK-1F-GEN-MEC-MOM-0007 | MECHANICAL DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 27-May-2026 10:11:15 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000607 | MM-ZTK-1F-GEN-MEC-MOM-0008 | MECHANICAL DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 27-May-2026 10:11:44 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000607 | MM-ZTK-1F-GEN-MEC-MOM-0009 | MECHANICAL DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 27-May-2026 10:12:15 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000607 | MM-ZTK-1F-GEN-MEC-MOM-0010 | MECHANICAL DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 27-May-2026 10:12:38 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000026 | MM-ZTK-1F-GEN-MEC-MOM-1001 | MECHANICAL DISCIPLINE KOM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 19-Mar-2026 10:44:24 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000121 | MM-ZTK-1F-GEN-MEC-MR-0001 | MATERIAL REQUISITION FOR OFFSHORE PEDESTAL CRANE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 13-Apr-2026 10:12:27 | zm169dc@jutal.com | 13-Apr-2026 11:09:31 | Jumpol Sudjitjul | 22-Apr-2026 | 14-Apr-2026 08:15:31 | Aphisit Pinkaew | 24-Apr-2026 | 22-Apr-2026 20:05:32 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 23-Apr-2026 07:50:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 23-Apr-2026 08:06:53 | 23-Apr-2026 01:31:15 | 0 |  |  | Approver | Locate
AO-001151 | MM-ZTK-1F-GEN-MEC-MR-0001 | MATERIAL REQUISITION FOR OFFSHORE PEDESTAL CRANE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 20:29:53 | wisuda.c@jutal.com | 16-Jul-2026 20:39:42 | Jumpol Sudjitjul | 24-Jul-2026 |  | Aphisit Pinkaew | 30-Jul-2026 | 29-Jul-2026 09:43:28 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 30-Jul-2026 18:11:21 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 30-Jul-2026 19:10:46 | 30-Jul-2026 12:32:28 | 0 |  |  | Approver | Locate
AO-000152 | MM-ZTK-1F-GEN-MEC-MR-0002 | MATERIAL REQUISITION FOR PRESSURE VESSELS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 17-Apr-2026 23:40:01 | wisuda.c@jutal.com | 19-Apr-2026 21:58:38 | Jumpol Sudjitjul | 27-Apr-2026 | 22-Apr-2026 18:01:09 | Aphisit Pinkaew | 29-Apr-2026 | 27-Apr-2026 21:24:36 | Pornlert Wanaphattharaphan | 30-Apr-2026 | 01-May-2026 19:31:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-May-2026 | 03-May-2026 16:16:02 | 03-May-2026 10:20:42 | 0 |  |  | Approver | Locate
AO-001168 | MM-ZTK-1F-GEN-MEC-MR-0002 | MATERIAL REQUISITION FOR PRESSURE VESSELS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:26:50 | wisuda.c@jutal.com | 20-Jul-2026 14:17:34 | Jumpol Sudjitjul | 27-Jul-2026 | 24-Jul-2026 09:16:17 | Aphisit Pinkaew | 31-Jul-2026 | 04-Aug-2026 19:12:06 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 05-Aug-2026 20:47:06 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 06-Aug-2026 09:33:14 | 06-Aug-2026 04:01:53 | 0 |  |  | Approver | Locate
AO-000156 | MM-ZTK-1F-GEN-MEC-MR-0003 | MATERIAL REQUISITION FOR CLOSED DRAIN SUMP PUMP SKIDS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 18-Apr-2026 19:34:02 | wisuda.c@jutal.com | 19-Apr-2026 22:02:30 | Jumpol Sudjitjul | 27-Apr-2026 | 23-Apr-2026 08:55:59 | Aphisit Pinkaew | 29-Apr-2026 | 06-May-2026 21:49:04 | Pornlert Wanaphattharaphan | 30-Apr-2026 | 07-May-2026 11:49:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-May-2026 | 07-May-2026 13:53:40 | 07-May-2026 07:06:26 | 0 |  |  | Approver | Locate
AO-001606 | MM-ZTK-1F-GEN-MEC-MR-0003 | MATERIAL REQUISITION FOR CLOSED DRAIN SUMP PUMP SKIDS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 09:55:17 | wisuda.c@jutal.com | 19-Aug-2026 10:50:13 | Jumpol Sudjitjul | 26-Aug-2026 | 23-Aug-2026 23:03:43 | Aphisit Pinkaew | 28-Aug-2026 | 30-Aug-2026 08:56:20 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 30-Aug-2026 15:40:19 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 30-Aug-2026 16:47:05 | 30-Aug-2026 10:14:41 | 0 |  |  | Approver | Locate
AO-000159 | MM-ZTK-1F-GEN-MEC-MR-0004 | MATERIAL REQUISITION FOR CHEMICAL INJECTION PUMP SKIDS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 18-Apr-2026 19:34:28 | wisuda.c@jutal.com | 19-Apr-2026 22:06:26 | Jumpol Sudjitjul | 27-Apr-2026 | 23-Apr-2026 08:58:36 | Aphisit Pinkaew | 29-Apr-2026 | 07-May-2026 16:49:25 | Pornlert Wanaphattharaphan | 30-Apr-2026 | 07-May-2026 20:38:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-May-2026 | 08-May-2026 08:22:54 | 08-May-2026 01:36:12 | 0 |  |  | Approver | Locate
AO-001606 | MM-ZTK-1F-GEN-MEC-MR-0004 | MATERIAL REQUISITION FOR CHEMICAL INJECTION PUMP SKIDS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 09:56:09 | wisuda.c@jutal.com | 19-Aug-2026 10:51:09 | Jumpol Sudjitjul | 26-Aug-2026 | 26-Aug-2026 22:39:47 | Aphisit Pinkaew | 28-Aug-2026 | 30-Aug-2026 08:59:24 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 30-Aug-2026 15:41:10 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 30-Aug-2026 16:48:01 | 30-Aug-2026 10:17:02 | 0 |  |  | Approver | Locate
AO-000164 | MM-ZTK-1F-GEN-MEC-MR-0005 | MATERIAL REQUISITION FOR CHEMICAL STORAGE TANKS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 17:25:08 | wisuda.c@jutal.com | 21-Apr-2026 09:18:00 | Jumpol Sudjitjul | 28-Apr-2026 | 26-Apr-2026 09:10:05 | Aphisit Pinkaew | 30-Apr-2026 | 08-May-2026 16:13:10 | Pornlert Wanaphattharaphan | 05-May-2026 | 08-May-2026 22:57:32 | APPR | Approved | Jumpol Sudjitjul | 06-May-2026 | 09-May-2026 08:17:36 | 09-May-2026 02:19:51 | 0 |  |  | Approver | Locate
AO-001306 | MM-ZTK-1F-GEN-MEC-MR-0005 | MATERIAL REQUISITION FOR CHEMICAL STORAGE TANKS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 27-Jul-2026 08:36:32 | wisuda.c@jutal.com | 27-Jul-2026 16:27:11 | Jumpol Sudjitjul | 05-Aug-2026 | 05-Aug-2026 14:02:35 | Aphisit Pinkaew | 07-Aug-2026 | 06-Aug-2026 09:42:13 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:41:08 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 11:11:17 | 13-Aug-2026 05:53:37 | 0 |  |  | Approver | Locate
AO-000372 | MM-ZTK-1F-GEN-MEC-MR-0006 | MATERIAL REQUISITION FOR MATERIAL HANDLING EQUIPMENT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 12-May-2026 10:08:32 | wisuda.c@jutal.com | 12-May-2026 11:24:38 | Jumpol Sudjitjul | 19-May-2026 |  | Aphisit Pinkaew | 21-May-2026 | 26-May-2026 20:46:05 | Pornlert Wanaphattharaphan | 22-May-2026 | 28-May-2026 01:08:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-May-2026 | 28-May-2026 08:29:17 | 28-May-2026 02:20:20 | 0 |  |  | Approver | Locate
AO-002335 | MM-ZTK-1F-GEN-MEC-MR-0006 | MATERIAL REQUISITION FOR MATERIAL HANDLING EQUIPMENT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 02-Oct-2026 11:58:49 | wisuda.c@jutal.com | 02-Oct-2026 17:54:21 | Jumpol Sudjitjul | 12-Oct-2026 | 07-Oct-2026 11:37:26 | Aphisit Pinkaew | 15-Oct-2026 | 11-Oct-2026 13:34:47 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 12-Oct-2026 01:49:49 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 12-Oct-2026 11:34:37 | 12-Oct-2026 05:48:33 | 0 |  |  | Approver | Locate
AO-000592 | MM-ZTK-1F-GEN-MEC-RPT-0001 | MATERIAL HANDLING STUDY REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 24-May-2026 15:28:21 | wisuda.c@jutal.com | 24-May-2026 20:45:54 | Jumpol Sudjitjul | 02-Jun-2026 |  | Aphisit Pinkaew | 05-Jun-2026 | 13-Jun-2026 22:46:07 | Pornlert Wanaphattharaphan | 08-Jun-2026 | 14-Jun-2026 01:02:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jun-2026 | 14-Jun-2026 21:44:13 | 14-Jun-2026 15:01:09 | 0 |  |  | Approver | Locate
AO-001294 | MM-ZTK-1F-GEN-MEC-RPT-0001 | MATERIAL HANDLING STUDY REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:17:36 | wisuda.c@jutal.com | 27-Jul-2026 16:01:08 | Jumpol Sudjitjul | 05-Aug-2026 |  | Aphisit Pinkaew | 07-Aug-2026 | 18-Aug-2026 11:07:39 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 20-Aug-2026 16:36:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 20-Aug-2026 19:48:27 | 20-Aug-2026 13:37:31 | 0 |  |  | Approver | Locate
AO-000182 | MM-ZTK-1F-GEN-MEC-RPT-0002 | CRITICAL RATING REPORT FOR EQUIPMENT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 14:48:19 | zm169dc@jutal.com | 21-Apr-2026 16:37:53 | Jumpol Sudjitjul | 28-Apr-2026 |  | Aphisit Pinkaew | 30-Apr-2026 | 30-Apr-2026 15:46:46 | Pornlert Wanaphattharaphan | 05-May-2026 | 01-May-2026 16:57:30 | NA | Not Approved | Jumpol Sudjitjul | 06-May-2026 | 05-May-2026 08:01:16 | 05-May-2026 01:16:37 | 0 |  |  | Approver | Locate
AO-000182 | MM-ZTK-1F-GEN-MEC-RPT-0003 | TEST SEPERATOR |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 21-Apr-2026 14:48:49 | zm169dc@jutal.com | 21-Apr-2026 16:38:24 | Jumpol Sudjitjul |  |  |  |  | 30-Apr-2026 15:50:28 |  |  | 01-May-2026 17:25:31 |  |  | Jumpol Sudjitjul |  | 03-May-2026 16:22:47 | 20-Apr-2026 11:39:32 | 0 |  |  | Approver | Locate
AO-000182 | MM-ZTK-1F-GEN-MEC-RPT-0004 | INSTRUMENT GAS FILTER COALESCER |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 21-Apr-2026 14:49:13 | zm169dc@jutal.com | 21-Apr-2026 16:38:38 | Jumpol Sudjitjul |  |  |  |  | 30-Apr-2026 15:52:32 |  |  | 01-May-2026 17:27:40 |  |  | Jumpol Sudjitjul |  | 05-May-2026 08:01:37 | 20-Apr-2026 11:40:25 | 0 |  |  | Approver | Locate
AO-000182 | MM-ZTK-1F-GEN-MEC-RPT-0005 | CLOSED DRAIN SUMP PUMP SKIDS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 21-Apr-2026 14:49:38 | zm169dc@jutal.com | 21-Apr-2026 16:38:52 | Jumpol Sudjitjul |  |  |  |  | 30-Apr-2026 15:57:42 |  |  | 01-May-2026 17:31:35 |  |  | Jumpol Sudjitjul |  | 03-May-2026 16:29:10 | 20-Apr-2026 11:41:18 | 0 |  |  | Approver | Locate
AO-000182 | MM-ZTK-1F-GEN-MEC-RPT-0006 | CHEMICAL INJECTION PUMP SKIDS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 21-Apr-2026 14:50:08 | zm169dc@jutal.com | 21-Apr-2026 16:41:04 | Jumpol Sudjitjul |  |  |  |  | 30-Apr-2026 16:00:55 |  |  | 01-May-2026 17:33:23 |  |  | Jumpol Sudjitjul |  | 03-May-2026 16:28:34 | 20-Apr-2026 11:40:50 | 0 |  |  | Approver | Locate
AO-000182 | MM-ZTK-1F-GEN-MEC-RPT-0007 | CHEMICAL STORAGE TANK |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 21-Apr-2026 13:08:26 | zm169dc@jutal.com | 21-Apr-2026 16:40:48 | Jumpol Sudjitjul |  |  |  |  | 30-Apr-2026 16:03:41 |  |  | 01-May-2026 17:24:30 |  |  | Jumpol Sudjitjul |  | 05-May-2026 08:01:58 | 20-Apr-2026 11:39:58 | 0 |  |  | Approver | Locate
AO-000182 | MM-ZTK-1F-GEN-MEC-RPT-0008 | MATERIAL HANDLING EQUIPMENT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 21-Apr-2026 13:08:49 | zm169dc@jutal.com | 21-Apr-2026 16:40:33 | Jumpol Sudjitjul |  |  |  |  | 30-Apr-2026 16:08:18 |  |  | 01-May-2026 17:36:12 |  |  | Jumpol Sudjitjul |  | 03-May-2026 16:30:26 | 20-Apr-2026 11:39:07 | 0 |  |  | Approver | Locate
AO-000682 | MM-ZTK-1F-GEN-MEC-RPT-0100 | CRITICALITY RATING ANALYSIS (MECHANICAL) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 13:51:51 | zm169dc@jutal.com | 05-Jun-2026 14:21:37 | Jumpol Sudjitjul | 12-Jun-2026 |  | Aphisit Pinkaew | 16-Jun-2026 | 15-Jun-2026 16:33:44 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 18-Jun-2026 09:39:59 | APPR | Approved | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 09:41:48 | 18-Jun-2026 02:47:11 | 0 |  |  | Approver | Locate
AO-001129 | MM-ZTK-1F-GEN-MEC-RPT-0100 | CRITICALITY RATING ANALYSIS (MECHANICAL) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 12:38:13 | zm169dc@jutal.com | 16-Jul-2026 14:08:09 | Jumpol Sudjitjul | 23-Jul-2026 |  | Aphisit Pinkaew | 27-Jul-2026 | 28-Jul-2026 19:46:42 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 29-Jul-2026 00:35:53 | APPR | Approved | Jumpol Sudjitjul | 31-Jul-2026 | 30-Jul-2026 09:30:39 | 30-Jul-2026 03:12:13 | 0 |  |  | Approver | Locate
AO-000122 | MM-ZTK-1F-GEN-MEC-SPE-0001 | PROJECT PARTICULAR SPECIFICATION FOR OFFSHORE PEDESTAL CRANES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 13-Apr-2026 10:12:50 | zm169dc@jutal.com | 13-Apr-2026 11:12:31 | Jumpol Sudjitjul | 22-Apr-2026 | 14-Apr-2026 08:16:02 | Aphisit Pinkaew | 24-Apr-2026 | 23-Apr-2026 08:38:54 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 27-Apr-2026 23:40:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 28-Apr-2026 10:10:34 | 28-Apr-2026 04:04:04 | 0 |  |  | Approver | Locate
AO-001151 | MM-ZTK-1F-GEN-MEC-SPE-0001 | PROJECT PARTICULAR SPECIFICATION FOR OFFSHORE PEDESTAL CRANES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 20:30:21 | wisuda.c@jutal.com | 16-Jul-2026 20:41:04 | Jumpol Sudjitjul | 24-Jul-2026 | 18-Jul-2026 08:24:22 | Aphisit Pinkaew | 30-Jul-2026 | 29-Jul-2026 10:51:24 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 30-Jul-2026 18:11:03 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 30-Jul-2026 19:11:34 | 30-Jul-2026 12:33:44 | 0 |  |  | Approver | Locate
AO-000153 | MM-ZTK-1F-GEN-MEC-SPE-0002 | PROJECT PARTICULAR SPECIFICATION FOR PRESSURE VESSELS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 17-Apr-2026 23:40:35 | wisuda.c@jutal.com | 19-Apr-2026 22:11:26 | Jumpol Sudjitjul | 27-Apr-2026 | 23-Apr-2026 09:01:27 | Aphisit Pinkaew | 29-Apr-2026 | 27-Apr-2026 20:34:09 | Pornlert Wanaphattharaphan | 30-Apr-2026 | 01-May-2026 17:22:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-May-2026 | 03-May-2026 16:27:30 | 03-May-2026 10:23:14 | 0 |  |  | Approver | Locate
AO-001168 | MM-ZTK-1F-GEN-MEC-SPE-0002 | PROJECT PARTICULAR SPECIFICATION FOR PRESSURE VESSELS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:27:22 | wisuda.c@jutal.com | 20-Jul-2026 14:18:42 | Jumpol Sudjitjul | 27-Jul-2026 |  | Aphisit Pinkaew | 31-Jul-2026 | 04-Aug-2026 19:13:50 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 05-Aug-2026 20:47:36 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 06-Aug-2026 09:34:59 | 06-Aug-2026 04:03:12 | 0 |  |  | Approver | Locate
AO-000157 | MM-ZTK-1F-GEN-MEC-SPE-0003 | PROJECT PARTICULAR SPECIFICATION FOR CLOSED DRAIN SUMP PUMP SKIDS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 18-Apr-2026 19:35:02 | wisuda.c@jutal.com | 19-Apr-2026 22:11:40 | Jumpol Sudjitjul | 27-Apr-2026 | 23-Apr-2026 09:02:10 | Aphisit Pinkaew | 29-Apr-2026 | 06-May-2026 20:31:06 | Pornlert Wanaphattharaphan | 30-Apr-2026 | 07-May-2026 11:42:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-May-2026 | 07-May-2026 11:45:57 | 07-May-2026 05:08:09 | 0 |  |  | Approver | Locate
AO-001606 | MM-ZTK-1F-GEN-MEC-SPE-0003 | PROJECT PARTICULAR SPECIFICATION FOR CLOSED DRAIN SUMP PUMP SKIDS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 09:56:42 | wisuda.c@jutal.com | 19-Aug-2026 10:59:44 | Jumpol Sudjitjul | 26-Aug-2026 | 21-Aug-2026 09:59:11 | Aphisit Pinkaew | 28-Aug-2026 | 30-Aug-2026 14:36:02 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 30-Aug-2026 15:42:57 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 30-Aug-2026 16:49:01 | 30-Aug-2026 10:19:21 | 0 |  |  | Approver | Locate
AO-000160 | MM-ZTK-1F-GEN-MEC-SPE-0004 | PROJECT PARTICULAR SPECIFICATION FOR CHEMICAL INJECTION PUMP SKIDS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 18-Apr-2026 19:35:34 | wisuda.c@jutal.com | 19-Apr-2026 22:11:55 | Jumpol Sudjitjul | 27-Apr-2026 | 23-Apr-2026 09:02:32 | Aphisit Pinkaew | 29-Apr-2026 | 07-May-2026 14:09:31 | Pornlert Wanaphattharaphan | 30-Apr-2026 | 07-May-2026 15:33:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-May-2026 | 07-May-2026 16:20:39 | 07-May-2026 09:45:53 | 0 |  |  | Approver | Locate
AO-001606 | MM-ZTK-1F-GEN-MEC-SPE-0004 | PROJECT PARTICULAR SPECIFICATION FOR CHEMICAL INJECTION PUMP SKIDS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 09:57:12 | wisuda.c@jutal.com | 19-Aug-2026 11:00:25 | Jumpol Sudjitjul | 26-Aug-2026 | 21-Aug-2026 10:14:20 | Aphisit Pinkaew | 28-Aug-2026 | 30-Aug-2026 15:48:58 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 30-Aug-2026 21:18:59 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 30-Aug-2026 21:22:43 | 30-Aug-2026 14:52:02 | 0 |  |  | Approver | Locate
AO-000165 | MM-ZTK-1F-GEN-MEC-SPE-0005 | PROJECT PARTICULAR SPECIFICATION FOR CHEMICAL STORAGE TANKS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 20-Apr-2026 17:25:35 | wisuda.c@jutal.com | 21-Apr-2026 09:19:43 | Jumpol Sudjitjul | 28-Apr-2026 | 26-Apr-2026 09:03:54 | Aphisit Pinkaew | 30-Apr-2026 | 08-May-2026 20:27:23 | Pornlert Wanaphattharaphan | 05-May-2026 | 08-May-2026 23:07:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 09-May-2026 08:19:12 | 09-May-2026 02:22:15 | 0 |  |  | Approver | Locate
AO-001606 | MM-ZTK-1F-GEN-MEC-SPE-0005 | PROJECT PARTICULAR SPECIFICATION FOR CHEMICAL STORAGE TANKS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 09:57:44 | wisuda.c@jutal.com | 19-Aug-2026 11:00:51 | Jumpol Sudjitjul | 26-Aug-2026 | 21-Aug-2026 10:45:17 | Aphisit Pinkaew | 28-Aug-2026 | 30-Aug-2026 16:49:08 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 30-Aug-2026 21:19:21 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 30-Aug-2026 21:24:30 | 30-Aug-2026 14:53:12 | 0 |  |  | Approver | Locate
AO-000161 | MM-ZTK-1F-GEN-MEC-SPE-0006 | PROJECT PARTICULAR SPECIFICATION FOR MATERIAL HANDLING EQUIPMENT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 18-Apr-2026 19:36:12 | wisuda.c@jutal.com | 19-Apr-2026 22:12:09 | Jumpol Sudjitjul | 27-Apr-2026 | 23-Apr-2026 09:02:49 | Aphisit Pinkaew | 29-Apr-2026 | 07-May-2026 16:37:54 | Pornlert Wanaphattharaphan | 30-Apr-2026 | 07-May-2026 20:27:10 | APPR | Approved | Jumpol Sudjitjul | 05-May-2026 | 08-May-2026 08:25:11 | 08-May-2026 01:39:19 | 0 |  |  | Approver | Locate
AO-002335 | MM-ZTK-1F-GEN-MEC-SPE-0006 | PROJECT PARTICULAR SPECIFICATION FOR MATERIAL HANDLING EQUIPMENT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 02-Oct-2026 11:59:17 | wisuda.c@jutal.com | 02-Oct-2026 17:39:04 | Jumpol Sudjitjul | 12-Oct-2026 | 07-Oct-2026 09:16:28 | Aphisit Pinkaew | 15-Oct-2026 | 11-Oct-2026 13:39:22 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 12-Oct-2026 01:50:38 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 12-Oct-2026 11:35:28 | 12-Oct-2026 05:49:48 | 0 |  |  | Approver | Locate
AO-000862 | MM-ZTK-1F-GEN-MEC-TBE-0001 | TECHNICAL BID EVALUATION FOR OFFSHORE PEDESTAL CRANE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 22-Jun-2026 13:14:26 | wisuda.c@jutal.com | 22-Jun-2026 14:40:51 | Jumpol Sudjitjul | 29-Jun-2026 |  | Aphisit Pinkaew | 01-Jul-2026 | 27-Jun-2026 22:02:38 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 28-Jun-2026 07:32:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 28-Jun-2026 08:40:03 | 28-Jun-2026 02:26:00 | 0 |  |  | Approver | Locate
AO-001074 | MM-ZTK-1F-GEN-MEC-TBE-0001 | TECHNICAL BID EVALUATION FOR OFFSHORE PEDESTAL CRANE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 12-Jul-2026 11:38:41 | wisuda.c@jutal.com | 12-Jul-2026 11:59:04 | Jumpol Sudjitjul | 17-Jul-2026 |  | Aphisit Pinkaew | 21-Jul-2026 | 13-Jul-2026 09:40:38 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 13-Jul-2026 13:19:20 | APPR | Approved | Jumpol Sudjitjul | 23-Jul-2026 | 13-Jul-2026 13:27:01 | 13-Jul-2026 06:59:58 | 0 |  |  | Approver | Locate
AO-000938 | MM-ZTK-1F-GEN-MEC-TBE-0002 | TECHNICAL BID EVALUATION FOR PRESSURE VESSELS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 29-Jun-2026 08:38:06 | wisuda.c@jutal.com | 30-Jun-2026 08:32:50 | Jumpol Sudjitjul | 07-Jul-2026 | 07-Jul-2026 16:34:04 | Aphisit Pinkaew | 09-Jul-2026 | 08-Jul-2026 13:39:18 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 08-Jul-2026 17:15:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 08-Jul-2026 17:24:06 | 08-Jul-2026 10:53:45 | 0 |  |  | Approver | Locate
AO-001287 | MM-ZTK-1F-GEN-MEC-TBE-0002 | TECHNICAL BID EVALUATION FOR PRESSURE VESSELS |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 27-Jul-2026 09:18:05 | wisuda.c@jutal.com | 27-Jul-2026 16:03:26 | Jumpol Sudjitjul | 05-Aug-2026 |  | Aphisit Pinkaew | 07-Aug-2026 | 06-Aug-2026 09:28:09 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 06-Aug-2026 20:20:09 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 07-Aug-2026 08:39:11 | 07-Aug-2026 02:14:45 | 0 |  |  | Approver | Locate
AO-001019 | MM-ZTK-1F-GEN-MEC-TBE-0003 | TECHNICAL BID EVALUATION FOR CLOSED DRAIN SUMP PUMP SKIDS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 03-Jul-2026 23:30:18 | wisuda.c@jutal.com | 04-Jul-2026 14:51:08 | Jumpol Sudjitjul | 10-Jul-2026 | 11-Jul-2026 06:05:10 | Aphisit Pinkaew | 14-Jul-2026 | 16-Jul-2026 22:06:49 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 17-Jul-2026 00:02:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 17-Jul-2026 09:26:47 | 17-Jul-2026 03:18:10 | 0 |  |  | Approver | Locate
AO-001427 | MM-ZTK-1F-GEN-MEC-TBE-0003 | TECHNICAL BID EVALUATION FOR CLOSED DRAIN SUMP PUMP SKIDS |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 05-Aug-2026 17:28:15 | wisuda.c@jutal.com | 05-Aug-2026 17:34:29 | Jumpol Sudjitjul | 14-Aug-2026 |  | Aphisit Pinkaew | 18-Aug-2026 | 06-Aug-2026 09:24:57 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 06-Aug-2026 14:17:47 | APPR | Approved | Jumpol Sudjitjul | 20-Aug-2026 | 06-Aug-2026 15:10:10 | 06-Aug-2026 08:38:58 | 0 |  |  | Approver | Locate
AO-000939 | MM-ZTK-1F-GEN-MEC-TBE-0004 | TECHNICAL BID EVALUATION FOR CORROSION INHIBITOR AND BIOCIDE INJECTION PUMP SKID |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 09-Jul-2026 12:50:31 | wisuda.c@jutal.com | 09-Jul-2026 13:16:29 | Jumpol Sudjitjul | 07-Jul-2026 | 11-Jul-2026 06:45:54 | Aphisit Pinkaew | 09-Jul-2026 |  | Pornlert Wanaphattharaphan | 10-Jul-2026 | 07-Jul-2026 00:34:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 07-Jul-2026 09:16:44 | 07-Jul-2026 03:11:45 | 0 |  |  | Approver | Locate
AO-001444 | MM-ZTK-1F-GEN-MEC-TBE-0004 | TECHNICAL BID EVALUATION FOR CORROSION INHIBITOR AND BIOCIDE INJECTION PUMP SKID |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 07-Aug-2026 12:39:57 | wisuda.c@jutal.com | 07-Aug-2026 13:29:58 | Jumpol Sudjitjul | 17-Aug-2026 |  | Aphisit Pinkaew | 19-Aug-2026 | 07-Aug-2026 13:54:12 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 07-Aug-2026 20:47:39 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 08-Aug-2026 10:18:54 | 08-Aug-2026 04:09:49 | 0 |  |  | Approver | Locate
AO-000973 | MM-ZTK-1F-GEN-MEC-TBE-0005 | TECHNICAL BID EVALUATION FOR CHEMICAL STORAGE TANKS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 01-Jul-2026 17:56:57 | wisuda.c@jutal.com | 02-Jul-2026 13:41:46 | Jumpol Sudjitjul | 09-Jul-2026 | 11-Jul-2026 06:04:52 | Aphisit Pinkaew | 13-Jul-2026 | 13-Jul-2026 14:48:05 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 13-Jul-2026 22:38:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jul-2026 | 14-Jul-2026 08:42:42 | 14-Jul-2026 02:05:58 | 0 |  |  | Approver | Locate
AO-001288 | MM-ZTK-1F-GEN-MEC-TBE-0005 | TECHNICAL BID EVALUATION FOR CHEMICAL STORAGE TANKS |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 27-Jul-2026 09:18:34 | wisuda.c@jutal.com | 27-Jul-2026 16:03:52 | Jumpol Sudjitjul | 05-Aug-2026 |  | Aphisit Pinkaew | 07-Aug-2026 | 06-Aug-2026 09:52:43 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 06-Aug-2026 20:59:28 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 07-Aug-2026 08:54:33 | 07-Aug-2026 02:21:13 | 0 |  |  | Approver | Locate
AO-001164 | MM-ZTK-1F-GEN-MEC-TBE-0006 | TECHNICAL BID EVALUATION FOR MATERIAL HANDLING EQUIPMENT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 20-Jul-2026 10:28:02 | wisuda.c@jutal.com | 20-Jul-2026 14:22:54 | Jumpol Sudjitjul | 27-Jul-2026 | 05-Aug-2026 13:56:23 | Aphisit Pinkaew | 31-Jul-2026 | 12-Aug-2026 19:47:27 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 12-Aug-2026 21:09:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 13-Aug-2026 10:53:57 | 13-Aug-2026 04:07:19 | 0 |  |  | Approver | Locate
AO-001890 | MM-ZTK-1F-GEN-MEC-TBE-0006 | TECHNICAL BID EVALUATION FOR MATERIAL HANDLING EQUIPMENT |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | MEC | Mechanical | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 07-Sep-2026 09:32:35 | wisuda.c@jutal.com | 08-Sep-2026 09:27:34 | Jumpol Sudjitjul | 15-Sep-2026 | 09-Sep-2026 13:59:16 | Aphisit Pinkaew | 17-Sep-2026 | 09-Sep-2026 15:39:48 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 11-Sep-2026 00:14:56 | APPR | Approved | Jumpol Sudjitjul | 21-Sep-2026 | 11-Sep-2026 08:13:33 | 11-Sep-2026 02:10:25 | 0 |  |  | Approver | Locate
AO-000219 | MM-ZTK-1F-GEN-NVA-BOD-0001 | NAVAL ARCHITECTURAL BASIS OF DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | NVA | Naval | BOD | Basis of Design | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 13:04:58 | wisuda.c@jutal.com | 24-Apr-2026 14:03:14 | Jumpol Sudjitjul | 05-May-2026 | 19-May-2026 13:13:25 | Sompop Singhatiraj | 07-May-2026 | 28-May-2026 16:25:17 | Pornlert Wanaphattharaphan | 08-May-2026 | 28-May-2026 22:44:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 29-May-2026 09:44:18 | 29-May-2026 03:25:53 | 0 |  |  | Approver | Locate
AO-001327 | MM-ZTK-1F-GEN-NVA-BOD-0001 | NAVAL ARCHITECTURAL BASIS OF DESIGN |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | NVA | Naval | BOD | Basis of Design | 0 | Submitted | IFA | Issued for Approval |  | 28-Jul-2026 09:14:05 | wisuda.c@jutal.com | 28-Jul-2026 20:27:34 | Jumpol Sudjitjul | 06-Aug-2026 |  | Sompop Singhatiraj | 10-Aug-2026 | 16-Sep-2026 15:48:53 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 17-Sep-2026 22:47:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Aug-2026 | 18-Sep-2026 19:12:17 | 18-Sep-2026 12:45:46 | 0 |  |  | Approver | Locate
AO-000902 | MM-ZTK-1F-GEN-NVA-CAL-1011 | TOPSIDES BARGE MOTION ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 16:39:16 | wisuda.c@jutal.com | 26-Jun-2026 17:06:10 | Jumpol Sudjitjul | 06-Jul-2026 |  | Sompop Singhatiraj | 08-Jul-2026 | 02-Jul-2026 18:29:48 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 11-Jul-2026 13:55:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 12-Jul-2026 11:29:46 | 12-Jul-2026 05:19:20 | 0 |  |  | Approver | Locate
AO-001770 | MM-ZTK-1F-GEN-NVA-CAL-1011 | TOPSIDES BARGE MOTION ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:43:35 | wisuda.c@jutal.com | 31-Aug-2026 13:27:32 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 14-Sep-2026 13:11:11 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 15-Sep-2026 22:29:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 17-Sep-2026 12:02:59 | 17-Sep-2026 05:55:51 | 0 |  |  | Approver | Locate
AO-002485 | MM-ZTK-1F-GEN-NVA-CAL-1011 | TOPSIDES BARGE MOTION ANALYSIS REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 12:07:19 | wisuda.c@jutal.com | 12-Oct-2026 13:37:38 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001589 | MM-ZTK-1F-GEN-PCC-PDR-5002 | PIPING PRESSURE TEST PACKAGE PREPARATION PROCEDURE |  | A1 | Project Document | Engineering Document | Part G - Pre-Comm & Comm | GEN |  |  | COM | Commissioning | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 18-Aug-2026 13:58:33 | zm169dc@jutal.com | 18-Aug-2026 14:15:14 | Jumpol Sudjitjul | 25-Aug-2026 | 26-Aug-2026 16:02:58 | Chananun Rojanarungruengporn | 27-Aug-2026 | 28-Aug-2026 08:37:02 | Prin Jitatisil | 28-Aug-2026 | 28-Aug-2026 09:12:24 | NA | Not Approved | Jumpol Sudjitjul | 31-Aug-2026 | 28-Aug-2026 10:48:42 | 28-Aug-2026 04:36:54 | 0 |  |  | Approver | Locate
AO-001619 | MM-ZTK-1F-GEN-PCC-PDR-5004 | PRESSURE TEST,FLUSHING,CLEANING AND REINSTATEMENT PROCEDURE FOR PIPING SYSTEM |  | A1 | Project Document | Engineering Document | Part G - Pre-Comm & Comm | GEN |  |  | COM | Commissioning | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 20-Aug-2026 07:52:42 | zm169dc@jutal.com | 20-Aug-2026 09:24:30 | Jumpol Sudjitjul | 27-Aug-2026 | 26-Aug-2026 22:49:43 | Chananun Rojanarungruengporn | 31-Aug-2026 | 28-Aug-2026 08:52:37 | Prin Jitatisil | 01-Sep-2026 | 28-Aug-2026 09:14:32 | NA | Not Approved | Jumpol Sudjitjul | 02-Sep-2026 | 28-Aug-2026 10:50:15 | 28-Aug-2026 04:26:01 | 0 |  |  | Approver | Locate
AO-001620 | MM-ZTK-1F-GEN-PCC-PDR-5007 | PRESSURE TEST,FLUSHING,CLEANING AND REINSTATEMENT PROCEDURE FOR PIPING SYSTEM |  | A1 | Project Document | Engineering Document | Part G - Pre-Comm & Comm | GEN |  |  | COM | Commissioning | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 20-Aug-2026 07:53:08 | zm169dc@jutal.com | 20-Aug-2026 09:28:02 | Jumpol Sudjitjul | 27-Aug-2026 | 27-Aug-2026 16:46:28 | Chananun Rojanarungruengporn | 31-Aug-2026 | 28-Aug-2026 08:57:36 | Prin Jitatisil | 01-Sep-2026 | 28-Aug-2026 09:15:26 | NA | Not Approved | Jumpol Sudjitjul | 02-Sep-2026 | 28-Aug-2026 10:51:08 | 28-Aug-2026 04:27:18 | 0 |  |  | Approver | Locate
AO-000108 | MM-ZTK-1F-GEN-PIP-BOD-0001 | PIPING BASIC OF DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | BOD | Basis of Design | 0 | Submitted | IFR | Issued for Review |  | 10-Apr-2026 10:19:36 | zm169dc@jutal.com | 10-Apr-2026 15:19:34 | Jumpol Sudjitjul | 22-Apr-2026 | 22-Apr-2026 13:30:12 | Aphisit Pinkaew | 24-Apr-2026 | 26-Apr-2026 14:41:51 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 28-Apr-2026 23:26:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 29-Apr-2026 08:36:39 | 30-Apr-2026 11:49:32 | 0 |  |  | Approver | Locate
AO-000770 | MM-ZTK-1F-GEN-PIP-BOD-0001 | PIPING BASIC OF DESIGN |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 13-Jun-2026 09:16:54 | wisuda.c@jutal.com | 13-Jun-2026 09:38:35 | Jumpol Sudjitjul | 19-Jun-2026 |  | Aphisit Pinkaew | 23-Jun-2026 | 23-Jun-2026 12:01:25 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 23:09:38 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 13:34:00 | 25-Jun-2026 07:30:07 | 0 |  |  | Approver | Locate
AO-000261 | MM-ZTK-1F-GEN-PIP-CAL-0001 | PIPING WALLTHICKNESS CALCULATION |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 18:29:03 | wisuda.c@jutal.com | 30-Apr-2026 10:10:03 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 14:19:29 | Aphisit Pinkaew | 13-May-2026 | 18-May-2026 16:26:24 | Pornlert Wanaphattharaphan | 14-May-2026 | 20-May-2026 13:40:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 14:37:53 | 20-May-2026 08:06:45 | 0 |  |  | Approver | Locate
AO-000910 | MM-ZTK-1F-GEN-PIP-CAL-0001 | PIPING WALLTHICKNESS CALCULATION |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 26-Jun-2026 20:32:33 | wisuda.c@jutal.com | 27-Jun-2026 18:45:31 | Jumpol Sudjitjul | 06-Jul-2026 |  | Aphisit Pinkaew | 08-Jul-2026 | 03-Jul-2026 14:35:17 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 11-Jul-2026 13:56:25 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 12-Jul-2026 11:30:17 | 12-Jul-2026 05:18:00 | 0 |  |  | Approver | Locate
AO-001289 | MM-ZTK-1F-GEN-PIP-CAL-0001 | PIPING WALLTHICKNESS CALCULATION |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 27-Jul-2026 09:19:31 | wisuda.c@jutal.com | 27-Jul-2026 15:58:42 | Jumpol Sudjitjul | 05-Aug-2026 | 12-Aug-2026 07:54:16 | Aphisit Pinkaew | 07-Aug-2026 | 16-Aug-2026 17:42:41 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 16-Aug-2026 22:01:41 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 17-Aug-2026 11:07:51 | 17-Aug-2026 05:10:38 | 0 |  |  | Approver | Locate
AO-000262 | MM-ZTK-1F-GEN-PIP-DTS-0001 | MANUAL VALVE DATASHEET |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 18:29:35 | wisuda.c@jutal.com | 30-Apr-2026 10:11:05 | Jumpol Sudjitjul | 11-May-2026 |  | Aphisit Pinkaew | 13-May-2026 | 19-May-2026 16:09:36 | Pornlert Wanaphattharaphan | 14-May-2026 | 20-May-2026 15:26:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 18:55:41 | 20-May-2026 12:18:11 | 0 |  |  | Approver | Locate
AO-000911 | MM-ZTK-1F-GEN-PIP-DTS-0001 | MANUAL VALVE DATASHEET |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 26-Jun-2026 20:33:02 | wisuda.c@jutal.com | 27-Jun-2026 18:46:28 | Jumpol Sudjitjul | 06-Jul-2026 |  | Aphisit Pinkaew | 08-Jul-2026 | 03-Jul-2026 14:28:31 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 11-Jul-2026 13:56:06 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 12-Jul-2026 11:30:46 | 12-Jul-2026 05:20:31 | 0 |  |  | Approver | Locate
AO-001289 | MM-ZTK-1F-GEN-PIP-DTS-0001 | MANUAL VALVE DATASHEET |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 27-Jul-2026 09:19:58 | wisuda.c@jutal.com | 27-Jul-2026 15:58:16 | Jumpol Sudjitjul | 05-Aug-2026 |  | Aphisit Pinkaew | 07-Aug-2026 | 16-Aug-2026 17:48:55 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 16-Aug-2026 22:02:52 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 17-Aug-2026 11:10:39 | 17-Aug-2026 05:11:53 | 0 |  |  | Approver | Locate
AO-000360 | MM-ZTK-1F-GEN-PIP-DTS-0002 | DATASHEET FOR CHEMICAL INJECTION QUILL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:07:14 | wisuda.c@jutal.com | 11-May-2026 11:22:33 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 16:23:00 | Aphisit Pinkaew | 20-May-2026 | 23-May-2026 11:57:23 | Pornlert Wanaphattharaphan | 21-May-2026 | 28-May-2026 22:55:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 29-May-2026 09:47:00 | 29-May-2026 03:22:14 | 0 |  |  | Approver | Locate
AO-001176 | MM-ZTK-1F-GEN-PIP-DTS-0002 | DATASHEET FOR CHEMICAL INJECTION QUILL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 08:45:26 | wisuda.c@jutal.com | 20-Jul-2026 14:25:05 | Jumpol Sudjitjul | 27-Jul-2026 | 04-Aug-2026 11:20:17 | Aphisit Pinkaew | 31-Jul-2026 | 09-Aug-2026 11:29:20 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 09-Aug-2026 17:23:55 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 09-Aug-2026 18:20:02 | 09-Aug-2026 11:24:19 | 0 |  |  | Approver | Locate
AO-002245 | MM-ZTK-1F-GEN-PIP-DTS-0002 | DATASHEET FOR CHEMICAL INJECTION QUILL |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 11:56:12 | wisuda.c@jutal.com | 24-Sep-2026 14:01:41 | Jumpol Sudjitjul | 01-Oct-2026 | 01-Oct-2026 17:15:12 | Aphisit Pinkaew | 05-Oct-2026 | 08-Oct-2026 13:10:31 | Pornlert Wanaphattharaphan | 06-Oct-2026 | 10-Oct-2026 00:20:21 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 10-Oct-2026 17:24:50 | 10-Oct-2026 11:24:03 | 0 |  |  | Approver | Locate
AO-000360 | MM-ZTK-1F-GEN-PIP-DTS-0003 | DATASHEET FOR HOSE AND HOSE CONNECTOR |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:07:39 | wisuda.c@jutal.com | 11-May-2026 11:15:26 | Jumpol Sudjitjul | 18-May-2026 | 12-May-2026 08:54:30 | Aphisit Pinkaew | 20-May-2026 | 23-May-2026 12:05:26 | Pornlert Wanaphattharaphan | 21-May-2026 | 29-May-2026 00:01:26 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 22-May-2026 | 29-May-2026 09:46:08 | 29-May-2026 03:20:55 | 0 |  |  | Approver | Locate
AO-001176 | MM-ZTK-1F-GEN-PIP-DTS-0003 | DATASHEET FOR HOSE AND HOSE CONNECTOR |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:32:37 | wisuda.c@jutal.com | 20-Jul-2026 14:25:32 | Jumpol Sudjitjul | 27-Jul-2026 | 24-Jul-2026 14:22:24 | Aphisit Pinkaew | 31-Jul-2026 | 09-Aug-2026 11:26:17 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 09-Aug-2026 17:11:40 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 09-Aug-2026 18:21:15 | 09-Aug-2026 11:29:07 | 0 |  |  | Approver | Locate
AO-000360 | MM-ZTK-1F-GEN-PIP-DTS-0004 | DATASHEET FOR STRAINER |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:08:04 | wisuda.c@jutal.com | 11-May-2026 11:17:29 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 15:47:39 | Aphisit Pinkaew | 20-May-2026 | 23-May-2026 12:21:49 | Pornlert Wanaphattharaphan | 21-May-2026 | 29-May-2026 00:06:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 29-May-2026 09:43:24 | 29-May-2026 03:19:38 | 0 |  |  | Approver | Locate
AO-001176 | MM-ZTK-1F-GEN-PIP-DTS-0004 | DATASHEET FOR STRAINER |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:33:13 | wisuda.c@jutal.com | 20-Jul-2026 14:26:00 | Jumpol Sudjitjul | 27-Jul-2026 | 24-Jul-2026 14:29:49 | Aphisit Pinkaew | 31-Jul-2026 | 09-Aug-2026 11:27:12 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 09-Aug-2026 17:23:27 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 09-Aug-2026 18:21:36 | 09-Aug-2026 11:31:33 | 0 |  |  | Approver | Locate
AO-000360 | MM-ZTK-1F-GEN-PIP-DTS-0005 | DATASHEET FOR LIQUID TRAP |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:08:30 | wisuda.c@jutal.com | 11-May-2026 11:17:13 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 14:10:34 | Aphisit Pinkaew | 20-May-2026 | 23-May-2026 12:30:28 | Pornlert Wanaphattharaphan | 21-May-2026 | 29-May-2026 00:08:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 29-May-2026 09:42:38 | 29-May-2026 03:18:20 | 0 |  |  | Approver | Locate
AO-001176 | MM-ZTK-1F-GEN-PIP-DTS-0005 | DATASHEET FOR LIQUID TRAP |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:33:45 | wisuda.c@jutal.com | 20-Jul-2026 14:26:28 | Jumpol Sudjitjul | 27-Jul-2026 | 04-Aug-2026 11:14:59 | Aphisit Pinkaew | 31-Jul-2026 | 09-Aug-2026 10:44:19 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 09-Aug-2026 17:10:44 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 09-Aug-2026 18:21:28 | 09-Aug-2026 11:30:22 | 0 |  |  | Approver | Locate
AO-000360 | MM-ZTK-1F-GEN-PIP-DTS-0006 | DATASHEET FOR CLAMP TYPE CONNECTOR AND TARGET TEE WITH CLAMP TYPE CONNECTOR |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:09:00 | wisuda.c@jutal.com | 11-May-2026 11:15:40 | Jumpol Sudjitjul | 18-May-2026 | 12-May-2026 07:32:22 | Aphisit Pinkaew | 20-May-2026 | 24-May-2026 16:51:38 | Pornlert Wanaphattharaphan | 21-May-2026 | 29-May-2026 19:32:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 29-May-2026 19:33:55 | 29-May-2026 12:53:23 | 0 |  |  | Approver | Locate
AO-001624 | MM-ZTK-1F-GEN-PIP-DTS-0006 | DATASHEET FOR CLAMP TYPE CONNECTOR AND TARGET TEE WITH CLAMP TYPE CONNECTOR |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 12:08:59 | wisuda.c@jutal.com | 20-Aug-2026 13:47:43 | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 13:18:06 | Aphisit Pinkaew | 31-Aug-2026 | 01-Sep-2026 12:58:41 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 02-Sep-2026 23:34:22 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 03-Sep-2026 09:50:07 | 03-Sep-2026 03:13:49 | 0 |  |  | Approver | Locate
AO-002245 | MM-ZTK-1F-GEN-PIP-DTS-0006 | DATASHEET FOR CLAMP TYPE CONNECTOR AND TARGET TEE WITH CLAMP TYPE CONNECTOR |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 11:56:41 | wisuda.c@jutal.com | 24-Sep-2026 14:02:14 | Jumpol Sudjitjul | 01-Oct-2026 | 01-Oct-2026 17:17:35 | Aphisit Pinkaew | 05-Oct-2026 | 09-Oct-2026 15:57:55 | Pornlert Wanaphattharaphan | 06-Oct-2026 | 10-Oct-2026 00:21:33 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 10-Oct-2026 17:25:24 | 10-Oct-2026 11:25:20 | 0 |  |  | Approver | Locate
AO-000360 | MM-ZTK-1F-GEN-PIP-DTS-0007 | DATASHEET FOR CORROSION FITTINGS (COUPON) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:09:24 | wisuda.c@jutal.com | 11-May-2026 11:15:13 | Jumpol Sudjitjul | 18-May-2026 | 12-May-2026 09:41:43 | Aphisit Pinkaew | 20-May-2026 | 24-May-2026 17:02:14 | Pornlert Wanaphattharaphan | 21-May-2026 | 29-May-2026 19:33:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 29-May-2026 19:35:24 | 29-May-2026 12:57:05 | 0 |  |  | Approver | Locate
AO-001654 | MM-ZTK-1F-GEN-PIP-DTS-0007 | DATASHEET FOR CORROSION FITTINGS (COUPON) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 18:43:08 | wisuda.c@jutal.com | 24-Aug-2026 18:38:56 | Jumpol Sudjitjul | 01-Sep-2026 | 02-Sep-2026 10:03:58 | Aphisit Pinkaew | 03-Sep-2026 | 07-Sep-2026 09:48:13 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 08-Sep-2026 22:29:09 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 09-Sep-2026 10:39:03 | 09-Sep-2026 04:33:44 | 0 |  |  | Approver | Locate
AO-000360 | MM-ZTK-1F-GEN-PIP-DTS-0008 | DATASHEET FOR BARRED TEE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:09:47 | wisuda.c@jutal.com | 11-May-2026 11:18:28 | Jumpol Sudjitjul | 18-May-2026 |  | Aphisit Pinkaew | 20-May-2026 | 24-May-2026 17:43:50 | Pornlert Wanaphattharaphan | 21-May-2026 | 29-May-2026 19:33:46 | APPR | Approved | Jumpol Sudjitjul | 22-May-2026 | 29-May-2026 19:34:51 | 29-May-2026 12:54:36 | 0 |  |  | Approver | Locate
AO-001248 | MM-ZTK-1F-GEN-PIP-DTS-0008 | DATASHEET FOR BARRED TEE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 10:46:00 | wisuda.c@jutal.com | 24-Jul-2026 11:27:36 | Jumpol Sudjitjul | 04-Aug-2026 |  | Aphisit Pinkaew | 06-Aug-2026 | 14-Aug-2026 14:44:50 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 15-Aug-2026 13:28:35 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 15-Aug-2026 14:42:43 | 15-Aug-2026 08:18:45 | 0 |  |  | Approver | Locate
AO-000360 | MM-ZTK-1F-GEN-PIP-DTS-0009 | DATASHEET FOR PORTABLE VALVE ACTUATOR |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:10:11 | wisuda.c@jutal.com | 11-May-2026 11:25:10 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 14:44:55 | Aphisit Pinkaew | 20-May-2026 | 26-May-2026 20:42:59 | Pornlert Wanaphattharaphan | 21-May-2026 | 30-May-2026 07:54:14 | APPR | Approved | Jumpol Sudjitjul | 22-May-2026 | 31-May-2026 20:49:09 | 31-May-2026 14:22:47 | 0 |  |  | Approver | Locate
AO-002245 | MM-ZTK-1F-GEN-PIP-DTS-0009 | DATASHEET FOR PORTABLE VALVE ACTUATOR |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 11:57:09 | wisuda.c@jutal.com | 24-Sep-2026 14:02:32 | Jumpol Sudjitjul | 01-Oct-2026 | 01-Oct-2026 17:20:04 | Aphisit Pinkaew | 05-Oct-2026 | 09-Oct-2026 16:10:01 | Pornlert Wanaphattharaphan | 06-Oct-2026 | 10-Oct-2026 00:22:39 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 10-Oct-2026 17:26:19 | 10-Oct-2026 11:26:33 | 0 |  |  | Approver | Locate
AO-000487 | MM-ZTK-1F-GEN-PIP-DTS-0010 | DATASHEET FOR 3D BEND |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 17-May-2026 00:13:06 | wisuda.c@jutal.com | 18-May-2026 19:40:04 | Jumpol Sudjitjul | 26-May-2026 |  | Aphisit Pinkaew | 28-May-2026 | 24-May-2026 18:11:07 | Pornlert Wanaphattharaphan | 29-May-2026 | 10-Jun-2026 20:58:39 | APPR | Approved | Jumpol Sudjitjul | 02-Jun-2026 | 11-Jun-2026 10:19:12 | 11-Jun-2026 04:11:01 | 0 |  |  | Approver | Locate
AO-001249 | MM-ZTK-1F-GEN-PIP-DTS-0010 | DATASHEET FOR 3D BEND |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 10:46:36 | wisuda.c@jutal.com | 24-Jul-2026 11:28:02 | Jumpol Sudjitjul | 04-Aug-2026 |  | Aphisit Pinkaew | 06-Aug-2026 | 14-Aug-2026 14:51:32 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 15-Aug-2026 13:31:37 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 15-Aug-2026 14:45:12 | 15-Aug-2026 08:21:16 | 0 |  |  | Approver | Locate
AO-000360 | MM-ZTK-1F-GEN-PIP-DTS-0011 | DATASHEET FOR BARREL REDUCER |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:10:40 | wisuda.c@jutal.com | 11-May-2026 11:25:41 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 14:54:07 | Aphisit Pinkaew | 20-May-2026 | 26-May-2026 20:40:28 | Pornlert Wanaphattharaphan | 21-May-2026 | 30-May-2026 07:50:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 31-May-2026 20:49:44 | 31-May-2026 14:24:00 | 0 |  |  | Approver | Locate
AO-001250 | MM-ZTK-1F-GEN-PIP-DTS-0011 | DATASHEET FOR BARREL REDUCER |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 10:47:07 | wisuda.c@jutal.com | 24-Jul-2026 11:28:17 | Jumpol Sudjitjul | 04-Aug-2026 | 04-Aug-2026 11:34:43 | Aphisit Pinkaew | 06-Aug-2026 | 16-Aug-2026 16:11:22 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 16-Aug-2026 16:59:11 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 17-Aug-2026 11:15:56 | 17-Aug-2026 05:19:27 | 0 |  |  | Approver | Locate
AO-000115 | MM-ZTK-1F-GEN-PIP-DTS-0012 | DATASHEET FOR QUICK OPENING CLOSURE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 13-Apr-2026 09:28:17 | zm169dc@jutal.com | 13-Apr-2026 09:41:52 | Jumpol Sudjitjul | 22-Apr-2026 | 22-Apr-2026 13:16:09 | Aphisit Pinkaew | 24-Apr-2026 | 25-Apr-2026 13:36:45 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 28-Apr-2026 23:49:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 29-Apr-2026 08:37:52 | 30-Apr-2026 04:49:48 | 0 |  |  | Approver | Locate
AO-001290 | MM-ZTK-1F-GEN-PIP-DTS-0012 | DATASHEET FOR QUICK OPENING CLOSURE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 27-Jul-2026 09:20:26 | wisuda.c@jutal.com | 27-Jul-2026 15:58:33 | Jumpol Sudjitjul | 05-Aug-2026 | 05-Aug-2026 23:38:04 | Aphisit Pinkaew | 07-Aug-2026 | 16-Aug-2026 17:58:22 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 16-Aug-2026 22:33:13 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 17-Aug-2026 11:28:50 | 17-Aug-2026 05:13:05 | 0 |  |  | Approver | Locate
AO-000488 | MM-ZTK-1F-GEN-PIP-DTS-0013 | DATASHEET FOR PIG LUANCHER / RECEIVER |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 17-May-2026 00:13:31 | wisuda.c@jutal.com | 18-May-2026 19:42:16 | Jumpol Sudjitjul | 26-May-2026 |  | Aphisit Pinkaew | 28-May-2026 | 03-Jun-2026 21:17:53 | Pornlert Wanaphattharaphan | 29-May-2026 | 10-Jun-2026 21:00:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 11-Jun-2026 10:32:10 | 11-Jun-2026 04:12:22 | 0 |  |  | Approver | Locate
AO-001291 | MM-ZTK-1F-GEN-PIP-DTS-0013 | DATASHEET FOR PIG LUANCHER / RECEIVER |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 27-Jul-2026 09:21:04 | wisuda.c@jutal.com | 27-Jul-2026 15:58:51 | Jumpol Sudjitjul | 05-Aug-2026 |  | Aphisit Pinkaew | 07-Aug-2026 | 16-Aug-2026 18:05:12 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 16-Aug-2026 22:34:35 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 17-Aug-2026 13:49:59 | 17-Aug-2026 07:09:41 | 0 |  |  | Approver | Locate
AO-000357 | MM-ZTK-1F-GEN-PIP-LIS-0001 | MANUAL VALVE LIST |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:11:09 | wisuda.c@jutal.com | 11-May-2026 11:28:03 | Jumpol Sudjitjul | 18-May-2026 |  | Aphisit Pinkaew | 20-May-2026 | 26-May-2026 20:12:45 | Pornlert Wanaphattharaphan | 21-May-2026 | 30-May-2026 06:00:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 31-May-2026 20:50:14 | 31-May-2026 14:25:14 | 0 |  |  | Approver | Locate
AO-001254 | MM-ZTK-1F-GEN-PIP-LIS-0001 | MANUAL VALVE LIST |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 08:40:27 | wisuda.c@jutal.com | 24-Jul-2026 10:55:56 | Jumpol Sudjitjul | 04-Aug-2026 |  | Aphisit Pinkaew | 06-Aug-2026 | 16-Aug-2026 16:13:29 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 16-Aug-2026 16:58:45 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 17-Aug-2026 13:54:51 | 17-Aug-2026 07:16:46 | 0 |  |  | Approver | Locate
AO-002263 | MM-ZTK-1F-GEN-PIP-LIS-0001 | MANUAL VALVE LIST |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 25-Sep-2026 16:11:13 | wisuda.c@jutal.com | 25-Sep-2026 17:22:06 | Jumpol Sudjitjul | 05-Oct-2026 |  | Aphisit Pinkaew | 07-Oct-2026 | 09-Oct-2026 16:24:02 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 10-Oct-2026 01:35:50 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 10-Oct-2026 17:26:45 | 10-Oct-2026 10:49:00 | 0 |  |  | Approver | Locate
AO-000358 | MM-ZTK-1F-GEN-PIP-LIS-0002 | PIPING SPECIAL ITEM LIST |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:11:33 | wisuda.c@jutal.com | 11-May-2026 11:27:31 | Jumpol Sudjitjul | 18-May-2026 |  | Aphisit Pinkaew | 20-May-2026 | 26-May-2026 20:27:53 | Pornlert Wanaphattharaphan | 21-May-2026 | 30-May-2026 06:17:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 31-May-2026 20:50:49 | 31-May-2026 14:26:28 | 0 |  |  | Approver | Locate
AO-001443 | MM-ZTK-1F-GEN-PIP-LIS-0002 | PIPING SPECIAL ITEM LIST |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 10:59:19 | wisuda.c@jutal.com | 07-Aug-2026 14:34:48 | Jumpol Sudjitjul | 17-Aug-2026 |  | Aphisit Pinkaew | 19-Aug-2026 | 16-Aug-2026 18:51:27 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:30:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 10:38:35 | 21-Aug-2026 04:27:04 | 0 |  |  | Approver | Locate
AO-001788 | MM-ZTK-1F-GEN-PIP-LIS-0002 | PIPING SPECIAL ITEM LIST |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 31-Aug-2026 08:40:03 | wisuda.c@jutal.com | 31-Aug-2026 13:00:05 | Jumpol Sudjitjul | 07-Sep-2026 |  | Aphisit Pinkaew | 09-Sep-2026 | 09-Sep-2026 10:57:25 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 23:06:29 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 12-Sep-2026 21:11:15 | 12-Sep-2026 14:37:17 | 0 |  |  | Approver | Locate
AO-002246 | MM-ZTK-1F-GEN-PIP-LIS-0002 | PIPING SPECIAL ITEM LIST |  | C3 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 14:11:02 | wisuda.c@jutal.com | 24-Sep-2026 14:26:24 | Jumpol Sudjitjul | 01-Oct-2026 |  | Aphisit Pinkaew | 05-Oct-2026 | 09-Oct-2026 16:19:10 | Pornlert Wanaphattharaphan | 06-Oct-2026 | 10-Oct-2026 00:24:03 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 10-Oct-2026 17:28:41 | 10-Oct-2026 11:27:46 | 0 |  |  | Approver | Locate
AO-001149 | MM-ZTK-1F-GEN-PIP-LIS-0003 | PIPING STRESS CRITICAL LINE LIST |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 16-Jul-2026 21:12:08 | wisuda.c@jutal.com | 17-Jul-2026 10:41:45 | Jumpol Sudjitjul | 24-Jul-2026 | 24-Jul-2026 23:39:53 | Aphisit Pinkaew | 30-Jul-2026 | 06-Aug-2026 10:10:05 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 07-Aug-2026 05:30:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 07-Aug-2026 08:38:07 | 07-Aug-2026 02:22:42 | 0 |  |  | Approver | Locate
AO-001730 | MM-ZTK-1F-GEN-PIP-LIS-0003 | PIPING STRESS CRITICAL LINE LIST |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 26-Aug-2026 19:20:20 | wisuda.c@jutal.com | 27-Aug-2026 11:26:16 | Jumpol Sudjitjul | 03-Sep-2026 | 03-Sep-2026 23:44:27 | Aphisit Pinkaew | 07-Sep-2026 | 07-Sep-2026 10:11:29 | Pornlert Wanaphattharaphan | 08-Sep-2026 | 08-Sep-2026 23:14:15 | APPR | Approved | Jumpol Sudjitjul | 09-Sep-2026 | 09-Sep-2026 11:09:50 | 09-Sep-2026 05:33:03 | 0 |  |  | Approver | Locate
AO-000032 | MM-ZTK-1F-GEN-PIP-MOM-0001 | PIPING DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 19-Mar-2026 14:56:36 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000049 | MM-ZTK-1F-GEN-PIP-MOM-0002 | PIPING DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 30-Mar-2026 18:20:45 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000061 | MM-ZTK-1F-GEN-PIP-MOM-0003 | PIPING DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 01-Apr-2026 16:54:48 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000102 | MM-ZTK-1F-GEN-PIP-MOM-0004 | PIPING DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 09-Apr-2026 08:56:22 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000138 | MM-ZTK-1F-GEN-PIP-MOM-0005 | PIPING DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 16-Apr-2026 11:24:25 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000315 | MM-ZTK-1F-GEN-PIP-MOM-0007 | PIPING DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-May-2026 09:47:33 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000332 | MM-ZTK-1F-GEN-PIP-MOM-0008 | PIPING DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-May-2026 16:33:49 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000380 | MM-ZTK-1F-GEN-PIP-MOM-0009 | PIPING DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 12-May-2026 15:32:56 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000516 | MM-ZTK-1F-GEN-PIP-MOM-0010 | PIPING DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 19-May-2026 16:55:20 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000624 | MM-ZTK-1F-GEN-PIP-MOM-0011 | PIPING DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 29-May-2026 15:41:54 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000753 | MM-ZTK-1F-GEN-PIP-MOM-0012 | PIPING DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 12-Jun-2026 09:27:29 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000873 | MM-ZTK-1F-GEN-PIP-MOM-0013 | PIPING DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 23-Jun-2026 11:29:57 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000891 | MM-ZTK-1F-GEN-PIP-MOM-0014 | PIPING DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 25-Jun-2026 09:26:12 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001428 | MM-ZTK-1F-GEN-PIP-MOM-0015 | PIPING DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Aug-2026 09:26:50 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001432 | MM-ZTK-1F-GEN-PIP-MOM-0016 | PIPING DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Aug-2026 14:03:17 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001432 | MM-ZTK-1F-GEN-PIP-MOM-0017 | PIPING DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Aug-2026 14:03:46 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001432 | MM-ZTK-1F-GEN-PIP-MOM-0018 | PIPING DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Aug-2026 14:04:15 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001743 | MM-ZTK-1F-GEN-PIP-MOM-0019 | PIPING DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 27-Aug-2026 19:04:03 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001952 | MM-ZTK-1F-GEN-PIP-MOM-0020 | PIPING DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 09-Sep-2026 15:26:01 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001953 | MM-ZTK-1F-GEN-PIP-MOM-0021 | PIPING DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 09-Sep-2026 15:26:25 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002037 | MM-ZTK-1F-GEN-PIP-MOM-0022 | PIPING DISCIPLINE WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Sep-2026 10:32:01 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000318 | MM-ZTK-1F-GEN-PIP-MR-0001 | MATERIAL REQUISITION FOR MANUAL VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 06-May-2026 11:11:41 | wisuda.c@jutal.com | 06-May-2026 13:16:26 | Jumpol Sudjitjul | 13-May-2026 |  | Aphisit Pinkaew | 15-May-2026 | 19-May-2026 21:48:41 | Pornlert Wanaphattharaphan | 18-May-2026 | 23-May-2026 23:29:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 24-May-2026 15:05:59 | 24-May-2026 08:32:34 | 0 |  |  | Approver | Locate
AO-001150 | MM-ZTK-1F-GEN-PIP-MR-0001 | MATERIAL REQUISITION FOR MANUAL VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 21:12:45 | wisuda.c@jutal.com | 17-Jul-2026 10:29:52 | Jumpol Sudjitjul | 24-Jul-2026 |  | Aphisit Pinkaew | 30-Jul-2026 | 09-Aug-2026 10:31:03 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 09-Aug-2026 17:05:32 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 09-Aug-2026 18:21:05 | 09-Aug-2026 11:27:57 | 0 |  |  | Approver | Locate
AO-000319 | MM-ZTK-1F-GEN-PIP-MR-0002 | MATERIAL REQUISITION FOR PIPES, FITTINGS AND FLANGES AND BULK MATERIAL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 06-May-2026 11:12:04 | wisuda.c@jutal.com | 06-May-2026 13:17:11 | Jumpol Sudjitjul | 13-May-2026 |  | Aphisit Pinkaew | 15-May-2026 | 21-May-2026 15:47:21 | Pornlert Wanaphattharaphan | 18-May-2026 | 23-May-2026 23:37:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 24-May-2026 15:04:48 | 24-May-2026 08:31:16 | 0 |  |  | Approver | Locate
AO-001150 | MM-ZTK-1F-GEN-PIP-MR-0002 | MATERIAL REQUISITION FOR PIPES, FITTINGS AND FLANGES AND BULK MATERIAL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 21:13:13 | wisuda.c@jutal.com | 17-Jul-2026 10:30:18 | Jumpol Sudjitjul | 24-Jul-2026 |  | Aphisit Pinkaew | 30-Jul-2026 | 09-Aug-2026 10:28:22 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 09-Aug-2026 17:02:55 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 09-Aug-2026 18:20:40 | 09-Aug-2026 11:26:41 | 0 |  |  | Approver | Locate
AO-000320 | MM-ZTK-1F-GEN-PIP-MR-0003 | MATERIAL REQUISITION FOR SPECIALTY ITEMS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 06-May-2026 11:12:29 | wisuda.c@jutal.com | 06-May-2026 13:17:49 | Jumpol Sudjitjul | 13-May-2026 |  | Aphisit Pinkaew | 15-May-2026 | 22-May-2026 22:13:43 | Pornlert Wanaphattharaphan | 18-May-2026 | 24-May-2026 00:12:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 24-May-2026 15:03:44 | 24-May-2026 08:29:59 | 0 |  |  | Approver | Locate
AO-001150 | MM-ZTK-1F-GEN-PIP-MR-0003 | MATERIAL REQUISITION FOR SPECIALTY ITEMS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 21:13:52 | wisuda.c@jutal.com | 17-Jul-2026 10:30:40 | Jumpol Sudjitjul | 24-Jul-2026 |  | Aphisit Pinkaew | 30-Jul-2026 | 09-Aug-2026 10:34:34 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 09-Aug-2026 17:06:04 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 09-Aug-2026 18:20:05 | 09-Aug-2026 11:25:31 | 0 |  |  | Approver | Locate
AO-001099 | MM-ZTK-1F-GEN-PIP-MR-0004 | MATERIAL REQUISITION FOR PIPELINE BULK (B31.8) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 14-Jul-2026 08:44:18 | wisuda.c@jutal.com | 14-Jul-2026 09:15:02 | Jumpol Sudjitjul | 21-Jul-2026 | 21-Jul-2026 08:27:25 | Aphisit Pinkaew | 23-Jul-2026 | 28-Jul-2026 20:30:04 | Pornlert Wanaphattharaphan | 24-Jul-2026 | 28-Jul-2026 23:42:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Jul-2026 | 30-Jul-2026 09:32:19 | 30-Jul-2026 02:47:03 | 0 |  |  | Approver | Locate
AO-001481 | MM-ZTK-1F-GEN-PIP-MR-0004 | MATERIAL REQUISITION FOR PIPELINE BULK (B31.8) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 10-Aug-2026 11:58:26 | wisuda.c@jutal.com | 10-Aug-2026 14:51:58 | Jumpol Sudjitjul | 18-Aug-2026 |  | Aphisit Pinkaew | 20-Aug-2026 | 20-Aug-2026 10:54:09 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:56:56 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 19:59:38 | 24-Aug-2026 13:46:58 | 0 |  |  | Approver | Locate
AO-001478 | MM-ZTK-1F-GEN-PIP-MTO-0001 | MATERIAL TAKE-OFF FOR PIPING BULK |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 10-Aug-2026 11:58:56 | wisuda.c@jutal.com | 10-Aug-2026 14:50:45 | Jumpol Sudjitjul | 18-Aug-2026 |  | Aphisit Pinkaew | 20-Aug-2026 | 29-Aug-2026 21:39:58 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 29-Aug-2026 21:50:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 30-Aug-2026 16:57:33 | 30-Aug-2026 10:38:15 | 0 |  |  | Approver | Locate
AO-000354 | MM-ZTK-1F-GEN-PIP-MTO-0002 | MATERIAL TAKE-OFF FOR PIPING VALVES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:54:19 | wisuda.c@jutal.com | 11-May-2026 11:29:29 | Jumpol Sudjitjul | 18-May-2026 |  | Aphisit Pinkaew | 20-May-2026 | 26-May-2026 20:14:44 | Pornlert Wanaphattharaphan | 21-May-2026 | 30-May-2026 06:11:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 31-May-2026 20:51:24 | 31-May-2026 14:39:46 | 0 |  |  | Approver | Locate
AO-001326 | MM-ZTK-1F-GEN-PIP-MTO-0002 | MATERIAL TAKE-OFF FOR PIPING VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MTO | Material Take Off | 0 | Submitted | AFC | Approved for Construction |  | 28-Jul-2026 09:12:31 | wisuda.c@jutal.com | 28-Jul-2026 20:29:52 | Jumpol Sudjitjul | 06-Aug-2026 |  | Aphisit Pinkaew | 10-Aug-2026 | 16-Aug-2026 18:38:54 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 16-Aug-2026 22:41:12 | APPR | Approved | Jumpol Sudjitjul | 13-Aug-2026 | 17-Aug-2026 13:49:26 | 17-Aug-2026 07:08:24 | 0 |  |  | Approver | Locate
AO-002264 | MM-ZTK-1F-GEN-PIP-MTO-0002 | MATERIAL TAKE-OFF FOR PIPING VALVES |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | MTO | Material Take Off | 0 | Submitted | AFC | Approved for Construction |  | 25-Sep-2026 16:11:54 | wisuda.c@jutal.com | 25-Sep-2026 17:23:19 | Jumpol Sudjitjul | 05-Oct-2026 |  | Aphisit Pinkaew | 07-Oct-2026 | 09-Oct-2026 16:22:05 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 10-Oct-2026 01:35:17 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 10-Oct-2026 17:29:13 | 10-Oct-2026 10:50:09 | 0 |  |  | Approver | Locate
AO-000688 | MM-ZTK-1F-GEN-PIP-RPT-0001 | 3D MODEL REVIEW AND CLOSE-OUT REPORT (30%, 60% AND 90%) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 20:58:13 | wisuda.c@jutal.com | 07-Jun-2026 18:04:40 | Jumpol Sudjitjul | 15-Jun-2026 | 17-Jun-2026 22:18:57 | Aphisit Pinkaew | 17-Jun-2026 | 24-Jun-2026 13:40:32 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 24-Jun-2026 20:46:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 25-Jun-2026 13:34:42 | 25-Jun-2026 07:12:21 | 0 |  |  | Approver | Locate
AO-001680 | MM-ZTK-1F-GEN-PIP-RPT-0001 | 3D MODEL REVIEW AND CLOSE-OUT REPORT (30%, 60% AND 90%) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:44:14 | wisuda.c@jutal.com | 25-Aug-2026 10:27:58 | Jumpol Sudjitjul | 01-Sep-2026 |  | Aphisit Pinkaew | 03-Sep-2026 | 09-Sep-2026 10:12:23 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 09-Sep-2026 23:02:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 10-Sep-2026 09:09:58 | 10-Sep-2026 02:41:27 | 0 |  |  | Approver | Locate
AO-001563 | MM-ZTK-1F-GEN-PIP-RPT-0002 | DRILLING RIGS CLASH CHECK REPORT (60%, 90% AND FINAL) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 17-Aug-2026 14:19:53 | wisuda.c@jutal.com | 17-Aug-2026 16:01:19 | Jumpol Sudjitjul | 24-Aug-2026 |  | Aphisit Pinkaew | 26-Aug-2026 | 04-Sep-2026 20:15:30 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 04-Sep-2026 23:23:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 05-Sep-2026 18:01:23 | 05-Sep-2026 11:34:14 | 0 |  |  | Approver | Locate
AO-000231 | MM-ZTK-1F-GEN-PIP-RPT-0003 | PIPE STRESS ANALYSIS REPORT FOR FLOWLINE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 14:33:06 | zm169dc@jutal.com | 27-Apr-2026 16:33:39 | Jumpol Sudjitjul | 06-May-2026 |  | Aphisit Pinkaew | 08-May-2026 | 30-Apr-2026 16:17:50 | Pornlert Wanaphattharaphan | 11-May-2026 | 01-May-2026 17:45:05 | NA | Not Approved | Jumpol Sudjitjul | 12-May-2026 | 04-May-2026 10:48:34 | 04-May-2026 04:39:47 | 0 |  |  | Approver | Locate
AO-000231 | MM-ZTK-1F-GEN-PIP-RPT-0004 | PIPE STRESS ANALYSIS REPORT FOR PIG LAUNCHER/RECEIVER |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 14:33:37 | zm169dc@jutal.com | 27-Apr-2026 16:34:09 | Jumpol Sudjitjul | 06-May-2026 |  | Aphisit Pinkaew | 08-May-2026 | 30-Apr-2026 16:21:45 | Pornlert Wanaphattharaphan | 11-May-2026 | 01-May-2026 17:47:07 | NA | Not Approved | Jumpol Sudjitjul | 12-May-2026 | 04-May-2026 10:50:43 | 04-May-2026 04:42:17 | 0 |  |  | Approver | Locate
AO-000231 | MM-ZTK-1F-GEN-PIP-RPT-0005 | PIPE STRESS ANALYSIS REPORT FOR OTHER GC LINES, IG LINES AND HP VENT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 14:34:06 | zm169dc@jutal.com | 27-Apr-2026 16:37:09 | Jumpol Sudjitjul | 06-May-2026 |  | Aphisit Pinkaew | 08-May-2026 | 30-Apr-2026 16:25:59 | Pornlert Wanaphattharaphan | 11-May-2026 | 01-May-2026 17:49:05 | NA | Not Approved | Jumpol Sudjitjul | 12-May-2026 | 04-May-2026 10:49:59 | 04-May-2026 04:41:02 | 0 |  |  | Approver | Locate
AO-000231 | MM-ZTK-1F-GEN-PIP-RPT-0006 | PIPE STRESS ANALYSIS REPORT FOR LP RELIEF AND DP LINES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 14:34:31 | zm169dc@jutal.com | 27-Apr-2026 16:37:37 | Jumpol Sudjitjul | 06-May-2026 |  | Aphisit Pinkaew | 08-May-2026 | 30-Apr-2026 16:27:41 | Pornlert Wanaphattharaphan | 11-May-2026 | 01-May-2026 18:15:18 | NA | Not Approved | Jumpol Sudjitjul | 12-May-2026 | 03-May-2026 16:35:24 | 03-May-2026 10:17:14 | 0 |  |  | Approver | Locate
AO-002477 | MM-ZTK-1F-GEN-PIP-RPT-0007 | QUANTITATIVE ASSESSMENT OF SMALL BORE CONNECTION |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | In Review | IFR | Issued for Review |  | 12-Oct-2026 11:47:19 | wisuda.c@jutal.com | 12-Oct-2026 13:35:33 | Jumpol Sudjitjul | 20-Oct-2026 |  | Aphisit Pinkaew | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 | 01-May-2026 18:21:48 |  |  | Jumpol Sudjitjul | 27-Oct-2026 | 03-May-2026 16:34:29 |  | 0 |  |  | Approver | Locate
AO-000231 | MM-ZTK-1F-GEN-PIP-RPT-0008 | 3D MODEL CLASH CHECK REPORT (90% AND FINAL) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 14:35:27 | zm169dc@jutal.com | 27-Apr-2026 16:38:35 | Jumpol Sudjitjul | 06-May-2026 |  | Aphisit Pinkaew | 08-May-2026 | 30-Apr-2026 16:39:20 | Pornlert Wanaphattharaphan | 11-May-2026 | 01-May-2026 18:21:23 | NA | Not Approved | Jumpol Sudjitjul | 12-May-2026 | 03-May-2026 16:32:32 | 03-May-2026 10:14:43 | 0 |  |  | Approver | Locate
AO-000231 | MM-ZTK-1F-GEN-PIP-RPT-0009 | SS & DSS FITTING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 27-Apr-2026 14:35:55 | zm169dc@jutal.com | 27-Apr-2026 16:44:26 | Jumpol Sudjitjul |  |  |  |  | 01-May-2026 19:47:27 |  |  | 06-May-2026 16:23:02 |  |  | Jumpol Sudjitjul |  | 06-May-2026 16:28:44 | 27-Apr-2026 05:20:37 | 0 |  |  |  | Locate
AO-000231 | MM-ZTK-1F-GEN-PIP-RPT-0010 | CS FLANGE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 27-Apr-2026 14:36:22 | zm169dc@jutal.com | 27-Apr-2026 16:45:05 | Jumpol Sudjitjul |  |  |  |  | 01-May-2026 19:51:36 |  |  | 06-May-2026 16:23:33 |  |  | Jumpol Sudjitjul |  | 06-May-2026 16:29:31 | 27-Apr-2026 05:21:03 | 0 |  |  |  | Locate
AO-000231 | MM-ZTK-1F-GEN-PIP-RPT-0011 | SS & DSS FLANGE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 27-Apr-2026 14:36:46 | zm169dc@jutal.com | 27-Apr-2026 16:45:22 | Jumpol Sudjitjul |  |  |  |  | 01-May-2026 19:53:46 |  |  | 06-May-2026 16:24:04 |  |  | Jumpol Sudjitjul |  | 06-May-2026 16:30:44 | 27-Apr-2026 05:21:29 | 0 |  |  |  | Locate
AO-000231 | MM-ZTK-1F-GEN-PIP-RPT-0012 | SAW WELDED PIPE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 27-Apr-2026 14:37:20 | zm169dc@jutal.com | 27-Apr-2026 16:45:38 | Jumpol Sudjitjul |  |  |  |  | 01-May-2026 19:55:46 |  |  | 06-May-2026 16:26:52 |  |  | Jumpol Sudjitjul |  | 06-May-2026 16:31:29 | 27-Apr-2026 05:21:56 | 0 |  |  |  | Locate
AO-000231 | MM-ZTK-1F-GEN-PIP-RPT-0013 | CS PIPE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 27-Apr-2026 14:37:46 | zm169dc@jutal.com | 27-Apr-2026 16:45:29 | Jumpol Sudjitjul |  |  |  |  | 01-May-2026 19:57:24 |  |  | 06-May-2026 16:27:27 |  |  | Jumpol Sudjitjul |  | 06-May-2026 16:33:06 | 27-Apr-2026 05:22:21 | 0 |  |  |  | Locate
AO-000231 | MM-ZTK-1F-GEN-PIP-RPT-0014 | DSS PIPES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 27-Apr-2026 14:38:13 | zm169dc@jutal.com | 27-Apr-2026 16:45:44 | Jumpol Sudjitjul |  |  |  |  | 01-May-2026 19:59:16 |  |  | 06-May-2026 16:28:05 |  |  | Jumpol Sudjitjul |  | 06-May-2026 16:34:59 | 27-Apr-2026 05:23:12 | 0 |  |  |  | Locate
AO-000231 | MM-ZTK-1F-GEN-PIP-RPT-0015 | SEAMLESS SS PIPES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 27-Apr-2026 14:38:41 | zm169dc@jutal.com | 27-Apr-2026 16:45:58 | Jumpol Sudjitjul |  |  |  |  | 01-May-2026 20:02:48 |  |  | 06-May-2026 16:28:39 |  |  | Jumpol Sudjitjul |  | 06-May-2026 16:36:47 | 27-Apr-2026 05:23:38 | 0 |  |  |  | Locate
AO-000231 | MM-ZTK-1F-GEN-PIP-RPT-0016 | BOLTS & NUTS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 27-Apr-2026 14:39:09 | zm169dc@jutal.com | 27-Apr-2026 16:46:20 | Jumpol Sudjitjul |  |  |  |  | 01-May-2026 20:04:11 |  |  | 06-May-2026 16:29:56 |  |  | Jumpol Sudjitjul |  | 06-May-2026 16:50:29 | 27-Apr-2026 05:24:03 | 0 |  |  |  | Locate
AO-000231 | MM-ZTK-1F-GEN-PIP-RPT-0017 | GASKET |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 27-Apr-2026 14:39:39 | zm169dc@jutal.com | 27-Apr-2026 16:46:50 | Jumpol Sudjitjul |  |  |  |  | 01-May-2026 20:06:05 |  |  | 06-May-2026 16:31:15 |  |  | Jumpol Sudjitjul |  | 06-May-2026 16:49:27 | 27-Apr-2026 05:24:28 | 0 |  |  |  | Locate
AO-000231 | MM-ZTK-1F-GEN-PIP-RPT-0018 | PIG LAUNCHER AND RECEIVER |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 27-Apr-2026 14:40:06 | zm169dc@jutal.com | 27-Apr-2026 16:37:32 | Jumpol Sudjitjul |  |  |  |  | 01-May-2026 20:08:09 |  |  | 06-May-2026 16:32:23 |  |  | Jumpol Sudjitjul |  | 06-May-2026 16:46:55 | 27-Apr-2026 05:24:54 | 0 |  |  |  | Locate
AO-000231 | MM-ZTK-1F-GEN-PIP-RPT-0019 | STRAINERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 27-Apr-2026 14:40:33 | zm169dc@jutal.com | 27-Apr-2026 16:37:07 | Jumpol Sudjitjul |  |  |  |  | 01-May-2026 20:09:38 |  |  | 06-May-2026 16:33:09 |  |  | Jumpol Sudjitjul |  | 06-May-2026 16:41:40 | 27-Apr-2026 05:25:20 | 0 |  |  |  | Locate
AO-000231 | MM-ZTK-1F-GEN-PIP-RPT-0020 | BUTTERFLY VALVE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 27-Apr-2026 14:40:57 | zm169dc@jutal.com | 27-Apr-2026 16:36:43 | Jumpol Sudjitjul |  |  |  |  | 01-May-2026 20:11:09 |  |  | 06-May-2026 16:33:52 |  |  | Jumpol Sudjitjul |  | 06-May-2026 16:39:07 | 27-Apr-2026 05:25:48 | 0 |  |  |  | Locate
AO-000231 | MM-ZTK-1F-GEN-PIP-RPT-0021 | BALL VALVE (WELDED END) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 27-Apr-2026 14:41:23 | zm169dc@jutal.com | 27-Apr-2026 16:36:13 | Jumpol Sudjitjul |  |  |  |  | 01-May-2026 20:13:55 |  |  | 06-May-2026 16:35:03 |  |  | Jumpol Sudjitjul |  | 06-May-2026 16:38:11 | 27-Apr-2026 05:26:14 | 0 |  |  |  | Locate
AO-000683 | MM-ZTK-1F-GEN-PIP-RPT-0100 | CRITICALITY RATING ANALYSIS (PIPING) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 13:52:22 | zm169dc@jutal.com | 05-Jun-2026 14:23:02 | Jumpol Sudjitjul | 12-Jun-2026 |  | Aphisit Pinkaew | 16-Jun-2026 | 15-Jun-2026 16:28:13 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 18-Jun-2026 09:41:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 09:43:13 | 18-Jun-2026 03:30:46 | 0 |  |  | Approver | Locate
AO-001059 | MM-ZTK-1F-GEN-PIP-RPT-0100 | CRITICALITY RATING ANALYSIS (PIPING) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 08-Jul-2026 15:31:32 | zm169dc@jutal.com | 10-Jul-2026 18:16:06 | Jumpol Sudjitjul | 20-Jul-2026 |  | Aphisit Pinkaew | 22-Jul-2026 | 28-Jul-2026 20:00:24 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 28-Jul-2026 22:32:23 | APPR | Approved | Jumpol Sudjitjul | 24-Jul-2026 | 30-Jul-2026 09:34:54 | 30-Jul-2026 04:02:00 | 0 |  |  | Approver | Locate
AO-000264 | MM-ZTK-1F-GEN-PIP-SPE-0001 | PARTICULAR PIPING AND VALVES MATERIAL SPECIFICATIONS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 18:30:05 | wisuda.c@jutal.com | 30-Apr-2026 10:12:20 | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 09:04:39 | Aphisit Pinkaew | 13-May-2026 | 18-May-2026 16:15:45 | Pornlert Wanaphattharaphan | 14-May-2026 | 20-May-2026 10:17:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 11:07:14 | 20-May-2026 04:29:23 | 0 |  |  | Approver | Locate
AO-000912 | MM-ZTK-1F-GEN-PIP-SPE-0001 | PARTICULAR PIPING AND VALVES MATERIAL SPECIFICATIONS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 26-Jun-2026 19:49:58 | wisuda.c@jutal.com | 26-Jun-2026 19:55:55 | Jumpol Sudjitjul | 06-Jul-2026 |  | Aphisit Pinkaew | 08-Jul-2026 | 03-Jul-2026 14:21:46 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 11-Jul-2026 13:55:30 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 12-Jul-2026 11:31:15 | 12-Jul-2026 04:47:50 | 0 |  |  | Approver | Locate
AO-001289 | MM-ZTK-1F-GEN-PIP-SPE-0001 | PARTICULAR PIPING AND VALVES MATERIAL SPECIFICATIONS |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 27-Jul-2026 09:21:37 | wisuda.c@jutal.com | 27-Jul-2026 15:57:16 | Jumpol Sudjitjul | 05-Aug-2026 | 05-Aug-2026 23:41:53 | Aphisit Pinkaew | 07-Aug-2026 | 14-Aug-2026 14:33:04 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 15-Aug-2026 20:04:35 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 16-Aug-2026 09:45:45 | 16-Aug-2026 02:59:03 | 0 |  |  | Approver | Locate
AO-000321 | MM-ZTK-1F-GEN-PIP-SPE-0002 | PARTICULAR PIG LAUNCHER AND PIG RECEIVER SPECIFICATIONS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 06-May-2026 11:12:53 | wisuda.c@jutal.com | 06-May-2026 13:05:17 | Jumpol Sudjitjul | 13-May-2026 | 13-May-2026 23:43:11 | Aphisit Pinkaew | 15-May-2026 | 20-May-2026 09:46:11 | Pornlert Wanaphattharaphan | 18-May-2026 | 23-May-2026 23:34:10 | NA | Not Approved | Jumpol Sudjitjul | 19-May-2026 | 24-May-2026 15:02:50 | 24-May-2026 15:28:41 | 0 |  |  | Approver | Locate
AO-000672 | MM-ZTK-1F-GEN-PIP-SPE-0002 | PARTICULAR PIG LAUNCHER AND PIG RECEIVER SPECIFICATIONS |  | X | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | SPE | Specification | 0 | Latest | VOID | Withdrawn or Superseded |  | 04-Jun-2026 20:46:57 | wisuda.c@jutal.com | 04-Jun-2026 21:23:53 | Jumpol Sudjitjul |  |  | Aphisit Pinkaew |  | 15-Jun-2026 15:53:05 |  |  |  | APPR | Approved |  |  |  |  | 0 |  |  | For Info | Locate
AO-000691 | MM-ZTK-1F-GEN-PIP-STD-0001 | PIPING DESIGN STANDARD |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | STD | Standard | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 20:58:43 | wisuda.c@jutal.com | 07-Jun-2026 18:08:42 | Jumpol Sudjitjul | 15-Jun-2026 |  | Aphisit Pinkaew | 17-Jun-2026 | 23-Jun-2026 11:11:33 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 24-Jun-2026 00:46:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 24-Jun-2026 13:33:42 | 24-Jun-2026 06:49:22 | 0 |  |  | Approver | Locate
AO-001910 | MM-ZTK-1F-GEN-PIP-STD-0001 | PIPING DESIGN STANDARD |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | STD | Standard | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 09:34:05 | wisuda.c@jutal.com | 08-Sep-2026 09:06:26 | Jumpol Sudjitjul | 15-Sep-2026 | 16-Sep-2026 13:50:46 | Aphisit Pinkaew | 17-Sep-2026 | 22-Sep-2026 19:44:17 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 25-Sep-2026 16:25:21 | APPR | Approved | Jumpol Sudjitjul | 21-Sep-2026 | 25-Sep-2026 16:56:00 | 25-Sep-2026 11:47:26 | 0 |  |  | Approver | Locate
AO-000692 | MM-ZTK-1F-GEN-PIP-STD-0002 | PIPE SUPPORT STANDARD |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | STD | Standard | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 20:59:13 | wisuda.c@jutal.com | 07-Jun-2026 18:08:56 | Jumpol Sudjitjul | 15-Jun-2026 |  | Aphisit Pinkaew | 17-Jun-2026 | 23-Jun-2026 11:51:09 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 24-Jun-2026 00:41:28 | APPR | Approved | Jumpol Sudjitjul | 19-Jun-2026 | 24-Jun-2026 13:34:23 | 24-Jun-2026 06:50:39 | 0 |  |  | Approver | Locate
AO-001912 | MM-ZTK-1F-GEN-PIP-STD-0002 | PIPE SUPPORT STANDARD |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | STD | Standard | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 09:34:36 | wisuda.c@jutal.com | 08-Sep-2026 09:06:52 | Jumpol Sudjitjul | 15-Sep-2026 | 16-Sep-2026 14:03:08 | Aphisit Pinkaew | 17-Sep-2026 | 22-Sep-2026 19:47:08 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 25-Sep-2026 16:26:07 | APPR | Approved | Jumpol Sudjitjul | 21-Sep-2026 | 25-Sep-2026 16:58:45 | 25-Sep-2026 11:48:37 | 0 |  |  | Approver | Locate
AO-001070 | MM-ZTK-1F-GEN-PIP-TBE-0001 | TECHNICAL BID EVALUATION FOR COMPACT CHECK VALVE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 10-Jul-2026 18:46:02 | wisuda.c@jutal.com | 10-Jul-2026 20:37:17 | Jumpol Sudjitjul | 20-Jul-2026 |  | Aphisit Pinkaew | 22-Jul-2026 | 28-Jul-2026 21:22:06 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 28-Jul-2026 23:35:26 | NA | Not Approved | Jumpol Sudjitjul | 24-Jul-2026 | 30-Jul-2026 09:39:38 | 30-Jul-2026 03:45:42 | 0 |  |  | Approver | Locate
AO-001425 | MM-ZTK-1F-GEN-PIP-TBE-0001 | TECHNICAL BID EVALUATION FOR COMPACT CHECK VALVE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 05-Aug-2026 17:28:53 | wisuda.c@jutal.com | 05-Aug-2026 17:36:54 | Jumpol Sudjitjul | 14-Aug-2026 |  | Aphisit Pinkaew | 18-Aug-2026 | 07-Aug-2026 08:57:58 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 07-Aug-2026 20:48:51 | APPR | Approved | Jumpol Sudjitjul | 20-Aug-2026 | 08-Aug-2026 10:19:38 | 08-Aug-2026 03:56:34 | 0 |  |  | Approver | Locate
AO-002006 | MM-ZTK-1F-GEN-PIP-TBE-0002 | TECHNICAL BID EVALUATION FOR BARRED TEES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 11-Sep-2026 12:46:21 | wisuda.c@jutal.com | 11-Sep-2026 19:32:46 | Jumpol Sudjitjul | 21-Sep-2026 | 19-Sep-2026 18:41:58 | Aphisit Pinkaew | 23-Sep-2026 | 24-Sep-2026 13:34:39 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 25-Sep-2026 00:11:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Sep-2026 | 25-Sep-2026 08:23:16 | 25-Sep-2026 01:54:19 | 0 |  |  | Approver | Locate
AO-002350 | MM-ZTK-1F-GEN-PIP-TBE-0002 | TECHNICAL BID EVALUATION FOR BARRED TEES |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 05-Oct-2026 09:14:12 | wisuda.c@jutal.com | 05-Oct-2026 10:41:11 | Jumpol Sudjitjul | 12-Oct-2026 |  | Aphisit Pinkaew | 15-Oct-2026 | 08-Oct-2026 19:58:59 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 09-Oct-2026 13:33:07 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 09-Oct-2026 13:35:54 | 09-Oct-2026 07:07:31 | 0 |  |  | Approver | Locate
AO-001161 | MM-ZTK-1F-GEN-PIP-TBE-0003 | TECHNICAL BID EVALUATION FOR BALL VALVES (WELDED TYPE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 17-Jul-2026 20:46:13 | wisuda.c@jutal.com | 17-Jul-2026 22:16:22 | Jumpol Sudjitjul | 27-Jul-2026 |  | Aphisit Pinkaew | 31-Jul-2026 | 06-Aug-2026 10:03:43 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 06-Aug-2026 20:55:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 07-Aug-2026 08:53:20 | 07-Aug-2026 02:07:36 | 0 |  |  | Approver | Locate
AO-001523 | MM-ZTK-1F-GEN-PIP-TBE-0003 | TECHNICAL BID EVALUATION FOR BALL VALVES (WELDED TYPE) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 14-Aug-2026 13:25:05 | wisuda.c@jutal.com | 14-Aug-2026 13:43:21 | Jumpol Sudjitjul | 21-Aug-2026 |  | Aphisit Pinkaew | 25-Aug-2026 | 17-Aug-2026 14:01:17 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 18-Aug-2026 22:21:01 | APPR | Approved | Jumpol Sudjitjul | 27-Aug-2026 | 19-Aug-2026 09:48:20 | 20-Aug-2026 12:19:32 | 0 |  |  | Approver | Locate
AO-001755 | MM-ZTK-1F-GEN-PIP-TBE-0004 | TECHNICAL BID EVALUATION FOR PIPES (SS AND DSS) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 28-Aug-2026 13:10:36 | wisuda.c@jutal.com | 28-Aug-2026 14:12:13 | Jumpol Sudjitjul | 04-Sep-2026 |  | Aphisit Pinkaew | 08-Sep-2026 | 28-Aug-2026 15:34:23 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 29-Aug-2026 01:06:29 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 29-Aug-2026 13:57:25 | 29-Aug-2026 07:08:14 | 0 |  |  | Approver | Locate
AO-001301 | MM-ZTK-1F-GEN-PIP-TBE-0005 | TECHNICAL BID EVALUATION FOR FITTINGS (DSS) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 27-Jul-2026 08:40:47 | wisuda.c@jutal.com | 27-Jul-2026 09:20:41 | Jumpol Sudjitjul | 05-Aug-2026 |  | Aphisit Pinkaew | 07-Aug-2026 | 11-Aug-2026 14:26:27 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 11-Aug-2026 18:11:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 11:10:12 | 13-Aug-2026 05:49:59 | 0 |  |  | Approver | Locate
AO-001610 | MM-ZTK-1F-GEN-PIP-TBE-0005 | TECHNICAL BID EVALUATION FOR FITTINGS (DSS) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 19-Aug-2026 13:51:50 | wisuda.c@jutal.com | 19-Aug-2026 15:16:53 | Jumpol Sudjitjul | 26-Aug-2026 |  | Aphisit Pinkaew | 28-Aug-2026 | 20-Aug-2026 10:37:01 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 22-Aug-2026 14:12:50 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 24-Aug-2026 19:59:09 | 24-Aug-2026 13:34:16 | 0 |  |  | Approver | Locate
AO-001130 | MM-ZTK-1F-GEN-PIP-TBE-0007 | TECHNICAL BID EVALUTION FOR CHECK VALVES AND BUTTERFLY VALVES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 16-Jul-2026 14:04:28 | wisuda.c@jutal.com | 16-Jul-2026 14:12:19 | Jumpol Sudjitjul | 23-Jul-2026 |  | Aphisit Pinkaew | 27-Jul-2026 | 30-Jul-2026 16:15:09 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 30-Jul-2026 17:44:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Jul-2026 | 30-Jul-2026 19:12:31 | 02-Aug-2026 03:04:56 | 0 |  |  | Approver | Locate
AO-001454 | MM-ZTK-1F-GEN-PIP-TBE-0007 | TECHNICAL BID EVALUTION FOR CHECK VALVES AND BUTTERFLY VALVES |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 07-Aug-2026 17:30:46 | wisuda.c@jutal.com | 07-Aug-2026 17:43:38 | Jumpol Sudjitjul | 18-Aug-2026 |  | Aphisit Pinkaew | 20-Aug-2026 | 11-Aug-2026 09:48:22 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 11-Aug-2026 18:35:32 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 13-Aug-2026 11:08:48 | 13-Aug-2026 05:35:28 | 0 |  |  | Approver | Locate
AO-001302 | MM-ZTK-1F-GEN-PIP-TBE-0008 | TECHNICAL BID EVALUATION FOR FITTINGS (SS) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 27-Jul-2026 08:41:13 | wisuda.c@jutal.com | 27-Jul-2026 09:20:38 | Jumpol Sudjitjul | 05-Aug-2026 |  | Aphisit Pinkaew | 07-Aug-2026 | 12-Aug-2026 14:43:45 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 19:27:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 11:10:44 | 13-Aug-2026 05:52:29 | 0 |  |  | Approver | Locate
AO-001591 | MM-ZTK-1F-GEN-PIP-TBE-0008 | TECHNICAL BID EVALUATION FOR FITTINGS (SS) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 18-Aug-2026 14:45:13 | wisuda.c@jutal.com | 18-Aug-2026 14:50:44 | Jumpol Sudjitjul | 25-Aug-2026 |  | Aphisit Pinkaew | 27-Aug-2026 | 20-Aug-2026 10:25:03 | Pornlert Wanaphattharaphan | 28-Aug-2026 | 20-Aug-2026 13:20:07 | APPR | Approved | Jumpol Sudjitjul | 31-Aug-2026 | 20-Aug-2026 13:29:13 | 20-Aug-2026 06:59:58 | 0 |  |  | Approver | Locate
AO-001127 | MM-ZTK-1F-GEN-PIP-TBE-0009 | TECHNICAL BID EVALUATION FOR GLOBE VALVES (WITHOUT EQUAL PERCENTAGE GLOBE VALVE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 16-Jul-2026 12:38:48 | wisuda.c@jutal.com | 16-Jul-2026 13:23:44 | Jumpol Sudjitjul | 23-Jul-2026 |  | Aphisit Pinkaew | 27-Jul-2026 | 31-Jul-2026 16:23:44 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 02-Aug-2026 10:13:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Jul-2026 | 02-Aug-2026 21:14:43 | 02-Aug-2026 14:45:02 | 0 |  |  | Approver | Locate
AO-001445 | MM-ZTK-1F-GEN-PIP-TBE-0009 | TECHNICAL BID EVALUATION FOR GLOBE VALVES (WITHOUT EQUAL PERCENTAGE GLOBE VALVE) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 07-Aug-2026 14:08:39 | wisuda.c@jutal.com | 07-Aug-2026 14:28:32 | Jumpol Sudjitjul | 17-Aug-2026 |  | Aphisit Pinkaew | 19-Aug-2026 | 11-Aug-2026 09:39:38 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 11-Aug-2026 18:34:16 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 13-Aug-2026 11:11:03 | 13-Aug-2026 05:20:42 | 0 |  |  | Approver | Locate
AO-001126 | MM-ZTK-1F-GEN-PIP-TBE-0012 | TECHNICAL BID EVALUATION FOR BALL VALVES (FLANGE TYPE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 16-Jul-2026 12:39:18 | wisuda.c@jutal.com | 16-Jul-2026 13:24:18 | Jumpol Sudjitjul | 23-Jul-2026 |  | Aphisit Pinkaew | 27-Jul-2026 | 01-Aug-2026 23:16:33 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 02-Aug-2026 11:47:21 | NA | Not Approved | Jumpol Sudjitjul | 31-Jul-2026 | 02-Aug-2026 21:13:41 | 06-Aug-2026 09:21:31 | 0 |  |  | Approver | Locate
AO-001564 | MM-ZTK-1F-GEN-PIP-TBE-0012 | TECHNICAL BID EVALUATION FOR BALL VALVES (FLANGE TYPE) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 17-Aug-2026 14:20:41 | wisuda.c@jutal.com | 17-Aug-2026 15:58:34 | Jumpol Sudjitjul | 24-Aug-2026 |  | Aphisit Pinkaew | 26-Aug-2026 | 18-Aug-2026 10:03:21 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 18-Aug-2026 22:44:47 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 19-Aug-2026 09:48:44 | 20-Aug-2026 12:18:07 | 0 |  |  | Approver | Locate
AO-001303 | MM-ZTK-1F-GEN-PIP-TBE-0013 | TECHNICAL BID EVALUATION FOR PIPES (CS) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 27-Jul-2026 08:41:39 | wisuda.c@jutal.com | 27-Jul-2026 09:20:36 | Jumpol Sudjitjul | 05-Aug-2026 |  | Aphisit Pinkaew | 07-Aug-2026 | 10-Aug-2026 12:49:41 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 11-Aug-2026 06:26:59 | NA | Not Approved | Jumpol Sudjitjul | 11-Aug-2026 | 11-Aug-2026 08:16:38 | 11-Aug-2026 01:25:30 | 0 |  |  | Approver | Locate
AO-001583 | MM-ZTK-1F-GEN-PIP-TBE-0013 | TECHNICAL BID EVALUATION FOR PIPES (CS) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 18-Aug-2026 08:54:29 | wisuda.c@jutal.com | 18-Aug-2026 09:21:23 | Jumpol Sudjitjul | 25-Aug-2026 |  | Aphisit Pinkaew | 27-Aug-2026 | 18-Aug-2026 10:12:08 | Pornlert Wanaphattharaphan | 28-Aug-2026 | 19-Aug-2026 07:52:05 | NA | Not Approved | Jumpol Sudjitjul | 31-Aug-2026 | 19-Aug-2026 09:49:49 | 19-Aug-2026 03:04:13 | 0 |  |  | Approver | Locate
AO-001672 | MM-ZTK-1F-GEN-PIP-TBE-0013 | TECHNICAL BID EVALUATION FOR PIPES (CS) |  | C3 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 24-Aug-2026 09:45:01 | wisuda.c@jutal.com | 25-Aug-2026 10:32:24 | Jumpol Sudjitjul | 01-Sep-2026 | 25-Aug-2026 14:20:03 | Aphisit Pinkaew | 03-Sep-2026 | 27-Aug-2026 13:06:18 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 29-Aug-2026 00:46:08 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 29-Aug-2026 13:56:43 | 29-Aug-2026 07:07:06 | 0 |  |  | Approver | Locate
AO-001880 | MM-ZTK-1F-GEN-PIP-TBE-0016 | TECHNICAL BID EVALUATION FOR STUD BOLTS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 04-Sep-2026 16:14:25 | wisuda.c@jutal.com | 05-Sep-2026 19:39:43 | Jumpol Sudjitjul | 14-Sep-2026 | 08-Sep-2026 15:33:55 | Aphisit Pinkaew | 16-Sep-2026 | 09-Sep-2026 13:32:29 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 11-Sep-2026 00:28:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 11-Sep-2026 08:13:56 | 11-Sep-2026 01:33:45 | 0 |  |  | Approver | Locate
AO-002344 | MM-ZTK-1F-GEN-PIP-TBE-0016 | TECHNICAL BID EVALUATION FOR STUD BOLTS |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 02-Oct-2026 17:57:18 | wisuda.c@jutal.com | 02-Oct-2026 18:09:30 | Jumpol Sudjitjul | 12-Oct-2026 | 08-Oct-2026 09:27:31 | Aphisit Pinkaew | 15-Oct-2026 | 11-Oct-2026 13:45:55 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 12-Oct-2026 01:52:29 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 12-Oct-2026 11:37:01 | 12-Oct-2026 05:44:33 | 0 |  |  | Approver | Locate
AO-001752 | MM-ZTK-1F-GEN-PIP-TBE-0017 | TECHNICAL BID EVALUATION FOR STRAINERS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 28-Aug-2026 10:30:35 | wisuda.c@jutal.com | 28-Aug-2026 14:12:32 | Jumpol Sudjitjul | 04-Sep-2026 | 07-Sep-2026 14:52:29 | Aphisit Pinkaew | 08-Sep-2026 | 07-Sep-2026 16:29:21 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 09-Sep-2026 23:38:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 10-Sep-2026 09:10:25 | 10-Sep-2026 02:45:23 | 0 |  |  | Approver | Locate
AO-002142 | MM-ZTK-1F-GEN-PIP-TBE-0017 | TECHNICAL BID EVALUATION FOR STRAINERS |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 18-Sep-2026 14:59:54 | wisuda.c@jutal.com | 18-Sep-2026 17:23:29 | Jumpol Sudjitjul | 28-Sep-2026 | 30-Sep-2026 17:18:00 | Aphisit Pinkaew | 30-Sep-2026 | 01-Oct-2026 20:30:53 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 01-Oct-2026 22:32:48 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 02-Oct-2026 13:06:12 | 02-Oct-2026 06:35:47 | 0 |  |  | Approver | Locate
AO-002081 | MM-ZTK-1F-GEN-PIP-TBE-0019 | TECHNICAL BID EVALUATION FOR HOSE AND CONNECTOR |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 15-Sep-2026 16:12:08 | wisuda.c@jutal.com | 15-Sep-2026 17:12:31 | Jumpol Sudjitjul | 23-Sep-2026 | 30-Sep-2026 15:36:03 | Aphisit Pinkaew | 25-Sep-2026 | 01-Oct-2026 20:45:47 | Pornlert Wanaphattharaphan | 28-Sep-2026 | 01-Oct-2026 22:27:12 | APPR | Approved | Jumpol Sudjitjul | 29-Sep-2026 | 02-Oct-2026 13:07:10 | 02-Oct-2026 06:29:24 | 0 |  |  | Approver | Locate
AO-002328 | MM-ZTK-1F-GEN-PIP-TBE-0020 | TECHNICAL BID EVALUATION FOR CHEMICAL INJECTION QUILLS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 01-Oct-2026 18:02:47 | wisuda.c@jutal.com | 02-Oct-2026 14:18:48 | Jumpol Sudjitjul | 09-Oct-2026 | 07-Oct-2026 09:08:17 | Aphisit Pinkaew | 14-Oct-2026 | 11-Oct-2026 15:08:35 | Pornlert Wanaphattharaphan | 15-Oct-2026 | 12-Oct-2026 01:46:07 | APPR | Approved | Jumpol Sudjitjul | 16-Oct-2026 | 12-Oct-2026 08:42:44 | 12-Oct-2026 02:01:48 | 0 |  |  | Approver | Locate
AO-002082 | MM-ZTK-1F-GEN-PIP-TBE-0021 | TECHNICAL BID EVALUATION FOR LIIQUID TRAP |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 15-Sep-2026 16:12:45 | wisuda.c@jutal.com | 15-Sep-2026 17:12:51 | Jumpol Sudjitjul | 23-Sep-2026 | 30-Sep-2026 15:40:21 | Aphisit Pinkaew | 25-Sep-2026 | 01-Oct-2026 20:53:50 | Pornlert Wanaphattharaphan | 28-Sep-2026 | 01-Oct-2026 22:29:31 | APPR | Approved | Jumpol Sudjitjul | 29-Sep-2026 | 02-Oct-2026 13:09:36 | 02-Oct-2026 06:30:36 | 0 |  |  | Approver | Locate
AO-001477 | MM-ZTK-1F-GEN-PIP-TBE-0022 | TECHNICAL BID EVALUATION FOR GLOBE VALVES (EQUAL PERCENTAGE GLOBE VALVE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 10-Aug-2026 11:59:28 | wisuda.c@jutal.com | 10-Aug-2026 14:49:10 | Jumpol Sudjitjul | 18-Aug-2026 |  | Aphisit Pinkaew | 20-Aug-2026 | 11-Aug-2026 09:38:57 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 11-Aug-2026 17:49:44 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 11-Aug-2026 17:53:50 | 11-Aug-2026 11:31:14 | 0 |  |  | Approver | Locate
AO-002007 | MM-ZTK-1F-GEN-PIP-TBE-0023 | TECHNICAL BID EVALUATION FOR BARREL REDUCERS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 11-Sep-2026 12:46:47 | wisuda.c@jutal.com | 11-Sep-2026 19:33:18 | Jumpol Sudjitjul | 21-Sep-2026 | 19-Sep-2026 18:44:57 | Aphisit Pinkaew | 23-Sep-2026 | 24-Sep-2026 08:56:17 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 25-Sep-2026 00:15:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Sep-2026 | 25-Sep-2026 08:25:33 | 25-Sep-2026 01:55:39 | 0 |  |  | Approver | Locate
AO-002351 | MM-ZTK-1F-GEN-PIP-TBE-0023 | TECHNICAL BID EVALUATION FOR BARREL REDUCERS |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 05-Oct-2026 09:15:09 | wisuda.c@jutal.com | 05-Oct-2026 10:41:41 | Jumpol Sudjitjul | 12-Oct-2026 |  | Aphisit Pinkaew | 15-Oct-2026 | 08-Oct-2026 20:03:44 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 09-Oct-2026 13:38:55 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 09-Oct-2026 13:41:38 | 09-Oct-2026 07:10:11 | 0 |  |  | Approver | Locate
AO-001274 | MM-ZTK-1F-GEN-PIP-TBE-0024 | TECHNICAL BID EVALUATION FOR QUICK OPENING CLOSURES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 25-Jul-2026 09:13:40 | wisuda.c@jutal.com | 27-Jul-2026 09:20:38 | Jumpol Sudjitjul | 05-Aug-2026 |  | Aphisit Pinkaew | 07-Aug-2026 | 11-Aug-2026 09:30:45 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 11-Aug-2026 17:36:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 11-Aug-2026 17:48:11 | 11-Aug-2026 11:30:00 | 0 |  |  | Approver | Locate
AO-001565 | MM-ZTK-1F-GEN-PIP-TBE-0024 | TECHNICAL BID EVALUATION FOR QUICK OPENING CLOSURES |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 17-Aug-2026 14:21:32 | wisuda.c@jutal.com | 17-Aug-2026 15:58:59 | Jumpol Sudjitjul | 24-Aug-2026 |  | Aphisit Pinkaew | 26-Aug-2026 | 18-Aug-2026 09:44:27 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 18-Aug-2026 22:40:17 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 19-Aug-2026 09:55:00 | 19-Aug-2026 03:14:11 | 0 |  |  | Approver | Locate
AO-001160 | MM-ZTK-1F-GEN-PIP-TBE-0025 | TECHNICAL BID EVALUATION FOR FLANGES (SS AND DSS) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 17-Jul-2026 20:46:44 | wisuda.c@jutal.com | 17-Jul-2026 22:16:48 | Jumpol Sudjitjul | 27-Jul-2026 |  | Aphisit Pinkaew | 31-Jul-2026 | 02-Aug-2026 15:08:24 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 02-Aug-2026 17:06:03 | NA | Not Approved | Jumpol Sudjitjul | 04-Aug-2026 | 02-Aug-2026 21:13:02 | 02-Aug-2026 14:54:36 | 0 |  |  | Approver | Locate
AO-001426 | MM-ZTK-1F-GEN-PIP-TBE-0025 | TECHNICAL BID EVALUATION FOR FLANGES (SS AND DSS) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 05-Aug-2026 17:29:26 | wisuda.c@jutal.com | 05-Aug-2026 17:37:19 | Jumpol Sudjitjul | 14-Aug-2026 |  | Aphisit Pinkaew | 18-Aug-2026 | 12-Aug-2026 15:09:08 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 12-Aug-2026 21:22:20 | APPR | Approved | Jumpol Sudjitjul | 20-Aug-2026 | 13-Aug-2026 11:10:03 | 13-Aug-2026 05:06:05 | 0 |  |  | Approver | Locate
AO-001304 | MM-ZTK-1F-GEN-PIP-TBE-0026 | TECHNICAL BID EVALUATION FOR FITTINGS (CS) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 27-Jul-2026 08:42:09 | wisuda.c@jutal.com | 27-Jul-2026 09:20:35 | Jumpol Sudjitjul | 05-Aug-2026 |  | Aphisit Pinkaew | 07-Aug-2026 | 12-Aug-2026 12:42:39 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 17:36:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 11:08:41 | 13-Aug-2026 05:48:42 | 0 |  |  | Approver | Locate
AO-001611 | MM-ZTK-1F-GEN-PIP-TBE-0026 | TECHNICAL BID EVALUATION FOR FITTINGS (CS) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 19-Aug-2026 13:52:27 | wisuda.c@jutal.com | 19-Aug-2026 15:17:27 | Jumpol Sudjitjul | 26-Aug-2026 |  | Aphisit Pinkaew | 28-Aug-2026 | 20-Aug-2026 10:13:30 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 20-Aug-2026 13:57:24 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 20-Aug-2026 14:16:06 | 20-Aug-2026 07:44:05 | 0 |  |  | Approver | Locate
AO-001305 | MM-ZTK-1F-GEN-PIP-TBE-0027 | TECHNICAL BID EVALUATION FOR FLANGES (CS) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 27-Jul-2026 08:42:35 | wisuda.c@jutal.com | 27-Jul-2026 09:20:35 | Jumpol Sudjitjul | 05-Aug-2026 |  | Aphisit Pinkaew | 07-Aug-2026 | 12-Aug-2026 11:02:38 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 19:21:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 11:10:26 | 13-Aug-2026 05:51:13 | 0 |  |  | Approver | Locate
AO-001614 | MM-ZTK-1F-GEN-PIP-TBE-0027 | TECHNICAL BID EVALUATION FOR FLANGES (CS) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 19-Aug-2026 15:57:18 | wisuda.c@jutal.com | 19-Aug-2026 16:03:56 | Jumpol Sudjitjul | 26-Aug-2026 |  | Aphisit Pinkaew | 28-Aug-2026 | 20-Aug-2026 10:17:52 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 22-Aug-2026 14:14:43 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 24-Aug-2026 19:58:37 | 24-Aug-2026 13:31:38 | 0 |  |  | Approver | Locate
AO-002092 | MM-ZTK-1F-GEN-PIP-TBE-0029 | TECHNICAL BID EVALUATION FOR UPVC PIPING MATERIALS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PIP | Piping | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 16-Sep-2026 09:16:18 | wisuda.c@jutal.com | 17-Sep-2026 10:16:04 | Jumpol Sudjitjul | 24-Sep-2026 | 30-Sep-2026 17:11:48 | Aphisit Pinkaew | 28-Sep-2026 | 01-Oct-2026 21:07:47 | Pornlert Wanaphattharaphan | 29-Sep-2026 | 01-Oct-2026 22:23:25 | APPR | Approved | Jumpol Sudjitjul | 30-Sep-2026 | 02-Oct-2026 13:09:06 | 02-Oct-2026 06:23:03 | 0 |  |  | Approver | Locate
AO-001061 | MM-ZTK-1F-GEN-PJM-COP-0001 | PIPE-SOIL INTERACTION ANALYSIS DUE TO CHANGE IN PIPE PROPERTIES |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | COP | Change Order Proposal (Contractor To Company) | 0 | Submitted | IFI | Issued for Information |  | 10-Jul-2026 14:50:14 | 26002z1fdcc@thoresen-jutal.com | 10-Jul-2026 18:03:57 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 29-Jul-2026 06:46:48 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 30-Jul-2026 09:40:45 | 30-Jul-2026 04:03:11 | 0 |  |  | For Info | Locate
AO-001715 | MM-ZTK-1F-GEN-PJM-COP-0002 | SERVICES AND FACILITIES TO COMPANY AT CONTRACTOR’S ENGINEERING OFFICE |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | COP | Change Order Proposal (Contractor To Company) | 0 | Latest | IFI | Issued for Information |  | 26-Aug-2026 08:44:56 | 26002z1fdcc@thoresen-jutal.com | 26-Aug-2026 12:18:29 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 27-Aug-2026 12:40:47 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000892 | MM-ZTK-1F-GEN-PJM-MDR-0001 | MASTER DOCUMENT DELIVERABLE REGISTER FOR GENERIC DOCUMENTS |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MDR | Master Deliverable Register | 0 | Submitted | IFR | Issued for Review |  | 25-Jun-2026 15:44:18 | 26002z1fdcc@thoresen-jutal.com | 25-Jun-2026 15:54:14 | Jumpol Sudjitjul | 02-Jul-2026 | 06-Jul-2026 22:37:50 | Prin Jitatisil | 06-Jul-2026 | 07-Jul-2026 08:57:50 |  |  |  | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Jul-2026 | 07-Jul-2026 09:18:10 | 07-Jul-2026 03:10:13 | 0 |  |  | Focal Point | Locate
AO-001037 | MM-ZTK-1F-GEN-PJM-MDR-0001 | MASTER DOCUMENT DELIVERABLE REGISTER FOR GENERIC DOCUMENTS |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MDR | Master Deliverable Register | 0 | Submitted | AFC | Approved for Construction |  | 08-Jul-2026 17:26:15 | 26002z1fdcc@thoresen-jutal.com | 09-Jul-2026 10:33:34 | Jumpol Sudjitjul | 16-Jul-2026 | 11-Jul-2026 06:44:06 | Prin Jitatisil | 20-Jul-2026 | 13-Jul-2026 11:23:56 |  |  |  | APPR | Approved | Jumpol Sudjitjul | 22-Jul-2026 | 13-Jul-2026 13:23:00 | 13-Jul-2026 07:03:40 | 0 |  |  | Focal Point | Locate
AO-000146 | MM-ZTK-1F-GEN-PJM-MDR-0003 | MASTER DOCUMENT DELIVERABLES REGISTER |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MDR | Master Deliverable Register | 0 | Submitted | IFR | Issued for Review |  | 17-Apr-2026 16:49:12 | zm169dc@jutal.com | 17-Apr-2026 16:53:57 | Jumpol Sudjitjul | 24-Apr-2026 | 28-Apr-2026 10:24:39 | Prin Jitatisil | 28-Apr-2026 | 28-Apr-2026 11:12:02 |  |  |  | NA | Not Approved | Jumpol Sudjitjul | 30-Apr-2026 | 28-Apr-2026 13:43:04 | 28-Apr-2026 06:56:18 | 0 |  |  | Focal Point | Locate
AO-000717 | MM-ZTK-1F-GEN-PJM-MDR-0003 | MASTER DOCUMENT DELIVERABLES REGISTER |  | X | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MDR | Master Deliverable Register | 0 | Latest | VOID | Withdrawn or Superseded |  | 09-Jun-2026 12:34:58 | zm169dc@jutal.com | 09-Jun-2026 13:38:34 | Jumpol Sudjitjul |  | 10-Jun-2026 16:26:11 | Prin Jitatisil |  | 11-Jun-2026 14:42:51 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000336 | MM-ZTK-1F-GEN-PJM-MDR-5001 | MASTER DOCUMENT DELIVERABLE REGISTER(TOPSIDES AND JACKETS) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MDR | Master Deliverable Register | 0 | Submitted | IFR | Issued for Review |  | 07-May-2026 10:37:08 | zm169dc@jutal.com | 07-May-2026 10:47:25 | Jumpol Sudjitjul | 14-May-2026 | 25-May-2026 13:20:22 | Prin Jitatisil | 18-May-2026 | 27-May-2026 09:05:10 |  |  |  | NA | Not Approved | Jumpol Sudjitjul | 20-May-2026 | 27-May-2026 10:39:59 | 27-May-2026 04:10:19 | 0 |  |  | Focal Point | Locate
AO-000686 | MM-ZTK-1F-GEN-PJM-MDR-5001 | MASTER DOCUMENT DELIVERABLE REGISTER(TOPSIDES AND JACKETS) |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MDR | Master Deliverable Register | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 15:04:04 | zm169dc@jutal.com | 05-Jun-2026 17:57:18 | Jumpol Sudjitjul | 15-Jun-2026 | 17-Jun-2026 22:13:16 | Prin Jitatisil | 17-Jun-2026 | 20-Jun-2026 22:51:20 |  |  |  | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 19-Jun-2026 | 22-Jun-2026 12:53:20 | 22-Jun-2026 06:43:18 | 0 |  |  | Focal Point | Locate
AO-001117 | MM-ZTK-1F-GEN-PJM-MDR-5001 | MASTER DOCUMENT DELIVERABLE REGISTER(TOPSIDES AND JACKETS) |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MDR | Master Deliverable Register | 0 | Submitted | AFC | Approved for Construction |  | 15-Jul-2026 09:32:09 | zm169dc@jutal.com | 15-Jul-2026 11:34:53 | Jumpol Sudjitjul | 22-Jul-2026 | 16-Jul-2026 15:21:54 | Prin Jitatisil | 24-Jul-2026 | 17-Jul-2026 11:36:34 |  |  |  | APPR | Approved | Jumpol Sudjitjul | 30-Jul-2026 | 17-Jul-2026 11:47:52 | 17-Jul-2026 05:12:54 | 0 |  |  | Focal Point | Locate
AO-000036 | MM-ZTK-1F-GEN-PJM-MDR-8001 | MASTER DOCUMENT DELIVERABLE REGISTER-WP1 T&I |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MDR | Master Deliverable Register | 0 | Submitted | IFR | Issued for Review |  | 20-Mar-2026 16:57:53 | kjb@coes.cn | 20-Mar-2026 17:02:39 | Jumpol Sudjitjul | 30-Mar-2026 | 26-Mar-2026 11:29:19 | Sukit Nualchanchai | 01-Apr-2026 | 02-Apr-2026 17:22:33 | Prin Jitatisil | 02-Apr-2026 | 06-Apr-2026 17:44:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Apr-2026 | 06-Apr-2026 21:39:50 | 06-Apr-2026 22:00:08 | 0 |  |  | Approver | Locate
AO-000381 | MM-ZTK-1F-GEN-PJM-MDR-8001 | MASTER DOCUMENT DELIVERABLE REGISTER-WP1 T&I |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MDR | Master Deliverable Register | 0 | Submitted | IFA | Issued for Approval |  | 12-May-2026 15:33:29 | kjb@coes.cn | 13-May-2026 10:07:37 | Jumpol Sudjitjul | 20-May-2026 | 14-May-2026 07:17:56 | Sukit Nualchanchai | 22-May-2026 | 19-May-2026 13:40:17 | Prin Jitatisil | 25-May-2026 | 27-May-2026 08:58:42 | APPR | Approved | Jumpol Sudjitjul | 26-May-2026 | 27-May-2026 10:41:13 | 27-May-2026 04:06:40 | 0 |  |  | Approver | Locate
AO-000867 | MM-ZTK-1F-GEN-PJM-MDR-8001 | MASTER DOCUMENT DELIVERABLE REGISTER-WP1 T&I |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MDR | Master Deliverable Register | 0 | Submitted | AFC | Approved for Construction |  | 22-Jun-2026 17:22:16 | kjb@coes.cn | 22-Jun-2026 17:47:39 | Jumpol Sudjitjul | 30-Jun-2026 |  | Sukit Nualchanchai | 02-Jul-2026 | 26-Jun-2026 15:55:30 | Prin Jitatisil | 03-Jul-2026 | 29-Jun-2026 10:50:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Jul-2026 | 30-Jun-2026 09:40:43 | 30-Jun-2026 03:19:40 | 0 |  |  | Approver | Locate
AO-001027 | MM-ZTK-1F-GEN-PJM-MDR-8001 | MASTER DOCUMENT DELIVERABLE REGISTER-WP1 T&I |  | C2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MDR | Master Deliverable Register | 0 | Submitted | AFC | Approved for Construction |  | 07-Jul-2026 10:47:40 | kjb@coes.cn | 07-Jul-2026 11:49:43 | Jumpol Sudjitjul | 14-Jul-2026 |  | Sukit Nualchanchai | 16-Jul-2026 | 10-Jul-2026 00:03:48 | Prin Jitatisil | 17-Jul-2026 | 11-Jul-2026 12:13:07 | APPR | Approved | Jumpol Sudjitjul | 20-Jul-2026 | 12-Jul-2026 11:31:42 | 12-Jul-2026 05:21:42 | 0 |  |  | Approver | Locate
AO-002150 | MM-ZTK-1F-GEN-PJM-MDR-8001 | MASTER DOCUMENT DELIVERABLE REGISTER-WP1 T&I |  | C3 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MDR | Master Deliverable Register | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:11:11 | kjb@coes.cn | 18-Sep-2026 17:03:49 | Jumpol Sudjitjul | 28-Sep-2026 | 19-Sep-2026 08:11:59 | Sukit Nualchanchai | 30-Sep-2026 | 28-Sep-2026 14:16:04 | Prin Jitatisil | 01-Oct-2026 | 29-Sep-2026 09:12:00 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 29-Sep-2026 14:15:16 | 29-Sep-2026 08:27:00 | 0 |  |  | Approver | Locate
AO-000030 | MM-ZTK-1F-GEN-PJM-MDR-9001 | MASTER DOCUMENT DELIVERABLES REGISTER - PIPELINE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MDR | Master Deliverable Register | 0 | Submitted | IFR | Issued for Review |  | 19-Mar-2026 14:13:30 | 26002z1fdcc@thoresen-jutal.com | 19-Mar-2026 14:33:56 | Jumpol Sudjitjul | 26-Mar-2026 |  | Akkarapat Suntornsuttiwat | 30-Mar-2026 | 24-Mar-2026 13:28:57 | Prin Jitatisil | 31-Mar-2026 | 31-Mar-2026 10:03:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Apr-2026 | 31-Mar-2026 10:06:17 | 31-Mar-2026 10:23:40 | 0 |  |  | Approver | Locate
AO-000309 | MM-ZTK-1F-GEN-PJM-MDR-9001 | MASTER DOCUMENT DELIVERABLES REGISTER - PIPELINE |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MDR | Master Deliverable Register | 0 | Submitted | IFA | Issued for Approval | 20-Apr-2026 | 05-May-2026 19:09:48 | 26002z1fdcc@thoresen-jutal.com | 06-May-2026 10:27:58 | Jumpol Sudjitjul | 13-May-2026 |  | Akkarapat Suntornsuttiwat | 15-May-2026 | 14-May-2026 10:36:03 | Prin Jitatisil | 18-May-2026 | 16-May-2026 23:49:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 17-May-2026 09:58:10 | 17-May-2026 10:07:16 | 0 |  |  | Approver | Locate
AO-000676 | MM-ZTK-1F-GEN-PJM-MDR-9001 | MASTER DOCUMENT DELIVERABLES REGISTER - PIPELINE |  | B2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MDR | Master Deliverable Register | 0 | Submitted | IFA | Issued for Approval |  | 05-Jun-2026 08:19:22 | 26002z1fdcc@thoresen-jutal.com | 05-Jun-2026 08:30:02 | Jumpol Sudjitjul | 12-Jun-2026 |  | Akkarapat Suntornsuttiwat | 16-Jun-2026 | 22-Jun-2026 11:03:34 | Prin Jitatisil | 17-Jun-2026 | 23-Jun-2026 16:26:56 | APPR | Approved | Jumpol Sudjitjul | 18-Jun-2026 | 23-Jun-2026 16:35:37 | 23-Jun-2026 10:06:06 | 0 |  |  | Approver | Locate
AO-000892 | MM-ZTK-1F-GEN-PJM-MDR-9001 | MASTER DOCUMENT DELIVERABLES REGISTER - PIPELINE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MDR | Master Deliverable Register | 0 | Submitted | AFC | Approved for Construction |  | 25-Jun-2026 14:24:54 | 26002z1fdcc@thoresen-jutal.com | 25-Jun-2026 15:16:20 | Jumpol Sudjitjul | 02-Jul-2026 |  | Akkarapat Suntornsuttiwat | 06-Jul-2026 | 06-Jul-2026 08:48:00 | Prin Jitatisil | 07-Jul-2026 | 06-Jul-2026 11:40:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jul-2026 | 06-Jul-2026 11:44:36 | 06-Jul-2026 05:33:22 | 0 |  |  | Approver | Locate
AO-001106 | MM-ZTK-1F-GEN-PJM-MDR-9001 | MASTER DOCUMENT DELIVERABLES REGISTER - PIPELINE |  | C2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MDR | Master Deliverable Register | 0 | Submitted | AFC | Approved for Construction |  | 14-Jul-2026 12:49:11 | 26002z1fdcc@thoresen-jutal.com | 14-Jul-2026 13:46:53 | Jumpol Sudjitjul | 21-Jul-2026 | 15-Jul-2026 22:49:28 | Akkarapat Suntornsuttiwat | 23-Jul-2026 | 21-Jul-2026 08:35:31 | Prin Jitatisil | 24-Jul-2026 | 21-Jul-2026 10:05:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Jul-2026 | 21-Jul-2026 10:13:17 | 21-Jul-2026 03:34:52 | 0 |  |  | Approver | Locate
AO-001359 | MM-ZTK-1F-GEN-PJM-MDR-9001 | MASTER DOCUMENT DELIVERABLES REGISTER - PIPELINE |  | C3 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MDR | Master Deliverable Register | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 16:24:36 | 26002z1fdcc@thoresen-jutal.com | 31-Jul-2026 17:11:38 | Jumpol Sudjitjul | 10-Aug-2026 |  | Akkarapat Suntornsuttiwat | 13-Aug-2026 | 05-Aug-2026 14:48:16 | Prin Jitatisil | 14-Aug-2026 | 05-Aug-2026 14:56:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 05-Aug-2026 15:08:47 | 05-Aug-2026 09:18:46 | 0 |  |  | Approver | Locate
AO-001502 | MM-ZTK-1F-GEN-PJM-MDR-9001 | MASTER DOCUMENT DELIVERABLES REGISTER - PIPELINE |  | C4 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MDR | Master Deliverable Register | 0 | Submitted | AFC | Approved for Construction |  | 10-Aug-2026 18:33:28 | 26002z1fdcc@thoresen-jutal.com | 11-Aug-2026 08:44:10 | Jumpol Sudjitjul | 19-Aug-2026 |  | Akkarapat Suntornsuttiwat | 21-Aug-2026 | 18-Aug-2026 10:24:34 | Prin Jitatisil | 24-Aug-2026 | 18-Aug-2026 14:06:57 | APPR | Approved | Jumpol Sudjitjul | 25-Aug-2026 | 18-Aug-2026 14:26:58 | 18-Aug-2026 07:32:17 | 0 |  |  | Approver | Locate
AO-000038 | MM-ZTK-1F-GEN-PJM-MOM-0001 | PMT WEEKLY MEETING |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 23-Mar-2026 09:35:42 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000050 | MM-ZTK-1F-GEN-PJM-MOM-0002 | PMT INTERIM PROGRESS MEETING |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 30-Mar-2026 18:21:08 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000051 | MM-ZTK-1F-GEN-PJM-MOM-0003 | PMT WEEKLY MEETING NO.03 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 31-Mar-2026 08:55:20 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000139 | MM-ZTK-1F-GEN-PJM-MOM-0004 | PMT WEEKLY MEETING NO.04 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 16-Apr-2026 16:23:01 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000140 | MM-ZTK-1F-GEN-PJM-MOM-0005 | PMT WEEKLY MEETING NO.05 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 16-Apr-2026 16:23:30 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000245 | MM-ZTK-1F-GEN-PJM-MOM-0006 | PMT WEEKLY MEETING NO.0ุ6 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 28-Apr-2026 14:29:33 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000246 | MM-ZTK-1F-GEN-PJM-MOM-0007 | PMT WEEKLY MEETING NO.0ุ7 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 28-Apr-2026 14:30:02 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000377 | MM-ZTK-1F-GEN-PJM-MOM-0008 | PMT WEEKLY MEETING NO.0ุ8 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 12-May-2026 10:10:18 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000384 | MM-ZTK-1F-GEN-PJM-MOM-0009 | PMT WEEKLY MEETING NO.09 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 13-May-2026 15:32:55 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000727 | MM-ZTK-1F-GEN-PJM-MOM-0010 | PMT WEEKLY MEETING NO.10 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 09-Jun-2026 15:29:56 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000727 | MM-ZTK-1F-GEN-PJM-MOM-0011 | PMT WEEKLY MEETING NO.11 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 09-Jun-2026 15:30:42 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000727 | MM-ZTK-1F-GEN-PJM-MOM-0012 | PMT WEEKLY MEETING NO.12 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 09-Jun-2026 17:22:48 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001093 | MM-ZTK-1F-GEN-PJM-MOM-0013 | PMT WEEKLY MEETING NO.13 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 13-Jul-2026 12:05:30 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001094 | MM-ZTK-1F-GEN-PJM-MOM-0014 | PMT WEEKLY MEETING NO.14 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 13-Jul-2026 12:05:56 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001092 | MM-ZTK-1F-GEN-PJM-MOM-0015 | PMT MONTHLY MEETING (DATED 26-JUN-2026) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 13-Jul-2026 12:06:20 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001095 | MM-ZTK-1F-GEN-PJM-MOM-0016 | PMT WEEKLY MEETING NO.16 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 13-Jul-2026 12:06:47 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001634 | MM-ZTK-1F-GEN-PJM-MOM-0018 | PMT WEEKLY MEETING NO.18 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 21-Aug-2026 10:28:04 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001634 | MM-ZTK-1F-GEN-PJM-MOM-0019 | PMT WEEKLY MEETING NO.19 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 21-Aug-2026 10:28:48 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001646 | MM-ZTK-1F-GEN-PJM-MOM-0020 | PMT MONTHLY MEETING (DATED 16-JUL-2026) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 21-Aug-2026 13:58:09 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001634 | MM-ZTK-1F-GEN-PJM-MOM-0021 | PMT WEEKLY MEETING NO.21 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 21-Aug-2026 10:29:45 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001955 | MM-ZTK-1F-GEN-PJM-MOM-0022 | PMT WEEKLY MEETING NO.22 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 09-Sep-2026 16:07:42 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001957 | MM-ZTK-1F-GEN-PJM-MOM-0023 | PMT MONTHLY MEETING (DATED 27-AUG-2026) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 09-Sep-2026 16:08:12 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001958 | MM-ZTK-1F-GEN-PJM-MOM-0024 | PMT WEEKLY MEETING NO.24 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 09-Sep-2026 16:08:41 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002075 | MM-ZTK-1F-GEN-PJM-MOM-0025 | PMT WEEKLY MEETING NO.25 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 15-Sep-2026 09:45:38 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000009 | MM-ZTK-1F-GEN-PJM-MOM-1001 | WORK PACKAGE 1 - JACKET DETAIL ENGINEERING DESIGN KICK OFF MEETING |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 04-Mar-2026 17:37:21 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000012 | MM-ZTK-1F-GEN-PJM-MOM-1002 | WORK PACKAGE 1 - TOPSIDE DETAIL ENGINEERING DESIGN KICK OFF MEETING |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 12-Mar-2026 15:34:30 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000013 | MM-ZTK-1F-GEN-PJM-MOM-1003 | PMT INTERIM PROGRESS MEETING |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 12-Mar-2026 15:34:54 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002080 | MM-ZTK-1F-GEN-PJM-MOM-1004 | PROJECT SPONSOR MEETING NO.1 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 15-Sep-2026 16:13:17 | 26002z1fdcc@thoresen-jutal.com | 15-Sep-2026 17:13:52 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 18-Sep-2026 10:08:27 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000031 | MM-ZTK-1F-GEN-PJM-MOM-9001 | WORK PACKAGE 2 – PIPELINE DETAILED DESIGN ENGINEERING MEETING |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 19-Mar-2026 14:57:23 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000085 | MM-ZTK-1F-GEN-PJM-MOM-9002 | WEEKLY PIPELINE DETAILED DESIGN ENGINEERING MEETING NO. 2 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 26-Mar-2026 15:14:12 | neeranuchn@pttep.com | [16 empty] | 0 |  |  |  | Locate
AO-000087 | MM-ZTK-1F-GEN-PJM-MOM-9003 | WEEKLY PIPELINE DETAILED DESIGN ENGINEERING MEETING NO. 3 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 08-Apr-2026 13:40:01 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000109 | MM-ZTK-1F-GEN-PJM-MOM-9004 | WEEKLY PIPELINE DETAILED DESIGN ENGINEERING MEETING NO. 4 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 10-Apr-2026 14:15:54 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000242 | MM-ZTK-1F-GEN-PJM-MOM-9005 | WEEKLY PIPELINE DETAILED DESIGN ENGINEERING MEETING NO. 5 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 28-Apr-2026 12:20:56 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000677 | MM-ZTK-1F-GEN-PJM-MOM-9010 | WEEKLY PIPELINE DETAILED DESIGN ENGINEERING MEETING NO.10 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 05-Jun-2026 08:19:48 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000903 | MM-ZTK-1F-GEN-PJM-MOM-9013 | WEEKLY PIPELINE DETAILED DESIGN ENGINEERING MEETING NO. 13 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 26-Jun-2026 16:39:45 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001037 | MM-ZTK-1F-GEN-PJM-MOM-9014 | WEEKLY PIPELINE DETAILED DESIGN ENGINEERING MEETING NO. 14 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 08-Jul-2026 17:26:43 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001037 | MM-ZTK-1F-GEN-PJM-MOM-9015 | WEEKLY PIPELINE DETAILED DESIGN ENGINEERING MEETING NO. 15 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 08-Jul-2026 17:27:09 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001513 | MM-ZTK-1F-GEN-PJM-MOM-9017 | WEEKLY PIPELINE DETAILED DESIGN ENGINEERING MEETING NO. 17 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 13-Aug-2026 11:45:39 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001634 | MM-ZTK-1F-GEN-PJM-MOM-9019 | WEEKLY PIPELINE DETAILED DESIGN ENGINEERING MEETING NO. 19 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 21-Aug-2026 10:30:15 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001634 | MM-ZTK-1F-GEN-PJM-MOM-9020 | WEEKLY PIPELINE DETAILED DESIGN ENGINEERING MEETING NO. 20 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 21-Aug-2026 10:30:47 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001913 | MM-ZTK-1F-GEN-PJM-MOM-9021 | WEEKLY PIPELINE DETAILED DESIGN ENGINEERING MEETING NO. 21 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 07-Sep-2026 09:37:18 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001914 | MM-ZTK-1F-GEN-PJM-MOM-9022 | WEEKLY PIPELINE DETAILED DESIGN ENGINEERING MEETING NO. 22 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 07-Sep-2026 09:37:44 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002076 | MM-ZTK-1F-GEN-PJM-MOM-9023 | WEEKLY PIPELINE DETAILED DESIGN ENGINEERING MEETING NO. 23 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 15-Sep-2026 09:46:21 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002199 | MM-ZTK-1F-GEN-PJM-MOM-9024 | WEEKLY PIPELINE DETAILED DESIGN ENGINEERING MEETING NO. 24 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 21-Sep-2026 11:55:22 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002393 | MM-ZTK-1F-GEN-PJM-MOM-9025 | WEEKLY PIPELINE DETAILED DESIGN ENGINEERING MEETING NO. 25 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Oct-2026 09:58:50 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002394 | MM-ZTK-1F-GEN-PJM-MOM-9026 | WEEKLY PIPELINE DETAILED DESIGN ENGINEERING MEETING NO. 26 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Oct-2026 09:59:33 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002509 | MM-ZTK-1F-GEN-PJM-MOM-9027 | WEEKLY PIPELINE DETAILED DESIGN ENGINEERING MEETING NO. 27 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Oct-2026 11:21:53 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002509 | MM-ZTK-1F-GEN-PJM-MOM-9028 | WEEKLY PIPELINE DETAILED DESIGN ENGINEERING MEETING NO. 28 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Oct-2026 11:22:28 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000054 | MM-ZTK-1F-GEN-PJM-MPR-0001 | MONTHLY PROGRESS REPORT NO. 0001 - CUT OFF 20 MARCH 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MPR | Monthly Progress Report | 0 | Submitted | IFI | Issued for Information |  | 31-Mar-2026 16:31:42 | 26002z1fdcc@thoresen-jutal.com | 01-Apr-2026 10:13:31 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 17-Apr-2026 11:28:50 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 17-Apr-2026 11:49:09 | 17-Apr-2026 12:11:30 | 0 |  |  | For Info | Locate
AO-000179 | MM-ZTK-1F-GEN-PJM-MPR-0001 | MONTHLY PROGRESS REPORT NO. 0001 - CUT OFF 20 MARCH 2026 |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MPR | Monthly Progress Report | 0 | Submitted | IFI | Issued for Information |  | 20-Apr-2026 17:53:46 | 26002z1fdcc@thoresen-jutal.com | 20-Apr-2026 18:05:21 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 28-Apr-2026 10:55:40 |  |  |  | REC | Received |  |  |  | 07-May-2026 05:10:44 | 0 |  |  | For Info | Locate
AO-000236 | MM-ZTK-1F-GEN-PJM-MPR-0002 | MONTHLY PROGRESS REPORT NO. 0002 - CUT OFF 17 APRIL 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MPR | Monthly Progress Report | 0 | Submitted | IFI | Issued for Information |  | 27-Apr-2026 16:39:18 | 26002z1fdcc@thoresen-jutal.com | 28-Apr-2026 08:51:13 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 07-May-2026 10:44:47 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 07-May-2026 10:53:08 | 07-May-2026 05:16:26 | 0 |  |  | For Info | Locate
AO-000613 | MM-ZTK-1F-GEN-PJM-MPR-0003 | MONTHLY PROGRESS REPORT NO. 0003 - CUT OFF 22 MAY 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MPR | Monthly Progress Report | 0 | Latest | IFI | Issued for Information |  | 26-May-2026 16:48:39 | 26002z1fdcc@thoresen-jutal.com | 28-May-2026 11:20:43 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 06-Jun-2026 10:59:18 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000943 | MM‐ZTK‐1F‐GEN‐PJM‐MPR‐0004 | MONTHLY PROGRESS REPORT NO. 0004 - CUT OFF 19 JUNE 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MPR | Monthly Progress Report | 0 | Latest | IFI | Issued for Information |  | 30-Jun-2026 08:34:25 | 26002z1fdcc@thoresen-jutal.com | 30-Jun-2026 11:16:16 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 01-Jul-2026 09:54:10 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-001339 | MM-ZTK-1F-GEN-PJM-MPR-0005 | MONTHLY PROGRESS REPORT NO. 0005 CUT OFF 24 JULY 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MPR | Monthly Progress Report | 0 | Latest | IFI | Issued for Information |  | 30-Jul-2026 15:05:28 | 26002z1fdcc@thoresen-jutal.com | 30-Jul-2026 15:19:08 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 30-Jul-2026 18:29:26 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-001751 | MM-ZTK-1F-GEN-PJM-MPR-0006 | MONTHLY PROGRESS REPORT NO. 0006 - CUT OFF 21 AUGUST 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MPR | Monthly Progress Report | 0 | Latest | IFI | Issued for Information |  | 28-Aug-2026 10:31:38 | 26002z1fdcc@thoresen-jutal.com | 28-Aug-2026 14:17:01 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 31-Aug-2026 14:31:21 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-002237 | MM-ZTK-1F-GEN-PJM-MPR-0007 | MONTHLY PROGRESS REPORT NO. 0007 CUT OFF 18 SEPTEMBER 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | MPR | Monthly Progress Report | 0 | Latest | IFI | Issued for Information |  | 23-Sep-2026 18:20:26 | 26002z1fdcc@thoresen-jutal.com | 24-Sep-2026 09:37:46 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 27-Sep-2026 06:12:08 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000014 | MM-ZTK-1F-GEN-PJM-PDR-0002 | PROJECT CHANGE MANAGEMENT PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 12-Mar-2026 19:19:13 | 26002z1fdcc@thoresen-jutal.com | 13-Mar-2026 08:29:34 | Jumpol Sudjitjul | 20-Mar-2026 | 22-Mar-2026 13:03:46 | Prin Jitatisil | 24-Mar-2026 | 22-Mar-2026 22:59:05 |  |  |  | NA | Not Approved | Jumpol Sudjitjul | 26-Mar-2026 | 23-Mar-2026 09:50:38 | 23-Mar-2026 03:27:05 | 0 |  |  | Focal Point | Locate
AO-000387 | MM-ZTK-1F-GEN-PJM-PDR-0002 | PROJECT CHANGE MANAGEMENT PROCEDURE |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | IFR | Issued for Review | 07-Apr-2026 | 13-May-2026 15:33:54 | 26002z1fdcc@thoresen-jutal.com | 13-May-2026 15:41:57 | Jumpol Sudjitjul | 20-May-2026 | 18-May-2026 13:16:33 | Prin Jitatisil | 22-May-2026 | 21-May-2026 09:51:43 |  |  |  | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 26-May-2026 | 21-May-2026 13:08:21 | 21-May-2026 13:22:02 | 0 |  |  | Focal Point | Locate
AO-000675 | MM-ZTK-1F-GEN-PJM-PDR-0002 | PROJECT CHANGE MANAGEMENT PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 05-Jun-2026 08:20:14 | 26002z1fdcc@thoresen-jutal.com | 05-Jun-2026 08:31:57 | Jumpol Sudjitjul | 12-Jun-2026 | 06-Jun-2026 10:32:14 | Prin Jitatisil | 16-Jun-2026 | 06-Jun-2026 11:22:45 |  |  |  | APPR | Approved | Jumpol Sudjitjul | 18-Jun-2026 | 07-Jun-2026 17:25:12 | 07-Jun-2026 11:39:07 | 0 |  |  | Focal Point | Locate
AO-000019 | MM-ZTK-1F-GEN-PJM-PDR-0003 | PROJECT DOCUMENT CONTROL AND NUMBERING PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 17-Mar-2026 16:11:40 | 26002z1fdcc@thoresen-jutal.com | 17-Mar-2026 16:37:48 | Jumpol Sudjitjul | 24-Mar-2026 | 31-Mar-2026 09:53:54 | Prin Jitatisil | 26-Mar-2026 | 02-Apr-2026 16:47:31 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul | 30-Mar-2026 | 02-Apr-2026 19:18:14 | 02-Apr-2026 21:07:03 | 0 |  |  | Focal Point | Locate
AO-000205 | MM-ZTK-1F-GEN-PJM-PDR-0003 | PROJECT DOCUMENT CONTROL AND NUMBERING PROCEDURE |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 22-Apr-2026 08:57:39 | 26002z1fdcc@thoresen-jutal.com | 22-Apr-2026 14:04:21 | Jumpol Sudjitjul | 29-Apr-2026 | 28-Apr-2026 10:28:15 | Prin Jitatisil | 05-May-2026 | 28-Apr-2026 10:51:02 |  |  |  | APPR | Approved | Jumpol Sudjitjul | 07-May-2026 | 28-Apr-2026 16:09:23 | 28-Apr-2026 09:22:38 | 0 |  |  | Focal Point | Locate
AO-000306 | MM-ZTK-1F-GEN-PJM-PDR-0003 | PROJECT DOCUMENT CONTROL AND NUMBERING PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 05-May-2026 15:44:08 | 26002z1fdcc@thoresen-jutal.com | 05-May-2026 16:26:08 | Jumpol Sudjitjul | 12-May-2026 | 10-May-2026 09:46:47 | Prin Jitatisil | 14-May-2026 | 10-May-2026 17:36:30 |  |  |  | APPR | Approved | Jumpol Sudjitjul | 18-May-2026 | 10-May-2026 23:22:18 | 10-May-2026 17:18:28 | 0 |  |  | Focal Point | Locate
AO-000021 | MM-ZTK-1F-GEN-PJM-PDR-0004 | PROGRESS MEASUREMENT AND REPORTING PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 18-Mar-2026 19:56:49 | 26002z1fdcc@thoresen-jutal.com | 19-Mar-2026 09:11:23 | Jumpol Sudjitjul | 26-Mar-2026 |  | Jirayu Pantito | 30-Mar-2026 | 25-Mar-2026 11:24:45 | Prin Jitatisil | 31-Mar-2026 | 31-Mar-2026 09:54:21 | NA | Not Approved | Jumpol Sudjitjul | 01-Apr-2026 | 31-Mar-2026 10:00:42 | 31-Mar-2026 10:27:52 | 0 |  |  | Approver | Locate
AO-000098 | MM-ZTK-1F-GEN-PJM-PDR-0004 | PROGRESS MEASUREMENT AND REPORTING PROCEDURE |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 08-Apr-2026 16:59:47 | 26002z1fdcc@thoresen-jutal.com | 10-Apr-2026 13:53:48 | Jumpol Sudjitjul | 22-Apr-2026 | 15-Apr-2026 17:05:06 | Jirayu Pantito | 24-Apr-2026 | 25-Apr-2026 07:09:03 | Prin Jitatisil | 27-Apr-2026 | 28-Apr-2026 08:24:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 28-Apr-2026 10:14:30 | 28-Apr-2026 04:00:44 | 0 |  |  | Approver | Locate
AO-000335 | MM-ZTK-1F-GEN-PJM-PDR-0004 | PROGRESS MEASUREMENT AND REPORTING PROCEDURE |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 06-May-2026 16:36:30 | 26002z1fdcc@thoresen-jutal.com | 06-May-2026 17:13:48 | Jumpol Sudjitjul | 14-May-2026 |  | Jirayu Pantito | 18-May-2026 | 12-May-2026 10:24:06 | Prin Jitatisil | 19-May-2026 | 13-May-2026 14:43:13 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 20-May-2026 | 13-May-2026 15:22:58 | 13-May-2026 09:03:11 | 0 |  |  | Approver | Locate
AO-000674 | MM-ZTK-1F-GEN-PJM-PDR-0004 | PROGRESS MEASUREMENT AND REPORTING PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction | 27-May-2026 | 05-Jun-2026 08:20:45 | 26002z1fdcc@thoresen-jutal.com | 05-Jun-2026 08:37:58 | Jumpol Sudjitjul | 12-Jun-2026 |  | Jirayu Pantito | 16-Jun-2026 | 12-Jun-2026 09:24:13 | Prin Jitatisil | 17-Jun-2026 | 15-Jun-2026 14:02:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Jun-2026 | 15-Jun-2026 14:09:09 | 15-Jun-2026 14:50:25 | 0 |  |  | Approver | Locate
AO-000814 | MM-ZTK-1F-GEN-PJM-PDR-0004 | PROGRESS MEASUREMENT AND REPORTING PROCEDURE |  | C2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 16-Jun-2026 10:45:04 | 26002z1fdcc@thoresen-jutal.com | 16-Jun-2026 13:55:41 | Jumpol Sudjitjul | 23-Jun-2026 |  | Jirayu Pantito | 25-Jun-2026 | 17-Jun-2026 09:59:23 | Jumpol Sudjitjul | 26-Jun-2026 | 18-Jun-2026 09:36:02 | APPR | Approved | Jumpol Sudjitjul | 29-Jun-2026 | 18-Jun-2026 09:38:43 | 18-Jun-2026 02:54:06 | 0 |  |  | Approver | Locate
AO-000015 | MM-ZTK-1F-GEN-PJM-PDR-0005 | PROJECT PLANNING & CONTROL PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 12-Mar-2026 19:19:38 | 26002z1fdcc@thoresen-jutal.com | 13-Mar-2026 08:30:07 | Jumpol Sudjitjul | 20-Mar-2026 | 22-Mar-2026 18:22:53 | Prin Jitatisil | 24-Mar-2026 | 22-Mar-2026 23:03:00 |  |  |  | NA | Not Approved | Jumpol Sudjitjul | 26-Mar-2026 | 23-Mar-2026 09:44:12 | 23-Mar-2026 10:05:34 | 0 |  |  | Focal Point | Locate
AO-000099 | MM-ZTK-1F-GEN-PJM-PDR-0005 | PROJECT PLANNING & CONTROL PROCEDURE |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | IFR | Issued for Review | 07-Apr-2026 | 08-Apr-2026 16:24:40 | 26002z1fdcc@thoresen-jutal.com | 10-Apr-2026 13:56:46 | Jumpol Sudjitjul | 22-Apr-2026 | 25-Apr-2026 06:57:30 | Prin Jitatisil | 24-Apr-2026 | 28-Apr-2026 10:53:54 |  |  |  | APPR | Approved | Jumpol Sudjitjul | 28-Apr-2026 | 28-Apr-2026 14:07:12 | 28-Apr-2026 14:43:21 | 0 |  |  | Focal Point | Locate
AO-000323 | MM-ZTK-1F-GEN-PJM-PDR-0005 | PROJECT PLANNING & CONTROL PROCEDURE |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 06-May-2026 15:58:21 | 26002z1fdcc@thoresen-jutal.com | 06-May-2026 16:20:31 | Jumpol Sudjitjul | 13-May-2026 | 13-May-2026 07:17:05 | Prin Jitatisil | 15-May-2026 | 16-May-2026 23:59:32 |  |  |  | APPR | Approved | Jumpol Sudjitjul | 19-May-2026 | 17-May-2026 10:00:46 | 17-May-2026 03:09:32 | 0 |  |  | Focal Point | Locate
AO-000503 | MM-ZTK-1F-GEN-PJM-PDR-0005 | PROJECT PLANNING & CONTROL PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 18-May-2026 20:11:41 | 26002z1fdcc@thoresen-jutal.com | 18-May-2026 20:22:30 | Jumpol Sudjitjul | 26-May-2026 | 25-May-2026 17:16:26 | Prin Jitatisil | 28-May-2026 | 27-May-2026 09:00:57 |  |  |  | APPR | Approved | Jumpol Sudjitjul | 02-Jun-2026 | 27-May-2026 10:35:10 | 27-May-2026 04:14:53 | 0 |  |  | Focal Point | Locate
AO-000040 | MM-ZTK-1F-GEN-PJM-PDR-0007 | PROJECT RISK ASSESSMENT PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 23-Mar-2026 10:10:02 | 26002z1fdcc@thoresen-jutal.com | 23-Mar-2026 10:56:00 | Jumpol Sudjitjul | 30-Mar-2026 | 07-Apr-2026 00:36:41 | Prin Jitatisil | 01-Apr-2026 | 17-Apr-2026 11:22:56 |  |  |  | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 03-Apr-2026 | 17-Apr-2026 11:47:25 | 17-Apr-2026 05:08:21 | 0 |  |  | Focal Point | Locate
AO-000324 | MM-ZTK-1F-GEN-PJM-PDR-0007 | PROJECT RISK ASSESSMENT PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 06-May-2026 15:58:51 | 26002z1fdcc@thoresen-jutal.com | 06-May-2026 16:21:06 | Jumpol Sudjitjul | 13-May-2026 |  | Prin Jitatisil | 15-May-2026 | 10-May-2026 17:34:26 |  |  |  | APPR | Approved | Jumpol Sudjitjul | 19-May-2026 | 10-May-2026 23:23:24 | 10-May-2026 17:19:41 | 0 |  |  | Focal Point | Locate
AO-000027 | MM-ZTK-1F-GEN-PJM-PEP-0001 | PROJECT EXECUTION PLAN |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PEP | Project Execution Plan | 0 | Submitted | IFR | Issued for Review |  | 19-Mar-2026 14:13:58 | 26002z1fdcc@thoresen-jutal.com | 19-Mar-2026 14:27:10 | Jumpol Sudjitjul | 26-Mar-2026 | 29-Mar-2026 16:21:54 | Prin Jitatisil | 30-Mar-2026 | 02-Apr-2026 17:00:56 |  |  |  | NA | Not Approved | Jumpol Sudjitjul | 01-Apr-2026 | 02-Apr-2026 19:16:29 | 02-Apr-2026 21:09:41 | 0 |  |  | Focal Point | Locate
AO-000838 | MM-ZTK-1F-GEN-PJM-PEP-0001 | PROJECT EXECUTION PLAN |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PEP | Project Execution Plan | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 22:41:43 | 26002z1fdcc@thoresen-jutal.com | 22-Jun-2026 14:06:03 | Jumpol Sudjitjul | 29-Jun-2026 | 29-Jun-2026 08:56:16 | Prin Jitatisil | 01-Jul-2026 | 29-Jun-2026 11:04:13 |  |  |  | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 03-Jul-2026 | 30-Jun-2026 09:41:36 | 30-Jun-2026 03:28:27 | 0 |  |  | Focal Point | Locate
AO-001038 | MM-ZTK-1F-GEN-PJM-PEP-0001 | PROJECT EXECUTION PLAN |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PEP | Project Execution Plan | 0 | Submitted | AFC | Approved for Construction |  | 08-Jul-2026 20:03:53 | 26002z1fdcc@thoresen-jutal.com | 09-Jul-2026 10:28:30 | Jumpol Sudjitjul | 16-Jul-2026 | 11-Jul-2026 06:38:17 | Prin Jitatisil | 20-Jul-2026 | 13-Jul-2026 11:22:49 |  |  |  | APPR | Approved | Jumpol Sudjitjul | 22-Jul-2026 | 13-Jul-2026 13:24:54 | 13-Jul-2026 07:05:06 | 0 |  |  | Focal Point | Locate
AO-000001 | MM-ZTK-1F-GEN-PJM-PLN-0003 | 60 DAY LOOK AHEAD PLAN FOR EARLY WORK |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 25-Feb-2026 16:40:14 | 26002z1fdcc@thoresen-jutal.com | 27-Feb-2026 15:30:20 | Jumpol Sudjitjul | 09-Mar-2026 | 09-Mar-2026 13:16:12 | Jirayu Pantito | 11-Mar-2026 | 10-Mar-2026 07:33:24 | Prin Jitatisil | 12-Mar-2026 | 11-Mar-2026 12:55:20 | NA | Not Approved | Jumpol Sudjitjul | 13-Mar-2026 | 11-Mar-2026 12:59:53 | 11-Mar-2026 13:15:31 | 0 |  |  | Approver | Locate
AO-000084 | MM-ZTK-1F-GEN-PJM-PLN-0003 | 60 DAY LOOK AHEAD PLAN FOR EARLY WORK |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PLN | Plan | 0 | Submitted | IFR | Issued for Review | 25-Mar-2026 | 07-Apr-2026 18:18:52 | 26002z1fdcc@thoresen-jutal.com | 08-Apr-2026 07:01:47 | Jumpol Sudjitjul | 20-Apr-2026 | 21-Apr-2026 09:10:34 | Jirayu Pantito | 22-Apr-2026 | 03-May-2026 19:10:19 | Prin Jitatisil | 23-Apr-2026 | 06-May-2026 08:47:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Apr-2026 | 06-May-2026 09:32:36 | 06-May-2026 09:50:17 | 0 |  |  | Approver | Locate
AO-000341 | MM-ZTK-1F-GEN-PJM-PLN-0003 | 60 DAY LOOK AHEAD PLAN FOR EARLY WORK |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PLN | Plan | 0 | Submitted | IFA | Issued for Approval | 20-May-2026 | 08-May-2026 08:48:05 | kanokon.i@mermaid-group.com | 08-May-2026 08:50:30 | Jumpol Sudjitjul | 15-May-2026 | 16-May-2026 15:36:37 | Jirayu Pantito | 19-May-2026 | 18-May-2026 10:22:43 | Prin Jitatisil | 20-May-2026 | 21-May-2026 09:32:09 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 21-May-2026 | 21-May-2026 13:09:35 | 21-May-2026 13:26:24 | 0 |  |  | Approver | Locate
AO-000610 | MM-ZTK-1F-GEN-PJM-PLN-0003 | 60 DAY LOOK AHEAD PLAN FOR EARLY WORK |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 28-May-2026 08:58:56 | 26002z1fdcc@thoresen-jutal.com | 28-May-2026 13:29:30 | Jumpol Sudjitjul | 08-Jun-2026 |  | Jirayu Pantito | 10-Jun-2026 | 29-May-2026 15:02:51 | Prin Jitatisil | 11-Jun-2026 | 30-May-2026 22:59:12 | APPR | Approved | Jumpol Sudjitjul | 12-Jun-2026 | 31-May-2026 20:52:57 | 31-May-2026 14:30:55 | 0 |  |  | Approver | Locate
AO-000017 | MM-ZTK-1F-GEN-PJM-PLN-0005 | DETAIL WORK TIME SCHEDULE L3/L4 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 17-Mar-2026 11:05:46 | 26002z1fdcc@thoresen-jutal.com | 17-Mar-2026 13:25:30 | Jumpol Sudjitjul | 24-Mar-2026 | 24-Mar-2026 15:31:09 | Jirayu Pantito | 26-Mar-2026 | 25-Mar-2026 11:55:01 | Prin Jitatisil | 27-Mar-2026 | 31-Mar-2026 10:00:27 | NA | Not Approved | Jumpol Sudjitjul | 30-Mar-2026 | 31-Mar-2026 10:03:30 | 31-Mar-2026 10:22:28 | 0 |  |  | Approver | Locate
AO-000526 | MM-ZTK-1F-GEN-PJM-SCD-0001 | DETAIL WORK TIME SCHEDULE L3/L4 |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | SCD | Schedule | 0 | Submitted | IFA | Issued for Approval |  | 20-May-2026 12:47:08 | 26002z1fdcc@thoresen-jutal.com | 20-May-2026 16:01:16 | Jumpol Sudjitjul | 27-May-2026 | 10-Jun-2026 00:39:51 | Jirayu Pantito | 29-May-2026 | 12-Jun-2026 15:40:40 | Prin Jitatisil | 02-Jun-2026 | 15-Jun-2026 14:07:32 | NA | Not Approved | Jumpol Sudjitjul | 04-Jun-2026 | 15-Jun-2026 14:10:59 | 15-Jun-2026 07:46:32 | 0 |  |  | Approver | Locate
AO-000954 | MM-ZTK-1F-GEN-PJM-SCD-0001 | DETAIL WORK TIME SCHEDULE L3/L4 |  | B2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | SCD | Schedule | 0 | Submitted | IFA | Issued for Approval |  | 23-Jun-2026 16:44:17 | 26002z1fdcc@thoresen-jutal.com | 30-Jun-2026 14:11:52 | Jumpol Sudjitjul | 07-Jul-2026 | 06-Jul-2026 08:50:09 | Jirayu Pantito | 09-Jul-2026 | 15-Jul-2026 09:46:39 | Prin Jitatisil | 10-Jul-2026 | 15-Jul-2026 13:31:42 | NA | Not Approved | Jumpol Sudjitjul | 13-Jul-2026 | 15-Jul-2026 13:50:13 | 15-Jul-2026 07:01:27 | 0 |  |  | Approver | Locate
AO-001397 | MM-ZTK-1F-GEN-PJM-SCD-0001 | DETAIL WORK TIME SCHEDULE L3/L4 |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | SCD | Schedule | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 10:21:06 | 26002z1fdcc@thoresen-jutal.com | 03-Aug-2026 13:34:21 | Jumpol Sudjitjul | 10-Aug-2026 | 04-Aug-2026 10:47:00 | Jirayu Pantito | 13-Aug-2026 | 04-Aug-2026 18:43:54 | Prin Jitatisil | 14-Aug-2026 | 05-Aug-2026 14:57:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 05-Aug-2026 15:14:10 | 05-Aug-2026 09:20:27 | 0 |  |  | Approver | Locate
AO-000037 | MM-ZTK-1F-GEN-PJM-SCD-0002 | DETAIL WORK TIME SCHEDULE L5/L6 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | SCD | Schedule | 0 | Submitted | IFR | Issued for Review |  | 20-Mar-2026 17:30:35 | 26002z1fdcc@thoresen-jutal.com | 20-Mar-2026 17:35:54 | Jumpol Sudjitjul | 30-Mar-2026 | 26-Mar-2026 11:19:30 | Jirayu Pantito | 01-Apr-2026 | 30-Mar-2026 07:58:22 | Prin Jitatisil | 02-Apr-2026 | 31-Mar-2026 10:07:18 | NA | Not Approved | Jumpol Sudjitjul | 03-Apr-2026 | 31-Mar-2026 10:08:40 | 31-Mar-2026 10:24:55 | 0 |  |  | Approver | Locate
AO-000657 | MM-ZTK-1F-GEN-PJM-SCD-0002 | DETAIL WORK TIME SCHEDULE L5/L6 |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | SCD | Schedule | 0 | Submitted | IFA | Issued for Approval |  | 02-Jun-2026 22:47:13 | 26002z1fdcc@thoresen-jutal.com | 03-Jun-2026 09:24:09 | Jumpol Sudjitjul | 10-Jun-2026 | 10-Jun-2026 00:59:02 | Jirayu Pantito | 12-Jun-2026 | 16-Jun-2026 10:32:38 | Prin Jitatisil | 15-Jun-2026 | 18-Jun-2026 09:36:55 | NA | Not Approved | Jumpol Sudjitjul | 16-Jun-2026 | 18-Jun-2026 09:39:53 | 18-Jun-2026 02:55:30 | 0 |  |  | Approver | Locate
AO-000955 | MM-ZTK-1F-GEN-PJM-SCD-0002 | DETAIL WORK TIME SCHEDULE L5/L6 |  | B2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | SCD | Schedule | 0 | Submitted | IFA | Issued for Approval |  | 23-Jun-2026 16:44:48 | 26002z1fdcc@thoresen-jutal.com | 30-Jun-2026 14:12:49 | Jumpol Sudjitjul | 07-Jul-2026 | 06-Jul-2026 08:51:44 | Jirayu Pantito | 09-Jul-2026 | 15-Jul-2026 10:11:31 | Prin Jitatisil | 10-Jul-2026 | 15-Jul-2026 13:32:01 | NA | Not Approved | Jumpol Sudjitjul | 13-Jul-2026 | 15-Jul-2026 13:51:04 | 15-Jul-2026 07:03:00 | 0 |  |  | Approver | Locate
AO-001398 | MM-ZTK-1F-GEN-PJM-SCD-0002 | DETAIL WORK TIME SCHEDULE L5/L6 |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | SCD | Schedule | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 10:22:03 | 26002z1fdcc@thoresen-jutal.com | 03-Aug-2026 13:35:03 | Jumpol Sudjitjul | 10-Aug-2026 | 04-Aug-2026 10:48:02 | Jirayu Pantito | 13-Aug-2026 | 04-Aug-2026 18:54:45 | Prin Jitatisil | 14-Aug-2026 | 05-Aug-2026 14:57:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 05-Aug-2026 15:15:57 | 05-Aug-2026 09:22:05 | 0 |  |  | Approver | Locate
AO-000022 | MM-ZTK-1F-GEN-PJM-WPR-0001 | WEEKLY REPORT NO:0001 CUT OFF 06 MARCH 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Submitted | IFI | Issued for Information |  | 18-Mar-2026 19:57:19 | 26002z1fdcc@thoresen-jutal.com | 19-Mar-2026 09:07:19 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 22-Mar-2026 23:07:28 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 23-Mar-2026 09:43:32 | 23-Mar-2026 10:15:42 | 0 |  |  | For Info | Locate
AO-000023 | MM-ZTK-1F-GEN-PJM-WPR-0002 | WEEKLY REPORT NO:0002 CUT OFF 13 MARCH 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Submitted | IFI | Issued for Information |  | 18-Mar-2026 19:57:55 | 26002z1fdcc@thoresen-jutal.com | 19-Mar-2026 09:08:30 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 22-Mar-2026 23:19:34 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 23-Mar-2026 09:41:38 | 23-Mar-2026 10:14:34 | 0 |  |  | For Info | Locate
AO-000142 | MM-ZTK-1F-GEN-PJM-WPR-0003 | WEEKLY REPORT NO.0003 CUT OFF 20 MARCH 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 17-Apr-2026 12:10:56 | 26002z1fdcc@thoresen-jutal.com | 17-Apr-2026 13:42:08 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 28-Apr-2026 10:39:22 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000143 | MM-ZTK-1F-GEN-PJM-WPR-0004 | WEEKLY REPORT NO.0003 CUT OFF 27 MARCH 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 17-Apr-2026 12:11:21 | 26002z1fdcc@thoresen-jutal.com | 17-Apr-2026 13:42:53 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 28-Apr-2026 10:40:03 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000144 | MM-ZTK-1F-GEN-PJM-WPR-0005 | WEEKLY REPORT NO.0005 CUT OFF 03 APRIL 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 17-Apr-2026 12:11:47 | 26002z1fdcc@thoresen-jutal.com | 17-Apr-2026 13:43:11 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 28-Apr-2026 10:40:39 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000154 | MM-ZTK-1F-GEN-PJM-WPR-0006 | WEEKLY REPORT NO.0006 CUT OFF 10 APRIL 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 18-Apr-2026 10:11:42 | 26002z1fdcc@thoresen-jutal.com | 19-Apr-2026 22:16:59 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 28-Apr-2026 10:42:00 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000204 | MM-ZTK-1F-GEN-PJM-WPR-0007 | WEEKLY REPORT NO. 0007 CUT OFF 17 APRIL 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 22-Apr-2026 08:58:25 | 26002z1fdcc@thoresen-jutal.com | 22-Apr-2026 13:16:33 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 28-Apr-2026 10:41:46 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000249 | MM-ZTK-1F-GEN-PJM-WPR-0008 | WEEKLY REPORT NO. 0008 CUT OFF 24 APRIL 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Submitted | IFI | Issued for Information |  | 28-Apr-2026 19:05:31 | 26002z1fdcc@thoresen-jutal.com | 29-Apr-2026 09:39:33 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 07-May-2026 10:51:41 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 07-May-2026 10:54:40 | 07-May-2026 05:13:52 | 0 |  |  | For Info | Locate
AO-000338 | MM-ZTK-1F-GEN-PJM-WPR-0009 | WEEKLY REPORT NO. 0009 CUT OFF 01 MAY 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 07-May-2026 11:27:57 | 26002z1fdcc@thoresen-jutal.com | 07-May-2026 11:38:09 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 10-May-2026 17:30:44 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000385 | MM-ZTK-1F-GEN-PJM-WPR-0010 | WEEKLY REPORT NO. 0010 CUT OFF 08 MAY 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 13-May-2026 15:34:56 | 26002z1fdcc@thoresen-jutal.com | 13-May-2026 15:55:28 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 17-May-2026 00:02:34 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000605 | MM-ZTK-1F-GEN-PJM-WPR-0011 | WEEKLY REPORT NO. 0011 CUT OFF 15 MAY 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 26-May-2026 16:49:13 | 26002z1fdcc@thoresen-jutal.com | 27-May-2026 09:39:18 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 06-Jun-2026 10:58:34 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000615 | MM-ZTK-1F-GEN-PJM-WPR-0012 | WEEKLY REPORT NO. 0012 CUT OFF 22 MAY 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 28-May-2026 10:01:49 | 26002z1fdcc@thoresen-jutal.com | 28-May-2026 13:32:39 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 06-Jun-2026 10:58:01 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000658 | MM-ZTK-1F-GEN-PJM-WPR-0013 | WEEKLY REPORT NO. 0013 CUT OFF 29 MAY 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 02-Jun-2026 22:47:41 | 26002z1fdcc@thoresen-jutal.com | 03-Jun-2026 09:26:06 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 06-Jun-2026 10:57:24 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000737 | MM-ZTK-1F-GEN-PJM-WPR-0014 | WEEKLY REPORT NO. 0014 CUT OFF 05 JUNE 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 10-Jun-2026 20:29:44 | 26002z1fdcc@thoresen-jutal.com | 11-Jun-2026 15:53:44 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 15-Jun-2026 14:33:16 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000817 | MM-ZTK-1F-GEN-PJM-WPR-0015 | WEEKLY REPORT NO. 0015 CUT OFF 12 JUNE 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 17-Jun-2026 12:50:23 | 26002z1fdcc@thoresen-jutal.com | 17-Jun-2026 15:39:05 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 20-Jun-2026 22:51:55 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-000944 | MM‐ZTK‐1F‐GEN‐PJM‐WPR‐0016 | WEEKLY REPORT NO. 0016 - CUT OFF 19 JUNE 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 29-Jun-2026 22:06:48 | 26002z1fdcc@thoresen-jutal.com | 30-Jun-2026 10:56:00 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 01-Jul-2026 09:53:43 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-001108 | MM-ZTK-1F-GEN-PJM-WPR-0017 | WEEKLY REPORT NO. 0017 CUT OFF 26 JUNE 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 14-Jul-2026 15:35:49 | 26002z1fdcc@thoresen-jutal.com | 14-Jul-2026 15:50:24 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 15-Jul-2026 13:32:55 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-001109 | MM-ZTK-1F-GEN-PJM-WPR-0018 | WEEKLY REPORT NO. 0018 CUT OFF 03 JULY 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 14-Jul-2026 15:36:27 | 26002z1fdcc@thoresen-jutal.com | 14-Jul-2026 15:51:44 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 15-Jul-2026 13:33:24 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-001199 | MM-ZTK-1F-GEN-PJM-WPR-0019 | WEEKLY REPORT NO. 0019 CUT OFF 10 JULY 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 20-Jul-2026 12:42:13 | 26002z1fdcc@thoresen-jutal.com | 20-Jul-2026 12:47:24 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 21-Jul-2026 10:06:16 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-001338 | MM-ZTK-1F-GEN-PJM-WPR-0020 | WEEKLY REPORT NO. 0020 CUT OFF 17 JULY 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 30-Jul-2026 15:05:57 | 26002z1fdcc@thoresen-jutal.com | 30-Jul-2026 15:14:04 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 30-Jul-2026 18:29:01 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-001337 | MM-ZTK-1F-GEN-PJM-WPR-0021 | WEEKLY REPORT NO. 0021 CUT OFF 24 JULY 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 30-Jul-2026 15:06:26 | 26002z1fdcc@thoresen-jutal.com | 30-Jul-2026 15:14:51 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 30-Jul-2026 18:29:13 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-001421 | MM-ZTK-1F-GEN-PJM-WPR-0022 | WEEKLY REPORT NO. 0022 CUT OFF 31 JULY 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 05-Aug-2026 11:59:00 | 26002z1fdcc@thoresen-jutal.com | 05-Aug-2026 13:38:39 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 05-Aug-2026 22:02:02 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-001518 | MM-ZTK-1F-GEN-PJM-WPR-0023 | WEEKLY REPORT NO. 0023 CUT OFF 07 AUGUST 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 13-Aug-2026 17:05:32 | 26002z1fdcc@thoresen-jutal.com | 13-Aug-2026 17:13:41 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 13-Aug-2026 23:39:07 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-001659 | MM-ZTK-1F-GEN-PJM-WPR-0024 | WEEKLY REPORT NO. 0024 CUT OFF 14 AUG 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 24-Aug-2026 11:03:54 | 26002z1fdcc@thoresen-jutal.com | 24-Aug-2026 20:32:43 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 26-Aug-2026 08:45:38 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-001813 | MM-ZTK-1F-GEN-PJM-WPR-0025 | WEEKLY REPORT NO. 0025 CUT OFF 21 AUGUST 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Submitted | IFI | Issued for Information |  | 01-Sep-2026 15:21:14 | 26002z1fdcc@thoresen-jutal.com | 01-Sep-2026 16:10:06 | Neeranuch Nutong | 08-Sep-2026 |  | Prin Jitatisil | 10-Sep-2026 | 06-Sep-2026 00:38:40 |  |  |  | REC | Received | Jumpol Sudjitjul | 14-Sep-2026 | 06-Sep-2026 09:30:16 | 06-Sep-2026 03:01:23 | 0 |  |  | Focal Point | Locate
AO-001817 | MM-ZTK-1F-GEN-PJM-WPR-0026 | WEEKLY REPORT NO. 0026 CUT OFF 28 AUGUST 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 02-Sep-2026 18:22:54 | 26002z1fdcc@thoresen-jutal.com | 03-Sep-2026 11:26:32 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 06-Sep-2026 00:39:02 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-001960 | MM-ZTK-1F-GEN-PJM-WPR-0027 | WEEKLY REPORT NO. 0027 CUT OFF 04-SEP-2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 09-Sep-2026 17:32:32 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002209 | MM-ZTK-1F-GEN-PJM-WPR-0028 | WEEKLY REPORT NO. 0028 CUT OFF 11 SEP 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WPR | Weekly Progress Report | 0 | Latest | IFI | Issued for Information |  | 22-Sep-2026 15:53:45 | 26002z1fdcc@thoresen-jutal.com | 22-Sep-2026 16:04:32 | Jumpol Sudjitjul |  |  | Prin Jitatisil |  | 27-Sep-2026 06:12:22 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-001333 | MM-ZTK-1F-GEN-PJM-WST-0001 | CONSORTIUM STATEMENT NO.1 (TJE) - 03 JULY 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WST | Work Statement | 0 | Latest | IFI | Issued for Information |  | 30-Jul-2026 10:59:02 | 26002z1fdcc@thoresen-jutal.com | 30-Jul-2026 11:10:12 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 04-Aug-2026 09:29:27 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-001715 | MM-ZTK-1F-GEN-PJM-WST-0002 | CONSORTIUM STATEMENT NO.2 (TJE) - 07 AUGUST 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WST | Work Statement | 0 | Latest | IFI | Issued for Information |  | 26-Aug-2026 09:30:56 | 26002z1fdcc@thoresen-jutal.com | 26-Aug-2026 13:05:14 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 27-Aug-2026 12:40:16 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-002304 | MM-ZTK-1F-GEN-PJM-WST-0003 | CONSORTIUM STATEMENT NO.3 (TJE) - MONTH 04 SEPTEMBER 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WST | Work Statement | 0 | Submitted | IFI | Issued for Information |  | 29-Sep-2026 12:00:46 | 26002z1fdcc@thoresen-jutal.com | 29-Sep-2026 14:56:08 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 06-Oct-2026 16:13:21 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 06-Oct-2026 17:17:44 | 06-Oct-2026 10:49:45 | 0 |  |  | For Info | Locate
AO-002314 | MM-ZTK-1F-GEN-PJM-WST-0101 | WORK STATEMENT FOR CO-0002 – SERVICES TO COMPANY AT CONTRACTOR’S ENGINEERING OFFICE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WST | Work Statement | 0 | Submitted | IFI | Issued for Information |  | 30-Sep-2026 11:28:29 | 26002z1fdcc@thoresen-jutal.com | 30-Sep-2026 16:10:48 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 06-Oct-2026 16:27:18 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 06-Oct-2026 17:19:09 | 06-Oct-2026 10:52:05 | 0 |  |  | For Info | Locate
AO-001333 | MM-ZTK-1F-GEN-PJM-WST-1001 | CONSORTIUM STATEMENT NO.1 (ALL) - 03 JULY 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WST | Work Statement | 0 | Latest | IFI | Issued for Information |  | 30-Jul-2026 10:59:34 | 26002z1fdcc@thoresen-jutal.com | 30-Jul-2026 11:10:35 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 04-Aug-2026 09:31:16 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-001715 | MM-ZTK-1F-GEN-PJM-WST-1002 | CONSORTIUM STATEMENT NO.2 (ALL) - 07 AUGUST 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WST | Work Statement | 0 | Latest | IFI | Issued for Information |  | 26-Aug-2026 09:31:26 | 26002z1fdcc@thoresen-jutal.com | 26-Aug-2026 13:05:33 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 27-Aug-2026 12:39:55 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-002304 | MM-ZTK-1F-GEN-PJM-WST-1003 | CONSORTIUM STATEMENT NO.3 (ALL) - MONTH 04 SEPTEMBER 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WST | Work Statement | 0 | Submitted | IFI | Issued for Information |  | 29-Sep-2026 12:01:10 | 26002z1fdcc@thoresen-jutal.com | 29-Sep-2026 14:56:31 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 06-Oct-2026 16:14:41 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 06-Oct-2026 17:21:11 | 06-Oct-2026 10:55:35 | 0 |  |  | For Info | Locate
AO-001333 | MM-ZTK-1F-GEN-PJM-WST-8001 | CONSORTIUM STATEMENT NO.1 (SSC) - 03 JULY 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WST | Work Statement | 0 | Latest | IFI | Issued for Information |  | 30-Jul-2026 11:00:04 | 26002z1fdcc@thoresen-jutal.com | 30-Jul-2026 11:10:51 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 04-Aug-2026 18:09:29 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-001715 | MM-ZTK-1F-GEN-PJM-WST-8002 | CONSORTIUM STATEMENT NO.2 (SSC) - 07 AUGUST 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WST | Work Statement | 0 | Latest | IFI | Issued for Information |  | 26-Aug-2026 09:32:01 | 26002z1fdcc@thoresen-jutal.com | 26-Aug-2026 13:05:51 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 27-Aug-2026 12:39:35 |  |  |  | REC | Received |  |  |  |  | 0 |  |  | For Info | Locate
AO-002304 | MM-ZTK-1F-GEN-PJM-WST-8003 | CONSORTIUM STATEMENT NO.3 (SSC) - MONTH 04 SEPTEMBER 2026 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PJM | Project Management | WST | Work Statement | 0 | Submitted | IFI | Issued for Information |  | 29-Sep-2026 12:01:36 | 26002z1fdcc@thoresen-jutal.com | 29-Sep-2026 14:56:46 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 06-Oct-2026 16:15:32 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 06-Oct-2026 17:18:09 | 06-Oct-2026 11:01:53 | 0 |  |  | For Info | Locate
AO-000250 | MM-ZTK-1F-GEN-PRC-MOM-1001 | PROCUREMENT WEEKLY MEETING - WP2 NO.001 (KICK-OFF MEETING) |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 29-Apr-2026 08:29:34 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001405 | MM-ZTK-1F-GEN-PRC-PDR-5002 | SUBCONTRACTING PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 19:14:12 | zm169dc@jutal.com | 04-Aug-2026 11:48:19 | Jumpol Sudjitjul | 11-Aug-2026 |  | Jirayu Pantito | 14-Aug-2026 | 11-Aug-2026 10:49:18 | Prin Jitatisil | 17-Aug-2026 | 11-Aug-2026 14:32:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 11-Aug-2026 14:44:49 | 11-Aug-2026 08:06:41 | 0 |  |  | Approver | Locate
AO-000018 | MM-ZTK-1F-GEN-PRC-PLN-0001 | PROJECT PROCUREMENT PLAN FOR WORK PACKAGE 1 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | PLN | Plan | 0 | Submitted | IFA | Issued for Review |  | 17-Mar-2026 11:05:20 | zm169dc@jutal.com | 17-Mar-2026 13:22:27 | Jumpol Sudjitjul | 24-Mar-2026 | 18-Mar-2026 06:42:41 | Jirayu Pantito | 26-Mar-2026 | 22-Mar-2026 06:55:40 | Prin Jitatisil | 27-Mar-2026 | 22-Mar-2026 22:28:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 30-Mar-2026 | 23-Mar-2026 09:39:43 | 23-Mar-2026 09:54:41 | 0 |  |  | Approver | Locate
AO-000055 | MM-ZTK-1F-GEN-PRC-PLN-0001 | PROJECT PROCUREMENT PLAN FOR WORK PACKAGE 1 |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | PLN | Plan | 0 | Submitted | IFA | Issued for Approval | 07-Apr-2026 | 31-Mar-2026 16:49:47 | zm169dc@jutal.com | 31-Mar-2026 16:53:06 | Jumpol Sudjitjul | 08-Apr-2026 |  | Jirayu Pantito | 10-Apr-2026 | 07-Apr-2026 10:04:05 | Prin Jitatisil | 16-Apr-2026 | 07-Apr-2026 23:23:35 | NA | Not Approved | Jumpol Sudjitjul | 17-Apr-2026 | 07-Apr-2026 23:37:58 | 08-Apr-2026 00:14:41 | 0 |  |  | Approver | Locate
AO-000583 | MM-ZTK-1F-GEN-PRC-PLN-0001 | PROJECT PROCUREMENT PLAN FOR WORK PACKAGE 1 |  | B2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | PLN | Plan | 0 | Submitted | IFA | Issued for Approval | 24-Apr-2026 | 23-May-2026 08:51:41 | zm169dc@jutal.com | 23-May-2026 09:32:05 | Jumpol Sudjitjul | 29-May-2026 |  | Jirayu Pantito | 04-Jun-2026 | 25-May-2026 05:35:12 | Prin Jitatisil | 05-Jun-2026 | 27-May-2026 08:57:59 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Jun-2026 | 27-May-2026 10:38:24 | 27-May-2026 11:16:16 | 0 |  |  | Approver | Locate
AO-000800 | MM-ZTK-1F-GEN-PRC-PLN-0001 | PROJECT PROCUREMENT PLAN FOR WORK PACKAGE 1 |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 15-Jun-2026 12:06:07 | zm169dc@jutal.com | 15-Jun-2026 16:46:03 | Jumpol Sudjitjul | 22-Jun-2026 |  | Jirayu Pantito | 24-Jun-2026 | 17-Jun-2026 09:58:26 | Prin Jitatisil | 25-Jun-2026 | 18-Jun-2026 09:37:12 | APPR | Approved | Jumpol Sudjitjul | 26-Jun-2026 | 18-Jun-2026 09:44:20 | 18-Jun-2026 03:55:12 | 0 |  |  | Approver | Locate
AO-001407 | MM-ZTK-1F-GEN-PRC-PLN-0001 | PROJECT PROCUREMENT PLAN FOR WORK PACKAGE 1 |  | C2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 04-Aug-2026 10:01:21 | zm169dc@jutal.com | 04-Aug-2026 10:38:35 | Jumpol Sudjitjul | 11-Aug-2026 | 04-Aug-2026 13:28:49 | Jirayu Pantito | 14-Aug-2026 | 04-Aug-2026 19:19:45 | Prin Jitatisil | 17-Aug-2026 | 05-Aug-2026 14:57:39 | APPR | Approved | Jumpol Sudjitjul | 18-Aug-2026 | 05-Aug-2026 15:20:10 | 05-Aug-2026 09:23:21 | 0 |  |  | Approver | Locate
AO-000002 | MM-ZTK-1F-GEN-PRC-PLN-3001 | PROJECT PROCUREMENT PLAN - PIPELINE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 27-Feb-2026 17:16:08 | 26002z1fdcc@thoresen-jutal.com | 27-Feb-2026 19:40:08 | Jumpol Sudjitjul | 10-Mar-2026 | 08-Mar-2026 08:33:51 | Jirayu Pantito | 12-Mar-2026 | 11-Mar-2026 15:49:34 | Prin Jitatisil | 13-Mar-2026 | 17-Mar-2026 09:53:15 | NA | Not Approved | Jumpol Sudjitjul | 16-Mar-2026 | 17-Mar-2026 10:01:15 | 17-Mar-2026 03:27:49 | 0 |  |  | Approver | Locate
AO-000226 | MM-ZTK-1F-GEN-PRC-PLN-8001 | PROJECT PROCUREMENT PLAN AND PROCEDURE - WHP T&I |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 16:39:17 | kjb@coes.cn | 24-Apr-2026 18:01:03 | Jumpol Sudjitjul | 06-May-2026 | 06-May-2026 08:18:33 | Jirayu Pantito | 08-May-2026 | 08-May-2026 12:10:03 | Prin Jitatisil | 11-May-2026 | 10-May-2026 17:27:29 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 12-May-2026 | 10-May-2026 23:24:23 | 11-May-2026 00:22:34 | 0 |  |  | Approver | Locate
AO-000663 | MM-ZTK-1F-GEN-PRC-PLN-8001 | PROJECT PROCUREMENT PLAN AND PROCEDURE - WHP T&I |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 04-Jun-2026 13:32:18 | kjb@coes.cn | 04-Jun-2026 16:44:12 | Jumpol Sudjitjul | 11-Jun-2026 | 15-Jun-2026 08:39:58 | Jirayu Pantito | 15-Jun-2026 | 17-Jun-2026 09:38:51 | Prin Jitatisil | 16-Jun-2026 | 18-Jun-2026 09:37:39 | APPR | Approved | Jumpol Sudjitjul | 17-Jun-2026 | 18-Jun-2026 09:45:27 | 18-Jun-2026 03:25:33 | 0 |  |  | Approver | Locate
AO-000046 | MM-ZTK-1F-GEN-PRC-PLN-9001 | PROJECT PROCUREMENT PLAN AND PROCEDURE - PIPELINE |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 25-Mar-2026 16:40:14 | 26002z1fdcc@thoresen-jutal.com | 26-Mar-2026 17:06:24 | Jumpol Sudjitjul | 03-Apr-2026 | 31-Mar-2026 09:51:34 | Jirayu Pantito | 08-Apr-2026 | 03-Apr-2026 09:15:20 | Prin Jitatisil | 09-Apr-2026 | 06-Apr-2026 17:35:29 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 10-Apr-2026 | 06-Apr-2026 21:37:04 | 06-Apr-2026 21:57:33 | 0 |  |  | Approver | Locate
AO-000567 | MM-ZTK-1F-GEN-PRC-PLN-9001 | PROJECT PROCUREMENT PLAN AND PROCEDURE - PIPELINE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | PLN | Plan | 0 | Submitted | AFC | Approved for Construction | 23-Apr-2026 | 22-May-2026 10:15:25 | 26002z1fdcc@thoresen-jutal.com | 22-May-2026 12:39:41 | Jumpol Sudjitjul | 29-May-2026 | 27-May-2026 08:25:20 | Jirayu Pantito | 04-Jun-2026 | 02-Jun-2026 09:01:57 | Prin Jitatisil | 05-Jun-2026 | 04-Jun-2026 16:58:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 04-Jun-2026 18:26:53 | 04-Jun-2026 21:29:12 | 0 |  |  | Approver | Locate
AO-000687 | MM-ZTK-1F-GEN-PRC-PLN-9001 | PROJECT PROCUREMENT PLAN AND PROCEDURE - PIPELINE |  | C2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 05-Jun-2026 17:58:20 | 26002z1fdcc@thoresen-jutal.com | 05-Jun-2026 20:03:30 | Jumpol Sudjitjul | 15-Jun-2026 | 15-Jun-2026 08:43:24 | Jirayu Pantito | 17-Jun-2026 | 17-Jun-2026 09:36:18 | Prin Jitatisil | 18-Jun-2026 | 18-Jun-2026 09:38:07 | APPR | Approved | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 09:46:18 | 18-Jun-2026 03:32:03 | 0 |  |  | Approver | Locate
AO-001930 | MM-ZTK-1F-GEN-PRC-PLN-9001 | PROJECT PROCUREMENT PLAN AND PROCEDURE - PIPELINE |  | C3 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 08-Sep-2026 10:12:33 | 26002z1fdcc@thoresen-jutal.com | 08-Sep-2026 11:16:29 | Jumpol Sudjitjul | 15-Sep-2026 | 17-Sep-2026 09:07:46 | Jirayu Pantito | 17-Sep-2026 | 19-Sep-2026 07:49:49 | Prin Jitatisil | 18-Sep-2026 | 20-Sep-2026 01:24:46 | APPR | Approved | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 17:10:10 | 20-Sep-2026 11:55:06 | 0 |  |  | Approver | Locate
AO-000684 | MM-ZTK-1F-GEN-PRC-TQ-1001 | TECHNICAL QUERY FOR PVL |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | TQ | Technical Query | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 15:02:51 | zm169dc@jutal.com | 05-Jun-2026 17:55:34 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 10-Jun-2026 16:39:32 |  |  |  | REC | Received |  |  |  | 12-Jun-2026 15:43:15 | 0 |  |  | For Info | Locate
AO-000685 | MM-ZTK-1F-GEN-PRC-TQ-1002 | TECHNICAL QUERY FOR PVL (BUNDLE4#) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | TQ | Technical Query | 0 | Submitted | IFI | Issued for Information |  | 05-Jun-2026 15:03:24 | zm169dc@jutal.com | 05-Jun-2026 17:55:53 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 10-Jun-2026 16:39:14 |  |  |  | REC | Received |  |  |  | 12-Jun-2026 15:44:30 | 0 |  |  | For Info | Locate
AO-001132 | MM-ZTK-1F-GEN-PRC-UPO-0001 | UNPRICED PO FOR PRESSURE VESSELS AND STORAGE TANK FOR TOPSIDE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 16-Jul-2026 14:03:10 | zm169dc@jutal.com | 16-Jul-2026 14:09:43 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 12-Aug-2026 08:09:45 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 13-Aug-2026 11:12:56 | 13-Aug-2026 05:36:39 | 0 |  |  | For Info | Locate
AO-001233 | MM-ZTK-1F-GEN-PRC-UPO-0002 | UNPRICED PO FOR ACTUATED CHOKE VALVE FOR TOPSIDE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 23-Jul-2026 18:08:04 | zm169dc@jutal.com | 24-Jul-2026 10:47:41 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 16-Aug-2026 14:50:59 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 17-Aug-2026 13:56:10 | 17-Aug-2026 07:18:20 | 0 |  |  | For Info | Locate
AO-001535 | MM-ZTK-1F-GEN-PRC-UPO-0003 | UNPRICED PO FOR OFF-SHORE PEDESTAL CRANE FOR TOPSIDE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 14-Aug-2026 17:26:58 | zm169dc@jutal.com | 14-Aug-2026 17:33:23 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 31-Aug-2026 13:13:47 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 31-Aug-2026 15:45:12 | 31-Aug-2026 09:28:01 | 0 |  |  | For Info | Locate
AO-001807 | MM-ZTK-1F-GEN-PRC-UPO-0003 | UNPRICED PO FOR OFF-SHORE PEDESTAL CRANE FOR TOPSIDE |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 01-Sep-2026 18:07:01 | zm169dc@jutal.com | 02-Sep-2026 08:31:33 | Neeranuch Nutong |  |  | Jirayu Pantito | [11 empty] | 0 |  |  | For Info | Locate
AO-001535 | MM-ZTK-1F-GEN-PRC-UPO-0004 | UNPRICED PO FOR AC,DCDB, NAVIGATION AID FOR TOPSIDE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 14-Aug-2026 17:27:24 | zm169dc@jutal.com | 14-Aug-2026 17:47:58 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 31-Aug-2026 13:21:12 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 31-Aug-2026 15:45:53 | 31-Aug-2026 09:29:21 | 0 |  |  | For Info | Locate
AO-001535 | MM-ZTK-1F-GEN-PRC-UPO-0005 | UNPRICED PO FOR GRIPPER, PACKER AND DIAPHRAGM FOR JACKET |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 14-Aug-2026 17:27:52 | zm169dc@jutal.com | 14-Aug-2026 17:47:59 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 31-Aug-2026 13:33:03 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 31-Aug-2026 15:47:03 | 31-Aug-2026 09:31:57 | 0 |  |  | For Info | Locate
AO-001535 | MM-ZTK-1F-GEN-PRC-UPO-0006 | UNPRICED PO FOR ACTUATED COMPACT BALL VALVE FOR TOPSIDE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 14-Aug-2026 17:28:18 | zm169dc@jutal.com | 14-Aug-2026 17:47:57 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 31-Aug-2026 13:47:03 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 31-Aug-2026 15:46:28 | 31-Aug-2026 09:30:40 | 0 |  |  | For Info | Locate
AO-002012 | MM-ZTK-1F-GEN-PRC-UPO-0006 | UNPRICED PO FOR ACTUATED COMPACT BALL VALVE FOR TOPSIDE |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 11-Sep-2026 20:34:41 | zm169dc@jutal.com | 11-Sep-2026 20:42:05 | Jumpol Sudjitjul |  |  | Jirayu Pantito | [11 empty] | 0 |  |  | For Info | Locate
AO-001535 | MM-ZTK-1F-GEN-PRC-UPO-0007 | UNPRICED PO FOR WELLHEAD CONTROL PANEL FOR TOPSIDE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 14-Aug-2026 17:28:48 | zm169dc@jutal.com | 14-Aug-2026 17:47:57 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 31-Aug-2026 13:53:17 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 31-Aug-2026 15:47:40 | 31-Aug-2026 09:34:02 | 0 |  |  | For Info | Locate
AO-001995 | MM-ZTK-1F-GEN-PRC-UPO-0007 | UNPRICED PO FOR WELLHEAD CONTROL PANEL FOR TOPSIDE |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 10-Sep-2026 19:55:42 | zhaoli@jutal.com | 10-Sep-2026 20:12:13 | Jumpol Sudjitjul |  |  | Jirayu Pantito | [11 empty] | 0 |  |  | For Info | Locate
AO-001535 | MM-ZTK-1F-GEN-PRC-UPO-0008 | UNPRICED PO FOR CLOSED DRAIN SUMP PUMP SKID AND CHEMICAL INJECTION PUMP SKID FOR TOPSIDE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 14-Aug-2026 17:29:18 | zm169dc@jutal.com | 14-Aug-2026 17:47:57 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 31-Aug-2026 13:58:19 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 31-Aug-2026 15:48:18 | 31-Aug-2026 09:36:13 | 0 |  |  | For Info | Locate
AO-002012 | MM-ZTK-1F-GEN-PRC-UPO-0008 | UNPRICED PO FOR CLOSED DRAIN SUMP PUMP SKID AND CHEMICAL INJECTION PUMP SKID FOR TOPSIDE |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 11-Sep-2026 20:35:30 | zm169dc@jutal.com | 11-Sep-2026 20:42:24 | Jumpol Sudjitjul |  |  | Jirayu Pantito | [11 empty] | 0 |  |  | For Info | Locate
AO-001535 | MM-ZTK-1F-GEN-PRC-UPO-0009 | UNPRICED PO FOR CHECK VALVE (COMPACT) FOR TOPSIDE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 14-Aug-2026 17:29:45 | zm169dc@jutal.com | 14-Aug-2026 17:47:57 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 16-Aug-2026 14:37:06 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 17-Aug-2026 13:57:03 | 17-Aug-2026 07:32:52 | 0 |  |  | For Info | Locate
AO-002012 | MM-ZTK-1F-GEN-PRC-UPO-0009 | UNPRICED PO FOR CHECK VALVE (COMPACT) FOR TOPSIDE |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 11-Sep-2026 20:35:58 | zm169dc@jutal.com | 11-Sep-2026 20:42:43 | Jumpol Sudjitjul |  |  | Jirayu Pantito | [11 empty] | 0 |  |  | For Info | Locate
AO-001809 | MM-ZTK-1F-GEN-PRC-UPO-0010 | UNPRICED PO FOR PRESSURE RELIEF VALVES FOR TOPSIDE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 01-Sep-2026 18:07:29 | zm169dc@jutal.com | 02-Sep-2026 08:31:58 | Neeranuch Nutong |  |  | Jirayu Pantito |  | 19-Sep-2026 10:44:03 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 20-Sep-2026 17:12:22 | 20-Sep-2026 11:56:15 | 0 |  |  | For Info | Locate
AO-001809 | MM-ZTK-1F-GEN-PRC-UPO-0011 | UNPRICED PO FOR BALL VALVE (FLANGE END), CHECK VALVE,BUTTERFLY VALVE FOR TOPSIDE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 01-Sep-2026 18:07:58 | zm169dc@jutal.com | 02-Sep-2026 08:32:22 | Neeranuch Nutong |  |  | Jirayu Pantito |  | 19-Sep-2026 09:28:24 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 20-Sep-2026 16:56:05 | 20-Sep-2026 10:24:00 | 0 |  |  | For Info | Locate
AO-001809 | MM-ZTK-1F-GEN-PRC-UPO-0012 | UNPRICED PO FOR BALL VALVE (WELD END), GLOBE VALVE(WITHOUT EUQAL PERCENTAGE) FOR TOPSIDE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 01-Sep-2026 18:08:26 | zm169dc@jutal.com | 02-Sep-2026 08:32:48 | Neeranuch Nutong |  |  | Jirayu Pantito |  | 19-Sep-2026 09:09:54 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 20-Sep-2026 16:55:23 | 20-Sep-2026 10:22:00 | 0 |  |  | For Info | Locate
AO-001809 | MM-ZTK-1F-GEN-PRC-UPO-0013 | UNPRICED PO FOR GLOBE VALVE(WITH EUQAL PERCENTAGE) FOR TOPSIDE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 01-Sep-2026 18:08:53 | zm169dc@jutal.com | 02-Sep-2026 08:17:19 | Neeranuch Nutong |  |  | Jirayu Pantito |  | 06-Oct-2026 17:24:19 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 07-Oct-2026 08:20:41 | 07-Oct-2026 01:56:07 | 0 |  |  | For Info | Locate
AO-001928 | MM-ZTK-1F-GEN-PRC-UPO-0014 | UNPRICED PO FOR MATERIAL HANDLING EQUIPMENT FOR TOPSIDE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 08-Sep-2026 09:17:57 | zhaoli@jutal.com | 09-Sep-2026 10:17:08 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  |  | Prin Jitatisil | [8 empty] | 0 |  |  | For Info | Locate
AO-001928 | MM-ZTK-1F-GEN-PRC-UPO-0015 | UNPRICED PO FOR ACTUATED BALL VALVE FOR TOPSIDE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 08-Sep-2026 09:18:33 | zhaoli@jutal.com | 09-Sep-2026 10:17:33 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  |  | Prin Jitatisil | [8 empty] | 0 |  |  | For Info | Locate
AO-001928 | MM-ZTK-1F-GEN-PRC-UPO-0016 | UNPRICED PO FOR CONTROL VALVES AND SELF-ACTUATED PRESSURE CONTROL VALVES FOR TOPSIDE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 08-Sep-2026 09:19:24 | zhaoli@jutal.com | 09-Sep-2026 10:17:59 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  |  | Prin Jitatisil | [8 empty] | 0 |  |  | For Info | Locate
AO-001044 | MM-ZTK-1F-GEN-PRC-UPO-5001 | UNPRICED PO FOR PRIMARY STEEL PLATES FOR TOPSIDE (CUT-OFF DATE 24-JUN-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 09-Jul-2026 15:34:53 | zm169dc@jutal.com | 09-Jul-2026 17:16:17 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 16-Aug-2026 12:10:31 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 17-Aug-2026 13:50:27 | 17-Aug-2026 07:11:11 | 0 |  |  | For Info | Locate
AO-001535 | MM-ZTK-1F-GEN-PRC-UPO-5002 | UNPRICED PO FOR GREASE FOR JACKET |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 14-Aug-2026 17:30:10 | zm169dc@jutal.com | 14-Aug-2026 17:50:02 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 16-Aug-2026 12:16:30 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 17-Aug-2026 13:51:03 | 17-Aug-2026 07:31:34 | 0 |  |  | For Info | Locate
AO-002121 | MM-ZTK-1F-GEN-PRC-UPO-5003 | UNPRICED PO FOR CS PIPE(CUT-OFF DATE 15-SEP-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 17-Sep-2026 13:31:04 | zm169dc@jutal.com | 18-Sep-2026 16:20:04 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  |  | Prin Jitatisil | [8 empty] | 0 |  |  | For Info | Locate
AO-002121 | MM-ZTK-1F-GEN-PRC-UPO-5004 | UNPRICED PO FOR CS FLANGE FOR TOPSIDE (CUT-OFF DATE 16-SEP-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 17-Sep-2026 13:31:35 | zm169dc@jutal.com | 18-Sep-2026 16:20:22 | Jumpol Sudjitjul |  | 17-Oct-2026 17:47:45 | Jirayu Pantito |  |  | Prin Jitatisil | [8 empty] | 0 |  |  | For Info | Locate
AO-002121 | MM-ZTK-1F-GEN-PRC-UPO-5005 | UNPRICED PO FOR FLANGE & FITTING FOR TOPSIDE(CUT-OFF DATE 16-SEP-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 17-Sep-2026 14:22:38 | zm169dc@jutal.com | 18-Sep-2026 16:20:35 | Jumpol Sudjitjul |  | 17-Oct-2026 17:46:10 | Jirayu Pantito |  |  | Prin Jitatisil | [8 empty] | 0 |  |  | For Info | Locate
AO-002121 | MM-ZTK-1F-GEN-PRC-UPO-5006 | UNPRICED PO FOR LIGHTING FIXTURES FOR TOPSIDE (CUT-OFF DATE 16-SEP-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 17-Sep-2026 14:23:19 | zm169dc@jutal.com | 18-Sep-2026 16:26:09 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  |  | Prin Jitatisil | [8 empty] | 0 |  |  | For Info | Locate
AO-002121 | MM-ZTK-1F-GEN-PRC-UPO-5007 | UNPRICED PO FOR FLOODING AND VENT SYSTEM |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 17-Sep-2026 13:32:25 | zm169dc@jutal.com | 18-Sep-2026 16:24:36 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  |  | Prin Jitatisil | [8 empty] | 0 |  |  | For Info | Locate
AO-002121 | MM-ZTK-1F-GEN-PRC-UPO-5008 | UNPRICED PO FOR QUICK OPENING CLOSURE FOR TOPSIDE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 17-Sep-2026 13:33:13 | zm169dc@jutal.com | 18-Sep-2026 16:20:51 | Jumpol Sudjitjul |  | 17-Oct-2026 17:44:18 | Jirayu Pantito |  |  | Prin Jitatisil | [8 empty] | 0 |  |  | For Info | Locate
AO-002158 | MM-ZTK-1F-GEN-PRC-UPO-5009 | UNPRICED PO FOR SS DSS PIPE FOR TOPSIDE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 18-Sep-2026 16:53:11 | zm169dc@jutal.com | 20-Sep-2026 12:58:05 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  |  | Prin Jitatisil | [8 empty] | 0 |  |  | For Info | Locate
AO-002501 | MM-ZTK-1F-GEN-PRC-UPO-5010 | UNPRICED PO FOR PAINT(CUT-OFF DATE 12-OCT-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 12-Oct-2026 18:00:14 | zhaoli@jutal.com | 12-Oct-2026 18:15:44 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  |  | Prin Jitatisil | [8 empty] | 0 |  |  | For Info | Locate
AO-002524 | MM-ZTK-1F-GEN-PRC-UPO-5011 | UNPRICED PO FOR BOLTS AND NUTS (CUT-OFF DATE 14-OCT-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 14-Oct-2026 17:37:21 | zhaoli@jutal.com | 15-Oct-2026 11:20:45 | Jumpol Sudjitjul |  |  | Jirayu Pantito | [11 empty] | 0 |  |  | For Info | Locate
AO-002524 | MM-ZTK-1F-GEN-PRC-UPO-5012 | UNPRICED PO FOR PIPELINE BULK (B31.8)-PIPES (CUT-OFF DATE 14-OCT-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 14-Oct-2026 17:37:47 | zhaoli@jutal.com | 15-Oct-2026 11:21:52 | Jumpol Sudjitjul |  |  | Jirayu Pantito | [11 empty] | 0 |  |  | For Info | Locate
AO-001091 | MM-ZTK-1F-GEN-PRC-UPO-5101 | UNPRICED PO FOR PRIMARY STEEL SEAMLESS PIPES FOR TOPSIDE (CUT-OFF DATE 10-JUL-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 13-Jul-2026 10:00:20 | zm169dc@jutal.com | 13-Jul-2026 13:13:28 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 16-Aug-2026 12:23:03 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 17-Aug-2026 13:51:38 | 17-Aug-2026 07:12:35 | 0 |  |  | For Info | Locate
AO-001133 | MM-ZTK-1F-GEN-PRC-UPO-5201 | UNPRICED PO FOR PRIMARY STEEL BEAM FOR TOPSIDE(CUT-OFF DATE 15-JUL-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 16-Jul-2026 14:03:49 | zm169dc@jutal.com | 16-Jul-2026 14:10:05 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 16-Aug-2026 14:23:51 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 17-Aug-2026 13:55:39 | 17-Aug-2026 07:37:14 | 0 |  |  | For Info | Locate
AO-001234 | MM-ZTK-1F-GEN-PRC-UPO-5301 | UNPRICED PO FOR SECONDARY STEEL BEAM FOR TOPSIDE(CUT-OFF DATE 15-JUL-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 23-Jul-2026 18:08:29 | zm169dc@jutal.com | 24-Jul-2026 10:47:58 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 16-Aug-2026 14:28:32 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 17-Aug-2026 13:52:42 | 17-Aug-2026 07:13:56 | 0 |  |  | For Info | Locate
AO-001334 | MM-ZTK-1F-GEN-PRC-UPO-5401 | UNPRICED PO FOR TIMBER FOR LAUNCH CRADLE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 30-Jul-2026 12:35:13 | zm169dc@jutal.com | 30-Jul-2026 13:33:34 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 16-Aug-2026 12:02:26 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 17-Aug-2026 13:57:44 | 17-Aug-2026 07:19:51 | 0 |  |  | For Info | Locate
AO-001438 | MM-ZTK-1F-GEN-PRC-UPO-6001 | UNPRICED PO FOR TUBULAR ROLLING--PCK |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 06-Aug-2026 17:36:04 | zm169dc@jutal.com | 07-Aug-2026 10:11:59 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 16-Aug-2026 09:53:26 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 17-Aug-2026 13:54:16 | 17-Aug-2026 07:15:28 | 0 |  |  | For Info | Locate
AO-001438 | MM-ZTK-1F-GEN-PRC-UPO-6101 | UNPRICED PO FOR TUBULAR ROLLING--ZI JIN |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 06-Aug-2026 17:36:30 | zm169dc@jutal.com | 07-Aug-2026 10:12:22 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 16-Aug-2026 09:23:02 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 16-Aug-2026 09:46:59 | 16-Aug-2026 02:57:53 | 0 |  |  | For Info | Locate
AO-001808 | MM-ZTK-1F-GEN-PRC-UPO-9001 | UNPRICED PURCHASE ORDER FOR 18" LSAW LINE PIPE AND BEND MOTHER PIPES |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 01-Sep-2026 18:09:24 | 26002z1fdcc@thoresen-jutal.com | 02-Sep-2026 08:17:37 | Neeranuch Nutong |  |  | Jirayu Pantito |  | 07-Oct-2026 08:07:35 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 07-Oct-2026 08:16:08 | 07-Oct-2026 01:54:55 | 0 |  |  | For Info | Locate
AO-002257 | MM-ZTK-1F-GEN-PRC-UPO-9002 | UNPRICED PURCHASE ORDER FOR 10" SEAMLESS PIPE AND BEND MOTHER PIPES |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 25-Sep-2026 13:24:57 | 26002z1fdcc@thoresen-jutal.com | 25-Sep-2026 14:11:49 | Jumpol Sudjitjul |  | 17-Oct-2026 17:43:16 | Jirayu Pantito |  |  | Prin Jitatisil | [8 empty] | 0 |  |  | For Info | Locate
AO-002257 | MM-ZTK-1F-GEN-PRC-UPO-9003 | UNPRICED PURCHASE ORDER FOR CONCRETE WEIGHT COATING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 25-Sep-2026 13:25:31 | 26002z1fdcc@thoresen-jutal.com | 25-Sep-2026 14:09:16 | Jumpol Sudjitjul |  | 25-Sep-2026 14:53:46 | Jirayu Pantito |  |  | Prin Jitatisil | [8 empty] | 0 |  |  | For Info | Locate
AO-002257 | MM-ZTK-1F-GEN-PRC-UPO-9004 | UNPRICED PURCHASE ORDER FOR INDUCTION BENDS |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 25-Sep-2026 13:26:01 | 26002z1fdcc@thoresen-jutal.com | 25-Sep-2026 14:12:07 | Jumpol Sudjitjul |  | 17-Oct-2026 17:38:42 | Jirayu Pantito |  |  | Prin Jitatisil | [8 empty] | 0 |  |  | For Info | Locate
AO-002257 | MM-ZTK-1F-GEN-PRC-UPO-9005 | UNPRICED PURCHASE ORDER FOR PIPELINE EXTERNAL ANTI-CORROSION COATING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 25-Sep-2026 13:26:34 | 26002z1fdcc@thoresen-jutal.com | 25-Sep-2026 14:09:57 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  |  | Prin Jitatisil | [8 empty] | 0 |  |  | For Info | Locate
AO-002257 | MM-ZTK-1F-GEN-PRC-UPO-9006 | UNPRICED PURCHASE ORDER FOR RISER EXTERNAL ANTI-CORROSION COATING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 25-Sep-2026 13:27:21 | 26002z1fdcc@thoresen-jutal.com | 25-Sep-2026 14:10:19 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  |  | Prin Jitatisil | [8 empty] | 0 |  |  | For Info | Locate
AO-002370 | MM-ZTK-1F-GEN-PRC-UPO-9007 | UNPRICED PURCHASE ORDER FOR SACRIFICIAL BRACELET ANODE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 05-Oct-2026 10:43:58 | 26002z1fdcc@thoresen-jutal.com | 06-Oct-2026 08:47:03 | Jumpol Sudjitjul |  |  | Jirayu Pantito | [11 empty] | 0 |  |  | For Info | Locate
AO-002003 | MM-ZTK-1F-GEN-PRC-UPO-9008 | UNPRICED PURCHASE ORDER FOR FLANGES |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 11-Sep-2026 12:43:32 | 26002z1fdcc@thoresen-jutal.com | 11-Sep-2026 19:35:42 | Jumpol Sudjitjul |  |  | Jirayu Pantito | [11 empty] | 0 |  |  | For Info | Locate
AO-000068 | MM-ZTK-1F-GEN-PRO-BOD-0001 | PROCESS BASIS OF DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | BOD | Basis of Design | 0 | Submitted | IFR | Issued for Review |  | 02-Apr-2026 21:35:44 | zm169dc@jutal.com | 03-Apr-2026 07:02:58 | Jumpol Sudjitjul | 16-Apr-2026 |  | Chananun Rojanarungruengporn | 20-Apr-2026 | 10-Apr-2026 09:10:28 | Pornlert Wanaphattharaphan | 21-Apr-2026 | 20-Apr-2026 08:54:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Apr-2026 | 20-Apr-2026 09:16:32 | 20-Apr-2026 10:02:14 | 0 |  |  | Approver | Locate
AO-000570 | MM-ZTK-1F-GEN-PRO-BOD-0001 | PROCESS BASIS OF DESIGN |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 23-May-2026 08:55:36 | wisuda.c@jutal.com | 23-May-2026 09:34:50 | Jumpol Sudjitjul | 29-May-2026 |  | Chananun Rojanarungruengporn | 04-Jun-2026 | 02-Jun-2026 11:21:05 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:08:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 10:28:24 | 11-Jun-2026 03:57:28 | 0 |  |  | Approver | Locate
AO-001781 | MM-ZTK-1F-GEN-PRO-BOD-0001 | PROCESS BASIS OF DESIGN |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 31-Aug-2026 08:43:31 | wisuda.c@jutal.com | 31-Aug-2026 12:57:28 | Jumpol Sudjitjul | 07-Sep-2026 |  | Chananun Rojanarungruengporn | 09-Sep-2026 | 01-Sep-2026 08:26:15 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 07-Sep-2026 00:14:29 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 07-Sep-2026 11:44:49 | 07-Sep-2026 05:31:53 | 0 |  |  | Approver | Locate
AO-000265 | MM-ZTK-1F-GEN-PRO-BOD-0002 | FLOW ASSURANCE DESIGN BASIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | BOD | Basis of Design | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 18:31:30 | wisuda.c@jutal.com | 30-Apr-2026 10:17:12 | Jumpol Sudjitjul | 11-May-2026 |  | Chananun Rojanarungruengporn | 13-May-2026 | 13-May-2026 23:41:13 | Pornlert Wanaphattharaphan | 14-May-2026 | 20-May-2026 09:46:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 11:09:31 | 20-May-2026 11:30:47 | 0 |  |  | Approver | Locate
AO-000732 | MM-ZTK-1F-GEN-PRO-BOD-0002 | FLOW ASSURANCE DESIGN BASIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 10-Jun-2026 15:12:57 | wisuda.c@jutal.com | 10-Jun-2026 15:37:47 | Jumpol Sudjitjul | 17-Jun-2026 |  | Chananun Rojanarungruengporn | 19-Jun-2026 | 18-Jun-2026 09:35:39 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 21-Jun-2026 07:54:18 | APPR | Approved | Jumpol Sudjitjul | 23-Jun-2026 | 22-Jun-2026 12:54:41 | 22-Jun-2026 06:44:46 | 0 |  |  | Approver | Locate
AO-001246 | MM-ZTK-1F-GEN-PRO-BOD-0002 | FLOW ASSURANCE DESIGN BASIS |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 10:49:19 | wisuda.c@jutal.com | 24-Jul-2026 11:31:39 | Jumpol Sudjitjul | 04-Aug-2026 | 05-Aug-2026 15:54:15 | Chananun Rojanarungruengporn | 06-Aug-2026 | 06-Aug-2026 15:52:11 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 07-Aug-2026 05:41:21 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 07-Aug-2026 08:52:16 | 07-Aug-2026 02:19:56 | 0 |  |  | Approver | Locate
AO-000070 | MM-ZTK-1F-GEN-PRO-CAL-0001 | PROCESS CALCULATION NOTE FOR LINE SIZING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 03-Apr-2026 15:00:51 | zm169dc@jutal.com | 05-Apr-2026 07:29:31 | Jumpol Sudjitjul | 16-Apr-2026 |  | Chananun Rojanarungruengporn | 20-Apr-2026 | 10-Apr-2026 16:30:56 | Pornlert Wanaphattharaphan | 21-Apr-2026 | 19-Apr-2026 23:24:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Apr-2026 | 20-Apr-2026 08:09:14 | 20-Apr-2026 08:40:16 | 0 |  |  | Approver | Locate
AO-000625 | MM-ZTK-1F-GEN-PRO-CAL-0001 | PROCESS CALCULATION NOTE FOR LINE SIZING |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 29-May-2026 16:25:20 | wisuda.c@jutal.com | 29-May-2026 16:39:54 | Jumpol Sudjitjul | 09-Jun-2026 |  | Chananun Rojanarungruengporn | 11-Jun-2026 | 05-Jun-2026 13:25:48 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 10-Jun-2026 21:30:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 11-Jun-2026 10:36:58 | 11-Jun-2026 04:09:06 | 0 |  |  | Approver | Locate
AO-001881 | MM-ZTK-1F-GEN-PRO-CAL-0001 | PROCESS CALCULATION NOTE FOR LINE SIZING |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 04-Sep-2026 16:16:48 | wisuda.c@jutal.com | 05-Sep-2026 19:34:07 | Jumpol Sudjitjul | 14-Sep-2026 |  | Chananun Rojanarungruengporn | 16-Sep-2026 | 07-Sep-2026 11:25:31 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 13-Sep-2026 17:09:45 | APPR | Approved | Jumpol Sudjitjul | 18-Sep-2026 | 13-Sep-2026 23:09:22 | 13-Sep-2026 17:17:04 | 0 |  |  | Approver | Locate
AO-000072 | MM-ZTK-1F-GEN-PRO-CAL-0002 | PROCESS CALCULATION NOTE FOR TEST SEPARATOR |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 03-Apr-2026 15:01:20 | zm169dc@jutal.com | 05-Apr-2026 07:28:20 | Jumpol Sudjitjul | 16-Apr-2026 |  | Chananun Rojanarungruengporn | 20-Apr-2026 | 09-Apr-2026 09:37:07 | Pornlert Wanaphattharaphan | 21-Apr-2026 | 24-Apr-2026 00:08:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Apr-2026 | 24-Apr-2026 08:19:56 | 24-Apr-2026 08:46:03 | 0 |  |  | Approver | Locate
AO-000626 | MM-ZTK-1F-GEN-PRO-CAL-0002 | PROCESS CALCULATION NOTE FOR TEST SEPARATOR |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 29-May-2026 17:08:19 | wisuda.c@jutal.com | 29-May-2026 17:24:06 | Jumpol Sudjitjul | 10-Jun-2026 |  | Chananun Rojanarungruengporn | 12-Jun-2026 | 05-Jun-2026 14:34:26 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 10-Jun-2026 21:37:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 11-Jun-2026 10:39:35 | 11-Jun-2026 04:03:42 | 0 |  |  | Approver | Locate
AO-001819 | MM-ZTK-1F-GEN-PRO-CAL-0002 | PROCESS CALCULATION NOTE FOR TEST SEPARATOR |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 18:23:33 | wisuda.c@jutal.com | 03-Sep-2026 11:23:22 | Jumpol Sudjitjul | 10-Sep-2026 |  | Chananun Rojanarungruengporn | 14-Sep-2026 | 07-Sep-2026 11:21:44 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 15:41:37 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 12-Sep-2026 20:41:42 | 12-Sep-2026 13:54:58 | 0 |  |  | Approver | Locate
AO-000504 | MM-ZTK-1F-GEN-PRO-CAL-0003 | PROCESS CALCULATION NOTE FOR INSTRUMENT GAS FILTER COALESCER AND STANDPIPE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 18-May-2026 19:38:22 | wisuda.c@jutal.com | 19-May-2026 17:05:47 | Jumpol Sudjitjul | 27-May-2026 |  | Chananun Rojanarungruengporn | 29-May-2026 | 28-May-2026 15:22:50 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 10-Jun-2026 21:01:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Jun-2026 | 11-Jun-2026 10:44:35 | 11-Jun-2026 04:05:13 | 0 |  |  | Approver | Locate
AO-002543 | MM-ZTK-1F-GEN-PRO-CAL-0003 | PROCESS CALCULATION NOTE FOR INSTRUMENT GAS FILTER COALESCER AND STANDPIPE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | In Review | AFC | Approved for Construction |  | 16-Oct-2026 10:13:50 | wisuda.c@jutal.com | 16-Oct-2026 16:18:30 | Jumpol Sudjitjul | 26-Oct-2026 | 17-Oct-2026 17:35:54 | Chananun Rojanarungruengporn | 28-Oct-2026 |  | Pornlert Wanaphattharaphan | 29-Oct-2026 |  |  |  |  | 30-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000104 | MM-ZTK-1F-GEN-PRO-CAL-0004 | PROCESS CALCULATION NOTE FOR CORROSION INHIBITOR TANK AND PUMP |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 09-Apr-2026 16:28:48 | zm169dc@jutal.com | 10-Apr-2026 15:27:48 | Jumpol Sudjitjul | 22-Apr-2026 |  | Chananun Rojanarungruengporn | 24-Apr-2026 | 20-Apr-2026 17:07:07 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 25-Apr-2026 23:52:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 27-Apr-2026 16:16:14 | 27-Apr-2026 17:24:04 | 0 |  |  | Approver | Locate
AO-000673 | MM-ZTK-1F-GEN-PRO-CAL-0004 | PROCESS CALCULATION NOTE FOR CORROSION INHIBITOR TANK AND PUMP |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 04-Jun-2026 20:47:26 | wisuda.c@jutal.com | 04-Jun-2026 21:21:22 | Jumpol Sudjitjul | 12-Jun-2026 |  | Chananun Rojanarungruengporn | 16-Jun-2026 | 16-Jun-2026 09:08:47 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 18-Jun-2026 10:04:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 10:24:36 | 18-Jun-2026 04:23:59 | 0 |  |  | Approver | Locate
AO-002357 | MM-ZTK-1F-GEN-PRO-CAL-0004 | PROCESS CALCULATION NOTE FOR CORROSION INHIBITOR TANK AND PUMP |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 09:40:35 | wisuda.c@jutal.com | 06-Oct-2026 08:43:25 | Jumpol Sudjitjul | 14-Oct-2026 |  | Chananun Rojanarungruengporn | 16-Oct-2026 | 07-Oct-2026 08:46:34 | Pornlert Wanaphattharaphan | 19-Oct-2026 | 11-Oct-2026 00:09:51 | APPR | Approved | Jumpol Sudjitjul | 20-Oct-2026 | 11-Oct-2026 09:58:18 | 11-Oct-2026 03:26:22 | 0 |  |  | Approver | Locate
AO-000105 | MM-ZTK-1F-GEN-PRO-CAL-0005 | PROCESS CALCULATION NOTE FOR BIOCIDE TANK AND PUMP |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 10-Apr-2026 10:20:28 | zm169dc@jutal.com | 10-Apr-2026 15:23:33 | Jumpol Sudjitjul | 22-Apr-2026 |  | Chananun Rojanarungruengporn | 24-Apr-2026 | 20-Apr-2026 17:07:57 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 25-Apr-2026 22:58:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 27-Apr-2026 16:15:23 | 27-Apr-2026 17:26:23 | 0 |  |  | Approver | Locate
AO-000636 | MM-ZTK-1F-GEN-PRO-CAL-0005 | PROCESS CALCULATION NOTE FOR BIOCIDE TANK AND PUMP |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 29-May-2026 20:51:47 | wisuda.c@jutal.com | 31-May-2026 21:07:56 | Jumpol Sudjitjul | 10-Jun-2026 |  | Chananun Rojanarungruengporn | 12-Jun-2026 | 11-Jun-2026 14:27:56 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 14-Jun-2026 00:19:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 14-Jun-2026 21:44:18 | 14-Jun-2026 15:14:50 | 0 |  |  | Approver | Locate
AO-002358 | MM-ZTK-1F-GEN-PRO-CAL-0005 | PROCESS CALCULATION NOTE FOR BIOCIDE TANK AND PUMP |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 09:41:16 | wisuda.c@jutal.com | 06-Oct-2026 08:43:49 | Jumpol Sudjitjul | 14-Oct-2026 |  | Chananun Rojanarungruengporn | 16-Oct-2026 | 07-Oct-2026 08:31:46 | Pornlert Wanaphattharaphan | 19-Oct-2026 | 11-Oct-2026 00:08:05 | APPR | Approved | Jumpol Sudjitjul | 20-Oct-2026 | 11-Oct-2026 09:58:51 | 11-Oct-2026 03:27:33 | 0 |  |  | Approver | Locate
AO-000235 | MM-ZTK-1F-GEN-PRO-CAL-0007 | PROCESS CALCULATION NOTE FOR CLOSED DRAIN SUMP VESSEL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 16:39:57 | wisuda.c@jutal.com | 28-Apr-2026 08:48:43 | Jumpol Sudjitjul | 07-May-2026 |  | Chananun Rojanarungruengporn | 11-May-2026 | 11-May-2026 23:40:54 | Pornlert Wanaphattharaphan | 12-May-2026 | 15-May-2026 01:06:13 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 13-May-2026 | 15-May-2026 10:37:11 | 15-May-2026 04:21:25 | 0 |  |  | Approver | Locate
AO-001080 | MM-ZTK-1F-GEN-PRO-CAL-0007 | PROCESS CALCULATION NOTE FOR CLOSED DRAIN SUMP VESSEL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 12-Jul-2026 11:40:55 | wisuda.c@jutal.com | 12-Jul-2026 12:07:03 | Jumpol Sudjitjul | 17-Jul-2026 |  | Chananun Rojanarungruengporn | 21-Jul-2026 | 15-Jul-2026 21:42:45 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 20-Jul-2026 02:55:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 20-Jul-2026 09:05:59 | 20-Jul-2026 03:34:58 | 0 |  |  | Approver | Locate
AO-002331 | MM-ZTK-1F-GEN-PRO-CAL-0007 | PROCESS CALCULATION NOTE FOR CLOSED DRAIN SUMP VESSEL |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 01-Oct-2026 18:03:23 | wisuda.c@jutal.com | 02-Oct-2026 14:16:49 | Jumpol Sudjitjul | 09-Oct-2026 |  | Chananun Rojanarungruengporn | 14-Oct-2026 | 07-Oct-2026 08:42:22 | Pornlert Wanaphattharaphan | 15-Oct-2026 | 10-Oct-2026 01:52:41 | APPR | Approved | Jumpol Sudjitjul | 16-Oct-2026 | 10-Oct-2026 17:29:44 | 10-Oct-2026 11:29:04 | 0 |  |  | Approver | Locate
AO-000113 | MM-ZTK-1F-GEN-PRO-CAL-0008 | PROCESS CALCULATION NOTE FOR CLOSED DRAIN SUMP PUMP |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 10-Apr-2026 17:41:37 | zm169dc@jutal.com | 11-Apr-2026 15:53:03 | Jumpol Sudjitjul | 22-Apr-2026 |  | Chananun Rojanarungruengporn | 24-Apr-2026 | 21-Apr-2026 13:53:01 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 26-Apr-2026 00:16:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 27-Apr-2026 16:14:17 | 27-Apr-2026 09:19:59 | 0 |  |  | Approver | Locate
AO-001081 | MM-ZTK-1F-GEN-PRO-CAL-0008 | PROCESS CALCULATION NOTE FOR CLOSED DRAIN SUMP PUMP |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 12-Jul-2026 11:41:24 | wisuda.c@jutal.com | 12-Jul-2026 12:07:17 | Jumpol Sudjitjul | 17-Jul-2026 |  | Chananun Rojanarungruengporn | 21-Jul-2026 | 15-Jul-2026 21:51:08 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 20-Jul-2026 02:59:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 20-Jul-2026 09:06:26 | 20-Jul-2026 03:36:20 | 0 |  |  | Approver | Locate
AO-001984 | MM-ZTK-1F-GEN-PRO-CAL-0008 | PROCESS CALCULATION NOTE FOR CLOSED DRAIN SUMP PUMP |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 19:58:47 | wisuda.c@jutal.com | 10-Sep-2026 20:11:03 | Jumpol Sudjitjul | 18-Sep-2026 |  | Chananun Rojanarungruengporn | 22-Sep-2026 | 14-Sep-2026 11:01:54 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 19-Sep-2026 21:36:59 | APPR | Approved | Jumpol Sudjitjul | 24-Sep-2026 | 20-Sep-2026 17:13:10 | 20-Sep-2026 11:57:25 | 0 |  |  | Approver | Locate
AO-000071 | MM-ZTK-1F-GEN-PRO-CAL-0101 | PROCESS CALCULATION NOTE FOR CHOKE VALVE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 03-Apr-2026 15:02:06 | zm169dc@jutal.com | 05-Apr-2026 07:30:23 | Jumpol Sudjitjul | 16-Apr-2026 |  | Chananun Rojanarungruengporn | 20-Apr-2026 | 17-Apr-2026 16:01:56 | Pornlert Wanaphattharaphan | 21-Apr-2026 | 20-Apr-2026 01:16:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Apr-2026 | 20-Apr-2026 08:10:26 | 20-Apr-2026 08:41:30 | 0 |  |  | Approver | Locate
AO-000747 | MM-ZTK-1F-GEN-PRO-CAL-0101 | PROCESS CALCULATION NOTE FOR CHOKE VALVE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 12-Jun-2026 08:41:45 | wisuda.c@jutal.com | 12-Jun-2026 14:21:38 | Jumpol Sudjitjul | 19-Jun-2026 |  | Chananun Rojanarungruengporn | 23-Jun-2026 | 22-Jun-2026 22:36:27 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 23:00:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 13:35:15 | 25-Jun-2026 07:07:28 | 0 |  |  | Approver | Locate
AO-001882 | MM-ZTK-1F-GEN-PRO-CAL-0101 | PROCESS CALCULATION NOTE FOR CHOKE VALVE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 04-Sep-2026 16:17:16 | wisuda.c@jutal.com | 05-Sep-2026 19:34:38 | Jumpol Sudjitjul | 14-Sep-2026 |  | Chananun Rojanarungruengporn | 16-Sep-2026 | 07-Sep-2026 10:57:09 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 13-Sep-2026 17:08:32 | APPR | Approved | Jumpol Sudjitjul | 18-Sep-2026 | 13-Sep-2026 23:10:35 | 13-Sep-2026 17:18:12 | 0 |  |  | Approver | Locate
AO-000210 | MM-ZTK-1F-GEN-PRO-CAL-0102 | PROCESS CALCULATION NOTE FOR CONTROL VALVE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 23-Apr-2026 10:59:21 | wisuda.c@jutal.com | 23-Apr-2026 11:04:20 | Jumpol Sudjitjul | 30-Apr-2026 |  | Chananun Rojanarungruengporn | 06-May-2026 | 30-Apr-2026 13:39:57 | Pornlert Wanaphattharaphan | 07-May-2026 | 08-May-2026 23:11:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-May-2026 | 09-May-2026 08:18:07 | 09-May-2026 01:34:09 | 0 |  |  | Approver | Locate
AO-000927 | MM-ZTK-1F-GEN-PRO-CAL-0102 | PROCESS CALCULATION NOTE FOR CONTROL VALVE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 27-Jun-2026 19:10:49 | wisuda.c@jutal.com | 27-Jun-2026 19:27:52 | Jumpol Sudjitjul | 06-Jul-2026 |  | Chananun Rojanarungruengporn | 08-Jul-2026 | 07-Jul-2026 08:37:35 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 11-Jul-2026 13:59:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 12-Jul-2026 11:32:08 | 12-Jul-2026 04:55:27 | 0 |  |  | Approver | Locate
AO-002286 | MM-ZTK-1F-GEN-PRO-CAL-0102 | PROCESS CALCULATION NOTE FOR CONTROL VALVE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 09:54:14 | wisuda.c@jutal.com | 28-Sep-2026 10:23:08 | Jumpol Sudjitjul | 05-Oct-2026 |  | Chananun Rojanarungruengporn | 07-Oct-2026 | 29-Sep-2026 08:21:41 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:09:44 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 13:08:29 | 30-Sep-2026 06:24:27 | 0 |  |  | Approver | Locate
AO-000211 | MM-ZTK-1F-GEN-PRO-CAL-0103 | PROCESS CALCULATION NOTE FOR RESTRICTION ORIFICE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 23-Apr-2026 10:59:55 | wisuda.c@jutal.com | 23-Apr-2026 11:04:42 | Jumpol Sudjitjul | 30-Apr-2026 |  | Chananun Rojanarungruengporn | 06-May-2026 | 06-May-2026 15:56:10 | Pornlert Wanaphattharaphan | 07-May-2026 | 08-May-2026 23:22:18 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 08-May-2026 | 09-May-2026 08:19:52 | 09-May-2026 01:35:27 | 0 |  |  | Approver | Locate
AO-001179 | MM-ZTK-1F-GEN-PRO-CAL-0103 | PROCESS CALCULATION NOTE FOR RESTRICTION ORIFICE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 10:41:37 | wisuda.c@jutal.com | 20-Jul-2026 15:04:22 | Jumpol Sudjitjul | 27-Jul-2026 |  | Chananun Rojanarungruengporn | 31-Jul-2026 | 21-Jul-2026 15:54:45 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 12:28:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:53:47 | 27-Jul-2026 08:46:44 | 0 |  |  | Approver | Locate
AO-002384 | MM-ZTK-1F-GEN-PRO-CAL-0103 | PROCESS CALCULATION NOTE FOR RESTRICTION ORIFICE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 18:31:20 | wisuda.c@jutal.com | 06-Oct-2026 08:44:07 | Jumpol Sudjitjul | 14-Oct-2026 |  | Chananun Rojanarungruengporn | 16-Oct-2026 | 07-Oct-2026 08:33:52 | Pornlert Wanaphattharaphan | 19-Oct-2026 | 11-Oct-2026 00:09:13 | APPR | Approved | Jumpol Sudjitjul | 20-Oct-2026 | 11-Oct-2026 09:59:27 | 11-Oct-2026 03:47:19 | 0 |  |  | Approver | Locate
AO-000114 | MM-ZTK-1F-GEN-PRO-CAL-0104 | PROCESS CALCULATION NOTE FOR PSV |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 10-Apr-2026 17:42:19 | zm169dc@jutal.com | 11-Apr-2026 15:54:07 | Jumpol Sudjitjul | 22-Apr-2026 |  | Chananun Rojanarungruengporn | 24-Apr-2026 | 16-Apr-2026 16:11:19 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 20-Apr-2026 01:20:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 20-Apr-2026 08:11:39 | 20-Apr-2026 08:32:32 | 0 |  |  | Approver | Locate
AO-000854 | MM-ZTK-1F-GEN-PRO-CAL-0104 | PROCESS CALCULATION NOTE FOR PSV |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 21-Jun-2026 22:45:29 | wisuda.c@jutal.com | 22-Jun-2026 14:18:20 | Jumpol Sudjitjul | 29-Jun-2026 |  | Chananun Rojanarungruengporn | 01-Jul-2026 | 01-Jul-2026 22:49:38 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 03-Jul-2026 00:47:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 03-Jul-2026 11:09:19 | 03-Jul-2026 04:56:40 | 0 |  |  | Approver | Locate
AO-001986 | MM-ZTK-1F-GEN-PRO-CAL-0104 | PROCESS CALCULATION NOTE FOR PSV |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 19:59:20 | wisuda.c@jutal.com | 10-Sep-2026 20:11:25 | Jumpol Sudjitjul | 18-Sep-2026 |  | Chananun Rojanarungruengporn | 22-Sep-2026 | 14-Sep-2026 10:49:56 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 19-Sep-2026 21:39:44 | APPR | Approved | Jumpol Sudjitjul | 24-Sep-2026 | 20-Sep-2026 17:13:47 | 20-Sep-2026 11:58:38 | 0 |  |  | Approver | Locate
AO-000396 | MM-ZTK-1F-GEN-PRO-MOM-0001 | WHP TOPSIDE DETAIL ENGINEERING DESIGN: WEEKLY PROCESS MEETING |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-May-2026 11:04:44 | jumpols@pttep.com | [16 empty] | 0 |  |  |  | Locate
AO-000879 | MM-ZTK-1F-GEN-PRO-MOM-0002 | WHP TOPSIDE DETAIL ENGINEERING DESIGN: WEEKLY PROCESS MEETING |  | - | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 23-Jun-2026 17:58:06 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002109 | MM-ZTK-1F-GEN-PRO-MOM-0003 | WHP TOPSIDE DETAIL ENGINEERING DESIGN: WEEKLY PROCESS MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 17-Sep-2026 10:41:11 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000756 | MM-ZTK-1F-GEN-PRO-PHI-0001 | OPERATING, CONTROL, SHUTDOWN AND BLACK START PHILOSOPHY |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | PHI | Philosophy | 0 | Submitted | IFR | Issued for Review |  | 12-Jun-2026 10:01:21 | wisuda.c@jutal.com | 12-Jun-2026 13:22:21 | Jumpol Sudjitjul | 19-Jun-2026 |  | Chananun Rojanarungruengporn | 23-Jun-2026 | 24-Jun-2026 10:58:43 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 24-Jun-2026 23:13:58 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 25-Jun-2026 | 25-Jun-2026 13:35:56 | 25-Jun-2026 07:59:12 | 0 |  |  | Approver | Locate
AO-001784 | MM-ZTK-1F-GEN-PRO-PHI-0001 | OPERATING, CONTROL, SHUTDOWN AND BLACK START PHILOSOPHY |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | PHI | Philosophy | 0 | Submitted | AFC | Approved for Construction |  | 31-Aug-2026 09:45:49 | wisuda.c@jutal.com | 31-Aug-2026 13:00:52 | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 23:54:15 | Chananun Rojanarungruengporn | 09-Sep-2026 | 10-Sep-2026 14:43:47 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 12-Sep-2026 14:49:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 12-Sep-2026 20:53:48 | 12-Sep-2026 14:28:36 | 0 |  |  | Approver | Locate
AO-000930 | MM-ZTK-1F-GEN-PRO-PHI-0004 | PROCESS CONTROL NARRATIVE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | PHI | Philosophy | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 19:11:18 | wisuda.c@jutal.com | 27-Jun-2026 19:29:47 | Jumpol Sudjitjul | 06-Jul-2026 |  | Chananun Rojanarungruengporn | 08-Jul-2026 | 09-Jul-2026 20:19:15 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 11-Jul-2026 13:59:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 12-Jul-2026 11:32:33 | 12-Jul-2026 04:57:53 | 0 |  |  | Approver | Locate
AO-002214 | MM-ZTK-1F-GEN-PRO-PHI-0004 | PROCESS CONTROL NARRATIVE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | PHI | Philosophy | 0 | Submitted | AFC | Approved for Construction |  | 22-Sep-2026 18:01:37 | wisuda.c@jutal.com | 23-Sep-2026 13:53:45 | Jumpol Sudjitjul | 30-Sep-2026 |  | Chananun Rojanarungruengporn | 02-Oct-2026 | 05-Oct-2026 08:18:17 | Pornlert Wanaphattharaphan | 05-Oct-2026 | 10-Oct-2026 00:17:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Oct-2026 | 10-Oct-2026 17:30:18 | 10-Oct-2026 11:05:28 | 0 |  |  | Approver | Locate
AO-000243 | MM-ZTK-1F-GEN-PRO-RPT-0001 | PROCESS SIMULATION REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 28-Apr-2026 13:59:03 | zm169dc@jutal.com | 28-Apr-2026 15:23:12 | Jumpol Sudjitjul | 07-May-2026 |  | Chananun Rojanarungruengporn | 11-May-2026 | 10-May-2026 15:09:59 | Pornlert Wanaphattharaphan | 12-May-2026 | 15-May-2026 00:38:37 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 13-May-2026 | 15-May-2026 10:35:23 | 15-May-2026 11:16:14 | 0 |  |  | Approver | Locate
AO-000582 | MM-ZTK-1F-GEN-PRO-RPT-0001 | PROCESS SIMULATION REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 23-May-2026 08:56:05 | wisuda.c@jutal.com | 23-May-2026 09:35:43 | Jumpol Sudjitjul | 29-May-2026 |  | Chananun Rojanarungruengporn | 04-Jun-2026 | 29-May-2026 14:13:07 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:07:12 | APPR | Approved | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 10:49:41 | 11-Jun-2026 03:58:39 | 0 |  |  | Approver | Locate
AO-000244 | MM-ZTK-1F-GEN-PRO-RPT-0002 | UTILITY BALANCE REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 28-Apr-2026 13:59:31 | zm169dc@jutal.com | 28-Apr-2026 15:23:38 | Jumpol Sudjitjul | 07-May-2026 |  | Chananun Rojanarungruengporn | 11-May-2026 | 11-May-2026 11:08:20 | Pornlert Wanaphattharaphan | 12-May-2026 | 15-May-2026 00:41:35 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 13-May-2026 | 15-May-2026 10:33:27 | 15-May-2026 04:14:58 | 0 |  |  | Approver | Locate
AO-001653 | MM-ZTK-1F-GEN-PRO-RPT-0002 | UTILITY BALANCE REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 18:45:07 | wisuda.c@jutal.com | 24-Aug-2026 18:39:48 | Jumpol Sudjitjul | 01-Sep-2026 | 31-Aug-2026 16:28:22 | Chananun Rojanarungruengporn | 03-Sep-2026 | 01-Sep-2026 08:12:00 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:14:48 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 11:47:19 | 07-Sep-2026 05:24:56 | 0 |  |  | Approver | Locate
AO-000370 | MM-ZTK-1F-GEN-PRO-RPT-0003 | INSTRUMENT GAS VERIFICATION REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 13:26:47 | wisuda.c@jutal.com | 11-May-2026 13:50:17 | Jumpol Sudjitjul | 18-May-2026 |  | Chananun Rojanarungruengporn | 20-May-2026 | 20-May-2026 16:44:05 | Pornlert Wanaphattharaphan | 21-May-2026 | 27-May-2026 20:12:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 28-May-2026 08:43:29 | 28-May-2026 01:57:20 | 0 |  |  | Approver | Locate
AO-001886 | MM-ZTK-1F-GEN-PRO-RPT-0003 | INSTRUMENT GAS VERIFICATION REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 04-Sep-2026 16:17:43 | wisuda.c@jutal.com | 05-Sep-2026 19:33:16 | Jumpol Sudjitjul | 14-Sep-2026 | 14-Sep-2026 09:45:44 | Chananun Rojanarungruengporn | 16-Sep-2026 | 14-Sep-2026 10:45:17 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 19-Sep-2026 00:08:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 20-Sep-2026 17:14:31 | 20-Sep-2026 11:34:36 | 0 |  |  | Approver | Locate
AO-002476 | MM-ZTK-1F-GEN-PRO-RPT-0003 | INSTRUMENT GAS VERIFICATION REPORT |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 12-Oct-2026 12:09:42 | wisuda.c@jutal.com | 12-Oct-2026 13:42:57 | Jumpol Sudjitjul | 20-Oct-2026 |  | Chananun Rojanarungruengporn | 22-Oct-2026 | 13-Oct-2026 13:07:50 | Pornlert Wanaphattharaphan | 26-Oct-2026 | 13-Oct-2026 14:43:59 | APPR | Approved | Jumpol Sudjitjul | 27-Oct-2026 | 14-Oct-2026 16:38:37 | 14-Oct-2026 10:23:24 | 0 |  |  | Approver | Locate
AO-000389 | MM-ZTK-1F-GEN-PRO-RPT-0004 | VENT AND RELIEF LOAD REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 13-May-2026 15:36:38 | wisuda.c@jutal.com | 13-May-2026 15:53:06 | Jumpol Sudjitjul | 20-May-2026 |  | Chananun Rojanarungruengporn | 22-May-2026 | 22-May-2026 14:53:45 | Pornlert Wanaphattharaphan | 25-May-2026 | 31-May-2026 13:56:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-May-2026 | 31-May-2026 20:53:39 | 31-May-2026 14:27:48 | 0 |  |  | Approver | Locate
AO-002146 | MM-ZTK-1F-GEN-PRO-RPT-0004 | VENT AND RELIEF LOAD REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:13:37 | wisuda.c@jutal.com | 18-Sep-2026 17:19:57 | Jumpol Sudjitjul | 28-Sep-2026 |  | Chananun Rojanarungruengporn | 30-Sep-2026 | 23-Sep-2026 13:27:26 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 26-Sep-2026 05:47:19 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 26-Sep-2026 14:12:10 | 26-Sep-2026 07:50:57 | 0 |  |  | Approver | Locate
AO-000587 | MM-ZTK-1F-GEN-PRO-RPT-0005 | DEPRESSURIZATION AND LOW TEMPERATURE STUDY REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 24-May-2026 15:31:03 | wisuda.c@jutal.com | 24-May-2026 20:52:15 | Jumpol Sudjitjul | 02-Jun-2026 |  | Chananun Rojanarungruengporn | 05-Jun-2026 | 05-Jun-2026 12:16:13 | Pornlert Wanaphattharaphan | 08-Jun-2026 | 10-Jun-2026 21:21:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jun-2026 | 11-Jun-2026 10:52:37 | 11-Jun-2026 04:06:36 | 0 |  |  | Approver | Locate
AO-002145 | MM-ZTK-1F-GEN-PRO-RPT-0005 | DEPRESSURIZATION AND LOW TEMPERATURE STUDY REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:14:24 | wisuda.c@jutal.com | 18-Sep-2026 17:20:13 | Jumpol Sudjitjul | 28-Sep-2026 | 28-Sep-2026 23:59:19 | Chananun Rojanarungruengporn | 30-Sep-2026 | 30-Sep-2026 16:52:12 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 01-Oct-2026 20:43:47 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 02-Oct-2026 13:20:55 | 02-Oct-2026 07:33:46 | 0 |  |  | Approver | Locate
AO-000494 | MM-ZTK-1F-GEN-PRO-RPT-0006 | ACOUSTIC INDUCED VIBRATION (AIV) AND FLOW INDUCED VIBRATION (FIV) STUDY REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 17-May-2026 00:16:42 | wisuda.c@jutal.com | 18-May-2026 19:44:54 | Jumpol Sudjitjul | 26-May-2026 |  | Chananun Rojanarungruengporn | 28-May-2026 | 27-May-2026 17:17:53 | Pornlert Wanaphattharaphan | 29-May-2026 | 10-Jun-2026 20:59:10 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 02-Jun-2026 | 11-Jun-2026 11:04:09 | 11-Jun-2026 04:59:34 | 0 |  |  | Approver | Locate
AO-002317 | MM-ZTK-1F-GEN-PRO-RPT-0006 | ACOUSTIC INDUCED VIBRATION (AIV) AND FLOW INDUCED VIBRATION (FIV) STUDY REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 30-Sep-2026 14:04:20 | wisuda.c@jutal.com | 30-Sep-2026 16:09:38 | Jumpol Sudjitjul | 07-Oct-2026 |  | Chananun Rojanarungruengporn | 09-Oct-2026 | 05-Oct-2026 08:46:20 | Pornlert Wanaphattharaphan | 12-Oct-2026 | 10-Oct-2026 01:41:15 | APPR | Approved | Jumpol Sudjitjul | 14-Oct-2026 | 10-Oct-2026 17:40:37 | 10-Oct-2026 11:00:30 | 0 |  |  | Approver | Locate
AO-000899 | MM-ZTK-1F-GEN-PRO-RPT-0007 | FLOW ASSURANCE REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 25-Jun-2026 23:17:32 | wisuda.c@jutal.com | 26-Jun-2026 09:19:47 | Jumpol Sudjitjul | 03-Jul-2026 | 07-Jul-2026 16:10:39 | Chananun Rojanarungruengporn | 07-Jul-2026 | 08-Jul-2026 22:53:10 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 11-Jul-2026 13:30:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 12-Jul-2026 11:33:04 | 12-Jul-2026 05:24:21 | 0 |  |  | Approver | Locate
AO-001247 | MM-ZTK-1F-GEN-PRO-RPT-0007 | FLOW ASSURANCE REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | PRO | Process | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 10:49:54 | wisuda.c@jutal.com | 24-Jul-2026 11:34:26 | Jumpol Sudjitjul | 04-Aug-2026 | 05-Aug-2026 09:52:56 | Chananun Rojanarungruengporn | 06-Aug-2026 | 06-Aug-2026 15:32:57 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 07-Aug-2026 05:40:41 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 07-Aug-2026 08:50:14 | 07-Aug-2026 02:18:39 | 0 |  |  | Approver | Locate
AO-000394 | MM-ZTK-1F-GEN-QAC-ITP-5001 | INSPECTION AND TEST PLAN - STRUCTURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | ITP | Inspection And Test Plan | 0 | Submitted | IFR | Issued for Review |  | 14-May-2026 09:52:49 | zm169dc@jutal.com | 14-May-2026 13:12:22 | Jumpol Sudjitjul | 21-May-2026 | 21-May-2026 09:59:08 | Poramate Kamlangkeng | 25-May-2026 | 01-Jun-2026 09:52:40 | Prin Jitatisil | 26-May-2026 | 04-Jun-2026 17:02:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-May-2026 | 04-Jun-2026 18:26:28 | 04-Jun-2026 14:31:58 | 0 |  |  | Approver | Locate
AO-001265 | MM-ZTK-1F-GEN-QAC-ITP-5001 | INSPECTION AND TEST PLAN - STRUCTURE |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | ITP | Inspection And Test Plan | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 17:37:39 | zm169dc@jutal.com | 26-Jul-2026 23:50:14 | Jumpol Sudjitjul | 05-Aug-2026 | 27-Jul-2026 09:48:35 | Poramate Kamlangkeng | 07-Aug-2026 | 30-Jul-2026 11:14:27 | Prin Jitatisil | 10-Aug-2026 | 30-Jul-2026 12:24:42 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-Aug-2026 | 30-Jul-2026 14:07:40 | 30-Jul-2026 07:32:58 | 0 |  |  | Approver | Locate
AO-001723 | MM-ZTK-1F-GEN-QAC-ITP-5001 | INSPECTION AND TEST PLAN - STRUCTURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | ITP | Inspection And Test Plan | 0 | Submitted | AFC | Approved for Construction |  | 26-Aug-2026 19:21:19 | zm169dc@jutal.com | 27-Aug-2026 11:24:38 | Jumpol Sudjitjul | 03-Sep-2026 | 28-Aug-2026 09:53:43 | Poramate Kamlangkeng | 07-Sep-2026 | 31-Aug-2026 12:56:24 | Prin Jitatisil | 08-Sep-2026 | 31-Aug-2026 14:29:31 | APPR | Approved | Jumpol Sudjitjul | 09-Sep-2026 | 31-Aug-2026 15:49:40 | 31-Aug-2026 10:40:04 | 0 |  |  | Approver | Locate
AO-001272 | MM-ZTK-1F-GEN-QAC-ITP-5002 | INSPECTION AND TEST PLAN - PIPING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | ITP | Inspection And Test Plan | 0 | Submitted | IFR | Issued for Review |  | 25-Jul-2026 09:16:24 | zm169dc@jutal.com | 27-Jul-2026 09:26:05 | Jumpol Sudjitjul | 05-Aug-2026 | 27-Jul-2026 09:50:21 | Poramate Kamlangkeng | 07-Aug-2026 | 30-Jul-2026 10:45:15 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 30-Jul-2026 18:18:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 30-Jul-2026 19:14:47 | 30-Jul-2026 12:36:15 | 0 |  |  | Approver | Locate
AO-000990 | MM-ZTK-1F-GEN-QAC-ITP-8001 | PROJECT INSPECT & TEST PLAN FOR WHP T&I |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | ITP | Inspection And Test Plan | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 09:49:18 | kjb@coes.cn | 03-Jul-2026 14:50:03 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sukit Nualchanchai | 14-Jul-2026 | 06-Jul-2026 16:03:37 | Prin Jitatisil | 15-Jul-2026 | 07-Jul-2026 08:53:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 07-Jul-2026 09:22:24 | 07-Jul-2026 02:50:59 | 0 |  |  | Approver | Locate
AO-001049 | MM-ZTK-1F-GEN-QAC-ITP-8001 | PROJECT INSPECT & TEST PLAN FOR WHP T&I |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | ITP | Inspection And Test Plan | 0 | Submitted | IFA | Issued for Approval |  | 10-Jul-2026 12:18:51 | kjb@coes.cn | 10-Jul-2026 13:04:12 | Jumpol Sudjitjul | 17-Jul-2026 |  | Sukit Nualchanchai | 21-Jul-2026 | 14-Jul-2026 12:11:29 | Prin Jitatisil | 22-Jul-2026 | 14-Jul-2026 13:47:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 14-Jul-2026 14:17:08 | 14-Jul-2026 08:35:34 | 0 |  |  | Approver | Locate
AO-001154 | MM-ZTK-1F-GEN-QAC-ITP-8001 | PROJECT INSPECT & TEST PLAN FOR WHP T&I |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | ITP | Inspection And Test Plan | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 13:23:36 | kjb@coes.cn | 17-Jul-2026 13:33:52 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sukit Nualchanchai | 30-Jul-2026 | 27-Jul-2026 10:16:16 | Prin Jitatisil | 31-Jul-2026 | 27-Jul-2026 18:24:51 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 28-Jul-2026 08:43:47 | 28-Jul-2026 01:52:30 | 0 |  |  | Approver | Locate
AO-002459 | MM-ZTK-1F-GEN-QAC-MOM-0001 | PRE-INSPECTION /PRE-PRODUCTION MEETING (PIM & PPM) FOR STEEL PLATE SUPPLY |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 09-Oct-2026 13:54:52 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002459 | MM-ZTK-1F-GEN-QAC-MOM-0002 | PRE-INSPECTION PRE-PRODUCTION MEETING (PIM & PPM) FOR BEAMS |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 09-Oct-2026 13:55:20 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002459 | MM-ZTK-1F-GEN-QAC-MOM-0003 | PRE-INSPECTION /PRE-PRODUCTION MEETING (PIM & PPM) FOR SEAMLESS TUBULAR |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 09-Oct-2026 13:55:51 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002459 | MM-ZTK-1F-GEN-QAC-MOM-0004 | PRE-INSPECTION PRE-PRODUCTION MEETING (PIM & PPM) FOR PEDESTAL CRANE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 09-Oct-2026 13:56:25 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002109 | MM-ZTK-1F-GEN-QAC-NCR-5001 | TIMBER INSPECTION-NCR FOR THE TIMBER |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | NCR | Nonconformity Report | 0 | Submitted | IFA | Issued for Approval |  | 17-Sep-2026 10:37:58 | zhaoli@jutal.com | 17-Sep-2026 16:07:18 | Jumpol Sudjitjul | 24-Sep-2026 | 24-Sep-2026 23:00:52 | Witsarut Wanitanukool | 28-Sep-2026 | 30-Sep-2026 10:39:40 | Prin Jitatisil | 29-Sep-2026 | 30-Sep-2026 11:03:40 | APPR | Approved | Jumpol Sudjitjul | 30-Sep-2026 | 30-Sep-2026 13:09:13 | 30-Sep-2026 06:25:39 | 0 |  |  | Approver | Locate
AO-000011 | MM-ZTK-1F-GEN-QAC-PDR-0001 | PROJECT QUALITY AUDIT PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 05-Mar-2026 18:05:39 | 26002z1fdcc@thoresen-jutal.com | 05-Mar-2026 18:13:15 | Jumpol Sudjitjul | 13-Mar-2026 | 18-Mar-2026 11:45:01 | Poramate Kamlangkeng | 17-Mar-2026 | 20-Mar-2026 09:12:33 | Prin Jitatisil | 18-Mar-2026 | 22-Mar-2026 22:31:26 | NA | Not Approved | Jumpol Sudjitjul | 19-Mar-2026 | 23-Mar-2026 09:38:25 | 23-Mar-2026 10:00:13 | 0 |  |  | Approver | Locate
AO-000147 | MM-ZTK-1F-GEN-QAC-PDR-0001 | PROJECT QUALITY AUDIT PROCEDURE |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review | 07-Apr-2026 | 17-Apr-2026 23:41:02 | 26002z1fdcc@thoresen-jutal.com | 19-Apr-2026 22:14:48 | Jumpol Sudjitjul | 27-Apr-2026 | 09-May-2026 22:36:00 | Poramate Kamlangkeng | 29-Apr-2026 | 11-May-2026 15:35:33 | Prin Jitatisil | 30-Apr-2026 | 13-May-2026 14:48:16 | APPR | Approved | Jumpol Sudjitjul | 05-May-2026 | 13-May-2026 15:17:13 | 13-May-2026 15:52:03 | 0 |  |  | Approver | Locate
AO-000500 | MM-ZTK-1F-GEN-QAC-PDR-0001 | PROJECT QUALITY AUDIT PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction | 27-May-2026 | 18-May-2026 20:12:07 | 26002z1fdcc@thoresen-jutal.com | 18-May-2026 20:17:35 | Jumpol Sudjitjul | 26-May-2026 | 20-May-2026 07:23:14 | Poramate Kamlangkeng | 28-May-2026 | 01-Jun-2026 15:12:00 | Prin Jitatisil | 29-May-2026 | 04-Jun-2026 17:02:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 04-Jun-2026 18:27:14 | 04-Jun-2026 21:27:48 | 0 |  |  | Approver | Locate
AO-000711 | MM-ZTK-1F-GEN-QAC-PDR-0001 | PROJECT QUALITY AUDIT PROCEDURE |  | C2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 08-Jun-2026 11:46:43 | 26002z1fdcc@thoresen-jutal.com | 08-Jun-2026 11:56:47 | Jumpol Sudjitjul | 15-Jun-2026 | 16-Jun-2026 09:00:22 | Poramate Kamlangkeng | 17-Jun-2026 | 17-Jun-2026 10:48:04 | Prin Jitatisil | 18-Jun-2026 | 18-Jun-2026 09:38:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 09:41:02 | 18-Jun-2026 03:00:14 | 0 |  |  | Approver | Locate
AO-000833 | MM-ZTK-1F-GEN-QAC-PDR-0001 | PROJECT QUALITY AUDIT PROCEDURE |  | C3 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 18-Jun-2026 17:25:22 | 26002z1fdcc@thoresen-jutal.com | 18-Jun-2026 17:52:19 | Jumpol Sudjitjul | 26-Jun-2026 | 21-Jun-2026 13:30:53 | Poramate Kamlangkeng | 30-Jun-2026 | 03-Jul-2026 08:18:12 | Prin Jitatisil | 01-Jul-2026 | 06-Jul-2026 11:39:35 | APPR | Approved | Jumpol Sudjitjul | 02-Jul-2026 | 06-Jul-2026 11:45:46 | 06-Jul-2026 05:28:46 | 0 |  |  | Approver | Locate
AO-000034 | MM-ZTK-1F-GEN-QAC-PDR-0002 | PROJECT QUALITY AUDIT PROGRAM |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 20-Mar-2026 08:38:21 | 26002z1fdcc@thoresen-jutal.com | 20-Mar-2026 08:41:49 | Jumpol Sudjitjul | 27-Mar-2026 | 01-Apr-2026 13:48:55 | Poramate Kamlangkeng | 31-Mar-2026 | 05-Apr-2026 10:52:47 | Prin Jitatisil | 01-Apr-2026 | 06-Apr-2026 17:37:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Apr-2026 | 06-Apr-2026 21:34:51 | 06-Apr-2026 21:58:50 | 0 |  |  | Approver | Locate
AO-000148 | MM-ZTK-1F-GEN-QAC-PDR-0002 | PROJECT QUALITY AUDIT PROGRAM |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval | 23-Apr-2026 | 17-Apr-2026 23:41:35 | 26002z1fdcc@thoresen-jutal.com | 19-Apr-2026 22:15:02 | Jumpol Sudjitjul | 27-Apr-2026 | 09-May-2026 22:37:01 | Poramate Kamlangkeng | 29-Apr-2026 | 11-May-2026 15:36:26 | Prin Jitatisil | 30-Apr-2026 | 13-May-2026 14:51:27 | APPR | Approved | Jumpol Sudjitjul | 05-May-2026 | 13-May-2026 15:21:51 | 13-May-2026 16:01:52 | 0 |  |  | Approver | Locate
AO-001031 | MM-ZTK-1F-GEN-QAC-PDR-0002 | PROJECT QUALITY AUDIT PROGRAM |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 07-Jul-2026 19:25:06 | 26002z1fdcc@thoresen-jutal.com | 09-Jul-2026 14:07:00 | Jumpol Sudjitjul | 16-Jul-2026 | 13-Jul-2026 16:18:38 | Poramate Kamlangkeng | 20-Jul-2026 | 14-Jul-2026 08:24:21 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 20-Jul-2026 02:57:52 | APPR | Approved | Jumpol Sudjitjul | 22-Jul-2026 | 20-Jul-2026 09:07:09 | 20-Jul-2026 02:51:55 | 0 |  |  | Approver | Locate
AO-000247 | MM-ZTK-1F-GEN-QAC-PDR-0003 | PROJECT NON-CONFORMANCE CONTROL PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 28-Apr-2026 14:30:30 | 26002z1fdcc@thoresen-jutal.com | 28-Apr-2026 15:29:54 | Jumpol Sudjitjul | 07-May-2026 | 11-May-2026 10:32:56 | Poramate Kamlangkeng | 11-May-2026 | 11-May-2026 15:37:35 | Prin Jitatisil | 12-May-2026 | 13-May-2026 14:48:39 | APPR | Approved | Jumpol Sudjitjul | 13-May-2026 | 13-May-2026 15:20:55 | 13-May-2026 15:53:20 | 0 |  |  | Approver | Locate
AO-000502 | MM-ZTK-1F-GEN-QAC-PDR-0003 | PROJECT NON-CONFORMANCE CONTROL PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction | 27-May-2026 | 18-May-2026 19:36:57 | 26002z1fdcc@thoresen-jutal.com | 18-May-2026 20:18:19 | Jumpol Sudjitjul | 26-May-2026 | 20-May-2026 07:22:37 | Poramate Kamlangkeng | 28-May-2026 | 01-Jun-2026 15:27:24 | Prin Jitatisil | 29-May-2026 | 04-Jun-2026 17:00:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 04-Jun-2026 18:29:19 | 04-Jun-2026 21:30:36 | 0 |  |  | Approver | Locate
AO-000711 | MM-ZTK-1F-GEN-QAC-PDR-0003 | PROJECT NON-CONFORMANCE CONTROL PROCEDURE |  | C2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 08-Jun-2026 11:47:12 | 26002z1fdcc@thoresen-jutal.com | 08-Jun-2026 11:57:09 | Jumpol Sudjitjul | 15-Jun-2026 | 15-Jun-2026 17:37:32 | Poramate Kamlangkeng | 17-Jun-2026 | 17-Jun-2026 10:34:59 | Prin Jitatisil | 18-Jun-2026 | 18-Jun-2026 09:39:26 | APPR | Approved | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 09:47:18 | 18-Jun-2026 03:28:06 | 0 |  |  | Approver | Locate
AO-000453 | MM-ZTK-1F-GEN-QAC-PDR-0004 | PROJECT QUALITY PERFORMANCE MONITORING PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 18:12:38 | 26002z1fdcc@thoresen-jutal.com | 15-May-2026 18:23:26 | Jumpol Sudjitjul | 25-May-2026 | 25-May-2026 17:09:17 | Poramate Kamlangkeng | 27-May-2026 | 01-Jun-2026 15:05:20 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 21:16:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 11-Jun-2026 11:06:42 | 11-Jun-2026 11:49:52 | 0 |  |  | Approver | Locate
AO-000760 | MM-ZTK-1F-GEN-QAC-PDR-0004 | PROJECT QUALITY PERFORMANCE MONITORING PROCEDURE |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 12-Jun-2026 12:30:08 | 26002z1fdcc@thoresen-jutal.com | 12-Jun-2026 13:20:07 | Jumpol Sudjitjul | 19-Jun-2026 | 22-Jun-2026 13:13:20 | Poramate Kamlangkeng | 23-Jun-2026 | 23-Jun-2026 12:52:07 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 30-Jun-2026 22:03:10 | APPR | Approved | Jumpol Sudjitjul | 25-Jun-2026 | 01-Jul-2026 08:32:31 | 01-Jul-2026 01:56:53 | 0 |  |  | Approver | Locate
AO-001031 | MM-ZTK-1F-GEN-QAC-PDR-0004 | PROJECT QUALITY PERFORMANCE MONITORING PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 07-Jul-2026 18:44:09 | 26002z1fdcc@thoresen-jutal.com | 07-Jul-2026 20:52:39 | Jumpol Sudjitjul | 15-Jul-2026 | 13-Jul-2026 16:12:31 | Poramate Kamlangkeng | 17-Jul-2026 | 14-Jul-2026 08:14:58 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 22-Jul-2026 22:57:54 | APPR | Approved | Jumpol Sudjitjul | 21-Jul-2026 | 23-Jul-2026 08:23:18 | 23-Jul-2026 01:55:01 | 0 |  |  | Approver | Locate
AO-000564 | MM-ZTK-1F-GEN-QAC-PDR-5001 | WELDER QUALIFICATION TESTING PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 22:36:27 | zhaoli@jutal.com | 22-May-2026 12:48:10 | Jumpol Sudjitjul | 29-May-2026 | 23-May-2026 05:53:37 | Poramate Kamlangkeng | 04-Jun-2026 | 05-Jun-2026 08:00:37 | Prin Jitatisil | 05-Jun-2026 | 05-Jun-2026 08:22:00 | NA | Not Approved | Jumpol Sudjitjul | 08-Jun-2026 | 05-Jun-2026 08:40:58 | 05-Jun-2026 02:02:22 | 0 |  |  | Approver | Locate
AO-001267 | MM-ZTK-1F-GEN-QAC-PDR-5001 | WELDER QUALIFICATION TESTING PROCEDURE |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 17:38:05 | zm169dc@jutal.com | 26-Jul-2026 23:50:39 | Jumpol Sudjitjul | 05-Aug-2026 | 27-Jul-2026 09:49:32 | Poramate Kamlangkeng | 07-Aug-2026 | 30-Jul-2026 10:52:40 | Prin Jitatisil | 10-Aug-2026 | 30-Jul-2026 12:24:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 30-Jul-2026 14:08:23 | 30-Jul-2026 07:34:26 | 0 |  |  | Approver | Locate
AO-001540 | MM-ZTK-1F-GEN-QAC-PDR-5001 | WELDER QUALIFICATION TESTING PROCEDURE |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 18:12:43 | zm169dc@jutal.com | 15-Aug-2026 15:02:53 | Jumpol Sudjitjul | 21-Aug-2026 | 17-Aug-2026 09:12:39 | Poramate Kamlangkeng | 25-Aug-2026 | 24-Aug-2026 12:45:06 | Prin Jitatisil | 26-Aug-2026 | 24-Aug-2026 15:12:59 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 19:57:54 | 24-Aug-2026 14:23:33 | 0 |  |  | Approver | Locate
AO-001722 | MM-ZTK-1F-GEN-QAC-PDR-5001 | WELDER QUALIFICATION TESTING PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 26-Aug-2026 18:36:54 | zm169dc@jutal.com | 27-Aug-2026 08:47:30 | Jumpol Sudjitjul | 03-Sep-2026 | 28-Aug-2026 09:30:55 | Poramate Kamlangkeng | 07-Sep-2026 | 31-Aug-2026 12:58:28 | Prin Jitatisil | 08-Sep-2026 | 31-Aug-2026 14:29:47 | APPR | Approved | Jumpol Sudjitjul | 09-Sep-2026 | 31-Aug-2026 15:50:44 | 31-Aug-2026 10:21:42 | 0 |  |  | Approver | Locate
AO-002099 | MM-ZTK-1F-GEN-QAC-PDR-5001 | WELDER QUALIFICATION TESTING PROCEDURE |  | C2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 16-Sep-2026 14:11:18 | zhaoli@jutal.com | 16-Sep-2026 16:55:36 | Jumpol Sudjitjul | 23-Sep-2026 | 17-Sep-2026 08:00:09 | Poramate Kamlangkeng | 25-Sep-2026 | 18-Sep-2026 09:53:43 | Prin Jitatisil | 28-Sep-2026 | 20-Sep-2026 01:25:02 | APPR | Approved | Jumpol Sudjitjul | 29-Sep-2026 | 20-Sep-2026 17:15:07 | 20-Sep-2026 11:08:55 | 0 |  |  | Approver | Locate
AO-000564 | MM-ZTK-1F-GEN-QAC-PDR-5002 | WELDING CONSUMABLES CONTROL PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 22:36:50 | zhaoli@jutal.com | 22-May-2026 12:48:23 | Jumpol Sudjitjul | 29-May-2026 | 29-May-2026 08:04:20 | Poramate Kamlangkeng | 04-Jun-2026 | 05-Jun-2026 07:48:30 | Prin Jitatisil | 05-Jun-2026 | 05-Jun-2026 08:52:25 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Jun-2026 | 05-Jun-2026 09:03:34 | 05-Jun-2026 02:34:21 | 0 |  |  | Approver | Locate
AO-001597 | MM-ZTK-1F-GEN-QAC-PDR-5002 | WELDING CONSUMABLES CONTROL PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 18-Aug-2026 17:33:16 | zm169dc@jutal.com | 19-Aug-2026 11:15:07 | Jumpol Sudjitjul | 26-Aug-2026 | 20-Aug-2026 14:24:19 | Poramate Kamlangkeng | 28-Aug-2026 | 21-Aug-2026 09:56:09 | Prin Jitatisil | 31-Aug-2026 | 21-Aug-2026 15:45:52 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 21-Aug-2026 15:50:27 | 21-Aug-2026 09:32:31 | 0 |  |  | Approver | Locate
AO-001418 | MM-ZTK-1F-GEN-QAC-PDR-5003 | WELD BUTTERING PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 05-Aug-2026 11:59:28 | zm169dc@jutal.com | 05-Aug-2026 14:20:30 | Jumpol Sudjitjul | 13-Aug-2026 | 07-Aug-2026 09:20:02 | Poramate Kamlangkeng | 17-Aug-2026 | 14-Aug-2026 15:31:00 | Prin Jitatisil | 18-Aug-2026 | 14-Aug-2026 15:56:57 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 19-Aug-2026 | 14-Aug-2026 16:21:17 | 14-Aug-2026 09:32:37 | 0 |  |  | Approver | Locate
AO-001599 | MM-ZTK-1F-GEN-QAC-PDR-5003 | WELD BUTTERING PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 18-Aug-2026 17:33:57 | zm169dc@jutal.com | 19-Aug-2026 11:15:22 | Jumpol Sudjitjul | 26-Aug-2026 | 20-Aug-2026 14:35:52 | Poramate Kamlangkeng | 28-Aug-2026 | 21-Aug-2026 09:55:22 | Prin Jitatisil | 31-Aug-2026 | 21-Aug-2026 15:46:09 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 21-Aug-2026 15:51:01 | 21-Aug-2026 09:33:41 | 0 |  |  | Approver | Locate
AO-000395 | MM-ZTK-1F-GEN-QAC-PDR-5004 | MATERIAL CONTROL AND TRACEABILITY PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 14-May-2026 10:22:12 | zm169dc@jutal.com | 14-May-2026 10:43:06 | Jumpol Sudjitjul | 21-May-2026 | 21-May-2026 10:03:06 | Poramate Kamlangkeng | 25-May-2026 | 01-Jun-2026 10:12:09 | Pornlert Wanaphattharaphan | 26-May-2026 | 01-Jun-2026 15:44:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-May-2026 | 01-Jun-2026 22:12:29 | 01-Jun-2026 15:30:17 | 0 |  |  | Approver | Locate
AO-001595 | MM-ZTK-1F-GEN-QAC-PDR-5004 | MATERIAL CONTROL AND TRACEABILITY PROCEDURE |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 18-Aug-2026 17:34:42 | zm169dc@jutal.com | 19-Aug-2026 11:15:37 | Jumpol Sudjitjul | 26-Aug-2026 | 20-Aug-2026 14:50:35 | Poramate Kamlangkeng | 28-Aug-2026 | 24-Aug-2026 12:47:33 | Prin Jitatisil | 31-Aug-2026 | 24-Aug-2026 15:13:26 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 24-Aug-2026 19:57:18 | 24-Aug-2026 14:13:56 | 0 |  |  | Approver | Locate
AO-001860 | MM-ZTK-1F-GEN-QAC-PDR-5004 | MATERIAL CONTROL AND TRACEABILITY PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 18:17:57 | zhaoli@jutal.com | 04-Sep-2026 08:05:13 | Jumpol Sudjitjul | 11-Sep-2026 | 07-Sep-2026 08:22:06 | Poramate Kamlangkeng | 15-Sep-2026 | 08-Sep-2026 10:15:04 | Prin Jitatisil | 16-Sep-2026 | 08-Sep-2026 11:17:48 | APPR | Approved | Jumpol Sudjitjul | 17-Sep-2026 | 08-Sep-2026 13:19:37 | 08-Sep-2026 07:16:07 | 0 |  |  | Approver | Locate
AO-001378 | MM-ZTK-1F-GEN-QAC-PDR-5005 | NDT EXTENT AND REQUIREMENTS |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 11:00:19 | zm169dc@jutal.com | 03-Aug-2026 14:19:43 | Jumpol Sudjitjul | 10-Aug-2026 | 04-Aug-2026 09:22:07 | Poramate Kamlangkeng | 13-Aug-2026 | 14-Aug-2026 15:27:18 | Prin Jitatisil | 14-Aug-2026 | 14-Aug-2026 15:57:23 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 14-Aug-2026 16:18:21 | 14-Aug-2026 10:03:49 | 0 |  |  | Approver | Locate
AO-001364 | MM-ZTK-1F-GEN-QAC-PDR-5006 | QAQC ORGANIZATION CHART WITH CV |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 31-Jul-2026 18:15:27 | zm169dc@jutal.com | 31-Jul-2026 21:41:43 | Jumpol Sudjitjul | 10-Aug-2026 |  | Poramate Kamlangkeng | 13-Aug-2026 | 14-Aug-2026 15:35:21 | Prin Jitatisil | 14-Aug-2026 | 14-Aug-2026 15:57:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 14-Aug-2026 16:19:26 | 14-Aug-2026 09:30:08 | 0 |  |  | Approver | Locate
AO-001275 | MM-ZTK-1F-GEN-QAC-PDR-5007 | WELD VISUAL INSPECTION PROCEDURE FOR STRUCTURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 25-Jul-2026 09:16:47 | zm169dc@jutal.com | 27-Jul-2026 09:28:13 | Jumpol Sudjitjul | 05-Aug-2026 | 29-Jul-2026 06:41:29 | Poramate Kamlangkeng | 07-Aug-2026 | 30-Jul-2026 10:37:10 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 30-Jul-2026 18:18:19 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 11-Aug-2026 | 30-Jul-2026 19:14:24 | 30-Jul-2026 12:34:57 | 0 |  |  | Approver | Locate
AO-001594 | MM-ZTK-1F-GEN-QAC-PDR-5007 | WELD VISUAL INSPECTION PROCEDURE FOR STRUCTURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 18-Aug-2026 17:35:15 | zm169dc@jutal.com | 19-Aug-2026 11:15:55 | Jumpol Sudjitjul | 26-Aug-2026 | 20-Aug-2026 15:11:07 | Poramate Kamlangkeng | 28-Aug-2026 | 21-Aug-2026 09:53:49 | Prin Jitatisil | 31-Aug-2026 | 21-Aug-2026 15:46:23 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 21-Aug-2026 15:51:32 | 21-Aug-2026 09:35:03 | 0 |  |  | Approver | Locate
AO-001927 | MM-ZTK-1F-GEN-QAC-PDR-5008 | WELD VISUAL INSPECTION PROCEDURE FOR PIPING,RISER |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 08-Sep-2026 09:20:09 | zhaoli@jutal.com | 08-Sep-2026 11:47:10 | Jumpol Sudjitjul | 15-Sep-2026 | 17-Sep-2026 10:59:16 | Poramate Kamlangkeng | 17-Sep-2026 | 18-Sep-2026 09:22:54 | Prin Jitatisil | 18-Sep-2026 | 20-Sep-2026 01:25:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 17:14:26 | 20-Sep-2026 12:38:01 | 0 |  |  | Approver | Locate
AO-002207 | MM-ZTK-1F-GEN-QAC-PDR-5008 | WELD VISUAL INSPECTION PROCEDURE FOR PIPING,RISER |  | C2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 22-Sep-2026 11:58:06 | zm169dc@jutal.com | 22-Sep-2026 16:12:18 | Jumpol Sudjitjul | 29-Sep-2026 | 25-Sep-2026 15:09:17 | Poramate Kamlangkeng | 01-Oct-2026 | 28-Sep-2026 12:20:29 | Prin Jitatisil | 02-Oct-2026 | 28-Sep-2026 14:18:34 | APPR | Approved | Jumpol Sudjitjul | 05-Oct-2026 | 29-Sep-2026 14:16:26 | 29-Sep-2026 08:54:28 | 0 |  |  | Approver | Locate
AO-001438 | MM-ZTK-1F-GEN-QAC-PDR-5009 | POSITIVE MATERIAL IDENTIFICATION PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 06-Aug-2026 17:37:17 | zm169dc@jutal.com | 07-Aug-2026 16:21:02 | Jumpol Sudjitjul | 17-Aug-2026 |  | Witsarut Wanitanukool | 19-Aug-2026 | 19-Aug-2026 19:12:00 | Prin Jitatisil | 20-Aug-2026 | 20-Aug-2026 10:45:45 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Aug-2026 | 20-Aug-2026 10:50:04 | 20-Aug-2026 04:26:47 | 0 |  |  | Approver | Locate
AO-001804 | MM-ZTK-1F-GEN-QAC-PDR-5009 | POSITIVE MATERIAL IDENTIFICATION PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 31-Aug-2026 16:48:18 | zm169dc@jutal.com | 31-Aug-2026 16:52:20 | Jumpol Sudjitjul | 07-Sep-2026 |  | Witsarut Wanitanukool | 09-Sep-2026 | 02-Sep-2026 10:24:40 | Prin Jitatisil | 10-Sep-2026 | 06-Sep-2026 00:37:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 06-Sep-2026 09:30:56 | 06-Sep-2026 03:12:11 | 0 |  |  | Approver | Locate
AO-002054 | MM-ZTK-1F-GEN-QAC-PDR-5009 | POSITIVE MATERIAL IDENTIFICATION PROCEDURE |  | C2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 20:08:59 | zhaoli@jutal.com | 15-Sep-2026 15:25:08 | Jumpol Sudjitjul | 22-Sep-2026 | 17-Sep-2026 22:50:07 | Witsarut Wanitanukool | 24-Sep-2026 | 30-Sep-2026 10:37:16 | Prin Jitatisil | 25-Sep-2026 | 30-Sep-2026 11:04:01 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 30-Sep-2026 13:09:58 | 30-Sep-2026 06:27:02 | 0 |  |  | Approver | Locate
AO-000575 | MM-ZTK-1F-GEN-QAC-PDR-5010 | UT PROCEDURE FOR STRUCTURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 23-May-2026 08:52:54 | zm169dc@jutal.com | 23-May-2026 09:38:10 | Jumpol Sudjitjul | 29-May-2026 |  | Poramate Kamlangkeng | 04-Jun-2026 | 05-Jun-2026 08:06:37 | Prin Jitatisil | 05-Jun-2026 | 05-Jun-2026 08:56:43 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Jun-2026 | 05-Jun-2026 09:04:55 | 05-Jun-2026 09:35:43 | 0 |  |  | Approver | Locate
AO-000808 | MM-ZTK-1F-GEN-QAC-PDR-5010 | UT PROCEDURE FOR STRUCTURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 15-Jun-2026 22:50:49 | zm169dc@jutal.com | 16-Jun-2026 11:00:18 | Jumpol Sudjitjul | 23-Jun-2026 |  | Poramate Kamlangkeng | 25-Jun-2026 | 17-Jun-2026 10:49:49 | Prin Jitatisil | 26-Jun-2026 | 18-Jun-2026 09:40:14 | APPR | Approved | Jumpol Sudjitjul | 29-Jun-2026 | 18-Jun-2026 09:48:13 | 18-Jun-2026 03:56:25 | 0 |  |  | Approver | Locate
AO-001503 | MM-ZTK-1F-GEN-QAC-PDR-5011 | UT PROCEDURE FOR PIPING, RISER／PIG TRAP |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 10-Aug-2026 18:33:58 | zm169dc@jutal.com | 11-Aug-2026 08:48:49 | Jumpol Sudjitjul | 19-Aug-2026 | 12-Aug-2026 07:16:03 | Poramate Kamlangkeng | 21-Aug-2026 | 15-Aug-2026 09:12:38 | Pornlert Wanaphattharaphan | 24-Aug-2026 | 21-Aug-2026 20:05:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Aug-2026 | 24-Aug-2026 20:00:39 | 24-Aug-2026 13:54:20 | 0 |  |  | Approver | Locate
AO-001712 | MM-ZTK-1F-GEN-QAC-PDR-5011 | UT PROCEDURE FOR PIPING, RISER／PIG TRAP |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 25-Aug-2026 18:34:25 | zm169dc@jutal.com | 26-Aug-2026 09:36:23 | Jumpol Sudjitjul | 02-Sep-2026 | 27-Aug-2026 16:20:29 | Poramate Kamlangkeng | 04-Sep-2026 | 31-Aug-2026 13:03:23 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 07-Sep-2026 00:15:45 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Sep-2026 | 07-Sep-2026 11:52:04 | 07-Sep-2026 05:52:21 | 0 |  |  | Approver | Locate
AO-001997 | MM-ZTK-1F-GEN-QAC-PDR-5011 | UT PROCEDURE FOR PIPING, RISER／PIG TRAP |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 09:17:32 | zhaoli@jutal.com | 11-Sep-2026 19:36:34 | Jumpol Sudjitjul | 21-Sep-2026 | 17-Sep-2026 11:08:18 | Poramate Kamlangkeng | 23-Sep-2026 | 18-Sep-2026 09:27:32 | Prin Jitatisil | 24-Sep-2026 | 20-Sep-2026 01:25:34 | APPR | Approved | Jumpol Sudjitjul | 25-Sep-2026 | 20-Sep-2026 17:13:51 | 20-Sep-2026 12:37:52 | 0 |  |  | Approver | Locate
AO-002038 | MM-ZTK-1F-GEN-QAC-PDR-5012 | FERRITE TEST PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:51:41 | zhaoli@jutal.com | 15-Sep-2026 15:44:30 | Jumpol Sudjitjul | 22-Sep-2026 | 17-Sep-2026 23:22:34 | Poramate Kamlangkeng | 24-Sep-2026 | 18-Sep-2026 09:52:54 | Prin Jitatisil | 25-Sep-2026 | 20-Sep-2026 01:25:49 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 20-Sep-2026 17:13:00 | 20-Sep-2026 11:29:03 | 0 |  |  | Approver | Locate
AO-000574 | MM-ZTK-1F-GEN-QAC-PDR-5013 | RT PROCEDURE FOR STRUCTURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 23-May-2026 08:53:18 | zm169dc@jutal.com | 23-May-2026 09:38:22 | Jumpol Sudjitjul | 29-May-2026 |  | Poramate Kamlangkeng | 04-Jun-2026 | 05-Jun-2026 08:18:32 | Prin Jitatisil | 05-Jun-2026 | 05-Jun-2026 09:09:35 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Jun-2026 | 05-Jun-2026 09:16:33 | 05-Jun-2026 09:37:00 | 0 |  |  | Approver | Locate
AO-000810 | MM-ZTK-1F-GEN-QAC-PDR-5013 | RT PROCEDURE FOR STRUCTURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 15-Jun-2026 22:51:14 | zm169dc@jutal.com | 16-Jun-2026 11:00:33 | Jumpol Sudjitjul | 23-Jun-2026 |  | Poramate Kamlangkeng | 25-Jun-2026 | 17-Jun-2026 10:49:07 | Prin Jitatisil | 26-Jun-2026 | 18-Jun-2026 09:41:05 | APPR | Approved | Jumpol Sudjitjul | 29-Jun-2026 | 18-Jun-2026 09:49:11 | 18-Jun-2026 03:34:44 | 0 |  |  | Approver | Locate
AO-001511 | MM-ZTK-1F-GEN-QAC-PDR-5014 | RT PROCEDURE FOR PIPING,RISER |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 13-Aug-2026 08:56:03 | zm169dc@jutal.com | 13-Aug-2026 16:43:30 | Jumpol Sudjitjul | 20-Aug-2026 |  | Poramate Kamlangkeng | 24-Aug-2026 | 15-Aug-2026 09:48:47 | Prin Jitatisil | 25-Aug-2026 | 15-Aug-2026 11:22:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Aug-2026 | 15-Aug-2026 14:38:22 | 15-Aug-2026 09:04:01 | 0 |  |  | Approver | Locate
AO-001575 | MM-ZTK-1F-GEN-QAC-PDR-5014 | RT PROCEDURE FOR PIPING,RISER |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 18:02:45 | zm169dc@jutal.com | 18-Aug-2026 08:28:47 | Jumpol Sudjitjul | 25-Aug-2026 | 20-Aug-2026 10:15:18 | Poramate Kamlangkeng | 27-Aug-2026 | 24-Aug-2026 12:46:16 | Prin Jitatisil | 28-Aug-2026 | 24-Aug-2026 15:13:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Aug-2026 | 25-Aug-2026 13:19:19 | 25-Aug-2026 07:26:35 | 0 |  |  | Approver | Locate
AO-001858 | MM-ZTK-1F-GEN-QAC-PDR-5014 | RT PROCEDURE FOR PIPING,RISER |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 18:18:26 | zhaoli@jutal.com | 04-Sep-2026 08:05:45 | Jumpol Sudjitjul | 11-Sep-2026 | 07-Sep-2026 09:28:15 | Poramate Kamlangkeng | 15-Sep-2026 | 08-Sep-2026 10:15:43 | Prin Jitatisil | 16-Sep-2026 | 08-Sep-2026 11:18:02 | APPR | Approved | Jumpol Sudjitjul | 17-Sep-2026 | 08-Sep-2026 13:21:16 | 08-Sep-2026 07:37:07 | 0 |  |  | Approver | Locate
AO-000573 | MM-ZTK-1F-GEN-QAC-PDR-5016 | MT PROCEDURE FOR STRUCTURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 23-May-2026 08:53:40 | zm169dc@jutal.com | 23-May-2026 09:38:36 | Jumpol Sudjitjul | 29-May-2026 |  | Poramate Kamlangkeng | 04-Jun-2026 | 05-Jun-2026 08:54:33 | Prin Jitatisil | 05-Jun-2026 | 05-Jun-2026 09:10:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 05-Jun-2026 09:23:08 | 05-Jun-2026 09:39:37 | 0 |  |  | Approver | Locate
AO-000735 | MM-ZTK-1F-GEN-QAC-PDR-5016 | MT PROCEDURE FOR STRUCTURE |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 10-Jun-2026 17:15:16 | zm169dc@jutal.com | 11-Jun-2026 12:53:33 | Jumpol Sudjitjul | 18-Jun-2026 |  | Poramate Kamlangkeng | 22-Jun-2026 | 16-Jun-2026 08:01:27 | Prin Jitatisil | 23-Jun-2026 | 18-Jun-2026 09:42:04 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 24-Jun-2026 | 18-Jun-2026 09:50:08 | 18-Jun-2026 03:36:05 | 0 |  |  | Approver | Locate
AO-001024 | MM-ZTK-1F-GEN-QAC-PDR-5016 | MT PROCEDURE FOR STRUCTURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 06-Jul-2026 11:53:59 | zm169dc@jutal.com | 06-Jul-2026 12:05:37 | Jumpol Sudjitjul | 13-Jul-2026 |  | Poramate Kamlangkeng | 15-Jul-2026 | 10-Jul-2026 07:49:50 | Prin Jitatisil | 16-Jul-2026 | 11-Jul-2026 12:13:30 | APPR | Approved | Jumpol Sudjitjul | 17-Jul-2026 | 12-Jul-2026 11:33:29 | 12-Jul-2026 05:25:33 | 0 |  |  | Approver | Locate
AO-001503 | MM-ZTK-1F-GEN-QAC-PDR-5017 | MT PROCEDURE FOR PIPING, RISER |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 10-Aug-2026 18:34:29 | zm169dc@jutal.com | 11-Aug-2026 08:49:10 | Jumpol Sudjitjul | 19-Aug-2026 | 12-Aug-2026 07:13:47 | Poramate Kamlangkeng | 21-Aug-2026 | 15-Aug-2026 09:24:33 | Prin Jitatisil | 24-Aug-2026 | 18-Aug-2026 14:07:28 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 25-Aug-2026 | 18-Aug-2026 14:27:54 | 18-Aug-2026 08:41:27 | 0 |  |  | Approver | Locate
AO-001618 | MM-ZTK-1F-GEN-QAC-PDR-5017 | MT PROCEDURE FOR PIPING, RISER |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 09:34:32 | zm169dc@jutal.com | 20-Aug-2026 09:56:57 | Jumpol Sudjitjul | 27-Aug-2026 | 20-Aug-2026 10:41:02 | Poramate Kamlangkeng | 31-Aug-2026 | 21-Aug-2026 09:50:11 | Prin Jitatisil | 01-Sep-2026 | 21-Aug-2026 15:46:41 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 21-Aug-2026 15:52:02 | 21-Aug-2026 09:37:21 | 0 |  |  | Approver | Locate
AO-001511 | MM-ZTK-1F-GEN-QAC-PDR-5018 | MEASURING & TESTING EQUIPMENT CONTROL PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 13-Aug-2026 08:56:51 | zm169dc@jutal.com | 14-Aug-2026 10:03:20 | Jumpol Sudjitjul | 21-Aug-2026 |  | Poramate Kamlangkeng | 25-Aug-2026 | 15-Aug-2026 10:04:03 | Prin Jitatisil | 26-Aug-2026 | 15-Aug-2026 11:23:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 15-Aug-2026 14:41:16 | 15-Aug-2026 09:04:07 | 0 |  |  | Approver | Locate
AO-001602 | MM-ZTK-1F-GEN-QAC-PDR-5018 | MEASURING & TESTING EQUIPMENT CONTROL PROCEDURE |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 19-Aug-2026 10:07:56 | zm169dc@jutal.com | 19-Aug-2026 11:16:14 | Jumpol Sudjitjul | 26-Aug-2026 | 20-Aug-2026 15:42:46 | Poramate Kamlangkeng | 28-Aug-2026 | 24-Aug-2026 12:48:50 | Prin Jitatisil | 31-Aug-2026 | 24-Aug-2026 15:14:14 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 24-Aug-2026 19:56:46 | 24-Aug-2026 14:25:39 | 0 |  |  | Approver | Locate
AO-001721 | MM-ZTK-1F-GEN-QAC-PDR-5018 | MEASURING & TESTING EQUIPMENT CONTROL PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 26-Aug-2026 18:37:20 | zm169dc@jutal.com | 27-Aug-2026 08:47:55 | Jumpol Sudjitjul | 03-Sep-2026 | 28-Aug-2026 09:45:22 | Poramate Kamlangkeng | 07-Sep-2026 | 31-Aug-2026 12:57:55 | Prin Jitatisil | 08-Sep-2026 | 31-Aug-2026 14:30:04 | APPR | Approved | Jumpol Sudjitjul | 09-Sep-2026 | 31-Aug-2026 15:51:22 | 31-Aug-2026 10:59:37 | 0 |  |  | Approver | Locate
AO-000572 | MM-ZTK-1F-GEN-QAC-PDR-5019 | PT PROCEDURE FOR STRUCTURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 23-May-2026 08:54:02 | zm169dc@jutal.com | 23-May-2026 09:38:51 | Jumpol Sudjitjul | 29-May-2026 |  | Poramate Kamlangkeng | 04-Jun-2026 | 05-Jun-2026 09:08:03 | Prin Jitatisil | 05-Jun-2026 | 05-Jun-2026 09:10:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 05-Jun-2026 09:18:19 | 05-Jun-2026 09:38:15 | 0 |  |  | Approver | Locate
AO-000736 | MM-ZTK-1F-GEN-QAC-PDR-5019 | PT PROCEDURE FOR STRUCTURE |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 10-Jun-2026 17:15:43 | zm169dc@jutal.com | 11-Jun-2026 12:53:50 | Jumpol Sudjitjul | 18-Jun-2026 |  | Poramate Kamlangkeng | 22-Jun-2026 | 16-Jun-2026 08:14:02 | Prin Jitatisil | 23-Jun-2026 | 18-Jun-2026 09:42:49 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 24-Jun-2026 | 18-Jun-2026 09:50:34 | 18-Jun-2026 03:37:26 | 0 |  |  | Approver | Locate
AO-001025 | MM-ZTK-1F-GEN-QAC-PDR-5019 | PT PROCEDURE FOR STRUCTURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 06-Jul-2026 11:54:29 | zm169dc@jutal.com | 06-Jul-2026 12:05:58 | Jumpol Sudjitjul | 13-Jul-2026 |  | Poramate Kamlangkeng | 15-Jul-2026 | 10-Jul-2026 07:50:14 | Prin Jitatisil | 16-Jul-2026 | 11-Jul-2026 12:14:04 | APPR | Approved | Jumpol Sudjitjul | 17-Jul-2026 | 12-Jul-2026 11:33:52 | 12-Jul-2026 05:26:40 | 0 |  |  | Approver | Locate
AO-001503 | MM-ZTK-1F-GEN-QAC-PDR-5020 | PT PROCEDURE FOR PIPING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 10-Aug-2026 18:34:58 | zm169dc@jutal.com | 11-Aug-2026 08:49:37 | Jumpol Sudjitjul | 19-Aug-2026 | 12-Aug-2026 07:12:34 | Poramate Kamlangkeng | 21-Aug-2026 | 15-Aug-2026 09:30:51 | Pornlert Wanaphattharaphan | 24-Aug-2026 | 16-Aug-2026 17:38:54 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 25-Aug-2026 | 17-Aug-2026 13:58:39 | 17-Aug-2026 07:21:09 | 0 |  |  | Approver | Locate
AO-001596 | MM-ZTK-1F-GEN-QAC-PDR-5020 | PT PROCEDURE FOR PIPING |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 18-Aug-2026 17:35:53 | zm169dc@jutal.com | 19-Aug-2026 15:28:07 | Jumpol Sudjitjul | 26-Aug-2026 |  | Poramate Kamlangkeng | 28-Aug-2026 | 21-Aug-2026 09:50:55 | Prin Jitatisil | 31-Aug-2026 | 21-Aug-2026 15:46:57 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 21-Aug-2026 15:52:32 | 21-Aug-2026 09:38:34 | 0 |  |  | Approver | Locate
AO-002248 | MM-ZTK-1F-GEN-QAC-PDR-5024 | HEAT STRAIGHTENING PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 15:01:05 | zm169dc@jutal.com | 24-Sep-2026 15:08:33 | Jumpol Sudjitjul | 01-Oct-2026 | 25-Sep-2026 15:11:23 | Poramate Kamlangkeng | 05-Oct-2026 | 28-Sep-2026 12:22:59 | Prin Jitatisil | 06-Oct-2026 | 28-Sep-2026 14:19:32 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 29-Sep-2026 14:17:55 | 29-Sep-2026 07:59:06 | 0 |  |  | Approver | Locate
AO-001438 | MM-ZTK-1F-GEN-QAC-PDR-5025 | HARDNESS TEST PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 06-Aug-2026 17:37:40 | zm169dc@jutal.com | 07-Aug-2026 16:11:58 | Jumpol Sudjitjul | 17-Aug-2026 | 08-Aug-2026 06:39:42 | Poramate Kamlangkeng | 19-Aug-2026 | 14-Aug-2026 16:16:41 | Prin Jitatisil | 20-Aug-2026 | 15-Aug-2026 11:23:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 15-Aug-2026 14:45:38 | 15-Aug-2026 08:39:55 | 0 |  |  | Approver | Locate
AO-001593 | MM-ZTK-1F-GEN-QAC-PDR-5025 | HARDNESS TEST PROCEDURE |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 18-Aug-2026 17:36:25 | zm169dc@jutal.com | 19-Aug-2026 15:28:33 | Jumpol Sudjitjul | 26-Aug-2026 | 24-Aug-2026 11:21:14 | Poramate Kamlangkeng | 28-Aug-2026 | 24-Aug-2026 12:58:41 | Prin Jitatisil | 31-Aug-2026 | 24-Aug-2026 15:15:01 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 01-Sep-2026 | 24-Aug-2026 19:56:12 | 24-Aug-2026 14:10:32 | 0 |  |  | Approver | Locate
AO-001803 | MM-ZTK-1F-GEN-QAC-PDR-5025 | HARDNESS TEST PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 31-Aug-2026 16:48:49 | zm169dc@jutal.com | 31-Aug-2026 16:52:40 | Jumpol Sudjitjul | 07-Sep-2026 | 04-Sep-2026 11:31:26 | Poramate Kamlangkeng | 09-Sep-2026 | 08-Sep-2026 09:31:06 | Prin Jitatisil | 10-Sep-2026 | 08-Sep-2026 09:37:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 08-Sep-2026 13:30:43 | 08-Sep-2026 07:32:59 | 0 |  |  | Approver | Locate
AO-002089 | MM-ZTK-1F-GEN-QAC-PDR-5025 | HARDNESS TEST PROCEDURE |  | C2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 15-Sep-2026 17:42:52 | zhaoli@jutal.com | 16-Sep-2026 16:55:56 | Jumpol Sudjitjul | 23-Sep-2026 | 17-Sep-2026 07:45:46 | Poramate Kamlangkeng | 25-Sep-2026 | 18-Sep-2026 09:54:20 | Prin Jitatisil | 28-Sep-2026 | 20-Sep-2026 01:26:04 | APPR | Approved | Jumpol Sudjitjul | 29-Sep-2026 | 20-Sep-2026 17:12:24 | 20-Sep-2026 11:25:54 | 0 |  |  | Approver | Locate
AO-001417 | MM-ZTK-1F-GEN-QAC-PDR-5030 | CTOD TEST PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 05-Aug-2026 11:59:57 | zm169dc@jutal.com | 05-Aug-2026 14:21:24 | Jumpol Sudjitjul | 13-Aug-2026 | 08-Aug-2026 06:47:44 | Poramate Kamlangkeng | 17-Aug-2026 | 14-Aug-2026 15:39:28 | Prin Jitatisil | 18-Aug-2026 | 14-Aug-2026 15:58:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Aug-2026 | 14-Aug-2026 16:20:22 | 14-Aug-2026 09:31:25 | 0 |  |  | Approver | Locate
AO-001601 | MM-ZTK-1F-GEN-QAC-PDR-5030 | CTOD TEST PROCEDURE |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 19-Aug-2026 10:08:35 | zm169dc@jutal.com | 19-Aug-2026 15:28:58 | Jumpol Sudjitjul | 26-Aug-2026 | 24-Aug-2026 11:36:54 | Poramate Kamlangkeng | 28-Aug-2026 | 24-Aug-2026 12:50:32 | Prin Jitatisil | 31-Aug-2026 | 24-Aug-2026 15:19:39 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 24-Aug-2026 19:55:24 | 24-Aug-2026 14:09:04 | 0 |  |  | Approver | Locate
AO-001720 | MM-ZTK-1F-GEN-QAC-PDR-5030 | CTOD TEST PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 26-Aug-2026 18:37:52 | zm169dc@jutal.com | 27-Aug-2026 08:48:20 | Jumpol Sudjitjul | 03-Sep-2026 | 28-Aug-2026 09:49:00 | Poramate Kamlangkeng | 07-Sep-2026 | 31-Aug-2026 12:57:04 | Prin Jitatisil | 08-Sep-2026 | 31-Aug-2026 14:30:19 | APPR | Approved | Jumpol Sudjitjul | 09-Sep-2026 | 31-Aug-2026 15:52:19 | 31-Aug-2026 10:23:54 | 0 |  |  | Approver | Locate
AO-001419 | MM-ZTK-1F-GEN-QAC-PDR-5032 | WELDING CONTROL PROCEDURE FOR STRUCTURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 05-Aug-2026 12:00:28 | zm169dc@jutal.com | 05-Aug-2026 14:22:51 | Jumpol Sudjitjul | 13-Aug-2026 | 08-Aug-2026 06:48:19 | Poramate Kamlangkeng | 17-Aug-2026 | 14-Aug-2026 15:51:47 | Prin Jitatisil | 18-Aug-2026 | 14-Aug-2026 15:58:12 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 19-Aug-2026 | 14-Aug-2026 16:26:24 | 14-Aug-2026 10:22:16 | 0 |  |  | Approver | Locate
AO-001600 | MM-ZTK-1F-GEN-QAC-PDR-5032 | WELDING CONTROL PROCEDURE FOR STRUCTURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 18-Aug-2026 17:36:53 | zm169dc@jutal.com | 19-Aug-2026 15:29:16 | Jumpol Sudjitjul | 26-Aug-2026 | 20-Aug-2026 10:53:52 | Poramate Kamlangkeng | 28-Aug-2026 | 21-Aug-2026 09:24:02 | Prin Jitatisil | 31-Aug-2026 | 21-Aug-2026 15:47:17 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 21-Aug-2026 15:51:57 | 21-Aug-2026 09:36:12 | 0 |  |  | Approver | Locate
AO-002501 | MM-ZTK-1F-GEN-QAC-PDR-5034 | WELDING CONSUMABLES BATCH TEST PROCEDURE FOR STRUCTURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 12-Oct-2026 18:01:12 | zhaoli@jutal.com | 12-Oct-2026 18:13:13 | Jumpol Sudjitjul | 21-Oct-2026 | 16-Oct-2026 15:39:32 | Poramate Kamlangkeng | 26-Oct-2026 | 17-Oct-2026 12:15:14 | Prin Jitatisil | 27-Oct-2026 | 17-Oct-2026 13:15:30 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 18-Oct-2026 09:22:20 | 18-Oct-2026 05:02:14 | 0 |  |  | Approver | Locate
AO-000889 | MM-ZTK-1F-GEN-QAC-PDR-8004 | WELDING CONSUMABLE CONTROL PROCEDURE - WP-1 (T&I) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 24-Jun-2026 14:11:05 | kjb@coes.cn | 24-Jun-2026 15:17:00 | Jumpol Sudjitjul | 01-Jul-2026 | 27-Jun-2026 07:03:01 | Sukit Nualchanchai | 03-Jul-2026 | 09-Jul-2026 18:06:05 | Prin Jitatisil | 06-Jul-2026 | 11-Jul-2026 12:14:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Jul-2026 | 12-Jul-2026 11:34:52 | 12-Jul-2026 04:41:12 | 0 |  |  | Approver | Locate
AO-000406 | MM-ZTK-1F-GEN-QAC-PDR-8007 | CRITICALITY ANALYSIS REPORT FOR WORK PACKAGE 1 T&I |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 10:51:43 | kjb@coes.cn | 15-May-2026 18:23:11 | Jumpol Sudjitjul | 25-May-2026 | 04-Jun-2026 11:37:34 | Sukit Nualchanchai | 27-May-2026 | 05-Jun-2026 17:26:49 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 21:17:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 11-Jun-2026 11:07:47 | 11-Jun-2026 04:54:49 | 0 |  |  | Approver | Locate
AO-000967 | MM-ZTK-1F-GEN-QAC-PDR-8007 | CRITICALITY ANALYSIS REPORT FOR WORK PACKAGE 1 T&I |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 01-Jul-2026 08:43:24 | kjb@coes.cn | 01-Jul-2026 10:51:19 | Jumpol Sudjitjul | 08-Jul-2026 | 02-Jul-2026 14:34:00 | Sukit Nualchanchai | 10-Jul-2026 | 03-Jul-2026 15:13:58 | Pornlert Wanaphattharaphan | 13-Jul-2026 | 08-Jul-2026 00:04:07 | NA | Not Approved | Jumpol Sudjitjul | 14-Jul-2026 | 08-Jul-2026 09:42:10 | 08-Jul-2026 03:33:56 | 0 |  |  | Approver | Locate
AO-001125 | MM-ZTK-1F-GEN-QAC-PDR-8007 | CRITICALITY ANALYSIS REPORT FOR WORK PACKAGE 1 T&I |  | B2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 11:32:16 | kjb@coes.cn | 16-Jul-2026 11:51:54 | Jumpol Sudjitjul | 23-Jul-2026 | 18-Jul-2026 08:57:37 | Sukit Nualchanchai | 27-Jul-2026 | 27-Jul-2026 10:12:33 | Prin Jitatisil | 30-Jul-2026 | 30-Jul-2026 10:10:26 | APPR | Approved | Jumpol Sudjitjul | 31-Jul-2026 | 30-Jul-2026 10:21:09 | 30-Jul-2026 04:07:25 | 0 |  |  | Approver | Locate
AO-001437 | MM-ZTK-1F-GEN-QAC-PDR-8007 | CRITICALITY ANALYSIS REPORT FOR WORK PACKAGE 1 T&I |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 06-Aug-2026 17:38:09 | kjb@coes.cn | 07-Aug-2026 16:09:36 | Jumpol Sudjitjul | 17-Aug-2026 | 08-Aug-2026 06:55:41 | Sukit Nualchanchai | 19-Aug-2026 | 10-Aug-2026 10:59:55 | Prin Jitatisil | 20-Aug-2026 | 10-Aug-2026 13:26:54 | NA | Not Approved | Jumpol Sudjitjul | 21-Aug-2026 | 10-Aug-2026 17:43:40 | 10-Aug-2026 11:04:30 | 0 |  |  | Approver | Locate
AO-001569 | MM-ZTK-1F-GEN-QAC-PDR-8007 | CRITICALITY ANALYSIS REPORT FOR WORK PACKAGE 1 T&I |  | C2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 17:16:03 | kjb@coes.cn | 18-Aug-2026 08:29:40 | Jumpol Sudjitjul | 25-Aug-2026 | 19-Aug-2026 06:09:53 | Sukit Nualchanchai | 27-Aug-2026 | 19-Aug-2026 11:29:23 | Prin Jitatisil | 28-Aug-2026 | 19-Aug-2026 14:13:04 | APPR | Approved | Jumpol Sudjitjul | 31-Aug-2026 | 19-Aug-2026 17:21:34 | 19-Aug-2026 10:52:39 | 0 |  |  | Approver | Locate
AO-001122 | MM-ZTK-1F-GEN-QAC-PDR-8010 | MATERIAL CONTROL PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 16-Jul-2026 11:00:22 | kjb@coes.cn | 16-Jul-2026 11:53:38 | Jumpol Sudjitjul | 23-Jul-2026 | 24-Jul-2026 14:12:59 | Sukit Nualchanchai | 27-Jul-2026 | 26-Jul-2026 23:40:53 | Prin Jitatisil | 30-Jul-2026 | 30-Jul-2026 10:10:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Jul-2026 | 30-Jul-2026 10:22:42 | 30-Jul-2026 03:42:55 | 0 |  |  | Approver | Locate
AO-001455 | MM-ZTK-1F-GEN-QAC-PDR-8010 | MATERIAL CONTROL PROCEDURE |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 17:32:28 | kjb@coes.cn | 07-Aug-2026 17:40:58 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sukit Nualchanchai | 20-Aug-2026 | 10-Aug-2026 11:10:52 | Prin Jitatisil | 21-Aug-2026 | 10-Aug-2026 13:27:54 | NA | Not Approved | Jumpol Sudjitjul | 24-Aug-2026 | 10-Aug-2026 17:44:37 | 10-Aug-2026 11:24:26 | 0 |  |  | Approver | Locate
AO-001570 | MM-ZTK-1F-GEN-QAC-PDR-8010 | MATERIAL CONTROL PROCEDURE |  | B2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 17:16:36 | kjb@coes.cn | 18-Aug-2026 08:30:53 | Jumpol Sudjitjul | 25-Aug-2026 | 19-Aug-2026 09:07:14 | Sukit Nualchanchai | 27-Aug-2026 | 19-Aug-2026 11:36:30 | Prin Jitatisil | 28-Aug-2026 | 19-Aug-2026 14:13:29 | APPR | Approved | Jumpol Sudjitjul | 31-Aug-2026 | 19-Aug-2026 17:20:50 | 19-Aug-2026 10:51:27 | 0 |  |  | Approver | Locate
AO-001644 | MM-ZTK-1F-GEN-QAC-PDR-8010 | MATERIAL CONTROL PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 10:31:27 | kjb@coes.cn | 21-Aug-2026 11:02:55 | Jumpol Sudjitjul | 28-Aug-2026 | 27-Aug-2026 16:23:41 | Sukit Nualchanchai | 01-Sep-2026 | 27-Aug-2026 16:57:35 | Prin Jitatisil | 02-Sep-2026 | 28-Aug-2026 09:09:34 | APPR | Approved | Jumpol Sudjitjul | 03-Sep-2026 | 28-Aug-2026 10:54:30 | 28-Aug-2026 04:51:27 | 0 |  |  | Approver | Locate
AO-001571 | MM-ZTK-1F-GEN-QAC-PDR-8011 | WELDING CONTROL PROCEDURE - WP-1 (T&I) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 17-Aug-2026 17:17:04 | kjb@coes.cn | 18-Aug-2026 08:33:30 | Jumpol Sudjitjul | 25-Aug-2026 | 19-Aug-2026 06:14:56 | Sukit Nualchanchai | 27-Aug-2026 | 31-Aug-2026 13:05:02 | Prin Jitatisil | 28-Aug-2026 | 31-Aug-2026 14:30:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Aug-2026 | 31-Aug-2026 15:50:12 | 31-Aug-2026 10:46:05 | 0 |  |  | Approver | Locate
AO-002320 | MM-ZTK-1F-GEN-QAC-PDR-9002 | WELDING PROCEDURE QUALIFICATION TEST (WPQT) FOR SUBSEA TIE-IN SPOOLS (C/W INSPECTION AND TEST PLAN) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 30-Sep-2026 17:22:01 | 26002z1fdcc@thoresen-jutal.com | 01-Oct-2026 10:01:17 | Jumpol Sudjitjul | 08-Oct-2026 | 07-Oct-2026 08:44:01 | Sukit Nualchanchai | 12-Oct-2026 | 13-Oct-2026 14:16:52 | Prin Jitatisil | 14-Oct-2026 | 14-Oct-2026 09:54:51 | APPR | Approved | Jumpol Sudjitjul | 15-Oct-2026 | 14-Oct-2026 16:39:09 | 14-Oct-2026 10:00:51 | 0 |  |  | Approver | Locate
AO-002318 | MM-ZTK-1F-GEN-QAC-PDR-9008 | WELDING CONSUMABLE HANDLING AND CONTROL PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | In Review | IFR | Issued for Review |  | 30-Sep-2026 16:14:01 | 26002z1fdcc@thoresen-jutal.com | 30-Sep-2026 17:27:41 | Jumpol Sudjitjul | 08-Oct-2026 | 16-Oct-2026 19:59:59 | Sukit Nualchanchai | 12-Oct-2026 |  | Prin Jitatisil | 14-Oct-2026 |  |  |  |  | 15-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000042 | MM-ZTK-1F-GEN-QAC-PDR-9024 | CRITICALITY ANALYSIS REPORT AND SURVEILANCE MANAGEMENT FOR WORK PACKAGE 2 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 23-Mar-2026 18:00:50 | 26002z1fdcc@thoresen-jutal.com | 24-Mar-2026 13:33:27 | Jumpol Sudjitjul | 31-Mar-2026 | 02-Apr-2026 09:28:38 | Sukit Nualchanchai | 02-Apr-2026 | 02-Apr-2026 17:37:43 | Prin Jitatisil | 03-Apr-2026 | 06-Apr-2026 17:38:51 | NA | Not Approved | Jumpol Sudjitjul | 07-Apr-2026 | 06-Apr-2026 21:32:12 | 06-Apr-2026 22:01:27 | 0 |  |  | Approver | Locate
AO-000307 | MM-ZTK-1F-GEN-QAC-PDR-9024 | CRITICALITY ANALYSIS REPORT AND SURVEILANCE MANAGEMENT FOR WORK PACKAGE 2 |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | IFR | Issued for Review | 23-Apr-2026 | 05-May-2026 17:50:48 | 26002z1fdcc@thoresen-jutal.com | 06-May-2026 10:23:15 | Jumpol Sudjitjul | 13-May-2026 | 19-May-2026 11:22:50 | Sukit Nualchanchai | 15-May-2026 | 19-May-2026 13:21:26 | Prin Jitatisil | 18-May-2026 | 21-May-2026 09:31:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 21-May-2026 13:11:36 | 21-May-2026 13:30:10 | 0 |  |  | Approver | Locate
AO-000715 | MM-ZTK-1F-GEN-QAC-PDR-9024 | CRITICALITY ANALYSIS REPORT AND SURVEILANCE MANAGEMENT FOR WORK PACKAGE 2 |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 08-Jun-2026 18:37:41 | 26002z1fdcc@thoresen-jutal.com | 09-Jun-2026 08:59:59 | Jumpol Sudjitjul | 16-Jun-2026 | 15-Jun-2026 16:31:03 | Sukit Nualchanchai | 18-Jun-2026 | 17-Jun-2026 15:20:24 | Prin Jitatisil | 19-Jun-2026 | 18-Jun-2026 09:43:53 | APPR | Approved | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 09:46:11 | 18-Jun-2026 03:26:52 | 0 |  |  | Approver | Locate
AO-002406 | MM-ZTK-1F-GEN-QAC-PDR-9025 | PWPS FOR RISER HANGER FLANGE AND INSTALLATION AIDS FABRICATION |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PDR | Procedure | 0 | In Review | IFR | Issued for Review |  | 07-Oct-2026 11:17:40 | 26002z1fdcc@thoresen-jutal.com | 07-Oct-2026 13:44:46 | Jumpol Sudjitjul | 15-Oct-2026 | 16-Oct-2026 18:39:28 | Sukit Nualchanchai | 19-Oct-2026 |  | Prin Jitatisil | 20-Oct-2026 |  |  |  |  | 21-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000008 | MM-ZTK-1F-GEN-QAC-PLN-0001 | PROJECT QUALITY PLAN |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 04-Mar-2026 14:47:36 | 26002z1fdcc@thoresen-jutal.com | 04-Mar-2026 17:45:16 | Jumpol Sudjitjul | 12-Mar-2026 | 17-Mar-2026 21:27:07 | Poramate Kamlangkeng | 16-Mar-2026 | 20-Mar-2026 09:05:40 | Prin Jitatisil | 17-Mar-2026 | 22-Mar-2026 22:39:20 | NA | Not Approved | Jumpol Sudjitjul | 18-Mar-2026 | 23-Mar-2026 09:35:57 | 23-Mar-2026 10:12:24 | 0 |  |  | Approver | Locate
AO-000151 | MM-ZTK-1F-GEN-QAC-PLN-0001 | PROJECT QUALITY PLAN |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PLN | Plan | 0 | Submitted | IFR | Issued for Review | 07-Apr-2026 | 17-Apr-2026 23:42:01 | 26002z1fdcc@thoresen-jutal.com | 19-Apr-2026 22:15:36 | Jumpol Sudjitjul | 27-Apr-2026 | 09-May-2026 22:38:07 | Poramate Kamlangkeng | 29-Apr-2026 | 11-May-2026 15:37:06 | Prin Jitatisil | 30-Apr-2026 | 13-May-2026 14:40:57 | APPR | Approved | Jumpol Sudjitjul | 05-May-2026 | 13-May-2026 15:19:14 | 13-May-2026 16:00:34 | 0 |  |  | Approver | Locate
AO-000728 | MM-ZTK-1F-GEN-QAC-PLN-0001 | PROJECT QUALITY PLAN |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PLN | Plan | 0 | Submitted | IFA | Issued for Approval |  | 10-Jun-2026 09:22:12 | 26002z1fdcc@thoresen-jutal.com | 10-Jun-2026 10:29:10 | Jumpol Sudjitjul | 17-Jun-2026 | 18-Jun-2026 00:25:52 | Poramate Kamlangkeng | 19-Jun-2026 | 23-Jun-2026 12:38:44 | Prin Jitatisil | 22-Jun-2026 | 23-Jun-2026 16:27:16 | APPR | Approved | Jumpol Sudjitjul | 23-Jun-2026 | 23-Jun-2026 16:39:39 | 23-Jun-2026 10:09:20 | 0 |  |  | Approver | Locate
AO-000886 | MM-ZTK-1F-GEN-QAC-PLN-0001 | PROJECT QUALITY PLAN |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 24-Jun-2026 13:19:26 | 26002z1fdcc@thoresen-jutal.com | 24-Jun-2026 14:52:45 | Jumpol Sudjitjul | 01-Jul-2026 | 27-Jun-2026 21:40:38 | Poramate Kamlangkeng | 03-Jul-2026 | 03-Jul-2026 08:15:58 | Prin Jitatisil | 06-Jul-2026 | 06-Jul-2026 11:44:34 | APPR | Approved | Jumpol Sudjitjul | 07-Jul-2026 | 06-Jul-2026 11:50:07 | 06-Jul-2026 05:36:28 | 0 |  |  | Approver | Locate
AO-000397 | MM-ZTK-1F-GEN-QAC-PLN-5002 | PROJECT QUALITY PLAN (WORK PACKAGE 1) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 14-May-2026 11:03:44 | zm169dc@jutal.com | 14-May-2026 13:13:58 | Jumpol Sudjitjul | 21-May-2026 | 25-May-2026 15:55:29 | Poramate Kamlangkeng | 25-May-2026 | 01-Jun-2026 14:22:55 | Prin Jitatisil | 26-May-2026 | 05-Jun-2026 08:13:41 | NA | Not Approved | Jumpol Sudjitjul | 27-May-2026 | 05-Jun-2026 08:41:31 | 05-Jun-2026 01:55:15 | 0 |  |  | Approver | Locate
AO-001433 | MM-ZTK-1F-GEN-QAC-PLN-5002 | PROJECT QUALITY PLAN (WORK PACKAGE 1) |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 06-Aug-2026 14:04:48 | zm169dc@jutal.com | 06-Aug-2026 14:48:34 | Jumpol Sudjitjul | 14-Aug-2026 | 08-Aug-2026 07:05:00 | Poramate Kamlangkeng | 18-Aug-2026 | 14-Aug-2026 16:10:27 | Prin Jitatisil | 19-Aug-2026 | 15-Aug-2026 11:24:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 15-Aug-2026 14:46:04 | 15-Aug-2026 08:22:36 | 0 |  |  | Approver | Locate
AO-002235 | MM-ZTK-1F-GEN-QAC-PLN-5002 | PROJECT QUALITY PLAN (WORK PACKAGE 1) |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 23-Sep-2026 18:20:54 | zm169dc@jutal.com | 24-Sep-2026 09:38:45 | Jumpol Sudjitjul | 01-Oct-2026 | 25-Sep-2026 11:29:20 | Poramate Kamlangkeng | 05-Oct-2026 | 28-Sep-2026 12:21:05 | Prin Jitatisil | 06-Oct-2026 | 28-Sep-2026 14:20:22 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 29-Sep-2026 14:18:29 | 29-Sep-2026 08:00:26 | 0 |  |  | Approver | Locate
AO-000398 | MM-ZTK-1F-GEN-QAC-PLN-5003 | WPQT ITP & WPQT PLAN FOR STEEL STRUCTURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 14-May-2026 11:04:13 | zm169dc@jutal.com | 14-May-2026 13:16:32 | Jumpol Sudjitjul | 21-May-2026 | 25-May-2026 16:09:25 | Poramate Kamlangkeng | 25-May-2026 | 01-Jun-2026 14:54:47 | Prin Jitatisil | 26-May-2026 | 05-Jun-2026 09:03:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-May-2026 | 05-Jun-2026 09:07:04 | 05-Jun-2026 02:28:50 | 0 |  |  | Approver | Locate
AO-000664 | MM-ZTK-1F-GEN-QAC-PLN-8001 | TRANSPORTATION AND OFFSHORE INSTALLATION QUALITY PLAN FOR WORK PACKAGE 1 T&I |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 04-Jun-2026 13:32:50 | kjb@coes.cn | 04-Jun-2026 20:21:46 | Jumpol Sudjitjul | 12-Jun-2026 | 05-Jun-2026 15:48:28 | Sukit Nualchanchai | 16-Jun-2026 | 11-Jun-2026 00:59:51 | Prin Jitatisil | 17-Jun-2026 | 11-Jun-2026 13:58:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Jun-2026 | 11-Jun-2026 14:05:58 | 11-Jun-2026 07:42:01 | 0 |  |  | Approver | Locate
AO-000884 | MM-ZTK-1F-GEN-QAC-PLN-8001 | TRANSPORTATION AND OFFSHORE INSTALLATION QUALITY PLAN FOR WORK PACKAGE 1 T&I |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PLN | Plan | 0 | Submitted | IFA | Issued for Approval |  | 24-Jun-2026 13:19:58 | kjb@coes.cn | 24-Jun-2026 14:53:13 | Jumpol Sudjitjul | 01-Jul-2026 | 27-Jun-2026 07:15:41 | Sukit Nualchanchai | 03-Jul-2026 | 02-Jul-2026 08:53:36 | Prin Jitatisil | 06-Jul-2026 | 06-Jul-2026 11:44:58 | APPR | Approved | Jumpol Sudjitjul | 07-Jul-2026 | 06-Jul-2026 11:46:43 | 06-Jul-2026 05:35:03 | 0 |  |  | Approver | Locate
AO-001936 | MM-ZTK-1F-GEN-QAC-PLN-8001 | TRANSPORTATION AND OFFSHORE INSTALLATION QUALITY PLAN FOR WORK PACKAGE 1 T&I |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 08-Sep-2026 18:02:12 | kjb@coes.cn | 09-Sep-2026 08:48:04 | Jumpol Sudjitjul | 16-Sep-2026 | 19-Sep-2026 15:40:09 | Sukit Nualchanchai | 18-Sep-2026 | 28-Sep-2026 15:01:36 | Prin Jitatisil | 21-Sep-2026 | 29-Sep-2026 09:12:31 | APPR | Approved | Jumpol Sudjitjul | 22-Sep-2026 | 29-Sep-2026 14:20:37 | 29-Sep-2026 07:44:08 | 0 |  |  | Approver | Locate
AO-000196 | MM-ZTK-1F-GEN-QAC-PLN-8002 | PROCUREMENT AND SUPPLY CHAIN QUALITY PLAN |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 14:04:43 | kjb@coes.cn | 22-Apr-2026 10:23:44 | Jumpol Sudjitjul | 29-Apr-2026 | 11-May-2026 17:41:31 | Sukit Nualchanchai | 05-May-2026 | 14-May-2026 17:24:19 | Prin Jitatisil | 06-May-2026 | 16-May-2026 23:49:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 17-May-2026 08:21:44 | 17-May-2026 08:34:31 | 0 |  |  | Approver | Locate
AO-000667 | MM-ZTK-1F-GEN-QAC-PLN-8002 | PROCUREMENT AND SUPPLY CHAIN QUALITY PLAN |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PLN | Plan | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 14:57:12 | kjb@coes.cn | 04-Jun-2026 16:41:54 | Jumpol Sudjitjul | 11-Jun-2026 | 06-Jun-2026 10:40:07 | Sukit Nualchanchai | 15-Jun-2026 | 10-Jun-2026 00:32:44 | Prin Jitatisil | 16-Jun-2026 | 10-Jun-2026 15:56:55 | APPR | Approved | Jumpol Sudjitjul | 17-Jun-2026 | 10-Jun-2026 17:07:30 | 10-Jun-2026 10:36:16 | 0 |  |  | Approver | Locate
AO-000893 | MM-ZTK-1F-GEN-QAC-PLN-8002 | PROCUREMENT AND SUPPLY CHAIN QUALITY PLAN |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 25-Jun-2026 14:25:40 | kjb@coes.cn | 25-Jun-2026 15:18:53 | Jumpol Sudjitjul | 02-Jul-2026 |  | Sukit Nualchanchai | 06-Jul-2026 | 02-Jul-2026 16:42:41 | Prin Jitatisil | 07-Jul-2026 | 06-Jul-2026 11:45:52 | APPR | Approved | Jumpol Sudjitjul | 08-Jul-2026 | 06-Jul-2026 11:49:07 | 06-Jul-2026 05:31:18 | 0 |  |  | Approver | Locate
AO-001802 | MM-ZTK-1F-GEN-QAC-PLN-9001 | QUALITY CONTROL PLAN - PIPELINE INSTALLATION (C/W INSPECTION AND TEST PLAN) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 31-Aug-2026 16:49:28 | 26002z1fdcc@thoresen-jutal.com | 02-Sep-2026 08:40:46 | Neeranuch Nutong | 09-Sep-2026 | 08-Sep-2026 16:29:46 | Sukit Nualchanchai | 11-Sep-2026 | 11-Sep-2026 17:47:04 | Prin Jitatisil | 14-Sep-2026 | 11-Sep-2026 22:39:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Sep-2026 | 12-Sep-2026 20:57:21 | 12-Sep-2026 14:24:40 | 0 |  |  | Approver | Locate
AO-002326 | MM-ZTK-1F-GEN-QAC-PLN-9001 | QUALITY CONTROL PLAN - PIPELINE INSTALLATION (C/W INSPECTION AND TEST PLAN) |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PLN | Plan | 0 | Submitted | IFA | Issued for Approval |  | 01-Oct-2026 17:23:21 | 26002z1fdcc@thoresen-jutal.com | 02-Oct-2026 14:28:40 | Jumpol Sudjitjul | 09-Oct-2026 | 06-Oct-2026 11:08:58 | Sukit Nualchanchai | 14-Oct-2026 | 15-Oct-2026 17:10:49 | Prin Jitatisil | 15-Oct-2026 | 15-Oct-2026 17:35:38 | APPR | Approved | Jumpol Sudjitjul | 16-Oct-2026 | 16-Oct-2026 14:08:17 | 16-Oct-2026 07:59:04 | 0 |  |  | Approver | Locate
AO-002048 | MM-ZTK-1F-GEN-QAC-PLN-9002 | QUALITY CONTROL PLAN FOR ONSHORE PRE-FABRICATION OF TIE-IN SPOOLS (C/W INSPECTION AND TEST PLAN) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 14-Sep-2026 19:32:36 | 26002z1fdcc@thoresen-jutal.com | 15-Sep-2026 15:54:22 | Jumpol Sudjitjul | 22-Sep-2026 | 29-Sep-2026 18:01:18 | Sukit Nualchanchai | 24-Sep-2026 | 29-Sep-2026 22:19:30 | Prin Jitatisil | 25-Sep-2026 | 30-Sep-2026 08:14:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 30-Sep-2026 13:06:30 | 30-Sep-2026 06:21:50 | 0 |  |  | Approver | Locate
AO-002465 | MM-ZTK-1F-GEN-QAC-PLN-9002 | QUALITY CONTROL PLAN FOR ONSHORE PRE-FABRICATION OF TIE-IN SPOOLS (C/W INSPECTION AND TEST PLAN) |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | PLN | Plan | 0 | Submitted | IFA | Issued for Approval |  | 09-Oct-2026 16:44:45 | 26002z1fdcc@thoresen-jutal.com | 09-Oct-2026 18:10:07 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sukit Nualchanchai | 22-Oct-2026 | 15-Oct-2026 17:16:48 | Prin Jitatisil | 26-Oct-2026 | 15-Oct-2026 17:35:58 | APPR | Approved | Jumpol Sudjitjul | 27-Oct-2026 | 16-Oct-2026 14:22:05 | 16-Oct-2026 07:47:35 | 0 |  |  | Approver | Locate
AO-002248 | MM-ZTK-1F-GEN-QAC-RGT-5001 | REGISTER OF QUALIFIED WELDERSWELDING OPERATORS FOR STRUCTURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | RGT | Register | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 15:01:33 | zm169dc@jutal.com | 24-Sep-2026 15:07:20 | Jumpol Sudjitjul | 01-Oct-2026 | 25-Sep-2026 11:36:05 | Poramate Kamlangkeng | 05-Oct-2026 | 28-Sep-2026 12:21:57 | Prin Jitatisil | 06-Oct-2026 | 28-Sep-2026 14:21:03 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 29-Sep-2026 14:21:27 | 29-Sep-2026 08:14:55 | 0 |  |  | Approver | Locate
AO-000571 | MM-ZTK-1F-GEN-QAC-RGT-5002 | NDE PERSONNEL REGISTER, RESUME AND QUALIFICATION |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | RGT | Register | 0 | Submitted | IFR | Issued for Review |  | 23-May-2026 08:54:27 | zm169dc@jutal.com | 23-May-2026 09:39:13 | Jumpol Sudjitjul | 29-May-2026 | 23-May-2026 23:15:05 | Poramate Kamlangkeng | 04-Jun-2026 | 05-Jun-2026 09:18:59 | Prin Jitatisil | 05-Jun-2026 | 06-Jun-2026 10:56:34 | NA | Not Approved | Jumpol Sudjitjul | 08-Jun-2026 | 07-Jun-2026 17:26:38 | 07-Jun-2026 11:26:41 | 0 |  |  | Approver | Locate
AO-001023 | MM-ZTK-1F-GEN-QAC-RGT-5002 | NDE PERSONNEL REGISTER, RESUME AND QUALIFICATION |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | RGT | Register | 0 | Submitted | IFR | Issued for Review |  | 06-Jul-2026 10:44:27 | zm169dc@jutal.com | 06-Jul-2026 10:47:10 | Jumpol Sudjitjul | 13-Jul-2026 | 07-Jul-2026 16:38:03 | Poramate Kamlangkeng | 15-Jul-2026 | 14-Jul-2026 08:14:07 | Prin Jitatisil | 16-Jul-2026 | 14-Jul-2026 08:56:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 14-Jul-2026 09:08:35 | 14-Jul-2026 03:21:27 | 0 |  |  | Approver | Locate
AO-001195 | MM-ZTK-1F-GEN-QAC-RGT-5002 | NDE PERSONNEL REGISTER, RESUME AND QUALIFICATION |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | RGT | Register | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 10:41:05 | zm169dc@jutal.com | 20-Jul-2026 15:42:17 | Jumpol Sudjitjul | 27-Jul-2026 | 24-Jul-2026 14:33:29 | Poramate Kamlangkeng | 31-Jul-2026 | 27-Jul-2026 10:47:45 | Prin Jitatisil | 03-Aug-2026 | 27-Jul-2026 18:25:02 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 28-Jul-2026 08:45:04 | 28-Jul-2026 02:21:49 | 0 |  |  | Approver | Locate
AO-001459 | MM-ZTK-1F-GEN-QAC-RGT-5002 | NDE PERSONNEL REGISTER, RESUME AND QUALIFICATION |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | RGT | Register | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 17:33:07 | zm169dc@jutal.com | 07-Aug-2026 17:40:02 | Jumpol Sudjitjul | 18-Aug-2026 | 12-Aug-2026 07:14:20 | Poramate Kamlangkeng | 20-Aug-2026 | 15-Aug-2026 08:46:51 | Prin Jitatisil | 21-Aug-2026 | 15-Aug-2026 11:25:56 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 15-Aug-2026 14:40:23 | 15-Aug-2026 08:13:53 | 0 |  |  | Approver | Locate
AO-002091 | MM-ZTK-1F-GEN-QAC-RGT-5002 | NDE PERSONNEL REGISTER, RESUME AND QUALIFICATION |  | C2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | RGT | Register | 0 | Submitted | AFC | Approved for Construction |  | 15-Sep-2026 17:43:29 | zhaoli@jutal.com | 16-Sep-2026 16:57:16 | Jumpol Sudjitjul | 23-Sep-2026 | 17-Sep-2026 08:10:02 | Poramate Kamlangkeng | 25-Sep-2026 | 18-Sep-2026 09:52:12 | Prin Jitatisil | 28-Sep-2026 | 20-Sep-2026 01:26:31 | APPR | Approved | Jumpol Sudjitjul | 29-Sep-2026 | 20-Sep-2026 17:10:06 | 20-Sep-2026 11:24:45 | 0 |  |  | Approver | Locate
AO-000978 | MM-ZTK-1F-GEN-QAC-RGT-5003 | NDT EQUIPMENTS & TOOLS CALIBRATION REGISTER LIST |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | RGT | Register | 0 | Submitted | IFR | Issued for Review |  | 02-Jul-2026 17:56:31 | zm169dc@jutal.com | 03-Jul-2026 14:51:15 | Jumpol Sudjitjul | 10-Jul-2026 | 15-Jul-2026 12:07:20 | Witsarut Wanitanukool | 14-Jul-2026 | 30-Jul-2026 17:09:40 | Prin Jitatisil | 15-Jul-2026 | 30-Jul-2026 18:28:20 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 16-Jul-2026 | 30-Jul-2026 19:15:20 | 30-Jul-2026 12:55:56 | 0 |  |  | Approver | Locate
AO-001576 | MM-ZTK-1F-GEN-QAC-RGT-5003 | NDT EQUIPMENTS & TOOLS CALIBRATION REGISTER LIST |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | RGT | Register | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 18:03:17 | zm169dc@jutal.com | 18-Aug-2026 15:16:15 | Jumpol Sudjitjul | 25-Aug-2026 | 18-Aug-2026 15:50:42 | Poramate Kamlangkeng | 27-Aug-2026 | 31-Aug-2026 12:55:09 | Prin Jitatisil | 28-Aug-2026 | 31-Aug-2026 14:30:49 | APPR | Approved | Jumpol Sudjitjul | 31-Aug-2026 | 31-Aug-2026 15:53:58 | 31-Aug-2026 09:59:58 | 0 |  |  | Approver | Locate
AO-002379 | MM-ZTK-1F-GEN-QAC-RGT-5003 | NDT EQUIPMENTS & TOOLS CALIBRATION REGISTER LIST |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | RGT | Register | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 18:05:14 | zhaoli@jutal.com | 06-Oct-2026 08:58:40 | Jumpol Sudjitjul | 14-Oct-2026 | 12-Oct-2026 14:03:16 | Poramate Kamlangkeng | 16-Oct-2026 | 17-Oct-2026 12:01:34 | Prin Jitatisil | 19-Oct-2026 | 17-Oct-2026 13:15:52 | APPR | Approved | Jumpol Sudjitjul | 20-Oct-2026 | 18-Oct-2026 09:21:53 | 18-Oct-2026 05:25:47 | 0 |  |  | Approver | Locate
AO-001041 | MM-ZTK-1F-GEN-QAC-TQ-5001 | ACCEPTANCE OF SAW FLUX SUPPLIED IN NON-COMPLIANT PACKAGING FOR WPQT |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | TQ | Technical Query | 0 | Submitted | IFI | Issued for Information |  | 09-Jul-2026 15:36:34 | zm169dc@jutal.com | 09-Jul-2026 17:20:14 | Jumpol Sudjitjul |  |  | Poramate Kamlangkeng |  | 10-Jul-2026 07:50:49 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 10-Jul-2026 08:02:32 | 10-Jul-2026 02:07:25 | 0 |  |  | For Info | Locate
AO-002066 | MM-ZTK-1F-GEN-QAC-WPS-5001 | WELDING PROCEDURE SPECIFICATION NO ZM169-S001 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:33:08 | zhaoli@jutal.com | 15-Sep-2026 15:40:15 | Jumpol Sudjitjul | 22-Sep-2026 | 17-Sep-2026 23:18:21 | Poramate Kamlangkeng | 24-Sep-2026 | 18-Sep-2026 09:39:01 | Prin Jitatisil | 25-Sep-2026 | 18-Sep-2026 09:41:22 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 18-Sep-2026 10:14:16 | 18-Sep-2026 03:54:41 | 0 |  |  | Approver | Locate
AO-002066 | MM-ZTK-1F-GEN-QAC-WPS-5002 | WELDING PROCEDURE SPECIFICATION NO ZM169-S002 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:33:45 | zhaoli@jutal.com | 15-Sep-2026 15:40:16 | Jumpol Sudjitjul | 22-Sep-2026 | 17-Sep-2026 23:21:03 | Poramate Kamlangkeng | 24-Sep-2026 | 18-Sep-2026 09:41:22 | Prin Jitatisil | 25-Sep-2026 | 20-Sep-2026 01:26:46 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 20-Sep-2026 17:09:32 | 20-Sep-2026 11:33:22 | 0 |  |  | Approver | Locate
AO-001831 | MM-ZTK-1F-GEN-QAC-WPS-5003 | WELDING PROCEDURE SPECIFICATION NO ZM169-S003 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 10:08:32 | zm169dc@jutal.com | 03-Sep-2026 11:46:22 | Jumpol Sudjitjul | 10-Sep-2026 | 04-Sep-2026 09:59:10 | Poramate Kamlangkeng | 14-Sep-2026 | 08-Sep-2026 09:48:41 | Prin Jitatisil | 15-Sep-2026 | 08-Sep-2026 11:18:16 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 08-Sep-2026 13:31:31 | 08-Sep-2026 07:34:17 | 0 |  |  | Approver | Locate
AO-002066 | MM-ZTK-1F-GEN-QAC-WPS-5004 | WELDING PROCEDURE SPECIFICATION NO ZM169-S004 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:34:20 | zhaoli@jutal.com | 15-Sep-2026 15:40:20 | Jumpol Sudjitjul | 22-Sep-2026 | 17-Sep-2026 23:19:34 | Poramate Kamlangkeng | 24-Sep-2026 | 18-Sep-2026 09:40:15 | Prin Jitatisil | 25-Sep-2026 | 18-Sep-2026 09:50:25 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 18-Sep-2026 10:08:12 | 18-Sep-2026 03:50:02 | 0 |  |  | Approver | Locate
AO-001831 | MM-ZTK-1F-GEN-QAC-WPS-5005 | WELDING PROCEDURE SPECIFICATION NO ZM169-S005 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 10:09:16 | zm169dc@jutal.com | 03-Sep-2026 11:46:24 | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 15:56:11 | Poramate Kamlangkeng | 14-Sep-2026 | 08-Sep-2026 09:50:51 | Prin Jitatisil | 15-Sep-2026 | 08-Sep-2026 11:18:30 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 08-Sep-2026 13:34:53 | 08-Sep-2026 07:35:32 | 0 |  |  | Approver | Locate
AO-002066 | MM-ZTK-1F-GEN-QAC-WPS-5006 | WELDING PROCEDURE SPECIFICATION NO ZM169-S006 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:34:53 | zhaoli@jutal.com | 15-Sep-2026 15:40:21 | Jumpol Sudjitjul | 22-Sep-2026 | 17-Sep-2026 23:20:17 | Poramate Kamlangkeng | 24-Sep-2026 | 18-Sep-2026 09:40:50 | Prin Jitatisil | 25-Sep-2026 | 20-Sep-2026 01:27:00 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 20-Sep-2026 17:08:55 | 20-Sep-2026 11:32:12 | 0 |  |  | Approver | Locate
AO-002066 | MM-ZTK-1F-GEN-QAC-WPS-5010 | WELDING PROCEDURE SPECIFICATION NO ZM169-S010 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:35:25 | zhaoli@jutal.com | 15-Sep-2026 15:40:22 | Jumpol Sudjitjul | 22-Sep-2026 | 17-Sep-2026 23:21:52 | Poramate Kamlangkeng | 24-Sep-2026 | 18-Sep-2026 09:42:03 | Prin Jitatisil | 25-Sep-2026 | 20-Sep-2026 01:27:14 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 20-Sep-2026 17:08:07 | 20-Sep-2026 11:30:56 | 0 |  |  | Approver | Locate
AO-001831 | MM-ZTK-1F-GEN-QAC-WPS-5013 | WELDING PROCEDURE SPECIFICATION NO ZM169-S013 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 10:09:55 | zm169dc@jutal.com | 03-Sep-2026 11:46:21 | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 15:30:13 | Poramate Kamlangkeng | 14-Sep-2026 | 08-Sep-2026 09:34:24 | Prin Jitatisil | 15-Sep-2026 | 08-Sep-2026 09:37:03 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 08-Sep-2026 13:37:42 | 08-Sep-2026 07:37:51 | 0 |  |  | Approver | Locate
AO-001831 | MM-ZTK-1F-GEN-QAC-WPS-5014 | WELDING PROCEDURE SPECIFICATION NO ZM169-S014 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 10:10:35 | zm169dc@jutal.com | 03-Sep-2026 11:46:23 | Jumpol Sudjitjul | 10-Sep-2026 | 04-Sep-2026 10:40:36 | Poramate Kamlangkeng | 14-Sep-2026 | 08-Sep-2026 09:50:04 | Prin Jitatisil | 15-Sep-2026 | 08-Sep-2026 11:18:50 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 08-Sep-2026 13:38:11 | 08-Sep-2026 07:39:01 | 0 |  |  | Approver | Locate
AO-001831 | MM-ZTK-1F-GEN-QAC-WPS-5015 | WELDING PROCEDURE SPECIFICATION NO ZM169-S015 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 10:11:09 | zm169dc@jutal.com | 03-Sep-2026 11:46:22 | Jumpol Sudjitjul | 10-Sep-2026 | 04-Sep-2026 10:44:10 | Poramate Kamlangkeng | 14-Sep-2026 | 08-Sep-2026 09:47:59 | Prin Jitatisil | 15-Sep-2026 | 08-Sep-2026 11:19:09 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 08-Sep-2026 13:38:40 | 08-Sep-2026 07:40:14 | 0 |  |  | Approver | Locate
AO-001831 | MM-ZTK-1F-GEN-QAC-WPS-5017 | WELDING PROCEDURE SPECIFICATION NO ZM169-S017 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 10:11:47 | zm169dc@jutal.com | 03-Sep-2026 11:46:24 | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 15:55:40 | Poramate Kamlangkeng | 14-Sep-2026 | 08-Sep-2026 09:51:51 | Prin Jitatisil | 15-Sep-2026 | 08-Sep-2026 11:19:49 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 08-Sep-2026 13:39:16 | 08-Sep-2026 07:41:29 | 0 |  |  | Approver | Locate
AO-001831 | MM-ZTK-1F-GEN-QAC-WPS-5018 | WELDING PROCEDURE SPECIFICATION NO ZM169-S018 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 10:12:19 | zm169dc@jutal.com | 03-Sep-2026 11:46:22 | Jumpol Sudjitjul | 10-Sep-2026 | 04-Sep-2026 10:49:19 | Poramate Kamlangkeng | 14-Sep-2026 | 08-Sep-2026 09:47:15 | Prin Jitatisil | 15-Sep-2026 | 08-Sep-2026 11:20:15 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 08-Sep-2026 13:42:03 | 08-Sep-2026 07:42:43 | 0 |  |  | Approver | Locate
AO-001831 | MM-ZTK-1F-GEN-QAC-WPS-5019 | WELDING PROCEDURE SPECIFICATION NO ZM169-S019 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 10:12:57 | zm169dc@jutal.com | 03-Sep-2026 11:46:22 | Jumpol Sudjitjul | 10-Sep-2026 | 04-Sep-2026 10:51:10 | Poramate Kamlangkeng | 14-Sep-2026 | 08-Sep-2026 09:49:24 | Prin Jitatisil | 15-Sep-2026 | 08-Sep-2026 11:20:31 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 08-Sep-2026 13:42:46 | 08-Sep-2026 07:43:52 | 0 |  |  | Approver | Locate
AO-001831 | MM-ZTK-1F-GEN-QAC-WPS-5021 | WELDING PROCEDURE SPECIFICATION NO ZM169-S021 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 10:13:31 | zm169dc@jutal.com | 03-Sep-2026 13:07:22 | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 15:30:38 | Poramate Kamlangkeng | 14-Sep-2026 | 08-Sep-2026 10:11:00 | Prin Jitatisil | 15-Sep-2026 | 08-Sep-2026 11:20:58 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 08-Sep-2026 13:43:30 | 08-Sep-2026 07:45:04 | 0 |  |  | Approver | Locate
AO-001831 | MM-ZTK-1F-GEN-QAC-WPS-5023 | WELDING PROCEDURE SPECIFICATION NO ZM169-S023 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 10:14:02 | zm169dc@jutal.com | 03-Sep-2026 13:07:45 | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 15:29:36 | Poramate Kamlangkeng | 14-Sep-2026 | 08-Sep-2026 10:12:31 | Prin Jitatisil | 15-Sep-2026 | 08-Sep-2026 11:21:13 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 08-Sep-2026 13:43:55 | 08-Sep-2026 07:46:19 | 0 |  |  | Approver | Locate
AO-001831 | MM-ZTK-1F-GEN-QAC-WPS-5024 | WELDING PROCEDURE SPECIFICATION NO ZM169-S024 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 09:25:05 | zm169dc@jutal.com | 03-Sep-2026 13:08:02 | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 14:25:04 | Poramate Kamlangkeng | 14-Sep-2026 | 08-Sep-2026 10:14:17 | Prin Jitatisil | 15-Sep-2026 | 08-Sep-2026 11:21:27 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 08-Sep-2026 13:44:19 | 08-Sep-2026 07:24:54 | 0 |  |  | Approver | Locate
AO-002066 | MM-ZTK-1F-GEN-QAC-WPS-5026 | WELDING PROCEDURE SPECIFICATION NO ZM169-S026 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:35:57 | zhaoli@jutal.com | 15-Sep-2026 15:40:24 | Jumpol Sudjitjul | 22-Sep-2026 | 17-Sep-2026 23:09:40 | Poramate Kamlangkeng | 24-Sep-2026 | 18-Sep-2026 09:46:51 | Prin Jitatisil | 25-Sep-2026 | 20-Sep-2026 01:27:28 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 20-Sep-2026 17:47:54 | 20-Sep-2026 11:37:04 | 0 |  |  | Approver | Locate
AO-001831 | MM-ZTK-1F-GEN-QAC-WPS-5027 | WELDING PROCEDURE SPECIFICATION NO ZM169-S027 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 09:25:36 | zm169dc@jutal.com | 03-Sep-2026 11:50:48 | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 15:34:27 | Poramate Kamlangkeng | 14-Sep-2026 | 08-Sep-2026 10:04:59 | Prin Jitatisil | 15-Sep-2026 | 08-Sep-2026 11:21:46 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 08-Sep-2026 13:45:02 | 08-Sep-2026 07:28:51 | 0 |  |  | Approver | Locate
AO-001831 | MM-ZTK-1F-GEN-QAC-WPS-5028 | WELDING PROCEDURE SPECIFICATION NO ZM169-S028 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 09:26:12 | zm169dc@jutal.com | 03-Sep-2026 11:50:45 | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 15:45:11 | Poramate Kamlangkeng | 14-Sep-2026 | 08-Sep-2026 09:53:55 | Prin Jitatisil | 15-Sep-2026 | 08-Sep-2026 11:21:59 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 08-Sep-2026 13:45:40 | 08-Sep-2026 07:31:39 | 0 |  |  | Approver | Locate
AO-002066 | MM-ZTK-1F-GEN-QAC-WPS-5029 | WELDING PROCEDURE SPECIFICATION NO ZM169-S029 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:36:34 | zhaoli@jutal.com | 15-Sep-2026 15:40:17 | Jumpol Sudjitjul | 22-Sep-2026 | 17-Sep-2026 23:18:56 | Poramate Kamlangkeng | 24-Sep-2026 | 18-Sep-2026 09:39:40 | Prin Jitatisil | 25-Sep-2026 | 18-Sep-2026 09:41:48 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 18-Sep-2026 09:58:16 | 18-Sep-2026 03:48:52 | 0 |  |  | Approver | Locate
AO-001831 | MM-ZTK-1F-GEN-QAC-WPS-5030 | WELDING PROCEDURE SPECIFICATION NO ZM169-S030 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 09:26:56 | zm169dc@jutal.com | 03-Sep-2026 11:50:51 | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 15:33:21 | Poramate Kamlangkeng | 14-Sep-2026 | 08-Sep-2026 10:08:19 | Prin Jitatisil | 15-Sep-2026 | 08-Sep-2026 11:22:39 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 08-Sep-2026 13:45:08 | 08-Sep-2026 07:30:13 | 0 |  |  | Approver | Locate
AO-002066 | MM-ZTK-1F-GEN-QAC-WPS-5031 | WELDING PROCEDURE SPECIFICATION NO ZM169-S031 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:37:17 | zhaoli@jutal.com | 15-Sep-2026 15:39:01 | Jumpol Sudjitjul | 22-Sep-2026 | 17-Sep-2026 23:13:27 | Poramate Kamlangkeng | 24-Sep-2026 | 18-Sep-2026 09:34:36 | Prin Jitatisil | 25-Sep-2026 | 18-Sep-2026 09:42:17 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 18-Sep-2026 09:55:44 | 18-Sep-2026 03:46:25 | 0 |  |  | Approver | Locate
AO-001831 | MM-ZTK-1F-GEN-QAC-WPS-5036 | WELDING PROCEDURE SPECIFICATION NO ZM169-S036 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 09:27:38 | zm169dc@jutal.com | 03-Sep-2026 11:50:53 | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 15:31:28 | Poramate Kamlangkeng | 14-Sep-2026 | 08-Sep-2026 10:09:26 | Prin Jitatisil | 15-Sep-2026 | 08-Sep-2026 11:22:55 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 08-Sep-2026 13:44:43 | 08-Sep-2026 07:27:35 | 0 |  |  | Approver | Locate
AO-002066 | MM-ZTK-1F-GEN-QAC-WPS-5037 | WELDING PROCEDURE SPECIFICATION NO ZM169-S037 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:37:50 | zhaoli@jutal.com | 15-Sep-2026 15:39:01 | Jumpol Sudjitjul | 22-Sep-2026 | 17-Sep-2026 23:10:37 | Poramate Kamlangkeng | 24-Sep-2026 | 18-Sep-2026 09:34:07 | Prin Jitatisil | 25-Sep-2026 | 18-Sep-2026 09:41:03 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 18-Sep-2026 09:54:47 | 18-Sep-2026 03:44:05 | 0 |  |  | Approver | Locate
AO-002066 | MM-ZTK-1F-GEN-QAC-WPS-5038 | WELDING PROCEDURE SPECIFICATION NO ZM169-S038 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:38:19 | zhaoli@jutal.com | 15-Sep-2026 15:39:02 | Jumpol Sudjitjul | 22-Sep-2026 | 17-Sep-2026 23:12:30 | Poramate Kamlangkeng | 24-Sep-2026 | 18-Sep-2026 09:32:19 | Prin Jitatisil | 25-Sep-2026 | 18-Sep-2026 09:50:07 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 18-Sep-2026 09:54:18 | 18-Sep-2026 03:42:49 | 0 |  |  | Approver | Locate
AO-002066 | MM-ZTK-1F-GEN-QAC-WPS-5039 | WELDING PROCEDURE SPECIFICATION NO ZM169-S039 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:38:49 | zhaoli@jutal.com | 15-Sep-2026 15:39:01 | Jumpol Sudjitjul | 22-Sep-2026 | 17-Sep-2026 23:14:18 | Poramate Kamlangkeng | 24-Sep-2026 | 18-Sep-2026 09:35:37 | Prin Jitatisil | 25-Sep-2026 | 18-Sep-2026 09:46:49 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 18-Sep-2026 09:53:47 | 18-Sep-2026 03:41:40 | 0 |  |  | Approver | Locate
AO-002066 | MM-ZTK-1F-GEN-QAC-WPS-5040 | WELDING PROCEDURE SPECIFICATION NO ZM169-S040 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:39:20 | zhaoli@jutal.com | 15-Sep-2026 15:39:05 | Jumpol Sudjitjul | 22-Sep-2026 | 17-Sep-2026 23:15:01 | Poramate Kamlangkeng | 24-Sep-2026 | 18-Sep-2026 09:36:11 | Prin Jitatisil | 25-Sep-2026 | 18-Sep-2026 09:46:01 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 18-Sep-2026 09:52:56 | 18-Sep-2026 03:40:30 | 0 |  |  | Approver | Locate
AO-001831 | MM-ZTK-1F-GEN-QAC-WPS-5043 | WELDING PROCEDURE SPECIFICATION NO ZM169-S043 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 09:28:35 | zm169dc@jutal.com | 03-Sep-2026 11:50:47 | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 15:37:41 | Poramate Kamlangkeng | 14-Sep-2026 | 08-Sep-2026 09:54:46 | Prin Jitatisil | 15-Sep-2026 | 08-Sep-2026 11:23:33 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 08-Sep-2026 13:44:16 | 08-Sep-2026 07:26:17 | 0 |  |  | Approver | Locate
AO-002066 | MM-ZTK-1F-GEN-QAC-WPS-5044 | WELDING PROCEDURE SPECIFICATION NO ZM169-S044 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:39:52 | zhaoli@jutal.com | 15-Sep-2026 15:39:09 | Jumpol Sudjitjul | 22-Sep-2026 | 17-Sep-2026 23:16:37 | Poramate Kamlangkeng | 24-Sep-2026 | 18-Sep-2026 09:37:16 | Prin Jitatisil | 25-Sep-2026 | 18-Sep-2026 09:47:13 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 18-Sep-2026 09:52:18 | 18-Sep-2026 03:39:13 | 0 |  |  | Approver | Locate
AO-002066 | MM-ZTK-1F-GEN-QAC-WPS-5045 | WELDING PROCEDURE SPECIFICATION NO ZM169-S045 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:40:26 | zhaoli@jutal.com | 15-Sep-2026 15:39:11 | Jumpol Sudjitjul | 22-Sep-2026 | 17-Sep-2026 23:15:38 | Poramate Kamlangkeng | 24-Sep-2026 | 18-Sep-2026 09:36:47 | Prin Jitatisil | 25-Sep-2026 | 18-Sep-2026 09:50:45 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 18-Sep-2026 10:11:03 | 18-Sep-2026 03:52:25 | 0 |  |  | Approver | Locate
AO-002066 | MM-ZTK-1F-GEN-QAC-WPS-5046 | WELDING PROCEDURE SPECIFICATION NO ZM169-S046 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:40:54 | zhaoli@jutal.com | 15-Sep-2026 15:39:09 | Jumpol Sudjitjul | 22-Sep-2026 | 17-Sep-2026 23:17:45 | Poramate Kamlangkeng | 24-Sep-2026 | 18-Sep-2026 09:38:27 | Prin Jitatisil | 25-Sep-2026 | 18-Sep-2026 10:04:55 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 18-Sep-2026 19:04:05 | 18-Sep-2026 12:59:37 | 0 |  |  | Approver | Locate
AO-002066 | MM-ZTK-1F-GEN-QAC-WPS-5058 | WELDING PROCEDURE SPECIFICATION NO ZM169-S058 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:41:27 | zhaoli@jutal.com | 15-Sep-2026 15:39:09 | Jumpol Sudjitjul | 22-Sep-2026 | 17-Sep-2026 23:11:37 | Poramate Kamlangkeng | 24-Sep-2026 | 18-Sep-2026 09:33:24 | Prin Jitatisil | 25-Sep-2026 | 18-Sep-2026 10:05:33 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 18-Sep-2026 19:01:31 | 18-Sep-2026 12:57:15 | 0 |  |  | Approver | Locate
AO-001831 | MM-ZTK-1F-GEN-QAC-WPS-5060 | WELDING PROCEDURE SPECIFICATION NO ZM169-S060 |  | C1 | Project Document | Engineering Document | Part E - Fabrication Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 09:29:17 | zm169dc@jutal.com | 03-Sep-2026 11:50:49 | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 15:33:59 | Poramate Kamlangkeng | 14-Sep-2026 | 08-Sep-2026 10:05:57 | Prin Jitatisil | 15-Sep-2026 | 08-Sep-2026 11:23:47 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 08-Sep-2026 13:43:50 | 08-Sep-2026 07:23:39 | 0 |  |  | Approver | Locate
AO-002523 | MM-ZTK-1F-GEN-QAC-WPS-5072 | WELDING PROCEDURE SPECIFICATION NO ZM169-S072 |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 16:41:01 | zhaoli@jutal.com | 15-Oct-2026 11:29:22 | Jumpol Sudjitjul | 22-Oct-2026 |  | Poramate Kamlangkeng | 27-Oct-2026 | 17-Oct-2026 12:21:12 | Prin Jitatisil | 28-Oct-2026 | 17-Oct-2026 13:16:13 | APPR | Approved | Jumpol Sudjitjul | 29-Oct-2026 | 18-Oct-2026 09:21:26 | 18-Oct-2026 05:05:34 | 0 |  |  | Approver | Locate
AO-001592 | MM-ZTK-1F-GEN-QAC-WPS-S001 | WELDING PROCEDURE SPECIFICATION NO.S001 |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Latest | AFC | Approved for Construction |  | 18-Aug-2026 16:38:39 | zm169dc@jutal.com | 19-Aug-2026 10:08:44 | Jumpol Sudjitjul | 26-Aug-2026 | 20-Aug-2026 11:36:41 | Poramate Kamlangkeng | 28-Aug-2026 |  | Prin Jitatisil | 31-Aug-2026 |  |  |  |  | 01-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001592 | MM-ZTK-1F-GEN-QAC-WPS-S002 | WELDING PROCEDURE SPECIFICATION NO.S002 |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Latest | AFC | Approved for Construction |  | 18-Aug-2026 16:40:14 | zm169dc@jutal.com | 19-Aug-2026 10:08:44 | Jumpol Sudjitjul | 26-Aug-2026 | 20-Aug-2026 11:35:37 | Poramate Kamlangkeng | 28-Aug-2026 |  | Prin Jitatisil | 31-Aug-2026 |  |  |  |  | 01-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001592 | MM-ZTK-1F-GEN-QAC-WPS-S004 | WELDING PROCEDURE SPECIFICATION NO.S004 |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Latest | AFC | Approved for Construction |  | 18-Aug-2026 16:41:49 | zm169dc@jutal.com | 19-Aug-2026 10:08:46 | Jumpol Sudjitjul | 26-Aug-2026 | 20-Aug-2026 11:40:17 | Poramate Kamlangkeng | 28-Aug-2026 |  | Prin Jitatisil | 31-Aug-2026 |  |  |  |  | 01-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001592 | MM-ZTK-1F-GEN-QAC-WPS-S006 | WELDING PROCEDURE SPECIFICATION NO.S006 |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Latest | AFC | Approved for Construction |  | 18-Aug-2026 16:43:28 | zm169dc@jutal.com | 19-Aug-2026 10:08:45 | Jumpol Sudjitjul | 26-Aug-2026 | 20-Aug-2026 11:38:34 | Poramate Kamlangkeng | 28-Aug-2026 |  | Prin Jitatisil | 31-Aug-2026 |  |  |  |  | 01-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001592 | MM-ZTK-1F-GEN-QAC-WPS-S010 | WELDING PROCEDURE SPECIFICATION NO.S010 |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Latest | AFC | Approved for Construction |  | 18-Aug-2026 16:44:55 | zm169dc@jutal.com | 19-Aug-2026 10:08:44 | Jumpol Sudjitjul | 26-Aug-2026 | 20-Aug-2026 11:37:24 | Poramate Kamlangkeng | 28-Aug-2026 |  | Prin Jitatisil | 31-Aug-2026 |  |  |  |  | 01-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001592 | MM-ZTK-1F-GEN-QAC-WPS-S029 | WELDING PROCEDURE SPECIFICATION NO.S029 |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Latest | AFC | Approved for Construction |  | 18-Aug-2026 16:46:20 | zm169dc@jutal.com | 19-Aug-2026 10:08:47 | Jumpol Sudjitjul | 26-Aug-2026 | 20-Aug-2026 11:39:33 | Poramate Kamlangkeng | 28-Aug-2026 |  | Prin Jitatisil | 31-Aug-2026 |  |  |  |  | 01-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001592 | MM-ZTK-1F-GEN-QAC-WPS-S031 | WELDING PROCEDURE SPECIFICATION NO.S031 |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Latest | AFC | Approved for Construction |  | 18-Aug-2026 15:22:22 | zm169dc@jutal.com | 19-Aug-2026 10:08:50 | Jumpol Sudjitjul | 26-Aug-2026 | 20-Aug-2026 11:40:57 | Poramate Kamlangkeng | 28-Aug-2026 |  | Prin Jitatisil | 31-Aug-2026 |  |  |  |  | 01-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001592 | MM-ZTK-1F-GEN-QAC-WPS-S037 | WELDING PROCEDURE SPECIFICATION NO.S037 |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Latest | AFC | Approved for Construction |  | 18-Aug-2026 15:23:08 | zm169dc@jutal.com | 19-Aug-2026 10:34:46 | Jumpol Sudjitjul | 26-Aug-2026 | 20-Aug-2026 11:45:49 | Poramate Kamlangkeng | 28-Aug-2026 |  | Prin Jitatisil | 31-Aug-2026 |  |  |  |  | 01-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001592 | MM-ZTK-1F-GEN-QAC-WPS-S038 | WELDING PROCEDURE SPECIFICATION NO.S038 |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Latest | AFC | Approved for Construction |  | 18-Aug-2026 15:23:42 | zm169dc@jutal.com | 19-Aug-2026 10:14:00 | Jumpol Sudjitjul | 26-Aug-2026 | 20-Aug-2026 11:45:09 | Poramate Kamlangkeng | 28-Aug-2026 |  | Prin Jitatisil | 31-Aug-2026 |  |  |  |  | 01-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001592 | MM-ZTK-1F-GEN-QAC-WPS-S040 | WELDING PROCEDURE SPECIFICATION NO.S040 |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Latest | AFC | Approved for Construction |  | 18-Aug-2026 15:24:14 | zm169dc@jutal.com | 19-Aug-2026 10:13:41 | Jumpol Sudjitjul | 26-Aug-2026 | 20-Aug-2026 11:44:30 | Poramate Kamlangkeng | 28-Aug-2026 |  | Prin Jitatisil | 31-Aug-2026 |  |  |  |  | 01-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001592 | MM-ZTK-1F-GEN-QAC-WPS-S044 | WELDING PROCEDURE SPECIFICATION NO.S044 |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Latest | AFC | Approved for Construction |  | 18-Aug-2026 15:24:52 | zm169dc@jutal.com | 19-Aug-2026 10:13:15 | Jumpol Sudjitjul | 26-Aug-2026 | 20-Aug-2026 11:43:36 | Poramate Kamlangkeng | 28-Aug-2026 |  | Prin Jitatisil | 31-Aug-2026 |  |  |  |  | 01-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001592 | MM-ZTK-1F-GEN-QAC-WPS-S045 | WELDING PROCEDURE SPECIFICATION NO.S045 |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Latest | AFC | Approved for Construction |  | 18-Aug-2026 15:25:28 | zm169dc@jutal.com | 19-Aug-2026 10:12:58 | Jumpol Sudjitjul | 26-Aug-2026 | 20-Aug-2026 11:42:53 | Poramate Kamlangkeng | 28-Aug-2026 |  | Prin Jitatisil | 31-Aug-2026 |  |  |  |  | 01-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-001592 | MM-ZTK-1F-GEN-QAC-WPS-S046 | WELDING PROCEDURE SPECIFICATION NO.S046 |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | QAC | Quality Assurance and Quality Control | WPS | Welding Procedure Specification | 0 | Latest | AFC | Approved for Construction |  | 18-Aug-2026 15:25:58 | zm169dc@jutal.com | 19-Aug-2026 10:12:37 | Jumpol Sudjitjul | 26-Aug-2026 | 20-Aug-2026 11:41:40 | Poramate Kamlangkeng | 28-Aug-2026 |  | Prin Jitatisil | 31-Aug-2026 |  |  |  |  | 01-Sep-2026 |  |  | 0 |  |  | Approver | Locate
AO-000300 | MM-ZTK-1F-GEN-SAF-DTS-0001 | DATASHEET FOR FIRE FIGHTING, SAFETY EQUIPMENT AND SAFETY SIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 05-May-2026 09:09:11 | wisuda.c@jutal.com | 05-May-2026 09:56:14 | Jumpol Sudjitjul | 12-May-2026 |  | Arnon Srisuwan | 14-May-2026 | 07-Jun-2026 18:45:02 | Pornlert Wanaphattharaphan | 15-May-2026 | 08-Jun-2026 00:03:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-May-2026 | 08-Jun-2026 08:47:47 | 08-Jun-2026 02:25:40 | 0 |  |  | Approver | Locate
AO-000841 | MM-ZTK-1F-GEN-SAF-DTS-0001 | DATASHEET FOR FIRE FIGHTING, SAFETY EQUIPMENT AND SAFETY SIGN |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 22:37:32 | wisuda.c@jutal.com | 22-Jun-2026 13:52:04 | Jumpol Sudjitjul | 29-Jun-2026 |  | Arnon Srisuwan | 01-Jul-2026 | 03-Aug-2026 10:07:04 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 03-Aug-2026 22:05:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 04-Aug-2026 08:53:49 | 04-Aug-2026 02:20:12 | 0 |  |  | Approver | Locate
AO-002457 | MM-ZTK-1F-GEN-SAF-DTS-0001 | DATASHEET FOR FIRE FIGHTING, SAFETY EQUIPMENT AND SAFETY SIGN |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | DTS | Data Sheet | 0 | In Review | AFC | Approved for Construction |  | 09-Oct-2026 13:09:55 | wisuda.c@jutal.com | 09-Oct-2026 15:34:10 | Jumpol Sudjitjul | 19-Oct-2026 |  | Arnon Srisuwan | 21-Oct-2026 |  | Pornlert Wanaphattharaphan | 22-Oct-2026 |  |  |  |  | 26-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000359 | MM-ZTK-1F-GEN-SAF-LIS-0001 | HAZARDOUS EQUIPMENT SCHEDULE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:11:59 | wisuda.c@jutal.com | 11-May-2026 11:31:43 | Jumpol Sudjitjul | 18-May-2026 | 19-May-2026 13:45:00 | Arnon Srisuwan | 20-May-2026 | 07-Jun-2026 19:46:45 | Pornlert Wanaphattharaphan | 21-May-2026 | 08-Jun-2026 00:21:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 08-Jun-2026 08:52:49 | 08-Jun-2026 02:28:44 | 0 |  |  | Approver | Locate
AO-000896 | MM-ZTK-1F-GEN-SAF-LIS-0001 | HAZARDOUS EQUIPMENT SCHEDULE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 25-Jun-2026 23:08:06 | wisuda.c@jutal.com | 26-Jun-2026 08:43:29 | Jumpol Sudjitjul | 03-Jul-2026 |  | Arnon Srisuwan | 07-Jul-2026 | 17-Aug-2026 10:57:15 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 17-Aug-2026 20:48:08 | APPR | Approved | Jumpol Sudjitjul | 09-Jul-2026 | 18-Aug-2026 08:16:50 | 18-Aug-2026 01:32:26 | 0 |  |  | Approver | Locate
AO-000079 | MM-ZTK-1F-GEN-SAF-MOM-0001 | WHP TOPSIDE SAFETY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 07-Apr-2026 18:17:50 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000080 | MM-ZTK-1F-GEN-SAF-MOM-0002 | WHP TOPSIDE SAFETY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 07-Apr-2026 18:18:13 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000090 | MM-ZTK-1F-GEN-SAF-MOM-0003 | WHP TOPSIDE SAFETY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 08-Apr-2026 13:39:00 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000215 | MM-ZTK-1F-GEN-SAF-MOM-0004 | WHP TOPSIDE SAFETY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 23-Apr-2026 15:36:14 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000255 | MM-ZTK-1F-GEN-SAF-MOM-0005 | WHP TOPSIDE SAFETY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SAF | Safety Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 29-Apr-2026 09:49:47 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000342 | MM-ZTK-1F-GEN-SAF-MOM-0006 | WHP TOPSIDE SAFETY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 08-May-2026 12:45:08 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000386 | MM-ZTK-1F-GEN-SAF-MOM-0007 | WHP TOPSIDE SAFETY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 13-May-2026 15:29:31 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000719 | MM-ZTK-1F-GEN-SAF-MOM-0008 | WHP TOPSIDE SAFETY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 09-Jun-2026 13:57:33 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000726 | MM-ZTK-1F-GEN-SAF-MOM-0009 | WHP TOPSIDE SAFETY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 09-Jun-2026 17:21:43 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000815 | MM-ZTK-1F-GEN-SAF-MOM-0010 | WHP TOPSIDE SAFETY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 16-Jun-2026 16:28:36 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000888 | MM-ZTK-1F-GEN-SAF-MOM-0011 | WHP TOPSIDE SAFETY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 24-Jun-2026 14:10:34 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001107 | MM-ZTK-1F-GEN-SAF-MOM-0012 | WHP TOPSIDE SAFETY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Jul-2026 15:34:22 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001114 | MM-ZTK-1F-GEN-SAF-MOM-0013 | WHP TOPSIDE SAFETY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Jul-2026 17:33:49 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001259 | MM-ZTK-1F-GEN-SAF-MOM-0014 | WHP TOPSIDE SAFETY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 24-Jul-2026 09:58:28 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001416 | MM-ZTK-1F-GEN-SAF-MOM-0015 | WHP TOPSIDE SAFETY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 05-Aug-2026 11:58:23 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001592 | MM-ZTK-1F-GEN-SAF-MOM-0016 | WHP TOPSIDE SAFETY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 18-Aug-2026 15:21:08 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001617 | MM-ZTK-1F-GEN-SAF-MOM-0017 | WHP TOPSIDE SAFETY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 20-Aug-2026 09:33:47 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001711 | MM-ZTK-1F-GEN-SAF-MOM-0018 | WHP TOPSIDE SAFETY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 25-Aug-2026 18:33:30 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001947 | MM-ZTK-1F-GEN-SAF-MOM-0019 | WHP TOPSIDE SAFETY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 09-Sep-2026 10:16:45 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002280 | MM-ZTK-1F-GEN-SAF-MOM-0020 | WHP TOPSIDE SAFETY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 28-Sep-2026 09:42:33 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002407 | MM-ZTK-1F-GEN-SAF-MOM-0021 | WHP TOPSIDE SAFETY ENGINEERING PROGRESS MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 07-Oct-2026 11:17:12 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000733 | MM-ZTK-1F-GEN-SAF-MR-0001 | MATERIAL REQUISITION FOR FIRE FIGHTING, SAFETY EQUIPMENT (INCLUDING LIFESAVING) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 15:12:25 | wisuda.c@jutal.com | 10-Jun-2026 15:39:59 | Jumpol Sudjitjul | 17-Jun-2026 |  | Arnon Srisuwan | 19-Jun-2026 | 22-Jun-2026 08:55:53 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 22:21:45 | APPR | Approved | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 13:36:34 | 25-Jun-2026 08:00:30 | 0 |  |  | Approver | Locate
AO-001512 | MM-ZTK-1F-GEN-SAF-MR-0001 | MATERIAL REQUISITION FOR FIRE FIGHTING, SAFETY EQUIPMENT (INCLUDING LIFESAVING) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 13-Aug-2026 08:55:09 | wisuda.c@jutal.com | 13-Aug-2026 16:38:54 | Jumpol Sudjitjul | 20-Aug-2026 |  | Arnon Srisuwan | 24-Aug-2026 | 17-Aug-2026 10:58:44 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 17-Aug-2026 21:14:20 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 18-Aug-2026 08:19:33 | 18-Aug-2026 01:29:14 | 0 |  |  | Approver | Locate
AO-002457 | MM-ZTK-1F-GEN-SAF-MR-0001 | MATERIAL REQUISITION FOR FIRE FIGHTING, SAFETY EQUIPMENT (INCLUDING LIFESAVING) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MR | Material Requisition | 0 | In Review | AFC | Approved for Construction |  | 09-Oct-2026 13:10:22 | wisuda.c@jutal.com | 09-Oct-2026 15:29:13 | Jumpol Sudjitjul | 19-Oct-2026 |  | Arnon Srisuwan | 21-Oct-2026 |  | Pornlert Wanaphattharaphan | 22-Oct-2026 |  |  |  |  | 26-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000638 | MM-ZTK-1F-GEN-SAF-MR-0002 | MATERIAL REQUISITION FOR SAFETY SIGNS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 01-Jun-2026 10:04:07 | wisuda.c@jutal.com | 01-Jun-2026 12:33:33 | Jumpol Sudjitjul | 09-Jun-2026 |  | Arnon Srisuwan | 11-Jun-2026 | 07-Jun-2026 19:59:55 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 09-Jun-2026 12:17:32 | APPR | Approved | Jumpol Sudjitjul | 15-Jun-2026 | 09-Jun-2026 17:15:07 | 09-Jun-2026 17:46:43 | 0 |  |  | Approver | Locate
AO-000843 | MM-ZTK-1F-GEN-SAF-MR-0002 | MATERIAL REQUISITION FOR SAFETY SIGNS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 21-Jun-2026 22:37:57 | wisuda.c@jutal.com | 22-Jun-2026 13:52:41 | Jumpol Sudjitjul | 29-Jun-2026 |  | Arnon Srisuwan | 01-Jul-2026 | 17-Aug-2026 10:59:16 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 17-Aug-2026 20:45:31 | APPR | Approved | Jumpol Sudjitjul | 03-Jul-2026 | 18-Aug-2026 08:20:39 | 18-Aug-2026 01:36:46 | 0 |  |  | Approver | Locate
AO-002457 | MM-ZTK-1F-GEN-SAF-MR-0002 | MATERIAL REQUISITION FOR SAFETY SIGNS |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | MR | Material Requisition | 0 | In Review | AFC | Approved for Construction |  | 09-Oct-2026 13:10:50 | wisuda.c@jutal.com | 09-Oct-2026 15:29:35 | Jumpol Sudjitjul | 19-Oct-2026 |  | Arnon Srisuwan | 21-Oct-2026 |  | Pornlert Wanaphattharaphan | 22-Oct-2026 |  |  |  |  | 26-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001009 | MM-ZTK-1F-GEN-SAF-RAM-0001 | RELIABILITY, AVAILABILITY AND MAINTAINABILITY (RAM) STUDY |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RAM | Reliability Availability Maintainability | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 20:32:47 | wisuda.c@jutal.com | 04-Jul-2026 15:03:39 | Jumpol Sudjitjul | 10-Jul-2026 |  | Arnon Srisuwan | 14-Jul-2026 | 03-Aug-2026 10:09:44 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 03-Aug-2026 23:13:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 04-Aug-2026 09:14:09 | 04-Aug-2026 02:28:13 | 0 |  |  | Approver | Locate
AO-001465 | MM-ZTK-1F-GEN-SAF-RAM-0001 | RELIABILITY, AVAILABILITY AND MAINTAINABILITY (RAM) STUDY |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RAM | Reliability Availability Maintainability | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:59:59 | wisuda.c@jutal.com | 10-Aug-2026 14:46:44 | Jumpol Sudjitjul | 18-Aug-2026 |  | Arnon Srisuwan | 20-Aug-2026 | 17-Aug-2026 10:33:38 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:20:21 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 19:47:11 | 24-Aug-2026 13:43:09 | 0 |  |  | Approver | Locate
AO-002004 | MM-ZTK-1F-GEN-SAF-RAM-0001 | RELIABILITY, AVAILABILITY AND MAINTAINABILITY (RAM) STUDY |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RAM | Reliability Availability Maintainability | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 12:47:19 | wisuda.c@jutal.com | 11-Sep-2026 19:30:50 | Jumpol Sudjitjul | 21-Sep-2026 |  | Arnon Srisuwan | 23-Sep-2026 | 21-Sep-2026 15:11:05 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 24-Sep-2026 23:16:11 | APPR | Approved | Jumpol Sudjitjul | 25-Sep-2026 | 25-Sep-2026 08:26:37 | 25-Sep-2026 01:57:01 | 0 |  |  | Approver | Locate
AO-001353 | MM-ZTK-1F-GEN-SAF-RGT-0001 | HAZARD REGISTER |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RGT | Register | 0 | Submitted | IFR | Issued for Review |  | 31-Jul-2026 11:27:35 | wisuda.c@jutal.com | 31-Jul-2026 13:52:25 | Jumpol Sudjitjul | 07-Aug-2026 | 06-Aug-2026 22:33:14 | Arnon Srisuwan | 11-Aug-2026 | 17-Aug-2026 10:19:35 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 20-Aug-2026 21:23:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Aug-2026 | 21-Aug-2026 10:37:37 | 21-Aug-2026 04:03:25 | 0 |  |  | Approver | Locate
AO-001727 | MM-ZTK-1F-GEN-SAF-RGT-0001 | HAZARD REGISTER |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RGT | Register | 0 | Submitted | IFA | Issued for Approval |  | 26-Aug-2026 18:35:17 | wisuda.c@jutal.com | 27-Aug-2026 09:09:44 | Jumpol Sudjitjul | 03-Sep-2026 | 03-Sep-2026 23:42:12 | Arnon Srisuwan | 07-Sep-2026 | 07-Sep-2026 10:35:31 | Pornlert Wanaphattharaphan | 08-Sep-2026 | 08-Sep-2026 23:15:31 | APPR | Approved | Jumpol Sudjitjul | 09-Sep-2026 | 09-Sep-2026 10:42:56 | 09-Sep-2026 04:21:29 | 0 |  |  | Approver | Locate
AO-002069 | MM-ZTK-1F-GEN-SAF-RGT-0001 | HAZARD REGISTER |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RGT | Register | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 20:03:03 | wisuda.c@jutal.com | 15-Sep-2026 15:48:44 | Jumpol Sudjitjul | 22-Sep-2026 | 22-Sep-2026 23:49:13 | Arnon Srisuwan | 24-Sep-2026 | 08-Oct-2026 08:27:19 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 09-Oct-2026 13:46:02 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 09-Oct-2026 14:15:01 | 09-Oct-2026 07:31:28 | 0 |  |  | Approver | Locate
AO-000101 | MM-ZTK-1F-GEN-SAF-RPT-0001 | SAFETY CONCEPT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 09-Apr-2026 08:56:44 | neeranuchn@pttep.com | 10-Apr-2026 15:09:55 | Jumpol Sudjitjul | 22-Apr-2026 | 22-Apr-2026 13:19:04 | Arnon Srisuwan | 24-Apr-2026 | 11-May-2026 15:02:29 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 11-May-2026 20:02:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 12-May-2026 10:20:18 | 12-May-2026 10:35:51 | 0 |  |  | Approver | Locate
AO-000588 | MM-ZTK-1F-GEN-SAF-RPT-0001 | SAFETY CONCEPT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 24-May-2026 15:30:03 | wisuda.c@jutal.com | 24-May-2026 20:52:59 | Jumpol Sudjitjul | 02-Jun-2026 | 05-Jun-2026 15:44:13 | Arnon Srisuwan | 05-Jun-2026 | 07-Jun-2026 19:48:45 | Pornlert Wanaphattharaphan | 08-Jun-2026 | 10-Jun-2026 21:21:18 | APPR | Approved | Jumpol Sudjitjul | 09-Jun-2026 | 11-Jun-2026 11:10:58 | 11-Jun-2026 05:00:46 | 0 |  |  | Approver | Locate
AO-000890 | MM-ZTK-1F-GEN-SAF-RPT-0002 | SAFETY STUDIES ASSUMPTIONS REGISTER |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 25-Jun-2026 08:38:19 | wisuda.c@jutal.com | 25-Jun-2026 15:03:26 | Jumpol Sudjitjul | 02-Jul-2026 |  | Arnon Srisuwan | 06-Jul-2026 | 10-Aug-2026 10:04:06 | Pornlert Wanaphattharaphan | 07-Jul-2026 | 11-Aug-2026 23:30:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jul-2026 | 13-Aug-2026 11:24:13 | 13-Aug-2026 05:25:06 | 0 |  |  | Approver | Locate
AO-001584 | MM-ZTK-1F-GEN-SAF-RPT-0002 | SAFETY STUDIES ASSUMPTIONS REGISTER |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 18-Aug-2026 08:55:24 | wisuda.c@jutal.com | 18-Aug-2026 15:10:57 | Jumpol Sudjitjul | 25-Aug-2026 |  | Arnon Srisuwan | 27-Aug-2026 | 24-Aug-2026 10:52:38 | Pornlert Wanaphattharaphan | 28-Aug-2026 | 29-Aug-2026 23:08:23 | APPR | Approved | Jumpol Sudjitjul | 31-Aug-2026 | 30-Aug-2026 16:50:01 | 30-Aug-2026 10:52:44 | 0 |  |  | Approver | Locate
AO-000848 | MM-ZTK-1F-GEN-SAF-RPT-0003 | HAZID STUDY REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 22:38:28 | wisuda.c@jutal.com | 22-Jun-2026 13:54:49 | Jumpol Sudjitjul | 29-Jun-2026 | 06-Jul-2026 16:21:50 | Arnon Srisuwan | 01-Jul-2026 | 10-Aug-2026 10:02:16 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 11-Aug-2026 23:24:31 | APPR | Approved | Jumpol Sudjitjul | 03-Jul-2026 | 13-Aug-2026 11:12:14 | 13-Aug-2026 05:54:47 | 0 |  |  | Approver | Locate
AO-001623 | MM-ZTK-1F-GEN-SAF-RPT-0003 | HAZID STUDY REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 12:09:37 | wisuda.c@jutal.com | 20-Aug-2026 13:43:01 | Jumpol Sudjitjul | 27-Aug-2026 |  | Arnon Srisuwan | 31-Aug-2026 | 24-Aug-2026 10:53:32 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:30:33 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:51:07 | 30-Aug-2026 10:34:45 | 0 |  |  | Approver | Locate
AO-001961 | MM-ZTK-1F-GEN-SAF-RPT-0003 | HAZID STUDY REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 09-Sep-2026 18:09:05 | wisuda.c@jutal.com | 10-Sep-2026 10:30:42 | Jumpol Sudjitjul | 17-Sep-2026 | 17-Sep-2026 16:20:00 | Arnon Srisuwan | 21-Sep-2026 | 21-Sep-2026 15:11:53 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 24-Sep-2026 23:17:55 | APPR | Approved | Jumpol Sudjitjul | 23-Sep-2026 | 25-Sep-2026 08:25:41 | 25-Sep-2026 02:03:20 | 0 |  |  | Approver | Locate
AO-001064 | MM-ZTK-1F-GEN-SAF-RPT-0004 | HAZID CLOSE-OUT REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 10-Jul-2026 16:55:41 | wisuda.c@jutal.com | 10-Jul-2026 18:14:29 | Jumpol Sudjitjul | 20-Jul-2026 | 20-Jul-2026 15:42:06 | Arnon Srisuwan | 22-Jul-2026 | 03-Aug-2026 10:10:20 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 03-Aug-2026 23:15:00 | APPR | Approved | Jumpol Sudjitjul | 24-Jul-2026 | 04-Aug-2026 09:16:04 | 04-Aug-2026 02:24:27 | 0 |  |  | Approver | Locate
AO-001843 | MM-ZTK-1F-GEN-SAF-RPT-0004 | HAZID CLOSE-OUT REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 03-Sep-2026 16:48:23 | wisuda.c@jutal.com | 04-Sep-2026 08:09:58 | Jumpol Sudjitjul | 11-Sep-2026 | 04-Sep-2026 16:07:31 | Arnon Srisuwan | 15-Sep-2026 | 21-Sep-2026 14:11:04 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 24-Sep-2026 23:19:00 | APPR | Approved | Jumpol Sudjitjul | 17-Sep-2026 | 25-Sep-2026 08:24:07 | 25-Sep-2026 02:02:00 | 0 |  |  | Approver | Locate
AO-001113 | MM-ZTK-1F-GEN-SAF-RPT-0005 | HAZOP STUDY REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 14-Jul-2026 17:34:17 | wisuda.c@jutal.com | 14-Jul-2026 20:02:56 | Jumpol Sudjitjul | 22-Jul-2026 | 22-Jul-2026 14:33:25 | Arnon Srisuwan | 24-Jul-2026 | 03-Aug-2026 10:10:34 | Pornlert Wanaphattharaphan | 27-Jul-2026 | 03-Aug-2026 23:18:41 | APPR | Approved | Jumpol Sudjitjul | 30-Jul-2026 | 04-Aug-2026 09:17:32 | 04-Aug-2026 02:55:25 | 0 |  |  | Approver | Locate
AO-001476 | MM-ZTK-1F-GEN-SAF-RPT-0005 | HAZOP STUDY REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 12:00:37 | wisuda.c@jutal.com | 10-Aug-2026 14:43:34 | Jumpol Sudjitjul | 18-Aug-2026 |  | Arnon Srisuwan | 20-Aug-2026 | 17-Aug-2026 11:00:32 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:20:44 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 19:46:41 | 24-Aug-2026 13:42:01 | 0 |  |  | Approver | Locate
AO-001792 | MM-ZTK-1F-GEN-SAF-RPT-0005 | HAZOP STUDY REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 31-Aug-2026 08:40:36 | wisuda.c@jutal.com | 31-Aug-2026 12:55:47 | Jumpol Sudjitjul | 07-Sep-2026 | 04-Sep-2026 15:56:58 | Arnon Srisuwan | 09-Sep-2026 | 07-Sep-2026 10:37:00 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 22:41:03 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 12-Sep-2026 20:55:23 | 12-Sep-2026 14:32:32 | 0 |  |  | Approver | Locate
AO-001370 | MM-ZTK-1F-GEN-SAF-RPT-0006 | HAZOP CLOSE-OUT REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 10:54:57 | wisuda.c@jutal.com | 03-Aug-2026 14:21:14 | Jumpol Sudjitjul | 10-Aug-2026 | 09-Aug-2026 23:59:35 | Arnon Srisuwan | 13-Aug-2026 | 10-Aug-2026 10:12:50 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 10-Aug-2026 11:21:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 17:45:38 | 10-Aug-2026 11:09:47 | 0 |  |  | Approver | Locate
AO-001547 | MM-ZTK-1F-GEN-SAF-RPT-0006 | HAZOP CLOSE-OUT REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:22:18 | wisuda.c@jutal.com | 17-Aug-2026 15:53:42 | Jumpol Sudjitjul | 24-Aug-2026 | 23-Aug-2026 23:56:12 | Arnon Srisuwan | 26-Aug-2026 | 24-Aug-2026 10:54:30 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 27-Aug-2026 22:31:29 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 28-Aug-2026 10:55:25 | 28-Aug-2026 04:28:31 | 0 |  |  | Approver | Locate
AO-001185 | MM-ZTK-1F-GEN-SAF-RPT-0007 | SIL CLASSIFICATION REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 10:34:28 | wisuda.c@jutal.com | 20-Jul-2026 14:58:39 | Jumpol Sudjitjul | 27-Jul-2026 |  | Arnon Srisuwan | 31-Jul-2026 | 10-Aug-2026 10:27:04 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 11-Aug-2026 23:41:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 13-Aug-2026 11:11:42 | 13-Aug-2026 05:56:11 | 0 |  |  | Approver | Locate
AO-001623 | MM-ZTK-1F-GEN-SAF-RPT-0007 | SIL CLASSIFICATION REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 12:10:13 | wisuda.c@jutal.com | 20-Aug-2026 13:43:34 | Jumpol Sudjitjul | 27-Aug-2026 |  | Arnon Srisuwan | 31-Aug-2026 | 24-Aug-2026 10:55:44 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:32:02 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:42:28 | 30-Aug-2026 10:29:46 | 0 |  |  | Approver | Locate
AO-001961 | MM-ZTK-1F-GEN-SAF-RPT-0007 | SIL CLASSIFICATION REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 09-Sep-2026 18:09:46 | wisuda.c@jutal.com | 10-Sep-2026 10:31:45 | Jumpol Sudjitjul | 17-Sep-2026 | 17-Sep-2026 22:23:18 | Arnon Srisuwan | 21-Sep-2026 | 08-Oct-2026 08:29:45 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 09-Oct-2026 13:45:14 | APPR | Approved | Jumpol Sudjitjul | 23-Sep-2026 | 09-Oct-2026 14:17:58 | 09-Oct-2026 07:26:02 | 0 |  |  | Approver | Locate
AO-001346 | MM-ZTK-1F-GEN-SAF-RPT-0008 | SIL CLOSE-OUT REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 31-Jul-2026 09:29:38 | wisuda.c@jutal.com | 31-Jul-2026 09:44:33 | Jumpol Sudjitjul | 07-Aug-2026 | 06-Aug-2026 22:05:09 | Arnon Srisuwan | 11-Aug-2026 | 10-Aug-2026 10:27:54 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 16-Aug-2026 10:35:50 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 17-Aug-2026 13:59:58 | 17-Aug-2026 07:22:27 | 0 |  |  | Approver | Locate
AO-001623 | MM-ZTK-1F-GEN-SAF-RPT-0008 | SIL CLOSE-OUT REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 12:10:42 | wisuda.c@jutal.com | 20-Aug-2026 13:44:00 | Jumpol Sudjitjul | 27-Aug-2026 |  | Arnon Srisuwan | 31-Aug-2026 | 24-Aug-2026 10:56:47 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:32:31 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:41:30 | 30-Aug-2026 10:27:19 | 0 |  |  | Approver | Locate
AO-002005 | MM-ZTK-1F-GEN-SAF-RPT-0008 | SIL CLOSE-OUT REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 12:47:48 | wisuda.c@jutal.com | 11-Sep-2026 19:29:00 | Jumpol Sudjitjul | 21-Sep-2026 |  | Arnon Srisuwan | 23-Sep-2026 | 21-Sep-2026 15:07:31 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 24-Sep-2026 23:19:56 | APPR | Approved | Jumpol Sudjitjul | 25-Sep-2026 | 25-Sep-2026 08:22:37 | 25-Sep-2026 01:53:03 | 0 |  |  | Approver | Locate
AO-002026 | MM-ZTK-1F-GEN-SAF-RPT-0009 | ALARP WORKSHOP REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 14-Sep-2026 10:32:54 | wisuda.c@jutal.com | 15-Sep-2026 16:27:52 | Jumpol Sudjitjul | 22-Sep-2026 |  | Arnon Srisuwan | 24-Sep-2026 | 21-Sep-2026 14:55:20 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 22-Sep-2026 15:26:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 22-Sep-2026 16:24:59 | 22-Sep-2026 09:43:39 | 0 |  |  | Approver | Locate
AO-002262 | MM-ZTK-1F-GEN-SAF-RPT-0009 | ALARP WORKSHOP REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 25-Sep-2026 15:30:59 | wisuda.c@jutal.com | 25-Sep-2026 15:59:12 | Jumpol Sudjitjul | 02-Oct-2026 | 26-Sep-2026 23:22:31 | Arnon Srisuwan | 06-Oct-2026 | 05-Oct-2026 08:45:13 | Pornlert Wanaphattharaphan | 07-Oct-2026 | 10-Oct-2026 00:45:11 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 10-Oct-2026 17:41:01 | 10-Oct-2026 11:34:34 | 0 |  |  | Approver | Locate
AO-002561 | MM-ZTK-1F-GEN-SAF-RPT-0009 | ALARP WORKSHOP REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | In Review | AFC | Approved for Construction |  | 16-Oct-2026 19:14:22 | wisuda.c@jutal.com | 18-Oct-2026 16:41:54 | Jumpol Sudjitjul | 26-Oct-2026 |  | Arnon Srisuwan | 28-Oct-2026 |  | Pornlert Wanaphattharaphan | 29-Oct-2026 |  |  |  |  | 30-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-002177 | MM-ZTK-1F-GEN-SAF-RPT-0010 | ALARP CLOSE-OUT REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 21-Sep-2026 11:06:14 | wisuda.c@jutal.com | 21-Sep-2026 17:43:30 | Jumpol Sudjitjul | 29-Sep-2026 | 26-Sep-2026 23:22:57 | Arnon Srisuwan | 01-Oct-2026 | 05-Oct-2026 08:56:27 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 07-Oct-2026 23:35:45 | APPR | Approved | Jumpol Sudjitjul | 05-Oct-2026 | 08-Oct-2026 09:35:10 | 08-Oct-2026 03:56:04 | 0 |  |  | Approver | Locate
AO-002540 | MM-ZTK-1F-GEN-SAF-RPT-0010 | ALARP CLOSE-OUT REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | In Review | IFA | Issued for Approval |  | 16-Oct-2026 10:51:45 | wisuda.c@jutal.com | 16-Oct-2026 16:22:21 | Jumpol Sudjitjul | 26-Oct-2026 | 17-Oct-2026 17:23:15 | Arnon Srisuwan | 28-Oct-2026 |  | Pornlert Wanaphattharaphan | 29-Oct-2026 |  |  |  |  | 30-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001011 | MM-ZTK-1F-GEN-SAF-RPT-0011 | FIRE AND EXPLOSION RISK ANALYSIS (FERA) REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 20:33:13 | wisuda.c@jutal.com | 04-Jul-2026 15:02:15 | Jumpol Sudjitjul | 10-Jul-2026 | 12-Jul-2026 10:08:51 | Arnon Srisuwan | 14-Jul-2026 | 03-Aug-2026 10:11:53 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 03-Aug-2026 23:14:23 | APPR | Approved | Jumpol Sudjitjul | 16-Jul-2026 | 04-Aug-2026 09:19:49 | 04-Aug-2026 02:56:40 | 0 |  |  | Approver | Locate
AO-001466 | MM-ZTK-1F-GEN-SAF-RPT-0011 | FIRE AND EXPLOSION RISK ANALYSIS (FERA) REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 12:01:12 | wisuda.c@jutal.com | 10-Aug-2026 14:43:58 | Jumpol Sudjitjul | 18-Aug-2026 |  | Arnon Srisuwan | 20-Aug-2026 | 17-Aug-2026 11:04:22 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:21:04 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 19:47:34 | 24-Aug-2026 13:44:28 | 0 |  |  | Approver | Locate
AO-001782 | MM-ZTK-1F-GEN-SAF-RPT-0011 | FIRE AND EXPLOSION RISK ANALYSIS (FERA) REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 31-Aug-2026 08:41:05 | wisuda.c@jutal.com | 31-Aug-2026 12:56:18 | Jumpol Sudjitjul | 07-Sep-2026 |  | Arnon Srisuwan | 09-Sep-2026 | 07-Sep-2026 10:37:50 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 22:45:08 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 12-Sep-2026 20:59:24 | 12-Sep-2026 14:36:07 | 0 |  |  | Approver | Locate
AO-000871 | MM-ZTK-1F-GEN-SAF-RPT-0012 | VENT GAS DISPERSION & THERMAL RADIATION STUDY |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 23-Jun-2026 11:30:29 | wisuda.c@jutal.com | 23-Jun-2026 12:44:47 | Jumpol Sudjitjul | 30-Jun-2026 | 30-Jun-2026 22:18:27 | Arnon Srisuwan | 02-Jul-2026 | 08-Jul-2026 16:11:46 | Pornlert Wanaphattharaphan | 03-Jul-2026 | 10-Jul-2026 00:04:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Jul-2026 | 10-Jul-2026 08:09:41 | 10-Jul-2026 02:08:56 | 0 |  |  | Approver | Locate
AO-001255 | MM-ZTK-1F-GEN-SAF-RPT-0012 | VENT GAS DISPERSION & THERMAL RADIATION STUDY |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 08:40:59 | wisuda.c@jutal.com | 27-Jul-2026 15:49:02 | Jumpol Sudjitjul | 05-Aug-2026 | 05-Aug-2026 23:59:26 | Arnon Srisuwan | 07-Aug-2026 | 10-Aug-2026 11:04:34 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:55:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 11:25:11 | 13-Aug-2026 05:57:38 | 0 |  |  | Approver | Locate
AO-002254 | MM-ZTK-1F-GEN-SAF-RPT-0012 | VENT GAS DISPERSION & THERMAL RADIATION STUDY |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 18:10:30 | wisuda.c@jutal.com | 24-Sep-2026 18:15:57 | Jumpol Sudjitjul | 02-Oct-2026 | 04-Oct-2026 21:12:10 | Arnon Srisuwan | 06-Oct-2026 | 08-Oct-2026 08:40:01 | Pornlert Wanaphattharaphan | 07-Oct-2026 | 10-Oct-2026 01:13:58 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 10-Oct-2026 17:43:10 | 10-Oct-2026 11:37:36 | 0 |  |  | Approver | Locate
AO-001354 | MM-ZTK-1F-GEN-SAF-RPT-0015 | QUANTITATIVE RISK ASSESSMENT (QRA) REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 31-Jul-2026 11:28:03 | wisuda.c@jutal.com | 31-Jul-2026 13:54:04 | Jumpol Sudjitjul | 07-Aug-2026 | 06-Aug-2026 22:55:09 | Arnon Srisuwan | 11-Aug-2026 | 10-Aug-2026 11:23:37 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 16-Aug-2026 10:36:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Aug-2026 | 17-Aug-2026 14:01:42 | 17-Aug-2026 08:53:43 | 0 |  |  | Approver | Locate
AO-001674 | MM-ZTK-1F-GEN-SAF-RPT-0015 | QUANTITATIVE RISK ASSESSMENT (QRA) REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 09:45:37 | wisuda.c@jutal.com | 25-Aug-2026 11:56:48 | Jumpol Sudjitjul | 01-Sep-2026 | 01-Sep-2026 13:03:43 | Arnon Srisuwan | 03-Sep-2026 | 07-Sep-2026 10:40:12 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 08-Sep-2026 22:57:10 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 09-Sep-2026 11:06:47 | 09-Sep-2026 05:29:06 | 0 |  |  | Approver | Locate
AO-001885 | MM-ZTK-1F-GEN-SAF-RPT-0016 | SAFETY CRITICAL ELEMENTS & PERFORMANCE STANDARDS (SCEPS) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 04-Sep-2026 16:15:23 | wisuda.c@jutal.com | 05-Sep-2026 19:37:29 | Jumpol Sudjitjul | 14-Sep-2026 |  | Arnon Srisuwan | 16-Sep-2026 | 07-Sep-2026 09:59:06 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 12-Sep-2026 23:14:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 13-Sep-2026 08:14:29 | 13-Sep-2026 01:18:09 | 0 |  |  | Approver | Locate
AO-002250 | MM-ZTK-1F-GEN-SAF-RPT-0016 | SAFETY CRITICAL ELEMENTS & PERFORMANCE STANDARDS (SCEPS) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 24-Sep-2026 16:30:02 | wisuda.c@jutal.com | 24-Sep-2026 16:47:27 | Jumpol Sudjitjul | 01-Oct-2026 | 26-Sep-2026 22:53:09 | Arnon Srisuwan | 05-Oct-2026 | 05-Oct-2026 08:44:40 | Pornlert Wanaphattharaphan | 06-Oct-2026 | 06-Oct-2026 23:08:51 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 07-Oct-2026 08:30:25 | 07-Oct-2026 02:01:12 | 0 |  |  | Approver | Locate
AO-001561 | MM-ZTK-1F-GEN-SAF-RPT-0017 | SAFETY ENGINEERING ACTION TRACKING SYSTEM (SEAMS) REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 17-Aug-2026 14:23:16 | wisuda.c@jutal.com | 17-Aug-2026 15:57:00 | Jumpol Sudjitjul | 24-Aug-2026 |  | Arnon Srisuwan | 26-Aug-2026 | 24-Aug-2026 11:19:04 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 27-Aug-2026 22:34:05 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 28-Aug-2026 10:56:25 | 28-Aug-2026 04:30:35 | 0 |  |  | Approver | Locate
AO-001841 | MM-ZTK-1F-GEN-SAF-RPT-0017 | SAFETY ENGINEERING ACTION TRACKING SYSTEM (SEAMS) REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 03-Sep-2026 16:49:05 | wisuda.c@jutal.com | 04-Sep-2026 08:10:23 | Jumpol Sudjitjul | 11-Sep-2026 |  | Arnon Srisuwan | 15-Sep-2026 | 07-Sep-2026 10:43:14 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 16:44:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 12-Sep-2026 20:44:18 | 12-Sep-2026 13:56:18 | 0 |  |  | Approver | Locate
AO-002284 | MM-ZTK-1F-GEN-SAF-RPT-0017 | SAFETY ENGINEERING ACTION TRACKING SYSTEM (SEAMS) REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 09:43:07 | wisuda.c@jutal.com | 28-Sep-2026 10:11:41 | Jumpol Sudjitjul | 05-Oct-2026 |  | Arnon Srisuwan | 07-Oct-2026 | 08-Oct-2026 09:09:54 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 10-Oct-2026 01:33:56 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 10-Oct-2026 17:43:36 | 10-Oct-2026 11:01:47 | 0 |  |  | Approver | Locate
AO-001371 | MM-ZTK-1F-GEN-SAF-RPT-0020 | SIL VERIFICATION REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 10:55:28 | wisuda.c@jutal.com | 03-Aug-2026 14:23:35 | Jumpol Sudjitjul | 10-Aug-2026 | 10-Aug-2026 00:00:05 | Arnon Srisuwan | 13-Aug-2026 | 10-Aug-2026 11:24:14 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 23:11:37 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 14:02:30 | 17-Aug-2026 09:07:08 | 0 |  |  | Approver | Locate
AO-001642 | MM-ZTK-1F-GEN-SAF-RPT-0020 | SIL VERIFICATION REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 21-Aug-2026 09:40:56 | wisuda.c@jutal.com | 21-Aug-2026 10:51:27 | Jumpol Sudjitjul | 28-Aug-2026 | 27-Aug-2026 21:50:24 | Arnon Srisuwan | 01-Sep-2026 | 07-Sep-2026 10:43:44 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 08-Sep-2026 21:49:58 | APPR | Approved | Jumpol Sudjitjul | 03-Sep-2026 | 09-Sep-2026 11:08:27 | 09-Sep-2026 05:15:35 | 0 |  |  | Approver | Locate
AO-002542 | MM-ZTK-1F-GEN-SAF-RPT-0020 | SIL VERIFICATION REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | In Review | AFC | Approved for Construction |  | 16-Oct-2026 10:11:37 | wisuda.c@jutal.com | 16-Oct-2026 16:22:46 | Jumpol Sudjitjul | 26-Oct-2026 | 17-Oct-2026 17:17:48 | Arnon Srisuwan | 28-Oct-2026 |  | Pornlert Wanaphattharaphan | 29-Oct-2026 |  |  |  |  | 30-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000834 | MM-ZTK-1F-GEN-SAF-RPT-0100 | CRITICAL RATING ANALYSIS REPORT(SAFETY) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 09:24:45 | zm169dc@jutal.com | 19-Jun-2026 10:27:41 | Jumpol Sudjitjul | 26-Jun-2026 |  | Arnon Srisuwan | 30-Jun-2026 | 22-Jun-2026 08:46:01 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 24-Jun-2026 23:23:53 | APPR | Approved | Jumpol Sudjitjul | 02-Jul-2026 | 25-Jun-2026 13:37:27 | 25-Jun-2026 08:01:49 | 0 |  |  | Approver | Locate
AO-001321 | MM-ZTK-1F-GEN-SAF-RPT-0100 | CRITICAL RATING ANALYSIS REPORT(SAFETY) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 27-Jul-2026 11:25:53 | zm169dc@jutal.com | 27-Jul-2026 15:48:22 | Jumpol Sudjitjul | 05-Aug-2026 | 05-Aug-2026 23:59:33 | Arnon Srisuwan | 07-Aug-2026 | 10-Aug-2026 11:25:18 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:55:54 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 11:25:40 | 13-Aug-2026 05:37:49 | 0 |  |  | Approver | Locate
AO-000285 | MM-ZTK-1F-GEN-SAF-RPT-0101 | FIRE FIGHTING EQUIPMENT AND LIVE SAVING AND SAFETY EQUIPMENT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 30-Apr-2026 16:50:34 | zm169dc@jutal.com | 01-May-2026 11:02:56 | Jumpol Sudjitjul |  | 10-May-2026 14:22:46 | [11 empty] | 30-Apr-2026 08:06:59 | 0 |  |  | Approver | Locate
AO-000286 | MM-ZTK-1F-GEN-SAF-RPT-0102 | SAFETY SIGNS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 30-Apr-2026 16:51:02 | zm169dc@jutal.com | 01-May-2026 11:03:20 | Jumpol Sudjitjul |  | 10-May-2026 14:23:21 | [11 empty] | 30-Apr-2026 08:07:17 | 0 |  |  | Approver | Locate
AO-000301 | MM-ZTK-1F-GEN-SAF-SPE-0001 | SPECIFICATION FOR FIRE FIGHTING, SAFETY EQUIPMENT AND SAFETY SIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 05-May-2026 11:06:33 | wisuda.c@jutal.com | 05-May-2026 11:32:36 | Jumpol Sudjitjul | 12-May-2026 |  | Arnon Srisuwan | 14-May-2026 | 07-Jun-2026 19:11:13 | Pornlert Wanaphattharaphan | 15-May-2026 | 08-Jun-2026 00:10:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-May-2026 | 08-Jun-2026 08:53:59 | 08-Jun-2026 09:15:31 | 0 |  |  | Approver | Locate
AO-000842 | MM-ZTK-1F-GEN-SAF-SPE-0001 | SPECIFICATION FOR FIRE FIGHTING, SAFETY EQUIPMENT AND SAFETY SIGN |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | SPE | Specification | 0 | Submitted | IFA | Issued for Approval |  | 21-Jun-2026 22:38:54 | wisuda.c@jutal.com | 22-Jun-2026 13:55:11 | Jumpol Sudjitjul | 29-Jun-2026 |  | Arnon Srisuwan | 01-Jul-2026 | 03-Aug-2026 10:12:28 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 03-Aug-2026 22:06:53 | APPR | Approved | Jumpol Sudjitjul | 03-Jul-2026 | 04-Aug-2026 09:18:25 | 04-Aug-2026 02:57:52 | 0 |  |  | Approver | Locate
AO-001468 | MM-ZTK-1F-GEN-SAF-SPE-0001 | SPECIFICATION FOR FIRE FIGHTING, SAFETY EQUIPMENT AND SAFETY SIGN |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 10-Aug-2026 12:01:46 | wisuda.c@jutal.com | 10-Aug-2026 14:45:32 | Jumpol Sudjitjul | 18-Aug-2026 |  | Arnon Srisuwan | 20-Aug-2026 | 17-Aug-2026 11:05:29 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:22:27 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 19:54:52 | 24-Aug-2026 13:45:44 | 0 |  |  | Approver | Locate
AO-002457 | MM-ZTK-1F-GEN-SAF-SPE-0001 | SPECIFICATION FOR FIRE FIGHTING, SAFETY EQUIPMENT AND SAFETY SIGN |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | SPE | Specification | 0 | In Review | AFC | Approved for Construction |  | 09-Oct-2026 13:11:25 | wisuda.c@jutal.com | 09-Oct-2026 15:30:17 | Jumpol Sudjitjul | 19-Oct-2026 |  | Arnon Srisuwan | 21-Oct-2026 |  | Pornlert Wanaphattharaphan | 22-Oct-2026 |  |  |  |  | 26-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001350 | MM-ZTK-1F-GEN-SAF-STU-0001 | BOW - TIE STUDY REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | STU | Study Report | 0 | Submitted | IFR | Issued for Review |  | 31-Jul-2026 09:30:12 | wisuda.c@jutal.com | 31-Jul-2026 09:40:27 | Jumpol Sudjitjul | 07-Aug-2026 | 06-Aug-2026 21:33:37 | Arnon Srisuwan | 11-Aug-2026 | 17-Aug-2026 10:21:29 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 20-Aug-2026 21:24:19 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 21-Aug-2026 10:38:13 | 21-Aug-2026 04:04:39 | 0 |  |  | Approver | Locate
AO-001728 | MM-ZTK-1F-GEN-SAF-STU-0001 | BOW - TIE STUDY REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | STU | Study Report | 0 | Submitted | IFR | Issued for Review |  | 26-Aug-2026 18:35:56 | wisuda.c@jutal.com | 27-Aug-2026 09:07:29 | Jumpol Sudjitjul | 03-Sep-2026 | 03-Sep-2026 23:42:00 | Arnon Srisuwan | 07-Sep-2026 | 07-Sep-2026 10:07:31 | Pornlert Wanaphattharaphan | 08-Sep-2026 | 08-Sep-2026 23:12:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Sep-2026 | 09-Sep-2026 11:06:04 | 09-Sep-2026 05:01:20 | 0 |  |  | Approver | Locate
AO-002090 | MM-ZTK-1F-GEN-SAF-STU-0001 | BOW - TIE STUDY REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | STU | Study Report | 0 | Submitted | AFC | Approved for Construction |  | 15-Sep-2026 17:41:59 | wisuda.c@jutal.com | 16-Sep-2026 08:26:29 | Jumpol Sudjitjul | 23-Sep-2026 |  | Arnon Srisuwan | 25-Sep-2026 | 21-Sep-2026 14:57:30 | Pornlert Wanaphattharaphan | 28-Sep-2026 | 24-Sep-2026 23:21:07 | APPR | Approved | Jumpol Sudjitjul | 29-Sep-2026 | 25-Sep-2026 08:20:32 | 25-Sep-2026 01:59:34 | 0 |  |  | Approver | Locate
AO-000897 | MM-ZTK-1F-GEN-SAF-STU-0002 | DROPPED OBJECT STUDY |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | STU | Study Report | 0 | Submitted | IFR | Issued for Review |  | 25-Jun-2026 23:08:38 | wisuda.c@jutal.com | 26-Jun-2026 08:52:58 | Jumpol Sudjitjul | 03-Jul-2026 | 06-Jul-2026 16:25:00 | Arnon Srisuwan | 07-Jul-2026 | 08-Jul-2026 15:52:15 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 11-Jul-2026 13:47:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 12-Jul-2026 11:35:22 | 12-Jul-2026 04:50:38 | 0 |  |  | Approver | Locate
AO-001349 | MM-ZTK-1F-GEN-SAF-STU-0002 | DROPPED OBJECT STUDY |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | STU | Study Report | 0 | Submitted | IFA | Issued for Approval |  | 31-Jul-2026 09:30:51 | wisuda.c@jutal.com | 31-Jul-2026 09:42:44 | Jumpol Sudjitjul | 07-Aug-2026 | 06-Aug-2026 09:33:15 | Arnon Srisuwan | 11-Aug-2026 | 17-Aug-2026 10:24:38 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 20-Aug-2026 21:24:56 | APPR | Approved | Jumpol Sudjitjul | 14-Aug-2026 | 21-Aug-2026 10:36:05 | 21-Aug-2026 04:02:08 | 0 |  |  | Approver | Locate
AO-002236 | MM-ZTK-1F-GEN-SAF-STU-0002 | DROPPED OBJECT STUDY |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | STU | Study Report | 0 | Submitted | AFC | Approved for Construction |  | 23-Sep-2026 18:19:54 | wisuda.c@jutal.com | 24-Sep-2026 09:39:25 | Jumpol Sudjitjul | 01-Oct-2026 |  | Arnon Srisuwan | 05-Oct-2026 | 08-Oct-2026 09:08:10 | Pornlert Wanaphattharaphan | 06-Oct-2026 | 10-Oct-2026 00:19:23 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 10-Oct-2026 17:44:08 | 10-Oct-2026 11:03:05 | 0 |  |  | Approver | Locate
AO-001753 | MM-ZTK-1F-GEN-SAF-STU-0014 | SAFETY, SECURITY, HEALTH AND ENVIRONMENT (SSHE) DESIGN CASE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | STU | Study Report | 0 | Submitted | IFR | Issued for Review |  | 28-Aug-2026 11:37:38 | wisuda.c@jutal.com | 28-Aug-2026 14:22:04 | Jumpol Sudjitjul | 04-Sep-2026 |  | Arnon Srisuwan | 08-Sep-2026 | 07-Sep-2026 10:32:11 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 08-Sep-2026 23:38:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 09-Sep-2026 11:07:31 | 09-Sep-2026 04:56:35 | 0 |  |  | Approver | Locate
AO-002070 | MM-ZTK-1F-GEN-SAF-STU-0014 | SAFETY, SECURITY, HEALTH AND ENVIRONMENT (SSHE) DESIGN CASE |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | SAF | Safety Engineering | STU | Study Report | 0 | Submitted | IFA | Issued for Approval |  | 14-Sep-2026 19:27:51 | wisuda.c@jutal.com | 15-Sep-2026 15:12:30 | Jumpol Sudjitjul | 22-Sep-2026 |  | Arnon Srisuwan | 24-Sep-2026 | 21-Sep-2026 15:05:27 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 24-Sep-2026 23:22:55 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 25-Sep-2026 08:19:46 | 25-Sep-2026 01:51:48 | 0 |  |  | Approver | Locate
AO-001404 | MM-ZTK-1F-GEN-SSHE-CER-5001 | SSHE COMMENCEMENT CERTIFICATE REPORTS WP-1(EPC) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | CER | Certificate | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 19:13:46 | zm169dc@jutal.com | 04-Aug-2026 08:26:48 | Jumpol Sudjitjul | 11-Aug-2026 |  | Ananchai Mongkonpanyanan | 14-Aug-2026 | 16-Aug-2026 12:45:11 | Prin Jitatisil | 17-Aug-2026 | 18-Aug-2026 14:08:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 18-Aug-2026 14:29:06 | 18-Aug-2026 08:42:55 | 0 |  |  | Approver | Locate
AO-001645 | MM-ZTK-1F-GEN-SSHE-CER-5001 | SSHE COMMENCEMENT CERTIFICATE REPORTS WP-1(EPC) |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | CER | Certificate | 0 | Submitted | IFA | Issued for Approval |  | 21-Aug-2026 11:31:52 | zm169dc@jutal.com | 21-Aug-2026 13:13:13 | Jumpol Sudjitjul | 28-Aug-2026 |  | Ananchai Mongkonpanyanan | 01-Sep-2026 | 23-Aug-2026 13:09:32 | Prin Jitatisil | 02-Sep-2026 | 24-Aug-2026 08:54:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Sep-2026 | 24-Aug-2026 19:54:26 | 24-Aug-2026 14:22:00 | 0 |  |  | Approver | Locate
AO-000605 | MM-ZTK-1F-GEN-SSHE-MOM-0001 | MONTHLY SSHE PROGRESS MEETING NO.01 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 26-May-2026 16:47:20 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002093 | MM-ZTK-1F-GEN-SSHE-MOM-0002 | MONTHLY SSHE PROGRESS MEETING NO.02 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 16-Sep-2026 11:20:36 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002094 | MM-ZTK-1F-GEN-SSHE-MOM-0003 | MONTHLY SSHE PROGRESS MEETING NO.03 |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 16-Sep-2026 11:21:08 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000251 | MM-ZTK-1F-GEN-SSHE-MOM-1001 | SSHE KICK OFF MEETING |  | - | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 29-Apr-2026 08:29:09 | 26002z1fdcc@thoresen-jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000746 | MM-ZTK-1F-GEN-SSHE-PDR-0001 | SSHE PROGRESS MEASUREMENT PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 12-Jun-2026 08:37:18 | 26002z1fdcc@thoresen-jutal.com | 12-Jun-2026 15:20:19 | Jumpol Sudjitjul | 19-Jun-2026 | 19-Jun-2026 01:41:34 | Ananchai Mongkonpanyanan | 23-Jun-2026 | 27-Jun-2026 11:09:31 | Prin Jitatisil | 24-Jun-2026 | 29-Jun-2026 10:50:37 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 25-Jun-2026 | 30-Jun-2026 09:42:35 | 30-Jun-2026 04:23:07 | 0 |  |  | Approver | Locate
AO-000999 | MM-ZTK-1F-GEN-SSHE-PDR-0001 | SSHE PROGRESS MEASUREMENT PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 13:20:20 | 26002z1fdcc@thoresen-jutal.com | 03-Jul-2026 13:44:51 | Jumpol Sudjitjul | 10-Jul-2026 |  | Ananchai Mongkonpanyanan | 14-Jul-2026 | 13-Jul-2026 08:59:30 | Prin Jitatisil | 15-Jul-2026 | 13-Jul-2026 11:13:57 | APPR | Approved | Jumpol Sudjitjul | 16-Jul-2026 | 13-Jul-2026 13:31:04 | 13-Jul-2026 07:16:47 | 0 |  |  | Approver | Locate
AO-000805 | MM-ZTK-1F-GEN-SSHE-PDR-5001 | SAFETY CRITICAL ELEMENT(SCE) PROCEDURE WP-1 (EPC) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 15-Jun-2026 16:52:17 | zm169dc@jutal.com | 16-Jun-2026 10:28:08 | Jumpol Sudjitjul | 23-Jun-2026 |  | Ananchai Mongkonpanyanan | 25-Jun-2026 | 30-Jun-2026 11:57:46 | Prin Jitatisil | 26-Jun-2026 | 01-Jul-2026 09:51:56 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 29-Jun-2026 | 01-Jul-2026 15:35:20 | 01-Jul-2026 09:02:40 | 0 |  |  | Approver | Locate
AO-001034 | MM-ZTK-1F-GEN-SSHE-PDR-5001 | SAFETY CRITICAL ELEMENT(SCE) PROCEDURE WP-1 (EPC) |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 08-Jul-2026 08:54:02 | zm169dc@jutal.com | 08-Jul-2026 14:35:34 | Jumpol Sudjitjul | 15-Jul-2026 |  | Ananchai Mongkonpanyanan | 17-Jul-2026 | 13-Jul-2026 11:09:29 | Prin Jitatisil | 20-Jul-2026 | 13-Jul-2026 11:13:49 | APPR | Approved | Jumpol Sudjitjul | 21-Jul-2026 | 13-Jul-2026 13:35:51 | 13-Jul-2026 07:02:29 | 0 |  |  | Approver | Locate
AO-000668 | MM-ZTK-1F-GEN-SSHE-PDR-8001 | INCIDENT AND ANOMALY MANAGEMENT PROCEDURE - WP01 (T&I) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 04-Jun-2026 14:56:07 | kjb@coes.cn | 04-Jun-2026 16:40:37 | Jumpol Sudjitjul | 11-Jun-2026 | 17-Jun-2026 22:05:19 | Ananchai Mongkonpanyanan | 15-Jun-2026 | 21-Jun-2026 18:36:01 | Prin Jitatisil | 16-Jun-2026 | 23-Jun-2026 16:27:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 23-Jun-2026 16:33:54 | 23-Jun-2026 10:04:27 | 0 |  |  | Approver | Locate
AO-000992 | MM-ZTK-1F-GEN-SSHE-PDR-8001 | INCIDENT AND ANOMALY MANAGEMENT PROCEDURE - WP01 (T&I) |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 09:47:21 | kjb@coes.cn | 03-Jul-2026 13:45:51 | Jumpol Sudjitjul | 10-Jul-2026 | 09-Jul-2026 16:11:46 | Ananchai Mongkonpanyanan | 14-Jul-2026 | 13-Jul-2026 11:37:45 | Prin Jitatisil | 15-Jul-2026 | 13-Jul-2026 13:20:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 13-Jul-2026 13:36:58 | 13-Jul-2026 07:13:13 | 0 |  |  | Approver | Locate
AO-001630 | MM-ZTK-1F-GEN-SSHE-PDR-8001 | INCIDENT AND ANOMALY MANAGEMENT PROCEDURE - WP01 (T&I) |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 14:22:29 | kjb@coes.cn | 20-Aug-2026 14:41:43 | Jumpol Sudjitjul | 27-Aug-2026 | 22-Aug-2026 06:55:16 | Ananchai Mongkonpanyanan | 31-Aug-2026 | 31-Aug-2026 19:04:59 | Prin Jitatisil | 01-Sep-2026 | 01-Sep-2026 13:22:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Sep-2026 | 01-Sep-2026 15:20:54 | 01-Sep-2026 09:04:21 | 0 |  |  | Approver | Locate
AO-000252 | MM-ZTK-1F-GEN-SSHE-PDR-8002 | SUB-CONTRACTOR SSHE MANAGEMENT, PRE- SELECTION AND AUDIT PROCEDURE WORK PACKAGE 1 (T&I) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:14:36 | kjb@coes.cn | 29-Apr-2026 09:43:59 | Jumpol Sudjitjul | 08-May-2026 | 04-May-2026 14:46:38 | Ananchai Mongkonpanyanan | 12-May-2026 | 06-May-2026 10:46:33 | Prin Jitatisil | 13-May-2026 | 07-May-2026 10:41:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 07-May-2026 10:55:26 | 07-May-2026 12:15:15 | 0 |  |  | Approver | Locate
AO-000669 | MM-ZTK-1F-GEN-SSHE-PDR-8002 | SUB-CONTRACTOR SSHE MANAGEMENT, PRE- SELECTION AND AUDIT PROCEDURE WORK PACKAGE 1 (T&I) |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 14:56:40 | kjb@coes.cn | 04-Jun-2026 16:41:04 | Jumpol Sudjitjul | 11-Jun-2026 | 05-Jun-2026 14:16:07 | Ananchai Mongkonpanyanan | 15-Jun-2026 | 09-Jun-2026 16:24:53 | Prin Jitatisil | 16-Jun-2026 | 10-Jun-2026 15:57:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 10-Jun-2026 17:07:00 | 10-Jun-2026 10:35:06 | 0 |  |  | Approver | Locate
AO-000885 | MM-ZTK-1F-GEN-SSHE-PDR-8002 | SUB-CONTRACTOR SSHE MANAGEMENT, PRE- SELECTION AND AUDIT PROCEDURE WORK PACKAGE 1 (T&I) |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 24-Jun-2026 13:18:51 | kjb@coes.cn | 24-Jun-2026 14:54:29 | Jumpol Sudjitjul | 01-Jul-2026 | 26-Jun-2026 10:00:42 | Ananchai Mongkonpanyanan | 03-Jul-2026 | 30-Jun-2026 14:53:23 | Prin Jitatisil | 06-Jul-2026 | 01-Jul-2026 09:52:13 | APPR | Approved | Jumpol Sudjitjul | 07-Jul-2026 | 01-Jul-2026 15:33:54 | 01-Jul-2026 09:01:15 | 0 |  |  | Approver | Locate
AO-001136 | MM-ZTK-1F-GEN-SSHE-PDR-8003 | PERMIT TO WORK (PTW) PROCEDURE - WP-1 (T&I) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 16-Jul-2026 17:51:08 | kjb@coes.cn | 16-Jul-2026 20:50:47 | Jumpol Sudjitjul | 24-Jul-2026 |  | Ananchai Mongkonpanyanan | 30-Jul-2026 | 01-Aug-2026 17:20:43 | Prin Jitatisil | 31-Jul-2026 | 03-Aug-2026 14:09:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 03-Aug-2026 14:27:02 | 03-Aug-2026 07:53:09 | 0 |  |  | Approver | Locate
AO-001649 | MM-ZTK-1F-GEN-SSHE-PDR-8003 | PERMIT TO WORK (PTW) PROCEDURE - WP-1 (T&I) |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 21-Aug-2026 13:10:12 | kjb@coes.cn | 21-Aug-2026 13:14:42 | Jumpol Sudjitjul | 28-Aug-2026 |  | Ananchai Mongkonpanyanan | 01-Sep-2026 | 20-Sep-2026 14:24:41 | Prin Jitatisil | 02-Sep-2026 | 21-Sep-2026 08:47:18 | NA | Not Approved | Jumpol Sudjitjul | 03-Sep-2026 | 21-Sep-2026 09:34:45 | 21-Sep-2026 02:50:00 | 0 |  |  | Approver | Locate
AO-001572 | MM-ZTK-1F-GEN-SSHE-PDR-8004 | EMERGENCY RESPONSE PLAN (ERP) AND MEDICAL EMERGENCY RESPONSE PLAN (MERP) PROCEDURE-WP-1 (T&I) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 17-Aug-2026 17:15:31 | kjb@coes.cn | 18-Aug-2026 08:41:01 | Jumpol Sudjitjul | 25-Aug-2026 |  | Ananchai Mongkonpanyanan | 27-Aug-2026 | 09-Sep-2026 17:56:25 | Prin Jitatisil | 28-Aug-2026 | 09-Sep-2026 21:50:35 | NA | Not Approved | Jumpol Sudjitjul | 31-Aug-2026 | 10-Sep-2026 09:10:55 | 10-Sep-2026 02:42:41 | 0 |  |  | Approver | Locate
AO-001137 | MM-ZTK-1F-GEN-SSHE-PDR-8005 | ENVIRONMENT AND WASTE MANAGEMENT PLAN (WMP) PROCEDURE - WP-1 (T&I) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 16-Jul-2026 17:51:32 | kjb@coes.cn | 16-Jul-2026 20:52:30 | Jumpol Sudjitjul | 24-Jul-2026 |  | Ananchai Mongkonpanyanan | 30-Jul-2026 | 01-Aug-2026 18:35:11 | Prin Jitatisil | 31-Jul-2026 | 03-Aug-2026 14:09:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 03-Aug-2026 14:28:13 | 03-Aug-2026 07:54:42 | 0 |  |  | Approver | Locate
AO-001629 | MM-ZTK-1F-GEN-SSHE-PDR-8005 | ENVIRONMENT AND WASTE MANAGEMENT PLAN (WMP) PROCEDURE - WP-1 (T&I) |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 14:23:07 | kjb@coes.cn | 20-Aug-2026 14:42:21 | Jumpol Sudjitjul | 27-Aug-2026 |  | Ananchai Mongkonpanyanan | 31-Aug-2026 | 20-Sep-2026 15:05:59 | Prin Jitatisil | 01-Sep-2026 | 21-Sep-2026 08:47:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Sep-2026 | 21-Sep-2026 09:37:03 | 21-Sep-2026 02:54:41 | 0 |  |  | Approver | Locate
AO-002522 | MM-ZTK-1F-GEN-SSHE-PDR-8005 | ENVIRONMENT AND WASTE MANAGEMENT PLAN (WMP) PROCEDURE - WP-1 (T&I) |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | In Review | AFC | Approved for Construction |  | 14-Oct-2026 16:39:35 | kjb@coes.cn | 15-Oct-2026 08:31:51 | Jumpol Sudjitjul | 22-Oct-2026 |  | Ananchai Mongkonpanyanan | 27-Oct-2026 |  | Prin Jitatisil | 28-Oct-2026 |  |  |  |  | 29-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001320 | MM-ZTK-1F-GEN-SSHE-PDR-8006 | INFECTIOUS DISEASE OUTBREAK MANAGEMENT PROCEDURE - WP-1 (T&I) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 27-Jul-2026 11:25:27 | kjb@coes.cn | 27-Jul-2026 15:51:17 | Jumpol Sudjitjul | 05-Aug-2026 |  | Ananchai Mongkonpanyanan | 07-Aug-2026 | 01-Aug-2026 19:27:29 | Prin Jitatisil | 10-Aug-2026 | 03-Aug-2026 14:09:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 03-Aug-2026 14:32:44 | 03-Aug-2026 07:56:09 | 0 |  |  | Approver | Locate
AO-001823 | MM-ZTK-1F-GEN-SSHE-PDR-8006 | INFECTIOUS DISEASE OUTBREAK MANAGEMENT PROCEDURE - WP-1 (T&I) |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:40:30 | kjb@coes.cn | 03-Sep-2026 11:19:53 | Jumpol Sudjitjul | 10-Sep-2026 |  | Ananchai Mongkonpanyanan | 14-Sep-2026 | 20-Sep-2026 15:54:51 | Prin Jitatisil | 15-Sep-2026 | 21-Sep-2026 08:47:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 21-Sep-2026 09:38:22 | 21-Sep-2026 03:55:36 | 0 |  |  | Approver | Locate
AO-002521 | MM-ZTK-1F-GEN-SSHE-PDR-8006 | INFECTIOUS DISEASE OUTBREAK MANAGEMENT PROCEDURE - WP-1 (T&I) |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | In Review | AFC | Approved for Construction |  | 14-Oct-2026 16:40:19 | kjb@coes.cn | 15-Oct-2026 08:33:07 | Jumpol Sudjitjul | 22-Oct-2026 |  | Ananchai Mongkonpanyanan | 27-Oct-2026 |  | Prin Jitatisil | 28-Oct-2026 |  |  |  |  | 29-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-002231 | MM-ZTK-1F-GEN-SSHE-PDR-8007 | SAFETY CRITICAL ELEMENT (SCE) LITS AND PROCEDURE - WORK PACKAGE 1 (T&I) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 23-Sep-2026 16:44:56 | kjb@coes.cn | 23-Sep-2026 17:32:04 | Jumpol Sudjitjul | 01-Oct-2026 |  | Ananchai Mongkonpanyanan | 05-Oct-2026 | 05-Oct-2026 16:20:57 | Prin Jitatisil | 06-Oct-2026 | 05-Oct-2026 16:45:51 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 07-Oct-2026 | 05-Oct-2026 18:03:00 | 05-Oct-2026 11:31:08 | 0 |  |  | Approver | Locate
AO-001526 | MM-ZTK-1F-GEN-SSHE-PDR-9001 | INCIDENT AND ANOMALY MANAGEMENT PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 16:15:37 | 26002z1fdcc@thoresen-jutal.com | 14-Aug-2026 16:44:23 | Jumpol Sudjitjul | 21-Aug-2026 | 20-Aug-2026 23:15:34 | Ananchai Mongkonpanyanan | 25-Aug-2026 | 31-Aug-2026 18:32:04 | Prin Jitatisil | 26-Aug-2026 | 01-Sep-2026 13:23:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 01-Sep-2026 15:19:15 | 01-Sep-2026 09:06:50 | 0 |  |  | Approver | Locate
AO-001828 | MM-ZTK-1F-GEN-SSHE-PDR-9001 | INCIDENT AND ANOMALY MANAGEMENT PROCEDURE |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:41:08 | 26002z1fdcc@thoresen-jutal.com | 03-Sep-2026 11:20:20 | Jumpol Sudjitjul | 10-Sep-2026 | 16-Sep-2026 13:15:05 | Ananchai Mongkonpanyanan | 14-Sep-2026 | 20-Sep-2026 16:27:34 | Prin Jitatisil | 15-Sep-2026 | 21-Sep-2026 08:48:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 21-Sep-2026 09:39:54 | 21-Sep-2026 03:56:52 | 0 |  |  | Approver | Locate
AO-002238 | MM-ZTK-1F-GEN-SSHE-PDR-9001 | INCIDENT AND ANOMALY MANAGEMENT PROCEDURE |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 10:48:06 | 26002z1fdcc@thoresen-jutal.com | 24-Sep-2026 14:03:49 | Jumpol Sudjitjul | 01-Oct-2026 | 01-Oct-2026 17:27:42 | Ananchai Mongkonpanyanan | 05-Oct-2026 | 06-Oct-2026 09:23:09 | Prin Jitatisil | 06-Oct-2026 | 06-Oct-2026 11:32:30 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 06-Oct-2026 13:48:52 | 06-Oct-2026 07:10:04 | 0 |  |  | Approver | Locate
AO-000033 | MM-ZTK-1F-GEN-SSHE-PDR-9002 | SUB-CONTRACTOR SSHE MANAGEMENT, PRE-SELECTION AND AUDIT PROCEDURE WORK PACKAGE 2 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 19-Mar-2026 18:04:16 | 26002z1fdcc@thoresen-jutal.com | 20-Mar-2026 08:39:11 | Jumpol Sudjitjul | 27-Mar-2026 | 06-Apr-2026 23:04:05 | Ananchai Mongkonpanyanan | 31-Mar-2026 | 23-Apr-2026 10:57:10 | Prin Jitatisil | 01-Apr-2026 | 28-Apr-2026 08:38:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Apr-2026 | 28-Apr-2026 10:04:35 | 30-Apr-2026 11:50:16 | 0 |  |  | Approver | Locate
AO-000527 | MM-ZTK-1F-GEN-SSHE-PDR-9002 | SUB-CONTRACTOR SSHE MANAGEMENT, PRE-SELECTION AND AUDIT PROCEDURE WORK PACKAGE 2 |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 20-May-2026 12:46:35 | 26002z1fdcc@thoresen-jutal.com | 20-May-2026 15:57:34 | Jumpol Sudjitjul | 27-May-2026 | 28-May-2026 14:07:25 | Ananchai Mongkonpanyanan | 29-May-2026 | 09-Jun-2026 14:59:21 | Prin Jitatisil | 02-Jun-2026 | 10-Jun-2026 15:57:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Jun-2026 | 10-Jun-2026 17:06:05 | 10-Jun-2026 10:33:29 | 0 |  |  | Approver | Locate
AO-000877 | MM-ZTK-1F-GEN-SSHE-PDR-9002 | SUB-CONTRACTOR SSHE MANAGEMENT, PRE-SELECTION AND AUDIT PROCEDURE WORK PACKAGE 2 |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 23-Jun-2026 16:42:45 | 26002z1fdcc@thoresen-jutal.com | 23-Jun-2026 17:28:17 | Jumpol Sudjitjul | 01-Jul-2026 | 26-Jun-2026 09:59:41 | Ananchai Mongkonpanyanan | 03-Jul-2026 | 30-Jun-2026 14:22:55 | Prin Jitatisil | 06-Jul-2026 | 01-Jul-2026 09:52:38 | APPR | Approved | Jumpol Sudjitjul | 07-Jul-2026 | 01-Jul-2026 15:32:11 | 01-Jul-2026 08:59:44 | 0 |  |  | Approver | Locate
AO-001626 | MM-ZTK-1F-GEN-SSHE-PDR-9003 | PERMIT TO WORK (PTW) PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 20-Aug-2026 14:23:43 | 26002z1fdcc@thoresen-jutal.com | 20-Aug-2026 14:42:39 | Jumpol Sudjitjul | 27-Aug-2026 | 22-Aug-2026 06:56:48 | Ananchai Mongkonpanyanan | 31-Aug-2026 | 15-Sep-2026 18:09:21 | Prin Jitatisil | 01-Sep-2026 | 17-Sep-2026 10:12:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Sep-2026 | 17-Sep-2026 11:58:26 | 17-Sep-2026 05:51:45 | 0 |  |  | Approver | Locate
AO-002239 | MM-ZTK-1F-GEN-SSHE-PDR-9003 | PERMIT TO WORK (PTW) PROCEDURE |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 24-Sep-2026 10:48:37 | 26002z1fdcc@thoresen-jutal.com | 24-Sep-2026 14:04:26 | Jumpol Sudjitjul | 01-Oct-2026 | 24-Sep-2026 15:55:43 | Ananchai Mongkonpanyanan | 05-Oct-2026 | 05-Oct-2026 15:41:58 | Prin Jitatisil | 06-Oct-2026 | 05-Oct-2026 16:14:47 | NA | Not Approved | Jumpol Sudjitjul | 07-Oct-2026 | 05-Oct-2026 16:20:35 | 05-Oct-2026 09:35:51 | 0 |  |  | Approver | Locate
AO-002447 | MM-ZTK-1F-GEN-SSHE-PDR-9003 | PERMIT TO WORK (PTW) PROCEDURE |  | B2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | In Review | IFA | Issued for Approval |  | 08-Oct-2026 15:36:20 | 26002z1fdcc@thoresen-jutal.com | 08-Oct-2026 15:48:37 | Jumpol Sudjitjul | 16-Oct-2026 |  | Ananchai Mongkonpanyanan | 20-Oct-2026 |  | Prin Jitatisil | 21-Oct-2026 |  |  |  |  | 22-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001949 | MM-ZTK-1F-GEN-SSHE-PDR-9004 | EMERGENCY AND MEDICAL EMERGENCY RESPONSE PLAN PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 09-Sep-2026 17:29:20 | 26002z1fdcc@thoresen-jutal.com | 09-Sep-2026 18:00:45 | Jumpol Sudjitjul | 17-Sep-2026 | 19-Sep-2026 16:38:55 | Ananchai Mongkonpanyanan | 21-Sep-2026 | 29-Sep-2026 14:45:01 | Prin Jitatisil | 22-Sep-2026 | 30-Sep-2026 08:14:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Sep-2026 | 30-Sep-2026 13:32:08 | 30-Sep-2026 07:05:42 | 0 |  |  | Approver | Locate
AO-002383 | MM-ZTK-1F-GEN-SSHE-PDR-9004 | EMERGENCY AND MEDICAL EMERGENCY RESPONSE PLAN PROCEDURE |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 06-Oct-2026 09:27:23 | 26002z1fdcc@thoresen-jutal.com | 06-Oct-2026 09:31:04 | Jumpol Sudjitjul | 14-Oct-2026 | 07-Oct-2026 10:17:51 | Ananchai Mongkonpanyanan | 16-Oct-2026 | 08-Oct-2026 17:25:57 | Prin Jitatisil | 19-Oct-2026 | 09-Oct-2026 16:24:38 | NA | Not Approved | Jumpol Sudjitjul | 20-Oct-2026 | 09-Oct-2026 17:23:23 | 09-Oct-2026 10:51:28 | 0 |  |  | Approver | Locate
AO-002096 | MM-ZTK-1F-GEN-SSHE-PDR-9005 | ENVIRONMENT AND WASTE MANAGEMENT PLAN (WMP) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 16-Sep-2026 12:18:42 | 26002z1fdcc@thoresen-jutal.com | 17-Sep-2026 10:04:51 | Jumpol Sudjitjul | 24-Sep-2026 |  | Ananchai Mongkonpanyanan | 28-Sep-2026 | 05-Oct-2026 15:03:48 | Prin Jitatisil | 29-Sep-2026 | 05-Oct-2026 16:15:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 30-Sep-2026 | 05-Oct-2026 16:19:03 | 05-Oct-2026 09:30:34 | 0 |  |  | Approver | Locate
AO-002526 | MM-ZTK-1F-GEN-SSHE-PDR-9005 | ENVIRONMENT AND WASTE MANAGEMENT PLAN (WMP) |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | In Review | IFA | Issued for Approval |  | 15-Oct-2026 09:26:59 | 26002z1fdcc@thoresen-jutal.com | 18-Oct-2026 16:45:26 | Jumpol Sudjitjul | 26-Oct-2026 |  | Ananchai Mongkonpanyanan | 28-Oct-2026 |  | Prin Jitatisil | 29-Oct-2026 |  |  |  |  | 30-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-002380 | MM-ZTK-1F-GEN-SSHE-PDR-9006 | INFECTIOUS DISEASE OUTBREAK MANAGEMENT PROCEDURE |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 05-Oct-2026 17:57:04 | 26002z1fdcc@thoresen-jutal.com | 06-Oct-2026 09:12:04 | Jumpol Sudjitjul | 14-Oct-2026 |  | Ananchai Mongkonpanyanan | 16-Oct-2026 | 06-Oct-2026 10:30:16 | Prin Jitatisil | 19-Oct-2026 | 06-Oct-2026 11:32:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Oct-2026 | 06-Oct-2026 13:49:59 | 06-Oct-2026 07:11:28 | 0 |  |  | Approver | Locate
AO-002448 | MM-ZTK-1F-GEN-SSHE-PDR-9006 | INFECTIOUS DISEASE OUTBREAK MANAGEMENT PROCEDURE |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PDR | Procedure | 0 | In Review | IFA | Issued for Approval |  | 08-Oct-2026 15:36:59 | 26002z1fdcc@thoresen-jutal.com | 08-Oct-2026 15:49:12 | Jumpol Sudjitjul | 16-Oct-2026 | 17-Oct-2026 09:17:54 | Ananchai Mongkonpanyanan | 20-Oct-2026 |  | Prin Jitatisil | 21-Oct-2026 |  |  |  |  | 22-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000020 | MM-ZTK-1F-GEN-SSHE-PLN-0001 | SSHE BRIDGING DOCUMENT |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 18-Mar-2026 09:51:00 | 26002z1fdcc@thoresen-jutal.com | 18-Mar-2026 10:42:31 | Jumpol Sudjitjul | 25-Mar-2026 |  | Ananchai Mongkonpanyanan | 27-Mar-2026 | 29-Mar-2026 18:07:02 | Prin Jitatisil | 30-Mar-2026 | 31-Mar-2026 10:10:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Mar-2026 | 31-Mar-2026 10:12:09 | 31-Mar-2026 10:20:07 | 0 |  |  | Approver | Locate
AO-000107 | MM-ZTK-1F-GEN-SSHE-PLN-0001 | SSHE BRIDGING DOCUMENT |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | IFR | Issued for Review | 20-Apr-2026 | 10-Apr-2026 10:19:08 | 26002z1fdcc@thoresen-jutal.com | 10-Apr-2026 15:13:53 | Jumpol Sudjitjul | 22-Apr-2026 | 16-Apr-2026 15:33:32 | Ananchai Mongkonpanyanan | 24-Apr-2026 | 03-May-2026 16:02:37 | Prin Jitatisil | 27-Apr-2026 | 06-May-2026 08:38:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 06-May-2026 09:33:50 | 06-May-2026 09:58:11 | 0 |  |  | Approver | Locate
AO-000399 | MM-ZTK-1F-GEN-SSHE-PLN-0001 | SSHE BRIDGING DOCUMENT |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 14-May-2026 16:15:37 | 26002z1fdcc@thoresen-jutal.com | 14-May-2026 16:28:22 | Jumpol Sudjitjul | 21-May-2026 |  | Ananchai Mongkonpanyanan | 25-May-2026 | 15-May-2026 08:08:04 | Prin Jitatisil | 26-May-2026 | 16-May-2026 23:50:12 | APPR | Approved | Jumpol Sudjitjul | 27-May-2026 | 17-May-2026 10:04:09 | 17-May-2026 03:37:57 | 0 |  |  | Approver | Locate
AO-000141 | MM-ZTK-1F-GEN-SSHE-PLN-0002 | SSHE MANAGEMENT AND EXECUTION PLAN WORK PACKAGE 1 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | Issued for Review | Issued for Review |  | 16-Apr-2026 22:40:05 | zm169dc@jutal.com | 17-Apr-2026 09:22:02 | Jumpol Sudjitjul |  |  |  |  | 03-May-2026 17:41:04 |  |  | 06-May-2026 08:40:16 |  |  | Jumpol Sudjitjul |  | 06-May-2026 09:35:46 | 16-Apr-2026 09:41:54 | 0 |  |  | Approver | Locate
AO-000213 | MM-ZTK-1F-GEN-SSHE-PLN-5001 | SSHE MANAGEMENT AND EXECUTION PLAN WORK PACKAGE 1 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 23-Apr-2026 13:35:49 | wangzhi@jutal.com | 23-Apr-2026 13:57:15 | Jumpol Sudjitjul | 30-Apr-2026 |  | Ananchai Mongkonpanyanan | 06-May-2026 | 03-May-2026 17:38:30 | Pornlert Wanaphattharaphan | 07-May-2026 | 08-May-2026 23:13:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-May-2026 | 09-May-2026 08:20:32 | 09-May-2026 08:49:09 | 0 |  |  | Approver | Locate
AO-000528 | MM-ZTK-1F-GEN-SSHE-PLN-5001 | SSHE MANAGEMENT AND EXECUTION PLAN WORK PACKAGE 1 |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 14:26:47 | zm169dc@jutal.com | 20-May-2026 16:10:07 | Jumpol Sudjitjul | 27-May-2026 |  | Ananchai Mongkonpanyanan | 29-May-2026 | 26-May-2026 12:22:43 | Prin Jitatisil | 02-Jun-2026 | 10-Jun-2026 15:57:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Jun-2026 | 10-Jun-2026 16:18:49 | 10-Jun-2026 09:43:51 | 0 |  |  | Approver | Locate
AO-000946 | MM-ZTK-1F-GEN-SSHE-PLN-5001 | SSHE MANAGEMENT AND EXECUTION PLAN WORK PACKAGE 1 |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 29-Jun-2026 22:05:49 | zm169dc@jutal.com | 30-Jun-2026 10:48:03 | Jumpol Sudjitjul | 07-Jul-2026 |  | Ananchai Mongkonpanyanan | 09-Jul-2026 | 13-Jul-2026 11:03:25 | Prin Jitatisil | 10-Jul-2026 | 13-Jul-2026 11:14:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 13-Jul-2026 13:39:10 | 13-Jul-2026 07:14:32 | 0 |  |  | Approver | Locate
AO-001138 | MM-ZTK-1F-GEN-SSHE-PLN-5001 | SSHE MANAGEMENT AND EXECUTION PLAN WORK PACKAGE 1 |  | C2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 17:52:00 | zm169dc@jutal.com | 16-Jul-2026 20:42:09 | Jumpol Sudjitjul | 24-Jul-2026 |  | Ananchai Mongkonpanyanan | 30-Jul-2026 | 27-Jul-2026 18:13:58 | Prin Jitatisil | 31-Jul-2026 | 27-Jul-2026 18:25:14 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 28-Jul-2026 08:46:00 | 28-Jul-2026 02:22:57 | 0 |  |  | Approver | Locate
AO-000253 | MM-ZTK-1F-GEN-SSHE-PLN-8001 | SSHE RISK ASSESSMENT PLAN, WORK PACKAGE 1 (T&I) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 09:49:14 | kjb@coes.cn | 29-Apr-2026 10:50:33 | Jumpol Sudjitjul | 08-May-2026 |  | Ananchai Mongkonpanyanan | 12-May-2026 | 06-May-2026 11:19:53 | Prin Jitatisil | 13-May-2026 | 07-May-2026 10:40:55 | NA | Not Approved | Jumpol Sudjitjul | 14-May-2026 | 07-May-2026 10:57:09 | 07-May-2026 12:09:28 | 0 |  |  | Approver | Locate
AO-000601 | MM-ZTK-1F-GEN-SSHE-PLN-8001 | SSHE RISK ASSESSMENT PLAN, WORK PACKAGE 1 (T&I) |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 26-May-2026 13:28:02 | kjb@coes.cn | 26-May-2026 14:45:33 | Jumpol Sudjitjul | 04-Jun-2026 | 02-Jun-2026 16:03:01 | Ananchai Mongkonpanyanan | 08-Jun-2026 | 09-Jun-2026 18:12:43 | Prin Jitatisil | 09-Jun-2026 | 10-Jun-2026 15:58:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jun-2026 | 10-Jun-2026 17:05:16 | 10-Jun-2026 10:32:07 | 0 |  |  | Approver | Locate
AO-001022 | MM-ZTK-1F-GEN-SSHE-PLN-8001 | SSHE RISK ASSESSMENT PLAN, WORK PACKAGE 1 (T&I) |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | IFA | Issued for Approval |  | 06-Jul-2026 09:16:22 | kjb@coes.cn | 06-Jul-2026 09:22:07 | Jumpol Sudjitjul | 13-Jul-2026 |  | Ananchai Mongkonpanyanan | 15-Jul-2026 | 13-Jul-2026 13:49:35 | Prin Jitatisil | 16-Jul-2026 | 13-Jul-2026 15:05:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 14-Jul-2026 08:49:00 | 14-Jul-2026 02:32:51 | 0 |  |  | Approver | Locate
AO-001208 | MM-ZTK-1F-GEN-SSHE-PLN-8001 | SSHE RISK ASSESSMENT PLAN, WORK PACKAGE 1 (T&I) |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 17:37:55 | kjb@coes.cn | 21-Jul-2026 07:48:25 | Jumpol Sudjitjul | 30-Jul-2026 |  | Ananchai Mongkonpanyanan | 03-Aug-2026 | 01-Aug-2026 19:16:30 | Prin Jitatisil | 04-Aug-2026 | 03-Aug-2026 14:09:33 | APPR | Approved | Jumpol Sudjitjul | 05-Aug-2026 | 03-Aug-2026 14:29:36 | 03-Aug-2026 08:02:06 | 0 |  |  | Approver | Locate
AO-000217 | MM-ZTK-1F-GEN-SSHE-PLN-8002 | SSHE MANAGEMENT & EXECUTION PLAN WORK PACKAGE 1 (T&I) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 12:28:36 | kjb@coes.cn | 24-Apr-2026 14:00:37 | Jumpol Sudjitjul | 05-May-2026 | 25-Apr-2026 14:26:36 | Ananchai Mongkonpanyanan | 07-May-2026 | 03-May-2026 20:14:27 | Prin Jitatisil | 08-May-2026 | 06-May-2026 08:39:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:00:28 | 07-May-2026 12:05:21 | 0 |  |  | Approver | Locate
AO-000670 | MM-ZTK-1F-GEN-SSHE-PLN-8002 | SSHE MANAGEMENT & EXECUTION PLAN WORK PACKAGE 1 (T&I) |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 15:52:23 | kjb@coes.cn | 04-Jun-2026 16:38:14 | Jumpol Sudjitjul | 11-Jun-2026 | 17-Jun-2026 16:29:08 | Ananchai Mongkonpanyanan | 15-Jun-2026 | 21-Jun-2026 16:54:38 | Prin Jitatisil | 16-Jun-2026 | 23-Jun-2026 16:28:21 | NA | Not Approved | Jumpol Sudjitjul | 17-Jun-2026 | 23-Jun-2026 16:30:26 | 23-Jun-2026 10:12:58 | 0 |  |  | Approver | Locate
AO-001123 | MM-ZTK-1F-GEN-SSHE-PLN-8002 | SSHE MANAGEMENT & EXECUTION PLAN WORK PACKAGE 1 (T&I) |  | B2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 11:31:09 | kjb@coes.cn | 16-Jul-2026 11:54:57 | Jumpol Sudjitjul | 23-Jul-2026 |  | Ananchai Mongkonpanyanan | 27-Jul-2026 | 01-Aug-2026 15:03:37 | Prin Jitatisil | 30-Jul-2026 | 03-Aug-2026 14:09:42 | NA | Not Approved | Jumpol Sudjitjul | 31-Jul-2026 | 03-Aug-2026 14:36:32 | 03-Aug-2026 07:57:37 | 0 |  |  | Approver | Locate
AO-001870 | MM-ZTK-1F-GEN-SSHE-PLN-8002 | SSHE MANAGEMENT & EXECUTION PLAN WORK PACKAGE 1 (T&I) |  | B3 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 11:20:23 | kjb@coes.cn | 04-Sep-2026 12:04:29 | Jumpol Sudjitjul | 11-Sep-2026 |  | Ananchai Mongkonpanyanan | 15-Sep-2026 | 25-Sep-2026 13:17:29 | Prin Jitatisil | 16-Sep-2026 | 25-Sep-2026 17:13:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 25-Sep-2026 17:49:07 | 25-Sep-2026 11:53:22 | 0 |  |  | Approver | Locate
AO-000623 | MM-ZTK-1F-GEN-SSHE-PLN-9001 | RISK ASSESSMENT PLAN - WORK PACKAGE 2 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 15:41:16 | 26002z1fdcc@thoresen-jutal.com | 29-May-2026 15:53:15 | Jumpol Sudjitjul | 09-Jun-2026 | 09-Jun-2026 16:45:12 | Ananchai Mongkonpanyanan | 11-Jun-2026 | 09-Jun-2026 20:36:22 | Prin Jitatisil | 12-Jun-2026 | 10-Jun-2026 15:58:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 10-Jun-2026 16:13:57 | 10-Jun-2026 16:17:44 | 0 |  |  | Approver | Locate
AO-000801 | MM-ZTK-1F-GEN-SSHE-PLN-9001 | RISK ASSESSMENT PLAN - WORK PACKAGE 2 |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | IFA | Issued for Approval |  | 15-Jun-2026 15:34:54 | 26002z1fdcc@thoresen-jutal.com | 15-Jun-2026 16:45:05 | Jumpol Sudjitjul | 22-Jun-2026 | 22-Jun-2026 13:14:36 | Ananchai Mongkonpanyanan | 24-Jun-2026 | 30-Jun-2026 11:05:34 | Prin Jitatisil | 25-Jun-2026 | 01-Jul-2026 09:53:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Jun-2026 | 01-Jul-2026 15:27:51 | 01-Jul-2026 08:58:15 | 0 |  |  | Approver | Locate
AO-000997 | MM-ZTK-1F-GEN-SSHE-PLN-9001 | RISK ASSESSMENT PLAN - WORK PACKAGE 2 |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 13:21:34 | 26002z1fdcc@thoresen-jutal.com | 03-Jul-2026 14:22:14 | Jumpol Sudjitjul | 10-Jul-2026 | 09-Jul-2026 16:14:36 | Ananchai Mongkonpanyanan | 14-Jul-2026 | 13-Jul-2026 13:15:19 | Prin Jitatisil | 15-Jul-2026 | 13-Jul-2026 13:20:45 | APPR | Approved | Jumpol Sudjitjul | 16-Jul-2026 | 13-Jul-2026 13:38:17 | 13-Jul-2026 07:17:59 | 0 |  |  | Approver | Locate
AO-000039 | MM-ZTK-1F-GEN-SSHE-PLN-9002 | SSHE MANAGEMENT & EXECUTION PLAN - WORK PACKAGE 2 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 23-Mar-2026 09:35:18 | 26002z1fdcc@thoresen-jutal.com | 23-Mar-2026 10:49:47 | Jumpol Sudjitjul | 30-Mar-2026 | 07-Apr-2026 00:21:23 | Ananchai Mongkonpanyanan | 01-Apr-2026 | 23-Apr-2026 15:36:34 | Prin Jitatisil | 02-Apr-2026 | 28-Apr-2026 08:39:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Apr-2026 | 28-Apr-2026 10:03:54 | 30-Apr-2026 11:50:27 | 0 |  |  | Approver | Locate
AO-000609 | MM-ZTK-1F-GEN-SSHE-PLN-9002 | SSHE MANAGEMENT & EXECUTION PLAN - WORK PACKAGE 2 |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | IFA | Issued for Approval |  | 28-May-2026 08:56:57 | 26002z1fdcc@thoresen-jutal.com | 28-May-2026 13:34:42 | Jumpol Sudjitjul | 08-Jun-2026 | 02-Jun-2026 16:25:26 | Ananchai Mongkonpanyanan | 10-Jun-2026 | 17-Jun-2026 22:52:00 | Prin Jitatisil | 11-Jun-2026 | 18-Jun-2026 09:45:29 | NA | Not Approved | Jumpol Sudjitjul | 12-Jun-2026 | 18-Jun-2026 09:47:39 | 18-Jun-2026 03:33:29 | 0 |  |  | Approver | Locate
AO-001026 | MM-ZTK-1F-GEN-SSHE-PLN-9002 | SSHE MANAGEMENT & EXECUTION PLAN - WORK PACKAGE 2 |  | B2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | IFA | Issued for Approval |  | 07-Jul-2026 10:47:06 | 26002z1fdcc@thoresen-jutal.com | 07-Jul-2026 11:52:03 | Jumpol Sudjitjul | 14-Jul-2026 |  | Ananchai Mongkonpanyanan | 16-Jul-2026 | 13-Jul-2026 15:10:35 | Prin Jitatisil | 17-Jul-2026 | 14-Jul-2026 08:56:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Jul-2026 | 14-Jul-2026 09:02:47 | 14-Jul-2026 03:20:07 | 0 |  |  | Approver | Locate
AO-001147 | MM-ZTK-1F-GEN-SSHE-PLN-9002 | SSHE MANAGEMENT & EXECUTION PLAN - WORK PACKAGE 2 |  | C1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 21:11:13 | 26002z1fdcc@thoresen-jutal.com | 17-Jul-2026 10:32:01 | Jumpol Sudjitjul | 24-Jul-2026 |  | Ananchai Mongkonpanyanan | 30-Jul-2026 | 01-Aug-2026 16:41:07 | Prin Jitatisil | 31-Jul-2026 | 03-Aug-2026 14:09:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 03-Aug-2026 14:35:16 | 03-Aug-2026 07:46:58 | 0 |  |  | Approver | Locate
AO-001508 | MM-ZTK-1F-GEN-SSHE-PLN-9002 | SSHE MANAGEMENT & EXECUTION PLAN - WORK PACKAGE 2 |  | C2 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 11-Aug-2026 12:42:34 | 26002z1fdcc@thoresen-jutal.com | 11-Aug-2026 13:06:52 | Jumpol Sudjitjul | 19-Aug-2026 |  | Ananchai Mongkonpanyanan | 21-Aug-2026 | 31-Aug-2026 17:08:18 | Prin Jitatisil | 24-Aug-2026 | 01-Sep-2026 13:23:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Aug-2026 | 01-Sep-2026 15:18:37 | 01-Sep-2026 09:02:51 | 0 |  |  | Approver | Locate
AO-001884 | MM-ZTK-1F-GEN-SSHE-PLN-9002 | SSHE MANAGEMENT & EXECUTION PLAN - WORK PACKAGE 2 |  | C3 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | PLN | Plan | 0 | Submitted | AFC | Approved for Construction |  | 04-Sep-2026 16:13:56 | 26002z1fdcc@thoresen-jutal.com | 05-Sep-2026 19:40:44 | Jumpol Sudjitjul | 14-Sep-2026 |  | Ananchai Mongkonpanyanan | 16-Sep-2026 | 25-Sep-2026 13:39:23 | Prin Jitatisil | 17-Sep-2026 | 27-Sep-2026 06:11:24 | APPR | Approved | Jumpol Sudjitjul | 18-Sep-2026 | 27-Sep-2026 12:57:54 | 27-Sep-2026 06:28:45 | 0 |  |  | Approver | Locate
AO-001335 | MM-ZTK-1F-GEN-SSHE-RPT-5001 | SSHE RISK ASSESSMENT AND JOB SAFETY ANALYSIS (JSA) REPORT WP-1 (EPC) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 30-Jul-2026 12:34:43 | zm169dc@jutal.com | 30-Jul-2026 13:37:59 | Jumpol Sudjitjul | 06-Aug-2026 |  | Ananchai Mongkonpanyanan | 10-Aug-2026 | 01-Aug-2026 15:24:34 | Prin Jitatisil | 11-Aug-2026 | 03-Aug-2026 14:10:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Aug-2026 | 03-Aug-2026 14:39:52 | 03-Aug-2026 07:49:47 | 0 |  |  | Approver | Locate
AO-001631 | MM-ZTK-1F-GEN-SSHE-RPT-5001 | SSHE RISK ASSESSMENT AND JOB SAFETY ANALYSIS (JSA) REPORT WP-1 (EPC) |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 17:24:39 | zm169dc@jutal.com | 21-Aug-2026 10:48:26 | Jumpol Sudjitjul | 28-Aug-2026 |  | Ananchai Mongkonpanyanan | 01-Sep-2026 | 23-Aug-2026 13:02:41 | Prin Jitatisil | 02-Sep-2026 | 24-Aug-2026 08:55:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Sep-2026 | 24-Aug-2026 19:53:44 | 24-Aug-2026 14:20:37 | 0 |  |  | Approver | Locate
AO-001467 | MM-ZTK-1F-GEN-SSHE-RPT-5002 | PRE-MOBILIZATION AUDIT REPORT AND ACTION TRACKING CLOSE-OUT REPORTS WP-1(EPC) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 10-Aug-2026 11:39:10 | zm169dc@jutal.com | 10-Aug-2026 16:12:06 | Jumpol Sudjitjul | 18-Aug-2026 |  | Ananchai Mongkonpanyanan | 20-Aug-2026 | 16-Aug-2026 13:06:36 | Prin Jitatisil | 21-Aug-2026 | 18-Aug-2026 14:08:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 18-Aug-2026 14:30:11 | 18-Aug-2026 09:33:50 | 0 |  |  | Approver | Locate
AO-002135 | MM-ZTK-1F-GEN-SSHE-RPT-5002 | PRE-MOBILIZATION AUDIT REPORT AND ACTION TRACKING CLOSE-OUT REPORTS WP-1(EPC) |  | B1 | Project Document | Engineering Document | Part A - Project Management Doc | GEN |  |  | SSHE | Safety, Security, Health and Environment | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 17-Sep-2026 16:05:13 | zm169dc@jutal.com | 17-Sep-2026 16:09:22 | Jumpol Sudjitjul | 24-Sep-2026 |  | Ananchai Mongkonpanyanan | 28-Sep-2026 | 29-Sep-2026 17:34:42 | Prin Jitatisil | 29-Sep-2026 | 30-Sep-2026 08:14:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 30-Sep-2026 | 30-Sep-2026 13:32:41 | 30-Sep-2026 07:25:34 | 0 |  |  | Approver | Locate
AO-000289 | MM-ZTK-1F-GEN-STR-BOD-0001 | STRUCTURAL DESIGN BASIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | BOD | Basis of Design | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 01:55:06 | wisuda.c@jutal.com | 04-May-2026 13:16:02 | Jumpol Sudjitjul | 11-May-2026 | 25-May-2026 09:07:31 | Sompop Singhatiraj | 13-May-2026 | 28-May-2026 14:38:25 | Pornlert Wanaphattharaphan | 14-May-2026 | 28-May-2026 22:49:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 29-May-2026 09:30:04 | 29-May-2026 03:29:13 | 0 |  |  | Approver | Locate
AO-001313 | MM-ZTK-1F-GEN-STR-BOD-0001 | STRUCTURAL DESIGN BASIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | BOD | Basis of Design | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 08:43:08 | wisuda.c@jutal.com | 27-Jul-2026 16:22:21 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 16-Sep-2026 15:18:17 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 17-Sep-2026 13:23:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 17-Sep-2026 13:34:39 | 17-Sep-2026 07:10:01 | 0 |  |  | Approver | Locate
AO-000759 | MM-ZTK-1F-GEN-STR-CAL-0001 | TOPSIDE BASIC STRUCTURAL ENGINEERING VERIFICATION REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | In Review | IFI | Issued for Information |  | 06-May-2026 08:28:12 | wisuda.c@jutal.com | 12-Jun-2026 13:33:17 | Jumpol Sudjitjul | 19-Jun-2026 |  | Sompop Singhatiraj | 23-Jun-2026 |  | Pornlert Wanaphattharaphan | 24-Jun-2026 |  |  |  |  | 25-Jun-2026 |  |  | 0 |  |  | Approver | Locate
AO-000316 | MM-ZTK-1F-GEN-STR-CAL-1001 | TOPSIDES COMPUTER MODELLING WITH VENT BOOM & LOAD FORMULATION REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Review |  | 06-May-2026 09:48:06 | wisuda.c@jutal.com | 06-May-2026 10:35:05 | Jumpol Sudjitjul | 13-May-2026 | 15-May-2026 16:38:26 | Sompop Singhatiraj | 15-May-2026 | 02-Jun-2026 16:51:33 | Pornlert Wanaphattharaphan | 18-May-2026 | 02-Jun-2026 20:41:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 03-Jun-2026 09:11:47 | 03-Jun-2026 02:54:38 | 0 |  |  | Approver | Locate
AO-001189 | MM-ZTK-1F-GEN-STR-CAL-1001 | TOPSIDES COMPUTER MODELLING WITH VENT BOOM & LOAD FORMULATION REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 10:35:08 | wisuda.c@jutal.com | 20-Jul-2026 14:29:15 | Jumpol Sudjitjul | 27-Jul-2026 |  | Sompop Singhatiraj | 31-Jul-2026 | 16-Aug-2026 12:38:59 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 16-Aug-2026 16:57:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 17-Aug-2026 14:03:02 | 17-Aug-2026 08:31:15 | 0 |  |  | Approver | Locate
AO-002167 | MM-ZTK-1F-GEN-STR-CAL-1001 | TOPSIDES COMPUTER MODELLING WITH VENT BOOM & LOAD FORMULATION REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 18:58:38 | wisuda.c@jutal.com | 20-Sep-2026 12:44:05 | Jumpol Sudjitjul | 25-Sep-2026 |  | Sompop Singhatiraj | 29-Sep-2026 | 29-Sep-2026 15:55:58 | Pornlert Wanaphattharaphan | 30-Sep-2026 | 30-Sep-2026 00:48:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Oct-2026 | 30-Sep-2026 13:34:51 | 30-Sep-2026 07:07:32 | 0 |  |  | Approver | Locate
AO-000514 | MM-ZTK-1F-GEN-STR-CAL-1011 | TOPSIDES IN-PLACE ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 16:14:28 | wisuda.c@jutal.com | 19-May-2026 16:39:48 | Jumpol Sudjitjul | 26-May-2026 | 02-Jun-2026 10:39:19 | Sompop Singhatiraj | 28-May-2026 | 02-Jun-2026 13:39:45 | Pornlert Wanaphattharaphan | 29-May-2026 | 02-Jun-2026 20:41:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 03-Jun-2026 09:12:19 | 03-Jun-2026 02:40:41 | 0 |  |  | Approver | Locate
AO-001368 | MM-ZTK-1F-GEN-STR-CAL-1011 | TOPSIDES IN-PLACE ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 03-Aug-2026 10:07:50 | wisuda.c@jutal.com | 03-Aug-2026 13:14:51 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 16-Aug-2026 13:59:58 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 23:20:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 14:01:06 | 17-Aug-2026 08:20:30 | 0 |  |  | Approver | Locate
AO-002316 | MM-ZTK-1F-GEN-STR-CAL-1011 | TOPSIDES IN-PLACE ANALYSIS REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 30-Sep-2026 16:13:29 | wisuda.c@jutal.com | 30-Sep-2026 16:42:03 | Jumpol Sudjitjul | 07-Oct-2026 |  | Sompop Singhatiraj | 09-Oct-2026 | 05-Oct-2026 15:29:27 | Pornlert Wanaphattharaphan | 12-Oct-2026 | 10-Oct-2026 01:41:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Oct-2026 | 10-Oct-2026 17:30:48 | 10-Oct-2026 11:06:58 | 0 |  |  | Approver | Locate
AO-000510 | MM-ZTK-1F-GEN-STR-CAL-1012 | TOPSIDES LOADOUT ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 13:31:00 | wisuda.c@jutal.com | 19-May-2026 13:45:06 | Jumpol Sudjitjul | 26-May-2026 | 26-May-2026 10:15:17 | Sompop Singhatiraj | 28-May-2026 | 03-Jun-2026 17:02:00 | Pornlert Wanaphattharaphan | 29-May-2026 | 05-Jun-2026 23:48:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 07-Jun-2026 17:25:43 | 07-Jun-2026 10:51:42 | 0 |  |  | Approver | Locate
AO-001261 | MM-ZTK-1F-GEN-STR-CAL-1012 | TOPSIDES LOADOUT ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 12:05:36 | wisuda.c@jutal.com | 26-Jul-2026 23:40:57 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 16-Aug-2026 10:10:51 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 16-Aug-2026 10:23:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 17-Aug-2026 14:05:18 | 17-Aug-2026 08:21:58 | 0 |  |  | Approver | Locate
AO-002253 | MM-ZTK-1F-GEN-STR-CAL-1012 | TOPSIDES LOADOUT ANALYSIS REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 18:11:02 | wisuda.c@jutal.com | 24-Sep-2026 18:14:29 | Jumpol Sudjitjul | 02-Oct-2026 |  | Sompop Singhatiraj | 06-Oct-2026 | 05-Oct-2026 16:09:03 | Pornlert Wanaphattharaphan | 07-Oct-2026 | 10-Oct-2026 00:45:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Oct-2026 | 10-Oct-2026 17:31:19 | 10-Oct-2026 11:30:32 | 0 |  |  | Approver | Locate
AO-000707 | MM-ZTK-1F-GEN-STR-CAL-1013 | TOPSIDES TRANSPORATION ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 09:21:53 | wisuda.c@jutal.com | 08-Jun-2026 12:02:25 | Jumpol Sudjitjul | 15-Jun-2026 | 17-Jun-2026 22:55:04 | Sompop Singhatiraj | 17-Jun-2026 | 21-Jun-2026 18:05:29 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 22-Jun-2026 12:00:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 22-Jun-2026 12:57:19 | 22-Jun-2026 06:46:42 | 0 |  |  | Approver | Locate
AO-001509 | MM-ZTK-1F-GEN-STR-CAL-1013 | TOPSIDES TRANSPORATION ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 11-Aug-2026 12:43:17 | wisuda.c@jutal.com | 11-Aug-2026 13:05:18 | Jumpol Sudjitjul | 19-Aug-2026 |  | Sompop Singhatiraj | 21-Aug-2026 | 14-Aug-2026 15:38:08 | Pornlert Wanaphattharaphan | 24-Aug-2026 | 17-Aug-2026 21:37:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Aug-2026 | 18-Aug-2026 08:21:32 | 18-Aug-2026 01:34:11 | 0 |  |  | Approver | Locate
AO-002296 | MM-ZTK-1F-GEN-STR-CAL-1013 | TOPSIDES TRANSPORATION ANALYSIS REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 09:44:16 | wisuda.c@jutal.com | 28-Sep-2026 09:53:43 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 05-Oct-2026 16:47:17 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 10-Oct-2026 01:22:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 10-Oct-2026 17:31:49 | 10-Oct-2026 10:52:42 | 0 |  |  | Approver | Locate
AO-000983 | MM-ZTK-1F-GEN-STR-CAL-1014 | TOPSIDES TRANSPORATION FATIGUE ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 10:44:37 | wisuda.c@jutal.com | 03-Jul-2026 14:24:40 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 10-Jul-2026 12:19:38 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 11-Jul-2026 11:03:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 12-Jul-2026 11:37:39 | 12-Jul-2026 05:00:37 | 0 |  |  | Approver | Locate
AO-001538 | MM-ZTK-1F-GEN-STR-CAL-1014 | TOPSIDES TRANSPORATION FATIGUE ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 17:30:48 | wisuda.c@jutal.com | 14-Aug-2026 17:44:21 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 16-Aug-2026 14:57:56 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 22:54:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 19:53:12 | 24-Aug-2026 13:30:24 | 0 |  |  | Approver | Locate
AO-002473 | MM-ZTK-1F-GEN-STR-CAL-1014 | TOPSIDES TRANSPORATION FATIGUE ANALYSIS REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 11:47:59 | wisuda.c@jutal.com | 12-Oct-2026 11:56:48 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000533 | MM-ZTK-1F-GEN-STR-CAL-1015 | TOPSIDES LIFTING ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 17:43:48 | wisuda.c@jutal.com | 20-May-2026 18:16:49 | Jumpol Sudjitjul | 28-May-2026 | 02-Jun-2026 11:49:25 | Sompop Singhatiraj | 02-Jun-2026 | 03-Jun-2026 18:05:16 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 06-Jun-2026 00:01:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 07-Jun-2026 17:27:15 | 07-Jun-2026 11:40:28 | 0 |  |  | Approver | Locate
AO-001279 | MM-ZTK-1F-GEN-STR-CAL-1015 | TOPSIDES LIFTING ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 25-Jul-2026 09:14:09 | wisuda.c@jutal.com | 26-Jul-2026 23:41:14 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 14-Aug-2026 16:09:49 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 15-Aug-2026 20:05:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 16-Aug-2026 09:47:58 | 16-Aug-2026 03:00:23 | 0 |  |  | Approver | Locate
AO-002233 | MM-ZTK-1F-GEN-STR-CAL-1015 | TOPSIDES LIFTING ANALYSIS REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 23-Sep-2026 16:46:43 | wisuda.c@jutal.com | 23-Sep-2026 17:24:52 | Jumpol Sudjitjul | 01-Oct-2026 |  | Sompop Singhatiraj | 05-Oct-2026 |  | Pornlert Wanaphattharaphan | 06-Oct-2026 |  |  |  |  | 07-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000878 | MM-ZTK-1F-GEN-STR-CAL-1016 | TOPSIDES MISCELLANEOUSD DESIGN REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 23-Jun-2026 16:43:21 | wisuda.c@jutal.com | 23-Jun-2026 17:30:29 | Jumpol Sudjitjul | 01-Jul-2026 |  | Sompop Singhatiraj | 03-Jul-2026 | 14-Jul-2026 14:10:50 | Pornlert Wanaphattharaphan | 06-Jul-2026 | 14-Jul-2026 18:55:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Jul-2026 | 14-Jul-2026 19:22:24 | 14-Jul-2026 12:26:29 | 0 |  |  | Approver | Locate
AO-001661 | MM-ZTK-1F-GEN-STR-CAL-1016 | TOPSIDES MISCELLANEOUSD DESIGN REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:46:29 | wisuda.c@jutal.com | 25-Aug-2026 09:49:01 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 17-Sep-2026 13:12:08 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 17-Sep-2026 22:49:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 18-Sep-2026 09:50:15 | 18-Sep-2026 03:36:43 | 0 |  |  | Approver | Locate
AO-001066 | MM-ZTK-1F-GEN-STR-CAL-1017 | TOPSIDE FINITE ELEMENT ANALYSIS FOR CASING SLOTS AND UNIHEAD SPACER REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 10-Jul-2026 17:31:39 | wisuda.c@jutal.com | 10-Jul-2026 18:13:09 | Jumpol Sudjitjul | 20-Jul-2026 |  | Sompop Singhatiraj | 22-Jul-2026 | 13-Jul-2026 11:52:01 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 14-Jul-2026 23:32:42 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 24-Jul-2026 | 15-Jul-2026 10:14:57 | 15-Jul-2026 04:04:23 | 0 |  |  | Approver | Locate
AO-000544 | MM-ZTK-1F-GEN-STR-MOM-0001 | WHP JACKET STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 21-May-2026 13:29:16 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000544 | MM-ZTK-1F-GEN-STR-MOM-0002 | WHP JACKET STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 21-May-2026 13:29:47 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000544 | MM-ZTK-1F-GEN-STR-MOM-0003 | WHP JACKET STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 21-May-2026 13:30:13 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000544 | MM-ZTK-1F-GEN-STR-MOM-0004 | WHP JACKET STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 21-May-2026 13:30:39 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000544 | MM-ZTK-1F-GEN-STR-MOM-0005 | WHP JACKET STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 21-May-2026 13:31:07 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000274 | MM-ZTK-1F-GEN-STR-MOM-0006 | WHP STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 30-Apr-2026 12:01:38 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000544 | MM-ZTK-1F-GEN-STR-MOM-0007 | WHP JACKET STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 21-May-2026 13:31:36 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000544 | MM-ZTK-1F-GEN-STR-MOM-0008 | WHP JACKET STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 21-May-2026 13:32:04 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000602 | MM-ZTK-1F-GEN-STR-MOM-0009 | WHP STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 26-May-2026 14:14:28 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000751 | MM-ZTK-1F-GEN-STR-MOM-0010 | WHP JACKET STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 12-Jun-2026 08:38:09 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000752 | MM-ZTK-1F-GEN-STR-MOM-0011 | WHP JACKET STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 12-Jun-2026 08:38:34 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000868 | MM-ZTK-1F-GEN-STR-MOM-0012 | WHP JACKET STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 22-Jun-2026 18:17:05 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000869 | MM-ZTK-1F-GEN-STR-MOM-0013 | WHP JACKET STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 22-Jun-2026 18:17:36 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000968 | MM-ZTK-1F-GEN-STR-MOM-0014 | WHP STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 01-Jul-2026 10:07:03 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001110 | MM-ZTK-1F-GEN-STR-MOM-0015 | WHP STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Jul-2026 15:35:07 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001118 | MM-ZTK-1F-GEN-STR-MOM-0016 | WHP STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 15-Jul-2026 09:31:26 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001202 | MM-ZTK-1F-GEN-STR-MOM-0017 | WHP STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 20-Jul-2026 13:47:35 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001351 | MM-ZTK-1F-GEN-STR-MOM-0018 | WHP STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 31-Jul-2026 09:31:25 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001717 | MM-ZTK-1F-GEN-STR-MOM-0019 | WHP STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 26-Aug-2026 10:48:45 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001739 | MM-ZTK-1F-GEN-STR-MOM-0020 | WHP STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 27-Aug-2026 19:04:28 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001740 | MM-ZTK-1F-GEN-STR-MOM-0021 | WHP STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 27-Aug-2026 19:04:52 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002268 | MM-ZTK-1F-GEN-STR-MOM-0022 | WHP STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 25-Sep-2026 16:12:32 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002115 | MM-ZTK-1F-GEN-STR-MOM-0023 | WHP STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 17-Sep-2026 10:33:30 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002156 | MM-ZTK-1F-GEN-STR-MOM-0024 | WHP STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 18-Sep-2026 17:27:59 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002216 | MM-ZTK-1F-GEN-STR-MOM-0025 | WHP STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 22-Sep-2026 18:35:30 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002405 | MM-ZTK-1F-GEN-STR-MOM-0026 | WHP STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 07-Oct-2026 09:16:22 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002410 | MM-ZTK-1F-GEN-STR-MOM-0027 | WHP STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 07-Oct-2026 17:12:41 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002512 | MM-ZTK-1F-GEN-STR-MOM-0028 | WHP STRUCTURAL DETAIL ENGINEERING DESIGN WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Oct-2026 12:28:51 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000361 | MM-ZTK-1F-GEN-STR-MR-0001 | MATERIAL REQUISITION FOR PILE GRIPPER WITH INTEGRAL DIAPHRAGM CLOSURE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:54:58 | wisuda.c@jutal.com | 11-May-2026 11:40:39 | Jumpol Sudjitjul | 18-May-2026 |  | Sompop Singhatiraj | 20-May-2026 | 14-May-2026 16:52:28 | Pornlert Wanaphattharaphan | 21-May-2026 | 15-May-2026 23:34:52 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 22-May-2026 | 17-May-2026 08:20:28 | 17-May-2026 01:38:37 | 0 |  |  | Approver | Locate
AO-001276 | MM-ZTK-1F-GEN-STR-MR-0001 | MATERIAL REQUISITION FOR PILE GRIPPER WITH INTEGRAL DIAPHRAGM CLOSURE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 25-Jul-2026 09:14:37 | wisuda.c@jutal.com | 26-Jul-2026 23:52:20 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 30-Jul-2026 11:00:44 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 03-Aug-2026 00:16:49 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 03-Aug-2026 09:03:33 | 03-Aug-2026 02:19:58 | 0 |  |  | Approver | Locate
AO-001434 | MM-ZTK-1F-GEN-STR-MR-0001 | MATERIAL REQUISITION FOR PILE GRIPPER WITH INTEGRAL DIAPHRAGM CLOSURE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 06-Aug-2026 16:10:52 | wisuda.c@jutal.com | 06-Aug-2026 16:16:26 | Jumpol Sudjitjul | 14-Aug-2026 |  | Sompop Singhatiraj | 18-Aug-2026 | 17-Aug-2026 08:36:14 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 20-Aug-2026 23:00:37 | APPR | Approved | Jumpol Sudjitjul | 20-Aug-2026 | 21-Aug-2026 10:21:40 | 21-Aug-2026 04:20:34 | 0 |  |  | Approver | Locate
AO-000363 | MM-ZTK-1F-GEN-STR-MR-0002 | MATERIAL REQUISITION FOR GROUT SEALS AND DIAPHRAGM CLOSURE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:55:32 | wisuda.c@jutal.com | 11-May-2026 11:41:04 | Jumpol Sudjitjul | 18-May-2026 |  | Sompop Singhatiraj | 20-May-2026 | 14-May-2026 17:21:37 | Pornlert Wanaphattharaphan | 21-May-2026 | 15-May-2026 23:35:25 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 22-May-2026 | 17-May-2026 10:05:40 | 17-May-2026 03:31:58 | 0 |  |  | Approver | Locate
AO-001277 | MM-ZTK-1F-GEN-STR-MR-0002 | MATERIAL REQUISITION FOR GROUT SEALS AND DIAPHRAGM CLOSURE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 25-Jul-2026 09:15:04 | wisuda.c@jutal.com | 26-Jul-2026 23:52:36 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 30-Jul-2026 11:27:21 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 03-Aug-2026 00:17:09 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 03-Aug-2026 09:02:17 | 03-Aug-2026 02:17:27 | 0 |  |  | Approver | Locate
AO-000947 | MM-ZTK-1F-GEN-STR-MR-0003 | MATERIAL REQUISTION FOR BUMPER AND FENDER |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Revised | IFR | Issued for Review |  | 29-Jun-2026 22:06:18 | wisuda.c@jutal.com | 04-May-2026 13:06:44 | Jumpol Sudjitjul |  | 09-May-2026 19:51:13 | Sompop Singhatiraj |  | 14-May-2026 17:45:08 | Pornlert Wanaphattharaphan |  | 15-May-2026 23:26:44 |  |  | Jumpol Sudjitjul |  | 17-May-2026 10:12:36 |  | 0 |  |  |  | Locate
AO-000953 | MM-ZTK-1F-GEN-STR-MR-0003 | MATERIAL REQUISTION FOR BUMPER AND FENDER |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  |  | wisuda.c@jutal.com | 30-Jun-2026 14:15:01 | Jumpol Sudjitjul | 07-Jul-2026 |  | Sompop Singhatiraj | 09-Jul-2026 | 02-Jul-2026 09:30:29 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 04-Jul-2026 21:00:33 | APPR | Approved | Jumpol Sudjitjul | 13-Jul-2026 | 05-Jul-2026 10:39:17 | 05-Jul-2026 04:03:57 | 0 |  |  | Approver | Locate
AO-001980 | MM-ZTK-1F-GEN-STR-MR-0003 | MATERIAL REQUISTION FOR BUMPER AND FENDER |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 18:05:31 | wisuda.c@jutal.com | 10-Sep-2026 19:50:00 | Jumpol Sudjitjul | 18-Sep-2026 |  | Sompop Singhatiraj | 22-Sep-2026 | 22-Sep-2026 08:07:41 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 22-Sep-2026 20:11:29 | APPR | Approved | Jumpol Sudjitjul | 24-Sep-2026 | 23-Sep-2026 11:29:57 | 23-Sep-2026 04:52:31 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-GEN-STR-MR-0004 | MATERIAL REQUISTION FOR ANODE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 01:55:56 | wisuda.c@jutal.com | 04-May-2026 13:06:59 | Jumpol Sudjitjul | 11-May-2026 | 09-May-2026 19:53:39 | Sompop Singhatiraj | 13-May-2026 | 14-May-2026 18:17:34 | Pornlert Wanaphattharaphan | 14-May-2026 | 15-May-2026 23:30:01 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 15-May-2026 | 17-May-2026 08:23:00 | 17-May-2026 01:37:14 | 0 |  |  | Approver | Locate
AO-001641 | MM-ZTK-1F-GEN-STR-MR-0004 | MATERIAL REQUISTION FOR ANODE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 09:41:28 | wisuda.c@jutal.com | 21-Aug-2026 10:49:43 | Jumpol Sudjitjul | 28-Aug-2026 |  | Sompop Singhatiraj | 01-Sep-2026 | 24-Aug-2026 16:21:40 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 30-Aug-2026 00:01:33 | APPR | Approved | Jumpol Sudjitjul | 03-Sep-2026 | 30-Aug-2026 16:40:12 | 30-Aug-2026 10:51:36 | 0 |  |  | Approver | Locate
AO-000364 | MM-ZTK-1F-GEN-STR-MR-0005 | MATERIAL REQUISTION FOR LAUNCH TIMBER |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:56:03 | wisuda.c@jutal.com | 11-May-2026 11:41:22 | Jumpol Sudjitjul | 18-May-2026 |  | Sompop Singhatiraj | 20-May-2026 | 14-May-2026 19:03:32 | Pornlert Wanaphattharaphan | 21-May-2026 | 15-May-2026 23:35:47 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 22-May-2026 | 17-May-2026 10:26:06 | 17-May-2026 03:33:21 | 0 |  |  | Approver | Locate
AO-000982 | MM-ZTK-1F-GEN-STR-MR-0005 | MATERIAL REQUISTION FOR LAUNCH TIMBER |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 10:45:46 | wisuda.c@jutal.com | 03-Jul-2026 14:21:04 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 06-Jul-2026 08:56:02 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 08-Jul-2026 00:03:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 08-Jul-2026 09:43:31 | 08-Jul-2026 03:00:55 | 0 |  |  | Approver | Locate
AO-001067 | MM-ZTK-1F-GEN-STR-MR-0005 | MATERIAL REQUISTION FOR LAUNCH TIMBER |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 17:32:19 | wisuda.c@jutal.com | 10-Jul-2026 18:11:56 | Jumpol Sudjitjul | 20-Jul-2026 |  | Sompop Singhatiraj | 22-Jul-2026 | 13-Jul-2026 08:18:00 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 13-Jul-2026 22:32:20 | APPR | Approved | Jumpol Sudjitjul | 24-Jul-2026 | 14-Jul-2026 08:50:21 | 14-Jul-2026 02:22:32 | 0 |  |  | Approver | Locate
AO-000290 | MM-ZTK-1F-GEN-STR-MR-1001 | MATERIAL REǪUISITION FOR TOPSIDES HIGH STRENGTH TUBULAR STEEL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 01:56:20 | wisuda.c@jutal.com | 04-May-2026 13:07:12 | Jumpol Sudjitjul | 11-May-2026 | 09-May-2026 19:55:58 | Sompop Singhatiraj | 13-May-2026 | 15-May-2026 13:43:14 | Pornlert Wanaphattharaphan | 14-May-2026 | 15-May-2026 23:30:40 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 15-May-2026 | 17-May-2026 10:28:38 | 17-May-2026 04:02:17 | 0 |  |  | Approver | Locate
AO-001013 | MM-ZTK-1F-GEN-STR-MR-1001 | MATERIAL REǪUISITION FOR TOPSIDES HIGH STRENGTH TUBULAR STEEL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 23:33:16 | wisuda.c@jutal.com | 04-Jul-2026 14:40:23 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 06-Jul-2026 10:09:30 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 06-Jul-2026 23:42:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 07-Jul-2026 08:29:56 | 07-Jul-2026 02:34:42 | 0 |  |  | Approver | Locate
AO-000580 | MM-ZTK-1F-GEN-STR-MR-1002 | MATERIAL REQUISITION FOR TOPSIDE LOW STRENGTH TUBULAR STEEL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 23-May-2026 08:52:07 | wisuda.c@jutal.com | 23-May-2026 09:31:15 | Jumpol Sudjitjul | 29-May-2026 |  | Sompop Singhatiraj | 04-Jun-2026 | 25-May-2026 12:03:44 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 25-May-2026 20:36:04 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Jun-2026 | 25-May-2026 21:10:45 | 25-May-2026 14:44:21 | 0 |  |  | Approver | Locate
AO-001213 | MM-ZTK-1F-GEN-STR-MR-1002 | MATERIAL REQUISITION FOR TOPSIDE LOW STRENGTH TUBULAR STEEL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 21-Jul-2026 08:36:05 | wisuda.c@jutal.com | 21-Jul-2026 09:13:35 | Jumpol Sudjitjul | 30-Jul-2026 |  | Sompop Singhatiraj | 03-Aug-2026 | 24-Jul-2026 15:13:30 | Pornlert Wanaphattharaphan | 04-Aug-2026 | 24-Jul-2026 23:41:40 | APPR | Approved | Jumpol Sudjitjul | 05-Aug-2026 | 27-Jul-2026 14:55:19 | 27-Jul-2026 08:49:22 | 0 |  |  | Approver | Locate
AO-000340 | MM-ZTK-1F-GEN-STR-MR-1011 | MATERIAL REǪUISITION FOR TOPSIDES HIGH STRENGTH HOT-ROLLED STEEL SECTIONS (SHAPE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 01:56:46 | wisuda.c@jutal.com | 08-May-2026 13:17:04 | Jumpol Sudjitjul | 15-May-2026 | 09-May-2026 19:59:25 | Sompop Singhatiraj | 19-May-2026 | 15-May-2026 13:10:21 | Pornlert Wanaphattharaphan | 20-May-2026 | 15-May-2026 23:34:18 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 21-May-2026 | 17-May-2026 10:00:37 | 17-May-2026 03:32:15 | 0 |  |  | Approver | Locate
AO-001013 | MM-ZTK-1F-GEN-STR-MR-1011 | MATERIAL REǪUISITION FOR TOPSIDES HIGH STRENGTH HOT-ROLLED STEEL SECTIONS (SHAPE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 23:33:51 | wisuda.c@jutal.com | 04-Jul-2026 14:40:41 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 06-Jul-2026 15:15:52 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 08-Jul-2026 00:02:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 08-Jul-2026 09:44:07 | 08-Jul-2026 03:35:45 | 0 |  |  | Approver | Locate
AO-000581 | MM-ZTK-1F-GEN-STR-MR-1012 | MATERIAL REQUISITION FOR TOPSIDE LOW STRENGTH HOT-ROLLED STEEL SECTION (SHAPE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 23-May-2026 08:52:32 | wisuda.c@jutal.com | 23-May-2026 09:31:31 | Jumpol Sudjitjul | 29-May-2026 |  | Sompop Singhatiraj | 04-Jun-2026 | 25-May-2026 11:46:51 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 25-May-2026 20:37:08 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Jun-2026 | 25-May-2026 21:12:47 | 25-May-2026 14:45:55 | 0 |  |  | Approver | Locate
AO-001212 | MM-ZTK-1F-GEN-STR-MR-1012 | MATERIAL REQUISITION FOR TOPSIDE LOW STRENGTH HOT-ROLLED STEEL SECTION (SHAPE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 21-Jul-2026 08:36:33 | wisuda.c@jutal.com | 21-Jul-2026 09:13:56 | Jumpol Sudjitjul | 30-Jul-2026 |  | Sompop Singhatiraj | 03-Aug-2026 | 24-Jul-2026 15:15:23 | Pornlert Wanaphattharaphan | 04-Aug-2026 | 24-Jul-2026 23:42:49 | APPR | Approved | Jumpol Sudjitjul | 05-Aug-2026 | 27-Jul-2026 14:56:24 | 27-Jul-2026 08:51:00 | 0 |  |  | Approver | Locate
AO-000532 | MM-ZTK-1F-GEN-STR-MR-1021 | MATERIAL REQUISITION FOR TOPSIDES HIGH STRENGTH STEEL PLATES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 17:44:21 | wisuda.c@jutal.com | 20-May-2026 18:20:49 | Jumpol Sudjitjul | 28-May-2026 |  | Sompop Singhatiraj | 02-Jun-2026 | 21-May-2026 10:18:16 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 22-May-2026 01:16:45 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 05-Jun-2026 | 22-May-2026 08:22:45 | 22-May-2026 01:58:52 | 0 |  |  | Approver | Locate
AO-001013 | MM-ZTK-1F-GEN-STR-MR-1021 | MATERIAL REQUISITION FOR TOPSIDES HIGH STRENGTH STEEL PLATES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 23:34:26 | wisuda.c@jutal.com | 04-Jul-2026 14:40:56 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 06-Jul-2026 15:20:25 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 07-Jul-2026 23:57:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 08-Jul-2026 09:44:48 | 08-Jul-2026 03:21:06 | 0 |  |  | Approver | Locate
AO-000629 | MM-ZTK-1F-GEN-STR-MR-1022 | MATERIAL REQUISITION FOR TOPSIDE LOW STRENGTH STEEL PLATE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 18:51:56 | wisuda.c@jutal.com | 29-May-2026 19:06:31 | Jumpol Sudjitjul | 10-Jun-2026 |  | Sompop Singhatiraj | 12-Jun-2026 | 31-May-2026 15:43:05 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 01-Jun-2026 00:01:00 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 16-Jun-2026 | 01-Jun-2026 09:19:45 | 01-Jun-2026 02:59:03 | 0 |  |  | Approver | Locate
AO-001388 | MM-ZTK-1F-GEN-STR-MR-1022 | MATERIAL REQUISITION FOR TOPSIDE LOW STRENGTH STEEL PLATE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 11:28:17 | wisuda.c@jutal.com | 03-Aug-2026 14:16:37 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 06-Aug-2026 10:58:34 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 10-Aug-2026 00:51:48 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 17:46:03 | 10-Aug-2026 10:56:57 | 0 |  |  | Approver | Locate
AO-000806 | MM-ZTK-1F-GEN-STR-MTO-1001 | TOPSIDES PRIMARY STEEL MTO REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 15-Jun-2026 22:47:10 | wisuda.c@jutal.com | 16-Jun-2026 10:31:59 | Jumpol Sudjitjul | 23-Jun-2026 |  | Sompop Singhatiraj | 25-Jun-2026 | 24-Jun-2026 14:19:29 | Pornlert Wanaphattharaphan | 26-Jun-2026 | 24-Jun-2026 23:22:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-Jun-2026 | 25-Jun-2026 13:38:37 | 25-Jun-2026 07:14:57 | 0 |  |  | Approver | Locate
AO-001311 | MM-ZTK-1F-GEN-STR-MTO-1001 | TOPSIDES PRIMARY STEEL MTO REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 08:43:38 | wisuda.c@jutal.com | 27-Jul-2026 16:12:27 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 11-Aug-2026 14:45:18 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 01:05:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 11:26:17 | 13-Aug-2026 05:39:09 | 0 |  |  | Approver | Locate
AO-000900 | MM-ZTK-1F-GEN-STR-MTO-1002 | TOPSIDE SECONDARY STEEL MTO REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 25-Jun-2026 23:09:10 | wisuda.c@jutal.com | 26-Jun-2026 09:23:03 | Jumpol Sudjitjul | 03-Jul-2026 |  | Sompop Singhatiraj | 07-Jul-2026 | 29-Jun-2026 10:59:56 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 29-Jun-2026 23:33:17 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 09-Jul-2026 | 30-Jun-2026 09:43:44 | 30-Jun-2026 03:55:55 | 0 |  |  | Approver | Locate
AO-000126 | MM-ZTK-1F-GEN-STR-PDR-0001 | WEIGHT CONTROL PROCEDURE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 14-Apr-2026 09:27:51 | zm169dc@jutal.com | 16-Apr-2026 12:49:49 | Jumpol Sudjitjul | 23-Apr-2026 | 21-Apr-2026 15:24:18 | Sompop Singhatiraj | 27-Apr-2026 | 24-Apr-2026 19:29:50 | Pornlert Wanaphattharaphan | 28-Apr-2026 | 29-Apr-2026 22:26:01 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 29-Apr-2026 | 30-Apr-2026 08:21:01 | 30-Apr-2026 08:57:30 | 0 |  |  | Approver | Locate
AO-000634 | MM-ZTK-1F-GEN-STR-PDR-0001 | WEIGHT CONTROL PROCEDURE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction | 18-May-2026 | 29-May-2026 19:29:56 | wisuda.c@jutal.com | 29-May-2026 19:41:25 | Jumpol Sudjitjul | 10-Jun-2026 |  | Sompop Singhatiraj | 12-Jun-2026 | 31-May-2026 09:58:07 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 02-Jun-2026 22:21:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 03-Jun-2026 09:12:51 | 03-Jun-2026 09:42:02 | 0 |  |  | Approver | Locate
AO-000706 | MM-ZTK-1F-GEN-STR-PDR-0001 | WEIGHT CONTROL PROCEDURE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 08-Jun-2026 08:39:33 | wisuda.c@jutal.com | 08-Jun-2026 11:58:18 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 17-Jun-2026 14:30:13 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 18-Jun-2026 10:14:15 | APPR | Approved | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 10:25:11 | 18-Jun-2026 04:26:24 | 0 |  |  | Approver | Locate
AO-000124 | MM-ZTK-1F-GEN-STR-RPT-0001 | CRITICALITY RATING ANALYSIS RECORD(JACKET PRIMARY STEEL PLATE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 13-Apr-2026 13:33:21 | zm169dc@jutal.com | 13-Apr-2026 13:37:24 | Jumpol Sudjitjul | 22-Apr-2026 | 17-Apr-2026 10:14:21 | Sompop Singhatiraj | 24-Apr-2026 | 21-Apr-2026 15:13:29 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 24-Apr-2026 00:26:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 24-Apr-2026 08:21:07 | 24-Apr-2026 08:43:37 | 0 |  |  | Approver | Locate
AO-000275 | MM-ZTK-1F-GEN-STR-RPT-0001 | CRITICALITY RATING ANALYSIS RECORD(JACKET PRIMARY STEEL PLATE) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 30-Apr-2026 12:02:03 | zm169dc@jutal.com | 30-Apr-2026 13:39:42 | Jumpol Sudjitjul | 22-Apr-2026 | 09-May-2026 19:07:13 | Sompop Singhatiraj | 24-Apr-2026 | 12-May-2026 11:38:03 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 19-May-2026 00:17:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 19-May-2026 14:34:11 | 24-Apr-2026 01:43:37 | 0 |  |  | Approver | Locate
AO-000125 | MM-ZTK-1F-GEN-STR-RPT-0002 | CRITICALITY RATING ANALYSIS RECORD(JACKET PRIMARY STEEL TUBULAR) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 13-Apr-2026 13:33:43 | zm169dc@jutal.com | 13-Apr-2026 13:37:37 | Jumpol Sudjitjul | 22-Apr-2026 | 17-Apr-2026 10:15:11 | Sompop Singhatiraj | 24-Apr-2026 | 21-Apr-2026 15:14:21 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 24-Apr-2026 00:28:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 24-Apr-2026 08:22:41 | 24-Apr-2026 08:44:49 | 0 |  |  | Approver | Locate
AO-000276 | MM-ZTK-1F-GEN-STR-RPT-0002 | CRITICALITY RATING ANALYSIS RECORD(JACKET PRIMARY STEEL TUBULAR) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 30-Apr-2026 12:02:29 | zm169dc@jutal.com | 30-Apr-2026 13:40:02 | Jumpol Sudjitjul | 22-Apr-2026 | 09-May-2026 19:08:53 | Sompop Singhatiraj | 24-Apr-2026 | 12-May-2026 11:39:20 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 19-May-2026 00:18:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 19-May-2026 14:36:32 | 24-Apr-2026 01:44:49 | 0 |  |  | Approver | Locate
AO-000277 | MM-ZTK-1F-GEN-STR-RPT-0003 | JACKET MISCELLANEOUS STEEL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 30-Apr-2026 12:02:53 | zm169dc@jutal.com | 30-Apr-2026 13:40:16 | Jumpol Sudjitjul |  | 10-May-2026 08:33:37 |  |  | 12-May-2026 11:40:13 |  |  | 19-May-2026 00:19:27 |  |  | Jumpol Sudjitjul |  | 19-May-2026 14:37:32 | 29-Apr-2026 09:41:41 | 0 |  |  | Approver | Locate
AO-000277 | MM-ZTK-1F-GEN-STR-RPT-0004 | JKT ANODE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 30-Apr-2026 12:03:16 | zm169dc@jutal.com | 30-Apr-2026 13:40:30 | Jumpol Sudjitjul |  | 10-May-2026 08:35:27 |  |  | 12-May-2026 11:43:10 |  |  | 19-May-2026 00:20:03 |  |  | Jumpol Sudjitjul |  | 19-May-2026 14:38:44 | 29-Apr-2026 09:42:10 | 0 |  |  | Approver | Locate
AO-000277 | MM-ZTK-1F-GEN-STR-RPT-0005 | GRIPPER, PACKER AND DIAPHRAGM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 30-Apr-2026 12:03:39 | zm169dc@jutal.com | 30-Apr-2026 13:42:08 | Jumpol Sudjitjul |  | 10-May-2026 08:37:00 |  |  | 12-May-2026 11:44:32 |  |  | 19-May-2026 00:20:33 |  |  | Jumpol Sudjitjul |  | 19-May-2026 14:39:33 | 29-Apr-2026 09:42:40 | 0 |  |  | Approver | Locate
AO-000277 | MM-ZTK-1F-GEN-STR-RPT-0006 | GROUTING SYSTEM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 30-Apr-2026 12:04:02 | zm169dc@jutal.com | 30-Apr-2026 13:42:31 | Jumpol Sudjitjul |  | 10-May-2026 08:38:57 |  |  | 12-May-2026 11:44:44 |  |  | 19-May-2026 00:21:07 |  |  | Jumpol Sudjitjul |  | 19-May-2026 14:47:35 | 29-Apr-2026 09:43:10 | 0 |  |  | Approver | Locate
AO-000277 | MM-ZTK-1F-GEN-STR-RPT-0007 | FLOODING SYSTEM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 30-Apr-2026 12:04:26 | zm169dc@jutal.com | 30-Apr-2026 13:42:47 | Jumpol Sudjitjul |  | 10-May-2026 08:42:44 |  |  | 12-May-2026 11:45:40 |  |  | 19-May-2026 00:21:43 |  |  | Jumpol Sudjitjul |  | 19-May-2026 14:48:50 | 29-Apr-2026 09:43:39 | 0 |  |  | Approver | Locate
AO-000277 | MM-ZTK-1F-GEN-STR-RPT-0008 | TOPSIDE PRIMARY STEEL-PLATE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 30-Apr-2026 12:04:48 | zm169dc@jutal.com | 30-Apr-2026 13:43:03 | Jumpol Sudjitjul |  | 10-May-2026 08:45:04 |  |  | 12-May-2026 11:45:49 |  |  | 19-May-2026 00:22:15 |  |  | Jumpol Sudjitjul |  | 19-May-2026 14:49:31 | 29-Apr-2026 09:44:08 | 0 |  |  | Approver | Locate
AO-000277 | MM-ZTK-1F-GEN-STR-RPT-0009 | TOPSIDE PRIMARY STEEL-BEAM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 30-Apr-2026 12:05:13 | zm169dc@jutal.com | 30-Apr-2026 13:50:45 | Jumpol Sudjitjul |  | 10-May-2026 08:47:45 |  |  | 12-May-2026 11:46:46 |  |  | 19-May-2026 00:22:42 |  |  | Jumpol Sudjitjul |  | 19-May-2026 14:50:53 | 29-Apr-2026 09:44:35 | 0 |  |  | Approver | Locate
AO-000277 | MM-ZTK-1F-GEN-STR-RPT-0010 | TOPSIDE PRIMARY STEEL-SEAMLESS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 30-Apr-2026 12:05:36 | zm169dc@jutal.com | 30-Apr-2026 13:51:04 | Jumpol Sudjitjul |  | 10-May-2026 08:49:30 |  |  | 12-May-2026 11:47:02 |  |  | 19-May-2026 00:23:14 |  |  | Jumpol Sudjitjul |  | 19-May-2026 14:51:45 | 29-Apr-2026 09:45:06 | 0 |  |  | Approver | Locate
AO-000277 | MM-ZTK-1F-GEN-STR-RPT-0011 | TOPSIDE SECONDARY STEEL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 30-Apr-2026 12:06:01 | zm169dc@jutal.com | 30-Apr-2026 13:51:19 | Jumpol Sudjitjul |  | 10-May-2026 08:51:39 |  |  | 12-May-2026 11:39:45 |  |  | 19-May-2026 00:19:00 |  |  | Jumpol Sudjitjul |  | 19-May-2026 15:05:51 | 29-Apr-2026 09:45:34 | 0 |  |  | Approver | Locate
AO-000277 | MM-ZTK-1F-GEN-STR-RPT-0012 | TOPSIDE TERTIARY STEEL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | RPT | Report | 0 | Submitted | Issued for Review | Issued for Review |  | 30-Apr-2026 12:06:25 | zm169dc@jutal.com | 30-Apr-2026 13:51:35 | Jumpol Sudjitjul |  | 10-May-2026 08:53:08 |  |  | 12-May-2026 11:47:45 |  |  | 19-May-2026 00:23:50 |  |  | Jumpol Sudjitjul |  | 19-May-2026 15:07:56 | 29-Apr-2026 09:46:03 | 0 |  |  | Approver | Locate
AO-000606 | MM-ZTK-1F-GEN-STR-RPT-0101 | CRITICALITY RATING ANALYSIS(STRUCTURAL) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 26-May-2026 18:10:37 | zm169dc@jutal.com | 27-May-2026 10:09:33 | Jumpol Sudjitjul | 05-Jun-2026 | 02-Jun-2026 15:52:20 | Sompop Singhatiraj | 09-Jun-2026 | 12-Jun-2026 09:59:01 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 13-Jun-2026 00:40:41 | APPR | Approved | Jumpol Sudjitjul | 11-Jun-2026 | 13-Jun-2026 07:05:44 | 13-Jun-2026 00:26:19 | 0 |  |  | Approver | Locate
AO-000132 | MM-ZTK-1F-GEN-STR-SPE-2001 | SPECIFICATION FOR GROUT SEALS AND DIAPHRAGM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 03-Apr-2026 14:58:33 | zm169dc@jutal.com | 16-Apr-2026 13:35:18 | Jumpol Sudjitjul | 23-Apr-2026 | 19-Apr-2026 08:19:09 | Sompop Singhatiraj | 27-Apr-2026 | 20-Apr-2026 09:18:47 | Pornlert Wanaphattharaphan | 28-Apr-2026 | 24-Apr-2026 00:21:25 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 29-Apr-2026 | 24-Apr-2026 08:24:02 | 24-Apr-2026 01:53:21 | 0 |  |  | Approver | Locate
AO-001143 | MM-ZTK-1F-GEN-STR-SPE-2001 | SPECIFICATION FOR GROUT SEALS AND DIAPHRAGM |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 18:44:58 | wisuda.c@jutal.com | 16-Jul-2026 20:35:23 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sompop Singhatiraj | 30-Jul-2026 | 24-Jul-2026 14:47:01 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 23:38:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 14:54:50 | 27-Jul-2026 08:48:02 | 0 |  |  | Approver | Locate
AO-001615 | MM-ZTK-1F-GEN-STR-SPE-2001 | SPECIFICATION FOR GROUT SEALS AND DIAPHRAGM |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 17:12:06 | wisuda.c@jutal.com | 19-Aug-2026 17:19:51 | Jumpol Sudjitjul | 27-Aug-2026 |  | Sompop Singhatiraj | 31-Aug-2026 | 20-Aug-2026 09:48:00 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 23-Aug-2026 23:43:14 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 24-Aug-2026 19:52:41 | 24-Aug-2026 14:07:40 | 0 |  |  | Approver | Locate
AO-000130 | MM-ZTK-1F-GEN-STR-SPE-2002 | SPECIFICATION FOR STAINLESS STEEL BUNDLES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 03-Apr-2026 14:59:01 | zm169dc@jutal.com | 16-Apr-2026 13:35:55 | Jumpol Sudjitjul | 23-Apr-2026 | 19-Apr-2026 08:26:50 | Sompop Singhatiraj | 27-Apr-2026 | 20-Apr-2026 09:40:55 | Pornlert Wanaphattharaphan | 28-Apr-2026 | 24-Apr-2026 00:23:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-Apr-2026 | 24-Apr-2026 08:25:08 | 24-Apr-2026 08:55:48 | 0 |  |  | Approver | Locate
AO-000631 | MM-ZTK-1F-GEN-STR-SPE-2002 | SPECIFICATION FOR STAINLESS STEEL BUNDLES |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | SPE | Specification | 0 | Submitted | IFA | Issued for Approval |  | 29-May-2026 18:52:20 | wisuda.c@jutal.com | 29-May-2026 19:02:55 | Jumpol Sudjitjul | 10-Jun-2026 |  | Sompop Singhatiraj | 12-Jun-2026 | 31-May-2026 10:27:39 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 02-Jun-2026 22:20:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 03-Jun-2026 09:13:19 | 03-Jun-2026 02:43:20 | 0 |  |  | Approver | Locate
AO-000908 | MM-ZTK-1F-GEN-STR-SPE-2002 | SPECIFICATION FOR STAINLESS STEEL BUNDLES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 26-Jun-2026 20:33:29 | wisuda.c@jutal.com | 27-Jun-2026 18:47:11 | Jumpol Sudjitjul | 06-Jul-2026 |  | Sompop Singhatiraj | 08-Jul-2026 | 28-Jun-2026 09:04:44 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 29-Jun-2026 01:33:21 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 30-Jun-2026 09:44:34 | 30-Jun-2026 03:53:13 | 0 |  |  | Approver | Locate
AO-000133 | MM-ZTK-1F-GEN-STR-SPE-2003 | SPECIFICATION FOR GRIPPER PERFORMANCE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 03-Apr-2026 14:59:25 | zm169dc@jutal.com | 16-Apr-2026 13:36:16 | Jumpol Sudjitjul | 23-Apr-2026 | 19-Apr-2026 08:35:53 | Sompop Singhatiraj | 27-Apr-2026 | 20-Apr-2026 10:26:24 | Pornlert Wanaphattharaphan | 28-Apr-2026 | 24-Apr-2026 00:18:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-Apr-2026 | 24-Apr-2026 08:26:47 | 24-Apr-2026 08:57:01 | 0 |  |  | Approver | Locate
AO-000632 | MM-ZTK-1F-GEN-STR-SPE-2003 | SPECIFICATION FOR GRIPPER PERFORMANCE |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | SPE | Specification | 0 | Submitted | IFA | Issued for Approval |  | 29-May-2026 18:52:44 | wisuda.c@jutal.com | 29-May-2026 19:03:20 | Jumpol Sudjitjul | 10-Jun-2026 |  | Sompop Singhatiraj | 12-Jun-2026 | 31-May-2026 10:50:59 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 01-Jun-2026 00:25:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 01-Jun-2026 09:21:54 | 01-Jun-2026 03:00:24 | 0 |  |  | Approver | Locate
AO-001145 | MM-ZTK-1F-GEN-STR-SPE-2003 | SPECIFICATION FOR GRIPPER PERFORMANCE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 18:45:26 | wisuda.c@jutal.com | 16-Jul-2026 20:35:38 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sompop Singhatiraj | 30-Jul-2026 | 24-Jul-2026 14:47:08 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 23:39:38 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 14:57:32 | 27-Jul-2026 08:53:36 | 0 |  |  | Approver | Locate
AO-000134 | MM-ZTK-1F-GEN-STR-SPE-2004 | SPECIFICATION FOR GROUTING AND INSTALLATION |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 03-Apr-2026 14:59:55 | zm169dc@jutal.com | 16-Apr-2026 13:36:34 | Jumpol Sudjitjul | 23-Apr-2026 | 19-Apr-2026 09:02:28 | Sompop Singhatiraj | 27-Apr-2026 | 20-Apr-2026 11:21:07 | Pornlert Wanaphattharaphan | 28-Apr-2026 | 24-Apr-2026 00:15:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-Apr-2026 | 24-Apr-2026 08:27:39 | 24-Apr-2026 08:58:14 | 0 |  |  | Approver | Locate
AO-000633 | MM-ZTK-1F-GEN-STR-SPE-2004 | SPECIFICATION FOR GROUTING AND INSTALLATION |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | SPE | Specification | 0 | Submitted | IFA | Issued for Approval |  | 29-May-2026 19:30:28 | wisuda.c@jutal.com | 29-May-2026 19:39:25 | Jumpol Sudjitjul | 10-Jun-2026 |  | Sompop Singhatiraj | 12-Jun-2026 | 31-May-2026 11:22:11 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 01-Jun-2026 00:13:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 01-Jun-2026 09:22:25 | 01-Jun-2026 02:57:42 | 0 |  |  | Approver | Locate
AO-001979 | MM-ZTK-1F-GEN-STR-SPE-2004 | SPECIFICATION FOR GROUTING AND INSTALLATION |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 18:06:00 | wisuda.c@jutal.com | 10-Sep-2026 19:49:06 | Jumpol Sudjitjul | 18-Sep-2026 |  | Sompop Singhatiraj | 22-Sep-2026 | 22-Sep-2026 08:18:45 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 22-Sep-2026 20:08:45 | APPR | Approved | Jumpol Sudjitjul | 24-Sep-2026 | 23-Sep-2026 11:31:03 | 23-Sep-2026 04:53:37 | 0 |  |  | Approver | Locate
AO-000135 | MM-ZTK-1F-GEN-STR-SPE-2005 | SPECIFICATION FOR HYDRAULIC DRIVEN FLOODING SYSTEM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 03-Apr-2026 15:00:23 | zm169dc@jutal.com | 16-Apr-2026 13:36:50 | Jumpol Sudjitjul | 23-Apr-2026 | 19-Apr-2026 09:13:17 | Sompop Singhatiraj | 27-Apr-2026 | 20-Apr-2026 12:44:43 | Pornlert Wanaphattharaphan | 28-Apr-2026 | 24-Apr-2026 00:17:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-Apr-2026 | 24-Apr-2026 08:29:19 | 24-Apr-2026 02:02:04 | 0 |  |  | Approver | Locate
AO-000909 | MM-ZTK-1F-GEN-STR-SPE-2005 | SPECIFICATION FOR HYDRAULIC DRIVEN FLOODING SYSTEM |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | SPE | Specification | 0 | Submitted | IFA | Issued for Approval |  | 26-Jun-2026 20:33:54 | wisuda.c@jutal.com | 27-Jun-2026 18:47:31 | Jumpol Sudjitjul | 06-Jul-2026 |  | Sompop Singhatiraj | 08-Jul-2026 | 28-Jun-2026 09:00:07 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 29-Jun-2026 01:33:02 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 10-Jul-2026 | 30-Jun-2026 09:45:37 | 30-Jun-2026 03:57:07 | 0 |  |  | Approver | Locate
AO-000994 | MM-ZTK-1F-GEN-STR-SPE-2005 | SPECIFICATION FOR HYDRAULIC DRIVEN FLOODING SYSTEM |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 14:32:03 | wisuda.c@jutal.com | 03-Jul-2026 14:45:22 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 03-Jul-2026 18:00:19 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 10-Jul-2026 01:04:55 | APPR | Approved | Jumpol Sudjitjul | 16-Jul-2026 | 10-Jul-2026 08:09:25 | 10-Jul-2026 01:47:35 | 0 |  |  | Approver | Locate
AO-001005 | MM-ZTK-1F-GEN-STR-TBE-1001 | TECHNICAL BID EVALUATION FOR TOPSIDES STRUCTURAL STEEL PLATE (ZWP20, ZWP21, ZWP22, ZWP23) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 03-Jul-2026 18:24:30 | wisuda.c@jutal.com | 03-Jul-2026 19:01:47 | Jumpol Sudjitjul | 13-Jul-2026 |  | Sompop Singhatiraj | 15-Jul-2026 | 06-Jul-2026 15:58:21 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 07-Jul-2026 00:40:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 07-Jul-2026 08:28:07 | 07-Jul-2026 02:18:33 | 0 |  |  | Approver | Locate
AO-001006 | MM-ZTK-1F-GEN-STR-TBE-1002 | TECHNICAL BID EVALUATION FOR TOPSIDES STRUCTURAL SEAMLESS PIPE (ZWP20, ZWP21, ZWP22, ZWP23) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 03-Jul-2026 19:12:24 | wisuda.c@jutal.com | 04-Jul-2026 14:42:53 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 10-Jul-2026 07:51:56 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 10-Jul-2026 11:22:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 10-Jul-2026 12:53:19 | 10-Jul-2026 06:38:58 | 0 |  |  | Approver | Locate
AO-001063 | MM-ZTK-1F-GEN-STR-TBE-1003 | TECHNICAL BID EVALUATION FOR TOPSIDES STRUCTURAL BEAMS (ZWP20, ZWP21, ZWP22, ZWP23) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 10-Jul-2026 16:56:09 | wisuda.c@jutal.com | 10-Jul-2026 18:07:56 | Jumpol Sudjitjul | 20-Jul-2026 |  | Sompop Singhatiraj | 22-Jul-2026 | 13-Jul-2026 12:00:01 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 13-Jul-2026 13:28:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 13-Jul-2026 13:40:36 | 13-Jul-2026 07:07:52 | 0 |  |  | Approver | Locate
AO-001098 | MM-ZTK-1F-GEN-STR-TBE-1004 | TECHNICAL BID EVALUATION FOR TEFLON PLATES (ZWP20, ZWP21, ZWP22, ZWP23) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 14-Jul-2026 08:45:01 | wisuda.c@jutal.com | 14-Jul-2026 09:07:54 | Jumpol Sudjitjul | 21-Jul-2026 | 15-Jul-2026 22:05:50 | Sompop Singhatiraj | 23-Jul-2026 | 16-Jul-2026 08:35:04 | Pornlert Wanaphattharaphan | 24-Jul-2026 | 16-Jul-2026 17:28:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Jul-2026 | 16-Jul-2026 17:55:29 | 16-Jul-2026 11:19:45 | 0 |  |  | Approver | Locate
AO-001307 | MM-ZTK-1F-GEN-STR-TBE-1005 | TECHNICAL BID EVALUATION FOR HYDRAULIC DRIVEN FLOODING AND VENTING SYSTEM (ZWP20, ZWP21, ZWP22, ZWP23) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 27-Jul-2026 08:44:05 | wisuda.c@jutal.com | 27-Jul-2026 16:08:00 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 30-Jul-2026 16:49:02 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 30-Jul-2026 17:29:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 30-Jul-2026 19:15:46 | 30-Jul-2026 12:24:29 | 0 |  |  | Approver | Locate
AO-001581 | MM-ZTK-1F-GEN-STR-TBE-1005 | TECHNICAL BID EVALUATION FOR HYDRAULIC DRIVEN FLOODING AND VENTING SYSTEM (ZWP20, ZWP21, ZWP22, ZWP23) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 18-Aug-2026 16:30:46 | wisuda.c@jutal.com | 19-Aug-2026 10:43:15 | Jumpol Sudjitjul | 26-Aug-2026 |  | Sompop Singhatiraj | 28-Aug-2026 | 20-Aug-2026 09:28:28 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 20-Aug-2026 13:45:57 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 20-Aug-2026 13:50:44 | 20-Aug-2026 07:38:11 | 0 |  |  | Approver | Locate
AO-001163 | MM-ZTK-1F-GEN-STR-TBE-1006 | TECHNICAL BID EVALUATION FOR PILE GRIPPER, DIAPHRAGM CLOSURE AND GROUT PACKER |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 20-Jul-2026 10:35:45 | wisuda.c@jutal.com | 20-Jul-2026 14:56:32 | Jumpol Sudjitjul | 27-Jul-2026 |  | Sompop Singhatiraj | 31-Jul-2026 | 24-Jul-2026 19:31:04 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 23:40:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:56:57 | 27-Jul-2026 08:52:24 | 0 |  |  | Approver | Locate
AO-001527 | MM-ZTK-1F-GEN-STR-TBE-1006 | TECHNICAL BID EVALUATION FOR PILE GRIPPER, DIAPHRAGM CLOSURE AND GROUT PACKER |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 14-Aug-2026 16:16:11 | wisuda.c@jutal.com | 14-Aug-2026 16:28:54 | Jumpol Sudjitjul | 21-Aug-2026 |  | Sompop Singhatiraj | 25-Aug-2026 | 17-Aug-2026 09:50:05 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 17-Aug-2026 16:36:08 | APPR | Approved | Jumpol Sudjitjul | 27-Aug-2026 | 17-Aug-2026 17:07:01 | 17-Aug-2026 10:49:43 | 0 |  |  | Approver | Locate
AO-001308 | MM-ZTK-1F-GEN-STR-TBE-1007 | TECHNICAL BID EVALUATION FOR JACKET ANODES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 27-Jul-2026 08:44:37 | wisuda.c@jutal.com | 27-Jul-2026 16:09:12 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 31-Jul-2026 10:55:46 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 02-Aug-2026 16:31:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 02-Aug-2026 21:11:48 | 02-Aug-2026 14:34:10 | 0 |  |  | Approver | Locate
AO-001613 | MM-ZTK-1F-GEN-STR-TBE-1007 | TECHNICAL BID EVALUATION FOR JACKET ANODES |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 19-Aug-2026 15:58:06 | wisuda.c@jutal.com | 19-Aug-2026 16:10:07 | Jumpol Sudjitjul | 26-Aug-2026 |  | Sompop Singhatiraj | 28-Aug-2026 | 24-Aug-2026 16:13:10 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 26-Aug-2026 00:35:59 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 26-Aug-2026 08:30:13 | 26-Aug-2026 01:59:12 | 0 |  |  | Approver | Locate
AO-001750 | MM-ZTK-1F-GEN-STR-TBE-1008 | TECHNICAL BID EVALUATION FOR RUBBER FENDER |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 28-Aug-2026 10:31:08 | wisuda.c@jutal.com | 28-Aug-2026 14:14:45 | Jumpol Sudjitjul | 04-Sep-2026 | 07-Sep-2026 15:01:35 | Sompop Singhatiraj | 08-Sep-2026 | 10-Sep-2026 17:34:24 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 11-Sep-2026 00:11:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 11-Sep-2026 08:14:23 | 11-Sep-2026 01:46:11 | 0 |  |  | Approver | Locate
AO-000292 | MM-ZTK-1F-GEN-STR-WCR-1001 | TOPSIDES WEIGHT CONTROL REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | WCR | Weight Control Report | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 01:57:14 | wisuda.c@jutal.com | 04-May-2026 13:14:08 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 09:56:41 | Sompop Singhatiraj | 13-May-2026 | 15-May-2026 18:05:56 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:24:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 14:37:23 | 19-May-2026 15:05:46 | 0 |  |  | Approver | Locate
AO-000811 | MM-ZTK-1F-GEN-STR-WCR-1001 | TOPSIDES WEIGHT CONTROL REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | WCR | Weight Control Report | 0 | Submitted | IFA | Issued for Approval |  | 15-Jun-2026 22:47:44 | wisuda.c@jutal.com | 16-Jun-2026 10:32:54 | Jumpol Sudjitjul | 23-Jun-2026 | 19-Jun-2026 01:18:13 | Sompop Singhatiraj | 25-Jun-2026 | 25-Jun-2026 08:19:32 | Pornlert Wanaphattharaphan | 26-Jun-2026 | 25-Jun-2026 21:23:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-Jun-2026 | 25-Jun-2026 22:49:36 | 25-Jun-2026 16:08:30 | 0 |  |  | Approver | Locate
AO-001369 | MM-ZTK-1F-GEN-STR-WCR-1001 | TOPSIDES WEIGHT CONTROL REPORT |  | B2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | WCR | Weight Control Report | 0 | Submitted | IFA | Issued for Approval |  | 03-Aug-2026 10:56:01 | wisuda.c@jutal.com | 03-Aug-2026 13:27:24 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 10-Aug-2026 20:46:59 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 12-Aug-2026 01:20:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 13-Aug-2026 11:27:00 | 13-Aug-2026 05:08:29 | 0 |  |  | Approver | Locate
AO-001891 | MM-ZTK-1F-GEN-STR-WCR-1001 | TOPSIDES WEIGHT CONTROL REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | STR | Structural | WCR | Weight Control Report | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 09:35:11 | wisuda.c@jutal.com | 08-Sep-2026 09:12:26 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 14:36:57 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 12:58:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 17:48:37 | 20-Sep-2026 12:04:33 | 0 |  |  | Approver | Locate
AO-000106 | MM-ZTK-1F-GEN-TEL-BOD-0001 | TELECOMMUNICATION BASIC OF DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | BOD | Basis of Design | 0 | Submitted | IFI | Issued for Information |  | 10-Apr-2026 10:20:02 | zm169dc@jutal.com | 10-Apr-2026 15:20:55 | Jumpol Sudjitjul | 22-Apr-2026 |  | Wichai Salee | 24-Apr-2026 | 27-Apr-2026 16:05:02 | Pornlert Wanaphattharaphan | 27-Apr-2026 | 28-Apr-2026 22:58:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Apr-2026 | 29-Apr-2026 08:39:07 | 30-Apr-2026 11:49:38 | 0 |  |  | Approver | Locate
AO-000620 | MM-ZTK-1F-GEN-TEL-BOD-0001 | TELECOMMUNICATION BASIC OF DESIGN |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 29-May-2026 14:06:55 | wisuda.c@jutal.com | 29-May-2026 15:11:58 | Jumpol Sudjitjul | 09-Jun-2026 |  | Wichai Salee | 11-Jun-2026 | 22-Jun-2026 16:40:52 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 22-Jun-2026 22:18:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 23-Jun-2026 09:43:33 | 23-Jun-2026 08:03:52 | 0 |  |  | Approver | Locate
AO-001700 | MM-ZTK-1F-GEN-TEL-BOD-0001 | TELECOMMUNICATION BASIC OF DESIGN |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 25-Aug-2026 11:54:59 | wisuda.c@jutal.com | 25-Aug-2026 15:11:45 | Jumpol Sudjitjul | 01-Sep-2026 |  | Wichai Salee | 03-Sep-2026 | 04-Sep-2026 11:14:50 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:17:11 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 11:52:59 | 07-Sep-2026 05:34:05 | 0 |  |  | Approver | Locate
AO-000345 | MM-ZTK-1F-GEN-TEL-DTS-0001 | DATASHEET FOR SCADA RADIO SYSTEM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:58:26 | wisuda.c@jutal.com | 11-May-2026 10:46:08 | Jumpol Sudjitjul | 18-May-2026 |  | Wichai Salee | 20-May-2026 | 23-May-2026 12:58:07 | Pornlert Wanaphattharaphan | 21-May-2026 | 29-May-2026 00:09:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 29-May-2026 09:41:13 | 29-May-2026 03:10:08 | 0 |  |  | Approver | Locate
AO-000969 | MM-ZTK-1F-GEN-TEL-DTS-0001 | DATASHEET FOR SCADA RADIO SYSTEM |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 01-Jul-2026 17:57:29 | wisuda.c@jutal.com | 02-Jul-2026 13:34:34 | Jumpol Sudjitjul | 09-Jul-2026 |  | Wichai Salee | 13-Jul-2026 | 20-Jul-2026 10:24:45 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 22-Jul-2026 22:37:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jul-2026 | 23-Jul-2026 08:22:31 | 23-Jul-2026 02:21:10 | 0 |  |  | Approver | Locate
AO-001701 | MM-ZTK-1F-GEN-TEL-DTS-0001 | DATASHEET FOR SCADA RADIO SYSTEM |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 25-Aug-2026 11:55:29 | wisuda.c@jutal.com | 25-Aug-2026 13:14:06 | Jumpol Sudjitjul | 01-Sep-2026 |  | Wichai Salee | 03-Sep-2026 | 02-Sep-2026 10:32:04 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:17:55 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 11:53:42 | 07-Sep-2026 05:36:26 | 0 |  |  | Approver | Locate
AO-000346 | MM-ZTK-1F-GEN-TEL-DTS-0002 | DATASHEET FOR TRUNK RADIO SYSTEM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:58:57 | wisuda.c@jutal.com | 11-May-2026 10:46:24 | Jumpol Sudjitjul | 18-May-2026 |  | Wichai Salee | 20-May-2026 | 23-May-2026 12:59:02 | Pornlert Wanaphattharaphan | 21-May-2026 | 29-May-2026 00:10:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 29-May-2026 09:38:31 | 29-May-2026 03:08:54 | 0 |  |  | Approver | Locate
AO-000969 | MM-ZTK-1F-GEN-TEL-DTS-0002 | DATASHEET FOR TRUNK RADIO SYSTEM |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 01-Jul-2026 17:57:58 | wisuda.c@jutal.com | 02-Jul-2026 13:35:17 | Jumpol Sudjitjul | 09-Jul-2026 |  | Wichai Salee | 13-Jul-2026 | 20-Jul-2026 10:26:00 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 22-Jul-2026 22:38:01 | APPR | Approved | Jumpol Sudjitjul | 15-Jul-2026 | 23-Jul-2026 08:16:55 | 23-Jul-2026 02:19:48 | 0 |  |  | Approver | Locate
AO-001701 | MM-ZTK-1F-GEN-TEL-DTS-0002 | DATASHEET FOR TRUNK RADIO SYSTEM |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 25-Aug-2026 11:55:55 | wisuda.c@jutal.com | 25-Aug-2026 13:14:19 | Jumpol Sudjitjul | 01-Sep-2026 |  | Wichai Salee | 03-Sep-2026 | 04-Sep-2026 11:06:17 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:18:51 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 11:57:11 | 07-Sep-2026 05:37:34 | 0 |  |  | Approver | Locate
AO-000350 | MM-ZTK-1F-GEN-TEL-DTS-0003 | DATASHEET FOR EXPLOSION PROOF TELEPHONE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:59:26 | wisuda.c@jutal.com | 11-May-2026 10:46:37 | Jumpol Sudjitjul | 18-May-2026 |  | Wichai Salee | 20-May-2026 | 23-May-2026 13:00:29 | Pornlert Wanaphattharaphan | 21-May-2026 | 29-May-2026 00:11:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 29-May-2026 09:36:56 | 29-May-2026 03:05:42 | 0 |  |  | Approver | Locate
AO-000969 | MM-ZTK-1F-GEN-TEL-DTS-0003 | DATASHEET FOR EXPLOSION PROOF TELEPHONE |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 01-Jul-2026 17:58:29 | wisuda.c@jutal.com | 02-Jul-2026 13:35:57 | Jumpol Sudjitjul | 09-Jul-2026 |  | Wichai Salee | 13-Jul-2026 | 03-Jul-2026 14:06:49 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 14-Jul-2026 23:55:12 | APPR | Approved | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 10:34:11 | 15-Jul-2026 04:09:55 | 0 |  |  | Approver | Locate
AO-001701 | MM-ZTK-1F-GEN-TEL-DTS-0003 | DATASHEET FOR EXPLOSION PROOF TELEPHONE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 25-Aug-2026 11:56:24 | wisuda.c@jutal.com | 25-Aug-2026 13:14:32 | Jumpol Sudjitjul | 01-Sep-2026 |  | Wichai Salee | 03-Sep-2026 | 02-Sep-2026 11:24:24 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:20:14 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 11:59:57 | 07-Sep-2026 05:27:18 | 0 |  |  | Approver | Locate
AO-000347 | MM-ZTK-1F-GEN-TEL-DTS-0004 | DATASHEET FOR MARINE RACON |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:59:51 | wisuda.c@jutal.com | 11-May-2026 10:47:43 | Jumpol Sudjitjul | 18-May-2026 |  | Wichai Salee | 20-May-2026 | 23-May-2026 13:01:29 | Pornlert Wanaphattharaphan | 21-May-2026 | 29-May-2026 00:13:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 29-May-2026 09:33:42 | 29-May-2026 03:00:34 | 0 |  |  | Approver | Locate
AO-000969 | MM-ZTK-1F-GEN-TEL-DTS-0004 | DATASHEET FOR MARINE RACON |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 01-Jul-2026 17:59:01 | wisuda.c@jutal.com | 02-Jul-2026 13:36:30 | Jumpol Sudjitjul | 09-Jul-2026 |  | Wichai Salee | 13-Jul-2026 | 20-Jul-2026 13:30:46 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 22-Jul-2026 22:38:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jul-2026 | 23-Jul-2026 08:16:09 | 23-Jul-2026 02:18:35 | 0 |  |  | Approver | Locate
AO-001701 | MM-ZTK-1F-GEN-TEL-DTS-0004 | DATASHEET FOR MARINE RACON |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | AFC | Approved for Construction |  | 25-Aug-2026 11:56:53 | wisuda.c@jutal.com | 25-Aug-2026 13:14:46 | Jumpol Sudjitjul | 01-Sep-2026 |  | Wichai Salee | 03-Sep-2026 | 02-Sep-2026 11:29:38 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:21:19 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 12:02:05 | 07-Sep-2026 05:28:28 | 0 |  |  | Approver | Locate
AO-000344 | MM-ZTK-1F-GEN-TEL-DTS-0005 | DATASHEET FOR VHF RADIO SYSTEM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 10-May-2026 23:38:41 | wisuda.c@jutal.com | 11-May-2026 10:47:58 | Jumpol Sudjitjul | 18-May-2026 |  | Wichai Salee | 20-May-2026 | 23-May-2026 13:02:13 | Pornlert Wanaphattharaphan | 21-May-2026 | 29-May-2026 00:14:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 29-May-2026 09:27:21 | 29-May-2026 03:23:31 | 0 |  |  | Approver | Locate
AO-000969 | MM-ZTK-1F-GEN-TEL-DTS-0005 | DATASHEET FOR VHF RADIO SYSTEM |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 01-Jul-2026 17:59:34 | wisuda.c@jutal.com | 02-Jul-2026 13:37:05 | Jumpol Sudjitjul | 09-Jul-2026 |  | Wichai Salee | 13-Jul-2026 | 21-Jul-2026 10:00:44 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 22-Jul-2026 22:41:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jul-2026 | 23-Jul-2026 08:13:24 | 23-Jul-2026 02:17:15 | 0 |  |  | Approver | Locate
AO-001676 | MM-ZTK-1F-GEN-TEL-DTS-0005 | DATASHEET FOR VHF RADIO SYSTEM |  | X | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | DTS | Data Sheet | 0 | Submitted | VOID | Withdrawn or Superseded |  | 24-Aug-2026 10:02:54 | wisuda.c@jutal.com | 25-Aug-2026 13:15:28 | Jumpol Sudjitjul |  |  | Wichai Salee |  | 26-Aug-2026 08:45:21 | Pornlert Wanaphattharaphan |  | 29-Aug-2026 23:12:17 | REC | Received | Jumpol Sudjitjul |  | 30-Aug-2026 16:53:07 | 30-Aug-2026 10:35:55 | 0 |  |  | For Info | Locate
AO-000820 | MM-ZTK-1F-GEN-TEL-LIS-0001 | TELECOMMUNICATION DOCUMENT INDEX |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 17-Jun-2026 21:58:12 | wisuda.c@jutal.com | 18-Jun-2026 09:55:13 | Jumpol Sudjitjul | 25-Jun-2026 |  | Wichai Salee | 29-Jun-2026 | 02-Jul-2026 17:20:44 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 02-Jul-2026 22:08:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 03-Jul-2026 11:10:10 | 03-Jul-2026 04:14:52 | 0 |  |  | Approver | Locate
AO-000577 | MM-ZTK-1F-GEN-TEL-LIS-0003 | TELECOMMUNICATION EQUIPMENT LIST |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 23-May-2026 08:54:50 | wisuda.c@jutal.com | 23-May-2026 09:33:49 | Jumpol Sudjitjul | 29-May-2026 |  | Wichai Salee | 04-Jun-2026 | 17-Jun-2026 10:26:31 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 17-Jun-2026 15:25:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 17-Jun-2026 15:31:59 | 17-Jun-2026 09:29:22 | 0 |  |  | Approver | Locate
AO-001909 | MM-ZTK-1F-GEN-TEL-LIS-0003 | TELECOMMUNICATION EQUIPMENT LIST |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 09:38:14 | wisuda.c@jutal.com | 08-Sep-2026 09:19:08 | Jumpol Sudjitjul | 15-Sep-2026 |  | Wichai Salee | 17-Sep-2026 | 12-Sep-2026 20:37:40 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 13-Sep-2026 22:42:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 23:12:30 | 13-Sep-2026 16:29:52 | 0 |  |  | Approver | Locate
AO-002290 | MM-ZTK-1F-GEN-TEL-LIS-0003 | TELECOMMUNICATION EQUIPMENT LIST |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 08:38:14 | wisuda.c@jutal.com | 28-Sep-2026 13:29:55 | Jumpol Sudjitjul | 05-Oct-2026 |  | Wichai Salee | 07-Oct-2026 | 01-Oct-2026 15:57:09 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 01-Oct-2026 23:17:34 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 02-Oct-2026 13:21:23 | 02-Oct-2026 06:59:00 | 0 |  |  | Approver | Locate
AO-000757 | MM-ZTK-1F-GEN-TEL-LIS-0004 | TELECOMMUNICATION CABLE SCHEDULE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 12-Jun-2026 10:00:11 | wisuda.c@jutal.com | 12-Jun-2026 13:27:07 | Jumpol Sudjitjul | 19-Jun-2026 |  | Wichai Salee | 23-Jun-2026 | 26-Jun-2026 15:39:12 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 28-Jun-2026 10:47:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 30-Jun-2026 09:44:32 | 30-Jun-2026 03:54:34 | 0 |  |  | Approver | Locate
AO-002171 | MM-ZTK-1F-GEN-TEL-LIS-0004 | TELECOMMUNICATION CABLE SCHEDULE |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 18-Sep-2026 20:21:37 | wisuda.c@jutal.com | 20-Sep-2026 12:41:17 | Jumpol Sudjitjul | 25-Sep-2026 |  | Wichai Salee | 29-Sep-2026 | 23-Sep-2026 22:53:59 | Pornlert Wanaphattharaphan | 30-Sep-2026 | 26-Sep-2026 05:50:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Oct-2026 | 26-Sep-2026 14:14:28 | 26-Sep-2026 07:52:11 | 0 |  |  | Approver | Locate
AO-000298 | MM-ZTK-1F-GEN-TEL-LIS-0005 | TELECOMMUNICATION POWER CONSUMPTION AND HEAT DISSIPATION LIST |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 05-May-2026 09:09:38 | wisuda.c@jutal.com | 05-May-2026 09:54:18 | Jumpol Sudjitjul | 12-May-2026 |  | Wichai Salee | 14-May-2026 | 16-May-2026 20:41:40 | Pornlert Wanaphattharaphan | 15-May-2026 | 20-May-2026 00:46:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-May-2026 | 20-May-2026 11:11:43 | 20-May-2026 04:26:49 | 0 |  |  | Approver | Locate
AO-002172 | MM-ZTK-1F-GEN-TEL-LIS-0005 | TELECOMMUNICATION POWER CONSUMPTION AND HEAT DISSIPATION LIST |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFA | Issued for Approval |  | 21-Sep-2026 11:12:28 | wisuda.c@jutal.com | 21-Sep-2026 14:30:18 | Jumpol Sudjitjul | 28-Sep-2026 |  | Wichai Salee | 30-Sep-2026 | 25-Sep-2026 22:52:59 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 26-Sep-2026 05:32:27 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 26-Sep-2026 14:15:05 | 26-Sep-2026 07:53:15 | 0 |  |  | Approver | Locate
AO-000578 | MM-ZTK-1F-GEN-TEL-LIS-0006 | TELECOMMUNICATION EQUIPMENT AND EX-CERTIFICATES LIST |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 23-May-2026 08:55:12 | wisuda.c@jutal.com | 23-May-2026 09:33:38 | Jumpol Sudjitjul | 29-May-2026 |  | Wichai Salee | 04-Jun-2026 | 17-Jun-2026 10:32:59 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 17-Jun-2026 15:28:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 17-Jun-2026 15:34:23 | 17-Jun-2026 09:30:47 | 0 |  |  | Approver | Locate
AO-000093 | MM-ZTK-1F-GEN-TEL-MOM-0001 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 08-Apr-2026 15:43:49 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000094 | MM-ZTK-1F-GEN-TEL-MOM-0002 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 08-Apr-2026 15:44:21 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000378 | MM-ZTK-1F-GEN-TEL-MOM-0003 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 12-May-2026 14:52:03 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000378 | MM-ZTK-1F-GEN-TEL-MOM-0004 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 12-May-2026 14:52:38 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000378 | MM-ZTK-1F-GEN-TEL-MOM-0005 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 12-May-2026 14:53:15 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000378 | MM-ZTK-1F-GEN-TEL-MOM-0006 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 12-May-2026 14:18:15 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000409 | MM-ZTK-1F-GEN-TEL-MOM-0007 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 15-May-2026 10:52:41 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000678 | MM-ZTK-1F-GEN-TEL-MOM-0008 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 05-Jun-2026 09:00:50 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000678 | MM-ZTK-1F-GEN-TEL-MOM-0009 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 05-Jun-2026 09:01:19 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000865 | MM-ZTK-1F-GEN-TEL-MOM-0010 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 22-Jun-2026 13:21:24 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000865 | MM-ZTK-1F-GEN-TEL-MOM-0011 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 22-Jun-2026 13:22:11 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001592 | MM-ZTK-1F-GEN-TEL-MOM-0012 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 18-Aug-2026 15:26:27 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001592 | MM-ZTK-1F-GEN-TEL-MOM-0013 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 18-Aug-2026 15:27:00 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001592 | MM-ZTK-1F-GEN-TEL-MOM-0014 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 18-Aug-2026 15:27:38 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-001592 | MM-ZTK-1F-GEN-TEL-MOM-0015 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 18-Aug-2026 15:28:22 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002066 | MM-ZTK-1F-GEN-TEL-MOM-0016 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Sep-2026 19:41:53 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002066 | MM-ZTK-1F-GEN-TEL-MOM-0017 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Sep-2026 19:42:21 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002066 | MM-ZTK-1F-GEN-TEL-MOM-0018 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Sep-2026 19:42:49 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002039 | MM-ZTK-1F-GEN-TEL-MOM-0019 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 14-Sep-2026 09:52:57 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002248 | MM-ZTK-1F-GEN-TEL-MOM-0020 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 24-Sep-2026 15:02:08 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002248 | MM-ZTK-1F-GEN-TEL-MOM-0021 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 24-Sep-2026 15:02:49 | zm169dc@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-002399 | MM-ZTK-1F-GEN-TEL-MOM-0022 | EIT DISCIPLINES WEEKLY MEETING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 06-Oct-2026 15:30:46 | zhaoli@jutal.com | [16 empty] | 0 |  |  |  | Locate
AO-000457 | MM-ZTK-1F-GEN-TEL-MR-0001 | MATERIAL REQUISITION FOR SCADA RADIO |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 14:14:28 | wisuda.c@jutal.com | 18-May-2026 19:37:43 | Jumpol Sudjitjul | 26-May-2026 | 20-May-2026 07:19:37 | Wichai Salee | 28-May-2026 | 12-Jun-2026 00:12:29 | Pornlert Wanaphattharaphan | 29-May-2026 | 13-Jun-2026 00:33:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 13-Jun-2026 07:04:24 | 13-Jun-2026 00:21:27 | 0 |  |  | Approver | Locate
AO-001783 | MM-ZTK-1F-GEN-TEL-MR-0001 | MATERIAL REQUISITION FOR SCADA RADIO |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 31-Aug-2026 09:44:45 | wisuda.c@jutal.com | 31-Aug-2026 12:54:28 | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 15:16:16 | Wichai Salee | 09-Sep-2026 | 10-Sep-2026 12:50:51 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 12-Sep-2026 12:17:26 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 12-Sep-2026 23:17:36 | 12-Sep-2026 16:53:58 | 0 |  |  | Approver | Locate
AO-000489 | MM-ZTK-1F-GEN-TEL-MR-0002 | MATERIAL REQUISITION FOR TRUNK RADIO |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 17-May-2026 00:14:55 | wisuda.c@jutal.com | 18-May-2026 19:38:05 | Jumpol Sudjitjul | 26-May-2026 | 20-May-2026 07:20:19 | Wichai Salee | 28-May-2026 | 12-Jun-2026 00:11:14 | Pornlert Wanaphattharaphan | 29-May-2026 | 13-Jun-2026 00:32:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 13-Jun-2026 07:05:17 | 13-Jun-2026 00:23:58 | 0 |  |  | Approver | Locate
AO-001783 | MM-ZTK-1F-GEN-TEL-MR-0002 | MATERIAL REQUISITION FOR TRUNK RADIO |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 31-Aug-2026 09:45:13 | wisuda.c@jutal.com | 31-Aug-2026 12:54:52 | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 15:18:17 | Wichai Salee | 09-Sep-2026 | 10-Sep-2026 12:51:10 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 12-Sep-2026 12:29:39 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 12-Sep-2026 21:07:37 | 12-Sep-2026 14:30:01 | 0 |  |  | Approver | Locate
AO-000490 | MM-ZTK-1F-GEN-TEL-MR-0003 | MATERIAL REQUISITION FOR EXPLOSION PROOF TELEPHONE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 17-May-2026 00:15:17 | wisuda.c@jutal.com | 18-May-2026 19:42:39 | Jumpol Sudjitjul | 26-May-2026 | 20-May-2026 07:21:00 | Wichai Salee | 28-May-2026 | 12-Jun-2026 00:07:42 | Pornlert Wanaphattharaphan | 29-May-2026 | 13-Jun-2026 00:30:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 13-Jun-2026 07:04:48 | 13-Jun-2026 00:22:44 | 0 |  |  | Approver | Locate
AO-001783 | MM-ZTK-1F-GEN-TEL-MR-0003 | MATERIAL REQUISITION FOR EXPLOSION PROOF TELEPHONE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 31-Aug-2026 08:41:35 | wisuda.c@jutal.com | 31-Aug-2026 12:55:07 | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 15:20:07 | Wichai Salee | 09-Sep-2026 | 09-Sep-2026 15:31:18 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 23:52:56 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 12-Sep-2026 23:18:19 | 12-Sep-2026 16:51:39 | 0 |  |  | Approver | Locate
AO-000491 | MM-ZTK-1F-GEN-TEL-MR-0004 | MATERIAL REQUISITION FOR MARINE RACON |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 17-May-2026 00:15:46 | wisuda.c@jutal.com | 18-May-2026 19:38:33 | Jumpol Sudjitjul | 26-May-2026 | 20-May-2026 07:21:36 | Wichai Salee | 28-May-2026 | 12-Jun-2026 00:10:15 | Pornlert Wanaphattharaphan | 29-May-2026 | 13-Jun-2026 00:30:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 13-Jun-2026 07:03:38 | 13-Jun-2026 00:20:12 | 0 |  |  | Approver | Locate
AO-001783 | MM-ZTK-1F-GEN-TEL-MR-0004 | MATERIAL REQUISITION FOR MARINE RACON |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 31-Aug-2026 08:42:03 | wisuda.c@jutal.com | 31-Aug-2026 12:55:24 | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 15:23:05 | Wichai Salee | 09-Sep-2026 | 09-Sep-2026 15:31:08 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 23:52:28 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 12-Sep-2026 21:09:48 | 12-Sep-2026 14:25:57 | 0 |  |  | Approver | Locate
AO-000492 | MM-ZTK-1F-GEN-TEL-MR-0005 | MATERIAL REQUISITION FOR VHF RADIO SYSTEM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 17-May-2026 00:16:11 | wisuda.c@jutal.com | 18-May-2026 19:38:48 | Jumpol Sudjitjul | 26-May-2026 | 19-May-2026 11:08:56 | Wichai Salee | 28-May-2026 | 12-Jun-2026 00:08:40 | Pornlert Wanaphattharaphan | 29-May-2026 | 13-Jun-2026 00:30:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 13-Jun-2026 07:03:14 | 13-Jun-2026 00:18:50 | 0 |  |  | Approver | Locate
AO-001675 | MM-ZTK-1F-GEN-TEL-MR-0005 | MATERIAL REQUISITION FOR VHF RADIO SYSTEM |  | X | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MR | Material Requisition | 0 | Submitted | VOID | Withdrawn or Superseded |  | 24-Aug-2026 10:03:33 | wisuda.c@jutal.com | 25-Aug-2026 14:27:33 | Jumpol Sudjitjul |  |  | Wichai Salee |  | 26-Aug-2026 08:45:40 | Pornlert Wanaphattharaphan |  | 29-Aug-2026 23:18:40 | REC | Received | Jumpol Sudjitjul |  | 30-Aug-2026 16:54:17 | 30-Aug-2026 10:37:04 | 0 |  |  | For Info | Locate
AO-000758 | MM-ZTK-1F-GEN-TEL-MTO-0001 | TELECOMMUNICATION BULK MATERIAL TAKE-OFF |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 12-Jun-2026 10:00:47 | wisuda.c@jutal.com | 12-Jun-2026 13:23:44 | Jumpol Sudjitjul | 19-Jun-2026 |  | Wichai Salee | 23-Jun-2026 | 26-Jun-2026 15:33:49 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 28-Jun-2026 10:42:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 30-Jun-2026 09:43:42 | 30-Jun-2026 03:51:59 | 0 |  |  | Approver | Locate
AO-001791 | MM-ZTK-1F-GEN-TEL-MTO-0001 | TELECOMMUNICATION BULK MATERIAL TAKE-OFF |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | MTO | Material Take Off | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 08:42:33 | wisuda.c@jutal.com | 31-Aug-2026 12:56:17 | Jumpol Sudjitjul | 07-Sep-2026 |  | Wichai Salee | 09-Sep-2026 | 10-Sep-2026 14:22:40 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 12-Sep-2026 12:31:11 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 12-Sep-2026 23:22:54 | 12-Sep-2026 16:52:48 | 0 |  |  | Approver | Locate
AO-000498 | MM-ZTK-1F-GEN-TEL-RPT-0001 | DESIGN REPORT FOR COMMUNICATION LINK |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | RPT | Report | 0 | Submitted | IFR | Issued for Review | 20-May-2026 | 18-May-2026 19:37:54 | wisuda.c@jutal.com | 18-May-2026 20:15:38 | Jumpol Sudjitjul | 26-May-2026 |  | Wichai Salee | 28-May-2026 | 21-May-2026 23:37:43 | Pornlert Wanaphattharaphan | 29-May-2026 | 27-May-2026 10:28:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 27-May-2026 10:35:57 | 27-May-2026 11:04:16 | 0 |  |  | Approver | Locate
AO-000695 | MM-ZTK-1F-GEN-TEL-RPT-0001 | DESIGN REPORT FOR COMMUNICATION LINK |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 05-Jun-2026 20:59:53 | wisuda.c@jutal.com | 07-Jun-2026 18:09:44 | Jumpol Sudjitjul | 15-Jun-2026 |  | Wichai Salee | 17-Jun-2026 | 23-Jun-2026 11:19:45 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 24-Jun-2026 00:42:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 24-Jun-2026 13:35:14 | 24-Jun-2026 06:52:00 | 0 |  |  | Approver | Locate
AO-001700 | MM-ZTK-1F-GEN-TEL-RPT-0001 | DESIGN REPORT FOR COMMUNICATION LINK |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 25-Aug-2026 11:57:23 | wisuda.c@jutal.com | 25-Aug-2026 15:15:24 | Jumpol Sudjitjul | 01-Sep-2026 |  | Wichai Salee | 03-Sep-2026 | 04-Sep-2026 11:36:56 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:21:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 11:57:00 | 07-Sep-2026 05:26:13 | 0 |  |  | Approver | Locate
AO-002291 | MM-ZTK-1F-GEN-TEL-RPT-0001 | DESIGN REPORT FOR COMMUNICATION LINK |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 08:38:50 | wisuda.c@jutal.com | 28-Sep-2026 13:26:58 | Jumpol Sudjitjul | 05-Oct-2026 |  | Wichai Salee | 07-Oct-2026 | 02-Oct-2026 08:57:47 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 10-Oct-2026 01:20:51 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 10-Oct-2026 17:45:06 | 12-Oct-2026 09:58:44 | 0 |  |  | Approver | Locate
AO-000689 | MM-ZTK-1F-GEN-TEL-RPT-0002 | DESIGN REPORT FOR OVERALL TRANSMISSION INTERFACE REQUIREMENT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 21:00:25 | wisuda.c@jutal.com | 07-Jun-2026 18:09:57 | Jumpol Sudjitjul | 15-Jun-2026 |  | Wichai Salee | 17-Jun-2026 | 23-Jun-2026 11:20:49 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 24-Jun-2026 00:42:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 24-Jun-2026 13:36:04 | 24-Jun-2026 06:53:20 | 0 |  |  | Approver | Locate
AO-002306 | MM-ZTK-1F-GEN-TEL-RPT-0002 | DESIGN REPORT FOR OVERALL TRANSMISSION INTERFACE REQUIREMENT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 30-Sep-2026 09:37:29 | wisuda.c@jutal.com | 30-Sep-2026 16:08:21 | Jumpol Sudjitjul | 07-Oct-2026 |  | Wichai Salee | 09-Oct-2026 | 02-Oct-2026 09:08:01 | Pornlert Wanaphattharaphan | 12-Oct-2026 | 10-Oct-2026 01:40:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Oct-2026 | 10-Oct-2026 17:32:27 | 10-Oct-2026 11:09:19 | 0 |  |  | Approver | Locate
AO-002560 | MM-ZTK-1F-GEN-TEL-RPT-0002 | DESIGN REPORT FOR OVERALL TRANSMISSION INTERFACE REQUIREMENT |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | RPT | Report | 0 | In Review | AFC | Approved for Construction |  | 16-Oct-2026 19:14:51 | wisuda.c@jutal.com | 18-Oct-2026 16:42:21 | Jumpol Sudjitjul | 26-Oct-2026 |  | Wichai Salee | 28-Oct-2026 |  | Pornlert Wanaphattharaphan | 29-Oct-2026 |  |  |  |  | 30-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000531 | MM-ZTK-1F-GEN-TEL-RPT-0100 | CRITICALITY RATING ANALYSIS (TELECOM) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 15:08:37 | zm169dc@jutal.com | 20-May-2026 16:12:16 | Jumpol Sudjitjul | 27-May-2026 |  | Wichai Salee | 29-May-2026 | 15-Jun-2026 09:51:05 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 15-Jun-2026 22:52:38 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 04-Jun-2026 | 16-Jun-2026 09:37:48 | 16-Jun-2026 03:32:49 | 0 |  |  | Approver | Locate
AO-001205 | MM-ZTK-1F-GEN-TEL-RPT-0100 | CRITICALITY RATING ANALYSIS (TELECOM) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 16:14:17 | zm169dc@jutal.com | 20-Jul-2026 16:16:46 | Jumpol Sudjitjul | 27-Jul-2026 |  | Wichai Salee | 31-Jul-2026 | 07-Aug-2026 14:00:20 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 07-Aug-2026 21:51:11 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 08-Aug-2026 10:20:08 | 08-Aug-2026 04:18:42 | 0 |  |  | Approver | Locate
AO-000220 | MM-ZTK-1F-GEN-TEL-SPE-0001 | PROJECT SPECIFICATION FOR TELECOMMUNICATION PACKAGE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 13:05:25 | wisuda.c@jutal.com | 24-Apr-2026 14:04:22 | Jumpol Sudjitjul | 05-May-2026 |  | Wichai Salee | 07-May-2026 | 30-Apr-2026 15:01:08 | Pornlert Wanaphattharaphan | 08-May-2026 | 09-May-2026 00:22:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 09-May-2026 08:23:36 | 09-May-2026 08:53:51 | 0 |  |  | Approver | Locate
AO-001700 | MM-ZTK-1F-GEN-TEL-SPE-0001 | PROJECT SPECIFICATION FOR TELECOMMUNICATION PACKAGE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | GEN |  |  | TEL | Telecommunication | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 25-Aug-2026 11:57:50 | wisuda.c@jutal.com | 25-Aug-2026 15:27:58 | Jumpol Sudjitjul | 01-Sep-2026 |  | Wichai Salee | 03-Sep-2026 | 08-Sep-2026 10:02:24 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 08-Sep-2026 22:59:52 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 09-Sep-2026 11:07:59 | 09-Sep-2026 05:30:28 | 0 |  |  | Approver | Locate
AO-000729 | MM-ZTK-1F-GEN-TNI-MOM-8001 | ZAWTIKA 1F TNI WORKSHOP MINUTES OF MEETING |  | - | Project Document | Engineering Document | Part F - Transportation & Installation | GEN |  |  | TNI | Transportation and Installation | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 10-Jun-2026 09:22:48 | kjb@coes.cn | [16 empty] | 0 |  |  |  | Locate
AO-001119 | MM-ZTK-1F-GEN-TNI-MOM-8002 | ZAWTIKA 1F TNI MINUTES OF MEETING |  | - | Project Document | Engineering Document | Part F - Transportation & Installation | GEN |  |  | TNI | Transportation and Installation | MOM | Minutes of Meeting | 0 | Latest | IFI | Issued for Information |  | 15-Jul-2026 13:59:07 | kjb@coes.cn | [16 empty] | 0 |  |  |  | Locate
AO-000256 | MM-ZTK-1F-GEN-TNI-PDR-8004 | AIR DIVING MANUAL, WORK PACKAGE 1 (T&I) |  | A1 | Project Document | Engineering Document | Part F - Transportation & Installation | GEN |  |  | TNI | Transportation and Installation | PDR | Procedure | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 11:02:02 | kjb@coes.cn | 29-Apr-2026 11:17:41 | Jumpol Sudjitjul | 08-May-2026 | 16-May-2026 15:31:42 | Sukit Nualchanchai | 12-May-2026 | 19-May-2026 08:43:52 | Prin Jitatisil | 13-May-2026 | 21-May-2026 09:30:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 21-May-2026 11:18:20 | 21-May-2026 12:09:40 | 0 |  |  | Approver | Locate
AO-000679 | MM-ZTK-1F-GEN-TNI-PDR-8004 | AIR DIVING MANUAL, WORK PACKAGE 1 (T&I) |  | B1 | Project Document | Engineering Document | Part F - Transportation & Installation | GEN |  |  | TNI | Transportation and Installation | PDR | Procedure | 0 | Submitted | IFA | Issued for Approval |  | 04-Jun-2026 15:52:56 | kjb@coes.cn | 05-Jun-2026 14:56:02 | Jumpol Sudjitjul | 12-Jun-2026 | 05-Jun-2026 15:48:00 | Sukit Nualchanchai | 16-Jun-2026 | 17-Jun-2026 15:14:51 | Prin Jitatisil | 17-Jun-2026 | 18-Jun-2026 09:46:16 | APPR | Approved | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 09:49:53 | 18-Jun-2026 03:46:22 | 0 |  |  | Approver | Locate
AO-000866 | MM-ZTK-1F-GEN-TNI-PDR-8004 | AIR DIVING MANUAL, WORK PACKAGE 1 (T&I) |  | C1 | Project Document | Engineering Document | Part F - Transportation & Installation | GEN |  |  | TNI | Transportation and Installation | PDR | Procedure | 0 | Submitted | AFC | Approved for Construction |  | 22-Jun-2026 17:23:09 | kjb@coes.cn | 22-Jun-2026 17:49:19 | Jumpol Sudjitjul | 30-Jun-2026 | 23-Jun-2026 08:10:23 | Sukit Nualchanchai | 02-Jul-2026 | 26-Jun-2026 17:14:05 | Prin Jitatisil | 03-Jul-2026 | 29-Jun-2026 10:51:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Jul-2026 | 30-Jun-2026 09:29:51 | 30-Jun-2026 03:13:10 | 0 |  |  | Approver | Locate
AO-000680 | MM-ZTK-1F-GEN-TNI-PLN-8001 | AIR DIVING PROJECT PLAN |  | A1 | Project Document | Engineering Document | Part F - Transportation & Installation | GEN |  |  | TNI | Transportation and Installation | PLN | Plan | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 13:04:11 | kjb@coes.cn | 05-Jun-2026 14:26:52 | Jumpol Sudjitjul | 12-Jun-2026 | 05-Jun-2026 15:47:03 | Sukit Nualchanchai | 16-Jun-2026 | 17-Jun-2026 11:14:42 | Prin Jitatisil | 17-Jun-2026 | 18-Jun-2026 09:47:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 09:48:39 | 18-Jun-2026 03:45:06 | 0 |  |  | Approver | Locate
AO-001356 | MM-ZTK-1F-GEN-TNI-RFQ-8001 | RFQ FOR SURVEY AND POSITION |  | A1 | Project Document | Engineering Document | Part F - Transportation & Installation | GEN |  |  | TNI | Transportation and Installation | RFQ | Request for Quotation | 0 | Submitted | IFR | Issued for Review |  | 31-Jul-2026 16:25:03 | kjb@coes.cn | 31-Jul-2026 21:37:37 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sukit Nualchanchai | 13-Aug-2026 | 04-Aug-2026 11:06:01 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 22:52:47 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 14:09:09 | 17-Aug-2026 08:34:07 | 0 |  |  | Approver | Locate
AO-001705 | MM-ZTK-1F-GEN-TNI-RFQ-8001 | RFQ FOR SURVEY AND POSITION |  | B1 | Project Document | Engineering Document | Part F - Transportation & Installation | GEN |  |  | TNI | Transportation and Installation | RFQ | Request for Quotation | 0 | Submitted | IFA | Issued for Approval |  | 25-Aug-2026 15:57:49 | kjb@coes.cn | 25-Aug-2026 16:18:04 | Jumpol Sudjitjul | 01-Sep-2026 | 28-Aug-2026 07:33:12 | Sukit Nualchanchai | 03-Sep-2026 | 31-Aug-2026 13:16:28 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:22:29 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 12:01:34 | 07-Sep-2026 05:39:50 | 0 |  |  | Approver | Locate
AO-001971 | MM-ZTK-1F-GEN-TNI-RFQ-8001 | RFQ FOR SURVEY AND POSITION |  | C1 | Project Document | Engineering Document | Part F - Transportation & Installation | GEN |  |  | TNI | Transportation and Installation | RFQ | Request for Quotation | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 14:01:45 | kjb@coes.cn | 10-Sep-2026 16:13:15 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sukit Nualchanchai | 21-Sep-2026 | 11-Sep-2026 17:33:58 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 26-Sep-2026 08:06:34 | APPR | Approved | Jumpol Sudjitjul | 23-Sep-2026 | 26-Sep-2026 14:17:05 | 26-Sep-2026 07:29:17 | 0 |  |  | Approver | Locate
AO-001357 | MM-ZTK-1F-GEN-TNI-RFQ-8002 | RFQ FOR PILE MONITORING SERVICE |  | A1 | Project Document | Engineering Document | Part F - Transportation & Installation | GEN |  |  | TNI | Transportation and Installation | RFQ | Request for Quotation | 0 | Submitted | IFR | Issued for Review |  | 31-Jul-2026 16:25:31 | kjb@coes.cn | 31-Jul-2026 21:38:10 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sukit Nualchanchai | 13-Aug-2026 | 04-Aug-2026 11:51:33 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 22:53:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 14:08:32 | 17-Aug-2026 08:32:44 | 0 |  |  | Approver | Locate
AO-001706 | MM-ZTK-1F-GEN-TNI-RFQ-8002 | RFQ FOR PILE MONITORING SERVICE |  | B1 | Project Document | Engineering Document | Part F - Transportation & Installation | GEN |  |  | TNI | Transportation and Installation | RFQ | Request for Quotation | 0 | Submitted | IFA | Issued for Approval |  | 25-Aug-2026 15:58:20 | kjb@coes.cn | 25-Aug-2026 16:18:38 | Jumpol Sudjitjul | 01-Sep-2026 | 28-Aug-2026 07:33:00 | Sukit Nualchanchai | 03-Sep-2026 | 09-Sep-2026 15:48:09 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 11-Sep-2026 22:38:02 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 12-Sep-2026 23:29:00 | 12-Sep-2026 16:56:26 | 0 |  |  | Approver | Locate
AO-002148 | MM-ZTK-1F-GEN-TNI-RFQ-8002 | RFQ FOR PILE MONITORING SERVICE |  | C1 | Project Document | Engineering Document | Part F - Transportation & Installation | GEN |  |  | TNI | Transportation and Installation | RFQ | Request for Quotation | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:11:47 | kjb@coes.cn | 18-Sep-2026 17:07:54 | Jumpol Sudjitjul | 28-Sep-2026 | 18-Sep-2026 22:11:19 | Sukit Nualchanchai | 30-Sep-2026 | 28-Sep-2026 16:48:49 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 28-Sep-2026 22:49:56 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 29-Sep-2026 14:22:02 | 29-Sep-2026 08:33:48 | 0 |  |  | Approver | Locate
AO-001422 | MM-ZTK-1F-GEN-TNI-RFQ-8003 | RFQ FOR PROVISION OF MARINE WARRANTY SURVEYOR SERVICE FOR STRUCTURE INSTALLATION - WP-1 (T&I) |  | A1 | Project Document | Engineering Document | Part F - Transportation & Installation | GEN |  |  | TNI | Transportation and Installation | RFQ | Request for Quotation | 0 | Submitted | IFR | Issued for Review |  | 05-Aug-2026 15:17:49 | kjb@coes.cn | 05-Aug-2026 15:23:42 | Jumpol Sudjitjul | 13-Aug-2026 |  | Sukit Nualchanchai | 17-Aug-2026 | 10-Aug-2026 10:51:45 | Prin Jitatisil | 18-Aug-2026 | 10-Aug-2026 13:31:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Aug-2026 | 10-Aug-2026 14:16:26 | 10-Aug-2026 08:18:05 | 0 |  |  | Approver | Locate
AO-001707 | MM-ZTK-1F-GEN-TNI-RFQ-8003 | RFQ FOR PROVISION OF MARINE WARRANTY SURVEYOR SERVICE FOR STRUCTURE INSTALLATION - WP-1 (T&I) |  | B1 | Project Document | Engineering Document | Part F - Transportation & Installation | GEN |  |  | TNI | Transportation and Installation | RFQ | Request for Quotation | 0 | Submitted | IFA | Issued for Approval |  | 25-Aug-2026 15:58:52 | kjb@coes.cn | 25-Aug-2026 16:19:16 | Jumpol Sudjitjul | 01-Sep-2026 | 02-Sep-2026 10:33:26 | Sukit Nualchanchai | 03-Sep-2026 | 09-Sep-2026 15:50:27 | Prin Jitatisil | 04-Sep-2026 | 09-Sep-2026 21:50:50 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 10-Sep-2026 09:11:16 | 10-Sep-2026 02:34:37 | 0 |  |  | Approver | Locate
AO-002084 | MM-ZTK-1F-GEN-TNI-RFQ-8003 | RFQ FOR PROVISION OF MARINE WARRANTY SURVEYOR SERVICE FOR STRUCTURE INSTALLATION - WP-1 (T&I) |  | C1 | Project Document | Engineering Document | Part F - Transportation & Installation | GEN |  |  | TNI | Transportation and Installation | RFQ | Request for Quotation | 0 | Submitted | AFC | Approved for Construction |  | 15-Sep-2026 16:13:52 | kjb@coes.cn | 15-Sep-2026 17:15:05 | Jumpol Sudjitjul | 23-Sep-2026 | 21-Sep-2026 09:30:15 | Sukit Nualchanchai | 25-Sep-2026 | 28-Sep-2026 16:50:28 | Prin Jitatisil | 28-Sep-2026 | 29-Sep-2026 09:13:13 | APPR | Approved | Jumpol Sudjitjul | 29-Sep-2026 | 29-Sep-2026 11:04:51 | 29-Sep-2026 04:24:32 | 0 |  |  | Approver | Locate
AO-001420 | MM-ZTK-1F-GEN-TNI-RFQ-8004 | RFQ FOR PROVISION OF CERTIFYING AUTHORITY SERVICES FOR STRUCTURE INSTALLATION - WP-1 (T&I) |  | A1 | Project Document | Engineering Document | Part F - Transportation & Installation | GEN |  |  | TNI | Transportation and Installation | RFQ | Request for Quotation | 0 | Submitted | IFR | Issued for Review |  | 05-Aug-2026 12:00:59 | kjb@coes.cn | 05-Aug-2026 14:24:30 | Jumpol Sudjitjul | 13-Aug-2026 |  | Sukit Nualchanchai | 17-Aug-2026 | 07-Aug-2026 15:56:32 | Prin Jitatisil | 18-Aug-2026 | 10-Aug-2026 13:31:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Aug-2026 | 10-Aug-2026 14:16:21 | 10-Aug-2026 07:50:10 | 0 |  |  | Approver | Locate
AO-001708 | MM-ZTK-1F-GEN-TNI-RFQ-8004 | RFQ FOR PROVISION OF CERTIFYING AUTHORITY SERVICES FOR STRUCTURE INSTALLATION - WP-1 (T&I) |  | B1 | Project Document | Engineering Document | Part F - Transportation & Installation | GEN |  |  | TNI | Transportation and Installation | RFQ | Request for Quotation | 0 | Submitted | IFA | Issued for Approval |  | 25-Aug-2026 15:59:21 | kjb@coes.cn | 25-Aug-2026 16:19:38 | Jumpol Sudjitjul | 01-Sep-2026 | 02-Sep-2026 10:30:44 | Sukit Nualchanchai | 03-Sep-2026 | 09-Sep-2026 15:53:40 | Prin Jitatisil | 04-Sep-2026 | 09-Sep-2026 21:51:04 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 10-Sep-2026 09:10:46 | 10-Sep-2026 02:33:15 | 0 |  |  | Approver | Locate
AO-002085 | MM-ZTK-1F-GEN-TNI-RFQ-8004 | RFQ FOR PROVISION OF CERTIFYING AUTHORITY SERVICES FOR STRUCTURE INSTALLATION - WP-1 (T&I) |  | C1 | Project Document | Engineering Document | Part F - Transportation & Installation | GEN |  |  | TNI | Transportation and Installation | RFQ | Request for Quotation | 0 | Submitted | AFC | Approved for Construction |  | 15-Sep-2026 16:14:18 | kjb@coes.cn | 15-Sep-2026 17:15:24 | Jumpol Sudjitjul | 23-Sep-2026 | 30-Sep-2026 15:46:41 | Sukit Nualchanchai | 25-Sep-2026 | 06-Oct-2026 09:59:18 | Prin Jitatisil | 28-Sep-2026 | 06-Oct-2026 11:33:06 | APPR | Approved | Jumpol Sudjitjul | 29-Sep-2026 | 06-Oct-2026 13:50:41 | 06-Oct-2026 07:12:42 | 0 |  |  | Approver | Locate
AO-001358 | MM-ZTK-1F-GEN-TNI-RFQ-8005 | RFQ FOR PROVISION OF NDT SERVICE FOR STRUCTURE INSTALLATION - WP-1 (T&I) |  | A1 | Project Document | Engineering Document | Part F - Transportation & Installation | GEN |  |  | TNI | Transportation and Installation | RFQ | Request for Quotation | 0 | Submitted | IFR | Issued for Review |  | 31-Jul-2026 16:26:02 | kjb@coes.cn | 31-Jul-2026 21:38:31 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sukit Nualchanchai | 13-Aug-2026 | 04-Aug-2026 14:17:16 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 22:55:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 14:10:04 | 17-Aug-2026 08:36:49 | 0 |  |  | Approver | Locate
AO-001704 | MM-ZTK-1F-GEN-TNI-RFQ-8005 | RFQ FOR PROVISION OF NDT SERVICE FOR STRUCTURE INSTALLATION - WP-1 (T&I) |  | B1 | Project Document | Engineering Document | Part F - Transportation & Installation | GEN |  |  | TNI | Transportation and Installation | RFQ | Request for Quotation | 0 | Submitted | IFA | Issued for Approval |  | 25-Aug-2026 15:59:54 | kjb@coes.cn | 25-Aug-2026 16:19:56 | Jumpol Sudjitjul | 01-Sep-2026 | 26-Aug-2026 08:02:36 | Sukit Nualchanchai | 03-Sep-2026 | 09-Sep-2026 16:09:02 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 11-Sep-2026 22:40:01 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 13-Sep-2026 07:58:16 | 13-Sep-2026 01:19:19 | 0 |  |  | Approver | Locate
AO-002147 | MM-ZTK-1F-GEN-TNI-RFQ-8005 | RFQ FOR PROVISION OF NDT SERVICE FOR STRUCTURE INSTALLATION - WP-1 (T&I) |  | C1 | Project Document | Engineering Document | Part F - Transportation & Installation | GEN |  |  | TNI | Transportation and Installation | RFQ | Request for Quotation | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:12:20 | kjb@coes.cn | 18-Sep-2026 17:08:11 | Jumpol Sudjitjul | 28-Sep-2026 | 18-Sep-2026 21:47:37 | Sukit Nualchanchai | 30-Sep-2026 | 06-Oct-2026 09:59:43 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 11-Oct-2026 00:30:06 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 11-Oct-2026 10:00:01 | 11-Oct-2026 03:44:42 | 0 |  |  | Approver | Locate
AO-000216 | MM-ZTK-1F-IP20-PLR-DWG-9001 | IP20 PIPELINE ROUTE DRAWING FROM ZWP20 TO ZWP16 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 23-Apr-2026 17:37:44 | 26002z1fdcc@thoresen-jutal.com | 23-Apr-2026 17:47:17 | Jumpol Sudjitjul | 05-May-2026 |  | Akkarapat Suntornsuttiwat | 07-May-2026 | 05-May-2026 08:49:25 | Pornlert Wanaphattharaphan | 08-May-2026 | 09-May-2026 00:23:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 09-May-2026 08:18:36 | 09-May-2026 09:15:13 | 0 |  |  | Approver | Locate
AO-000716 | MM-ZTK-1F-IP20-PLR-DWG-9001 | IP20 PIPELINE ROUTE DRAWING FROM ZWP20 TO ZWP16 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 08-Jun-2026 18:38:08 | 26002z1fdcc@thoresen-jutal.com | 09-Jun-2026 08:58:33 | Jumpol Sudjitjul | 16-Jun-2026 |  | Akkarapat Suntornsuttiwat | 18-Jun-2026 | 15-Jun-2026 09:33:22 | Pornlert Wanaphattharaphan | 19-Jun-2026 | 20-Jun-2026 22:45:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jun-2026 | 22-Jun-2026 12:57:40 | 22-Jun-2026 06:50:23 | 0 |  |  | Approver | Locate
AO-001031 | MM-ZTK-1F-IP20-PLR-DWG-9001 | IP20 PIPELINE ROUTE DRAWING FROM ZWP20 TO ZWP16 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Jul-2026 18:44:37 | 26002z1fdcc@thoresen-jutal.com | 07-Jul-2026 20:51:06 | Jumpol Sudjitjul | 15-Jul-2026 |  | Akkarapat Suntornsuttiwat | 17-Jul-2026 | 08-Jul-2026 14:24:27 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 20-Jul-2026 00:47:59 | APPR | Approved | Jumpol Sudjitjul | 21-Jul-2026 | 20-Jul-2026 09:07:38 | 20-Jul-2026 02:55:12 | 0 |  |  | Approver | Locate
AO-001559 | MM-ZTK-1F-IP20-PLR-DWG-9002 | IP20 PIPELINE ALIGNMENT SHEETS: ZWP20 TO ZWP16 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 17-Aug-2026 14:42:01 | 26002z1fdcc@thoresen-jutal.com | 17-Aug-2026 15:36:17 | Jumpol Sudjitjul | 24-Aug-2026 |  | Akkarapat Suntornsuttiwat | 26-Aug-2026 | 18-Aug-2026 15:46:03 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:08:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 19:47:26 | 24-Aug-2026 14:06:06 | 0 |  |  | Approver | Locate
AO-001798 | MM-ZTK-1F-IP20-PLR-DWG-9002 | IP20 PIPELINE ALIGNMENT SHEETS: ZWP20 TO ZWP16 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 14:01:43 | 26002z1fdcc@thoresen-jutal.com | 31-Aug-2026 14:27:35 | Jumpol Sudjitjul | 07-Sep-2026 |  | Akkarapat Suntornsuttiwat | 09-Sep-2026 | 03-Sep-2026 11:24:27 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 07-Sep-2026 00:22:59 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 07-Sep-2026 11:53:02 | 07-Sep-2026 05:35:16 | 0 |  |  | Approver | Locate
AO-002067 | MM-ZTK-1F-IP20-PLR-DWG-9002 | IP20 PIPELINE ALIGNMENT SHEETS: ZWP20 TO ZWP16 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 20:09:27 | 26002z1fdcc@thoresen-jutal.com | 15-Sep-2026 15:55:57 | Jumpol Sudjitjul | 22-Sep-2026 |  | Akkarapat Suntornsuttiwat | 24-Sep-2026 | 16-Sep-2026 11:05:30 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 19-Sep-2026 21:29:37 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 20-Sep-2026 17:49:25 | 20-Sep-2026 11:12:40 | 0 |  |  | Approver | Locate
AO-001658 | MM-ZTK-1F-IP20-PLR-DWG-9003 | IP20 PIPELINE SCHEMATIC DIAGRAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 11:04:20 | 26002z1fdcc@thoresen-jutal.com | 25-Aug-2026 14:32:10 | Jumpol Sudjitjul | 01-Sep-2026 |  | Akkarapat Suntornsuttiwat | 03-Sep-2026 | 27-Aug-2026 15:47:21 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 23:13:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 15:54:32 | 31-Aug-2026 10:26:32 | 0 |  |  | Approver | Locate
AO-002016 | MM-ZTK-1F-IP20-PLR-DWG-9003 | IP20 PIPELINE SCHEMATIC DIAGRAM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 11-Sep-2026 20:59:24 | 26002z1fdcc@thoresen-jutal.com | 11-Sep-2026 21:07:21 | Jumpol Sudjitjul | 21-Sep-2026 |  | Akkarapat Suntornsuttiwat | 23-Sep-2026 | 14-Sep-2026 10:50:44 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 19-Sep-2026 21:27:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Sep-2026 | 20-Sep-2026 17:50:08 | 20-Sep-2026 11:38:20 | 0 |  |  | Approver | Locate
AO-002267 | MM-ZTK-1F-IP20-PLR-DWG-9003 | IP20 PIPELINE SCHEMATIC DIAGRAM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 25-Sep-2026 16:15:19 | 26002z1fdcc@thoresen-jutal.com | 25-Sep-2026 16:21:54 | Jumpol Sudjitjul | 02-Oct-2026 |  | Akkarapat Suntornsuttiwat | 06-Oct-2026 | 28-Sep-2026 15:26:38 | Pornlert Wanaphattharaphan | 07-Oct-2026 | 28-Sep-2026 23:00:32 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 29-Sep-2026 14:21:46 | 29-Sep-2026 08:32:26 | 0 |  |  | Approver | Locate
AO-000537 | MM-ZTK-1F-IP20-PLR-DWG-9004 | IP20 PIPELINE PLATFORM APPROACH AT ZWP20 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 09:40:12 | 26002z1fdcc@thoresen-jutal.com | 21-May-2026 14:10:54 | Jumpol Sudjitjul | 28-May-2026 |  | Akkarapat Suntornsuttiwat | 02-Jun-2026 | 25-May-2026 14:23:49 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 09-Jun-2026 00:39:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 09-Jun-2026 07:48:10 | 09-Jun-2026 01:15:02 | 0 |  |  | Approver | Locate
AO-000915 | MM-ZTK-1F-IP20-PLR-DWG-9004 | IP20 PIPELINE PLATFORM APPROACH AT ZWP20 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Jun-2026 20:34:21 | 26002z1fdcc@thoresen-jutal.com | 27-Jun-2026 18:50:01 | Jumpol Sudjitjul | 06-Jul-2026 |  | Akkarapat Suntornsuttiwat | 08-Jul-2026 | 29-Jun-2026 15:06:01 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 02-Jul-2026 00:33:26 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 10-Jul-2026 | 02-Jul-2026 10:11:40 | 02-Jul-2026 03:54:39 | 0 |  |  | Approver | Locate
AO-001058 | MM-ZTK-1F-IP20-PLR-DWG-9004 | IP20 PIPELINE PLATFORM APPROACH AT ZWP20 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 12:59:32 | 26002z1fdcc@thoresen-jutal.com | 10-Jul-2026 13:03:23 | Jumpol Sudjitjul | 17-Jul-2026 |  | Akkarapat Suntornsuttiwat | 21-Jul-2026 | 10-Jul-2026 15:13:22 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 11-Jul-2026 12:32:53 | APPR | Approved | Jumpol Sudjitjul | 23-Jul-2026 | 12-Jul-2026 11:38:36 | 12-Jul-2026 05:42:42 | 0 |  |  | Approver | Locate
AO-000538 | MM-ZTK-1F-IP20-PLR-DWG-9005 | IP20 PIPELINE PLATFORM APPROACH AT ZWP16 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 09:40:52 | 26002z1fdcc@thoresen-jutal.com | 21-May-2026 14:11:32 | Jumpol Sudjitjul | 28-May-2026 |  | Akkarapat Suntornsuttiwat | 02-Jun-2026 | 25-May-2026 14:25:08 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 09-Jun-2026 00:41:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 09-Jun-2026 07:48:40 | 09-Jun-2026 01:16:23 | 0 |  |  | Approver | Locate
AO-000915 | MM-ZTK-1F-IP20-PLR-DWG-9005 | IP20 PIPELINE PLATFORM APPROACH AT ZWP16 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Jun-2026 20:34:45 | 26002z1fdcc@thoresen-jutal.com | 27-Jun-2026 18:50:02 | Jumpol Sudjitjul | 06-Jul-2026 |  | Akkarapat Suntornsuttiwat | 08-Jul-2026 | 29-Jun-2026 15:07:05 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 02-Jul-2026 00:39:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 02-Jul-2026 10:09:59 | 02-Jul-2026 03:48:21 | 0 |  |  | Approver | Locate
AO-001058 | MM-ZTK-1F-IP20-PLR-DWG-9005 | IP20 PIPELINE PLATFORM APPROACH AT ZWP16 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 13:00:01 | 26002z1fdcc@thoresen-jutal.com | 10-Jul-2026 13:03:23 | Jumpol Sudjitjul | 17-Jul-2026 |  | Akkarapat Suntornsuttiwat | 21-Jul-2026 | 10-Jul-2026 15:16:13 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 11-Jul-2026 12:29:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 12-Jul-2026 11:41:00 | 12-Jul-2026 05:43:57 | 0 |  |  | Approver | Locate
AO-001264 | MM-ZTK-1F-IP20-PLR-DWG-9005 | IP20 PIPELINE PLATFORM APPROACH AT ZWP16 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 14:11:26 | 26002z1fdcc@thoresen-jutal.com | 26-Jul-2026 22:01:54 | Jumpol Sudjitjul | 05-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 27-Jul-2026 16:01:48 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 29-Jul-2026 09:06:44 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 30-Jul-2026 09:40:16 | 30-Jul-2026 03:46:58 | 0 |  |  | Approver | Locate
AO-000523 | MM-ZTK-1F-IP20-PLR-GA-9001 | RISER GA DRAWING AT ZWP20 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 12:48:09 | 26002z1fdcc@thoresen-jutal.com | 20-May-2026 16:04:36 | Jumpol Sudjitjul | 27-May-2026 |  | Akkarapat Suntornsuttiwat | 29-May-2026 | 25-May-2026 09:16:43 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 09-Jun-2026 00:31:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Jun-2026 | 09-Jun-2026 07:49:15 | 09-Jun-2026 08:17:43 | 0 |  |  | Approver | Locate
AO-001032 | MM-ZTK-1F-IP20-PLR-GA-9001 | RISER GA DRAWING AT ZWP20 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFA | Issued for Approval |  | 07-Jul-2026 21:21:12 | 26002z1fdcc@thoresen-jutal.com | 08-Jul-2026 14:39:59 | Jumpol Sudjitjul | 15-Jul-2026 |  | Akkarapat Suntornsuttiwat | 17-Jul-2026 | 09-Jul-2026 15:02:01 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 20-Jul-2026 00:53:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Jul-2026 | 20-Jul-2026 09:08:08 | 20-Jul-2026 02:57:43 | 0 |  |  | Approver | Locate
AO-001375 | MM-ZTK-1F-IP20-PLR-GA-9001 | RISER GA DRAWING AT ZWP20 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 11:01:12 | 26002z1fdcc@thoresen-jutal.com | 03-Aug-2026 14:12:47 | Jumpol Sudjitjul | 10-Aug-2026 |  | Akkarapat Suntornsuttiwat | 13-Aug-2026 | 04-Aug-2026 10:20:06 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 10-Aug-2026 01:30:00 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 17:46:26 | 10-Aug-2026 10:58:08 | 0 |  |  | Approver | Locate
AO-002463 | MM-ZTK-1F-IP20-PLR-GA-9001 | RISER GA DRAWING AT ZWP20 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | AFC | Approved for Construction |  | 09-Oct-2026 16:45:51 | 26002z1fdcc@thoresen-jutal.com | 09-Oct-2026 17:32:21 | Jumpol Sudjitjul | 20-Oct-2026 |  | Akkarapat Suntornsuttiwat | 22-Oct-2026 | 12-Oct-2026 10:00:40 | Pornlert Wanaphattharaphan | 26-Oct-2026 | 13-Oct-2026 14:45:24 | APPR | Approved | Jumpol Sudjitjul | 27-Oct-2026 | 14-Oct-2026 16:40:32 | 14-Oct-2026 10:26:39 | 0 |  |  | Approver | Locate
AO-001266 | MM-ZTK-1F-IP20-PLR-GA-9002 | IP20 TIE-IN SPOOL GA DRAWING AT ZWP20 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 17:07:15 | 26002z1fdcc@thoresen-jutal.com | 26-Jul-2026 23:48:18 | Jumpol Sudjitjul | 05-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 30-Jul-2026 15:05:19 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 05-Aug-2026 23:57:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 06-Aug-2026 09:36:51 | 06-Aug-2026 03:35:52 | 0 |  |  | Approver | Locate
AO-001616 | MM-ZTK-1F-IP20-PLR-GA-9002 | IP20 TIE-IN SPOOL GA DRAWING AT ZWP20 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 09:35:12 | 26002z1fdcc@thoresen-jutal.com | 20-Aug-2026 09:41:57 | Jumpol Sudjitjul | 27-Aug-2026 |  | Akkarapat Suntornsuttiwat | 31-Aug-2026 | 20-Aug-2026 11:13:11 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 22-Aug-2026 23:25:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Sep-2026 | 24-Aug-2026 19:47:05 | 24-Aug-2026 14:19:13 | 0 |  |  | Approver | Locate
AO-001764 | MM-ZTK-1F-IP20-PLR-GA-9002 | IP20 TIE-IN SPOOL GA DRAWING AT ZWP20 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | AFC | Approved for Construction |  | 29-Aug-2026 14:05:48 | 26002z1fdcc@thoresen-jutal.com | 29-Aug-2026 14:14:21 | Jumpol Sudjitjul | 04-Sep-2026 | 01-Sep-2026 10:29:40 | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 08:51:50 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 00:24:41 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 13:07:10 | 07-Sep-2026 06:28:48 | 0 |  |  | Approver | Locate
AO-001266 | MM-ZTK-1F-IP20-PLR-GA-9003 | IP20 TIE-IN SPOOL GA DRAWING AT ZWP16 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 17:07:39 | 26002z1fdcc@thoresen-jutal.com | 26-Jul-2026 23:48:22 | Jumpol Sudjitjul | 05-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 30-Jul-2026 15:06:11 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 06-Aug-2026 00:02:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 06-Aug-2026 09:37:24 | 06-Aug-2026 03:37:07 | 0 |  |  | Approver | Locate
AO-001616 | MM-ZTK-1F-IP20-PLR-GA-9003 | IP20 TIE-IN SPOOL GA DRAWING AT ZWP16 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 09:36:16 | 26002z1fdcc@thoresen-jutal.com | 20-Aug-2026 09:41:57 | Jumpol Sudjitjul | 27-Aug-2026 |  | Akkarapat Suntornsuttiwat | 31-Aug-2026 | 20-Aug-2026 11:13:41 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 22-Aug-2026 23:24:23 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 24-Aug-2026 19:46:38 | 24-Aug-2026 14:04:40 | 0 |  |  | Approver | Locate
AO-001764 | MM-ZTK-1F-IP20-PLR-GA-9003 | IP20 TIE-IN SPOOL GA DRAWING AT ZWP16 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | AFC | Approved for Construction |  | 29-Aug-2026 14:06:15 | 26002z1fdcc@thoresen-jutal.com | 29-Aug-2026 14:14:21 | Jumpol Sudjitjul | 04-Sep-2026 | 01-Sep-2026 08:54:51 | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 08:52:14 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 00:25:08 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 13:09:23 | 07-Sep-2026 06:30:03 | 0 |  |  | Approver | Locate
AO-000520 | MM-ZTK-1F-IP20-PLR-ISO-9001 | IP20 RISER ISOMETRIC AT ZWP20 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 11:32:45 | 26002z1fdcc@thoresen-jutal.com | 20-May-2026 15:54:58 | Jumpol Sudjitjul | 27-May-2026 |  | Akkarapat Suntornsuttiwat | 29-May-2026 | 25-May-2026 09:25:37 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 09-Jun-2026 00:38:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Jun-2026 | 09-Jun-2026 07:49:43 | 09-Jun-2026 01:26:39 | 0 |  |  | Approver | Locate
AO-001033 | MM-ZTK-1F-IP20-PLR-ISO-9001 | IP20 RISER ISOMETRIC AT ZWP20 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Jul-2026 21:22:06 | 26002z1fdcc@thoresen-jutal.com | 08-Jul-2026 14:41:59 | Jumpol Sudjitjul | 15-Jul-2026 |  | Akkarapat Suntornsuttiwat | 17-Jul-2026 | 09-Jul-2026 16:02:08 | Pornlert Wanaphattharaphan | 20-Jul-2026 | 20-Jul-2026 00:55:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Jul-2026 | 20-Jul-2026 09:08:06 | 20-Jul-2026 02:56:27 | 0 |  |  | Approver | Locate
AO-001322 | MM-ZTK-1F-IP20-PLR-ISO-9001 | IP20 RISER ISOMETRIC AT ZWP20 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Jul-2026 09:14:32 | 26002z1fdcc@thoresen-jutal.com | 28-Jul-2026 20:30:57 | Jumpol Sudjitjul | 06-Aug-2026 |  | Akkarapat Suntornsuttiwat | 10-Aug-2026 | 30-Jul-2026 15:31:40 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 12-Aug-2026 09:26:27 | APPR | Approved | Jumpol Sudjitjul | 13-Aug-2026 | 13-Aug-2026 11:28:08 | 13-Aug-2026 05:26:15 | 0 |  |  | Approver | Locate
AO-000996 | MM-ZTK-1F-IP20-PLR-ISO-9002 | IP20 TIE-IN SPOOL ISOMETRIC AT ZWP20 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 13:25:15 | 26002z1fdcc@thoresen-jutal.com | 03-Jul-2026 14:15:38 | Jumpol Sudjitjul | 10-Jul-2026 |  | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 06-Jul-2026 14:16:34 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 22:27:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 10:59:30 | 15-Jul-2026 04:16:30 | 0 |  |  | Approver | Locate
AO-001560 | MM-ZTK-1F-IP20-PLR-ISO-9002 | IP20 TIE-IN SPOOL ISOMETRIC AT ZWP20 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:42:33 | 26002z1fdcc@thoresen-jutal.com | 17-Aug-2026 15:34:14 | Jumpol Sudjitjul | 24-Aug-2026 |  | Akkarapat Suntornsuttiwat | 26-Aug-2026 | 17-Aug-2026 16:25:55 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 17:49:02 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 19:45:34 | 24-Aug-2026 14:03:21 | 0 |  |  | Approver | Locate
AO-001763 | MM-ZTK-1F-IP20-PLR-ISO-9002 | IP20 TIE-IN SPOOL ISOMETRIC AT ZWP20 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 18:10:51 | 26002z1fdcc@thoresen-jutal.com | 29-Aug-2026 13:27:40 | Jumpol Sudjitjul | 04-Sep-2026 | 31-Aug-2026 16:31:28 | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 09:13:29 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 00:25:32 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 13:10:05 | 07-Sep-2026 06:24:55 | 0 |  |  | Approver | Locate
AO-000996 | MM-ZTK-1F-IP20-PLR-ISO-9003 | IP20 TIE-IN SPOOL ISOMETRIC AT ZWP16 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 13:26:45 | 26002z1fdcc@thoresen-jutal.com | 03-Jul-2026 14:15:28 | Jumpol Sudjitjul | 10-Jul-2026 |  | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 06-Jul-2026 14:17:31 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 20:57:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 11:02:58 | 15-Jul-2026 04:57:13 | 0 |  |  | Approver | Locate
AO-001560 | MM-ZTK-1F-IP20-PLR-ISO-9003 | IP20 TIE-IN SPOOL ISOMETRIC AT ZWP16 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:43:12 | 26002z1fdcc@thoresen-jutal.com | 17-Aug-2026 15:34:21 | Jumpol Sudjitjul | 24-Aug-2026 |  | Akkarapat Suntornsuttiwat | 26-Aug-2026 | 17-Aug-2026 16:26:29 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 17:52:57 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 19:45:01 | 24-Aug-2026 14:02:04 | 0 |  |  | Approver | Locate
AO-001763 | MM-ZTK-1F-IP20-PLR-ISO-9003 | IP20 TIE-IN SPOOL ISOMETRIC AT ZWP16 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 18:11:18 | 26002z1fdcc@thoresen-jutal.com | 29-Aug-2026 13:27:41 | Jumpol Sudjitjul | 04-Sep-2026 | 31-Aug-2026 16:22:32 | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 09:15:17 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 00:26:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 13:11:41 | 07-Sep-2026 06:26:17 | 0 |  |  | Approver | Locate
AO-002016 | MM-ZTK-1F-IP20-PLR-ISO-9003 | IP20 TIE-IN SPOOL ISOMETRIC AT ZWP16 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | IP20 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 20:59:53 | 26002z1fdcc@thoresen-jutal.com | 11-Sep-2026 21:08:56 | Jumpol Sudjitjul | 21-Sep-2026 |  | Akkarapat Suntornsuttiwat | 23-Sep-2026 | 14-Sep-2026 10:55:41 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 19-Sep-2026 21:24:48 | APPR | Approved | Jumpol Sudjitjul | 25-Sep-2026 | 20-Sep-2026 17:51:08 | 20-Sep-2026 11:39:27 | 0 |  |  | Approver | Locate
AO-000214 | MM-ZTK-1F-IP20-PLR-RPT-9001 | IP20 PIPELINE ROUTING STUDY AND DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 23-Apr-2026 15:02:49 | 26002z1fdcc@thoresen-jutal.com | 23-Apr-2026 15:10:57 | Jumpol Sudjitjul | 30-Apr-2026 |  | Akkarapat Suntornsuttiwat | 06-May-2026 | 05-May-2026 08:51:08 | Pornlert Wanaphattharaphan | 07-May-2026 | 08-May-2026 23:15:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-May-2026 | 09-May-2026 08:18:04 | 09-May-2026 02:21:04 | 0 |  |  | Approver | Locate
AO-000892 | MM-ZTK-1F-IP20-PLR-RPT-9001 | IP20 PIPELINE ROUTING STUDY AND DESIGN |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 14:26:38 | 26002z1fdcc@thoresen-jutal.com | 25-Jun-2026 15:13:59 | Jumpol Sudjitjul | 02-Jul-2026 |  | Akkarapat Suntornsuttiwat | 06-Jul-2026 | 26-Jun-2026 16:03:41 | Pornlert Wanaphattharaphan | 07-Jul-2026 | 29-Jun-2026 01:24:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jul-2026 | 30-Jun-2026 09:42:32 | 30-Jun-2026 03:26:33 | 0 |  |  | Approver | Locate
AO-001147 | MM-ZTK-1F-IP20-PLR-RPT-9001 | IP20 PIPELINE ROUTING STUDY AND DESIGN |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 21:15:07 | 26002z1fdcc@thoresen-jutal.com | 17-Jul-2026 10:33:28 | Jumpol Sudjitjul | 24-Jul-2026 |  | Akkarapat Suntornsuttiwat | 30-Jul-2026 | 17-Jul-2026 15:46:28 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 19-Jul-2026 23:40:04 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 20-Jul-2026 09:07:34 | 20-Jul-2026 02:54:02 | 0 |  |  | Approver | Locate
AO-000904 | MM-ZTK-1F-IP20-PLR-RPT-9002 | IP20 PIPELINE ON-BOTTOM ROUGHNESS AND IN-PLACE STRESS ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 16:40:25 | 26002z1fdcc@thoresen-jutal.com | 26-Jun-2026 19:52:30 | Jumpol Sudjitjul | 06-Jul-2026 |  | Akkarapat Suntornsuttiwat | 08-Jul-2026 | 06-Jul-2026 09:50:39 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 11-Jul-2026 13:58:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 12-Jul-2026 11:31:50 | 12-Jul-2026 05:23:02 | 0 |  |  | Approver | Locate
AO-001431 | MM-ZTK-1F-IP20-PLR-RPT-9002 | IP20 PIPELINE ON-BOTTOM ROUGHNESS AND IN-PLACE STRESS ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 06-Aug-2026 12:10:16 | 26002z1fdcc@thoresen-jutal.com | 06-Aug-2026 14:44:51 | Jumpol Sudjitjul | 14-Aug-2026 |  | Akkarapat Suntornsuttiwat | 18-Aug-2026 | 07-Aug-2026 14:48:14 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 20-Aug-2026 22:58:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 21-Aug-2026 10:18:56 | 21-Aug-2026 04:16:38 | 0 |  |  | Approver | Locate
AO-001764 | MM-ZTK-1F-IP20-PLR-RPT-9002 | IP20 PIPELINE ON-BOTTOM ROUGHNESS AND IN-PLACE STRESS ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 29-Aug-2026 14:06:46 | 26002z1fdcc@thoresen-jutal.com | 29-Aug-2026 14:15:22 | Jumpol Sudjitjul | 04-Sep-2026 |  | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 15:36:56 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 00:26:57 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 13:13:08 | 07-Sep-2026 06:31:31 | 0 |  |  | Approver | Locate
AO-002009 | MM-ZTK-1F-IP20-PLR-RPT-9002 | IP20 PIPELINE ON-BOTTOM ROUGHNESS AND IN-PLACE STRESS ANALYSIS |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 21:00:28 | 26002z1fdcc@thoresen-jutal.com | 11-Sep-2026 21:05:55 | Jumpol Sudjitjul | 21-Sep-2026 |  | Akkarapat Suntornsuttiwat | 23-Sep-2026 | 14-Sep-2026 11:04:35 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 19-Sep-2026 21:22:23 | APPR | Approved | Jumpol Sudjitjul | 25-Sep-2026 | 20-Sep-2026 17:52:19 | 20-Sep-2026 11:40:41 | 0 |  |  | Approver | Locate
AO-001076 | MM-ZTK-1F-IP20-PLR-RPT-9003 | IP20 PIPELINE LATERAL BUCLKING ANALYSIS LEVEL 1 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 12-Jul-2026 11:42:19 | 26002z1fdcc@thoresen-jutal.com | 13-Jul-2026 09:26:23 | Jumpol Sudjitjul | 20-Jul-2026 |  | Akkarapat Suntornsuttiwat | 22-Jul-2026 | 15-Jul-2026 11:23:49 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 20-Jul-2026 02:41:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 20-Jul-2026 09:07:03 | 20-Jul-2026 03:37:36 | 0 |  |  | Approver | Locate
AO-001555 | MM-ZTK-1F-IP20-PLR-RPT-9003 | IP20 PIPELINE LATERAL BUCLKING ANALYSIS LEVEL 1 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:43:56 | 26002z1fdcc@thoresen-jutal.com | 17-Aug-2026 15:38:50 | Jumpol Sudjitjul | 24-Aug-2026 |  | Akkarapat Suntornsuttiwat | 26-Aug-2026 | 20-Aug-2026 09:50:34 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:14:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 19:44:12 | 24-Aug-2026 14:00:43 | 0 |  |  | Approver | Locate
AO-001816 | MM-ZTK-1F-IP20-PLR-RPT-9003 | IP20 PIPELINE LATERAL BUCLKING ANALYSIS LEVEL 1 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 18:24:13 | 26002z1fdcc@thoresen-jutal.com | 03-Sep-2026 11:14:10 | Jumpol Sudjitjul | 10-Sep-2026 |  | Akkarapat Suntornsuttiwat | 14-Sep-2026 | 03-Sep-2026 13:34:45 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 07-Sep-2026 00:27:28 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 07-Sep-2026 13:16:50 | 07-Sep-2026 06:32:43 | 0 |  |  | Approver | Locate
AO-001578 | MM-ZTK-1F-IP20-PLR-RPT-9004 | IP20 PIPELINE WALKING ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 17-Aug-2026 18:03:50 | 26002z1fdcc@thoresen-jutal.com | 18-Aug-2026 08:58:40 | Jumpol Sudjitjul | 25-Aug-2026 |  | Akkarapat Suntornsuttiwat | 27-Aug-2026 | 20-Aug-2026 14:46:07 | Pornlert Wanaphattharaphan | 28-Aug-2026 | 23-Aug-2026 23:33:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Aug-2026 | 24-Aug-2026 19:43:38 | 24-Aug-2026 13:40:42 | 0 |  |  | Approver | Locate
AO-001938 | MM-ZTK-1F-IP20-PLR-RPT-9004 | IP20 PIPELINE WALKING ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 08-Sep-2026 18:34:15 | 26002z1fdcc@thoresen-jutal.com | 09-Sep-2026 08:50:30 | Jumpol Sudjitjul | 16-Sep-2026 |  | Akkarapat Suntornsuttiwat | 18-Sep-2026 | 09-Sep-2026 11:21:37 | Pornlert Wanaphattharaphan | 21-Sep-2026 | 13-Sep-2026 17:14:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Sep-2026 | 13-Sep-2026 23:13:24 | 13-Sep-2026 16:41:16 | 0 |  |  | Approver | Locate
AO-002154 | MM-ZTK-1F-IP20-PLR-RPT-9004 | IP20 PIPELINE WALKING ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 17:28:29 | 26002z1fdcc@thoresen-jutal.com | 18-Sep-2026 17:48:25 | Jumpol Sudjitjul | 28-Sep-2026 |  | Akkarapat Suntornsuttiwat | 30-Sep-2026 | 23-Sep-2026 14:53:50 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 26-Sep-2026 05:46:51 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 26-Sep-2026 14:21:30 | 26-Sep-2026 07:58:34 | 0 |  |  | Approver | Locate
AO-001375 | MM-ZTK-1F-IP20-PLR-RPT-9005 | IP20 AT ZWP20 : RISER AND TIE-IN SPOOL STRESS ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 11:01:38 | 26002z1fdcc@thoresen-jutal.com | 03-Aug-2026 14:08:35 | Jumpol Sudjitjul | 10-Aug-2026 |  | Akkarapat Suntornsuttiwat | 13-Aug-2026 | 04-Aug-2026 11:55:18 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 22:54:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 14:10:48 | 17-Aug-2026 08:38:19 | 0 |  |  | Approver | Locate
AO-001763 | MM-ZTK-1F-IP20-PLR-RPT-9005 | IP20 AT ZWP20 : RISER AND TIE-IN SPOOL STRESS ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 28-Aug-2026 18:11:49 | 26002z1fdcc@thoresen-jutal.com | 29-Aug-2026 13:29:35 | Jumpol Sudjitjul | 04-Sep-2026 |  | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 13:56:53 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 00:28:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 17:26:22 | 07-Sep-2026 11:35:49 | 0 |  |  | Approver | Locate
AO-002206 | MM-ZTK-1F-IP20-PLR-RPT-9005 | IP20 AT ZWP20 : RISER AND TIE-IN SPOOL STRESS ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 22-Sep-2026 11:58:40 | 26002z1fdcc@thoresen-jutal.com | 22-Sep-2026 16:01:01 | Jumpol Sudjitjul | 29-Sep-2026 |  | Akkarapat Suntornsuttiwat | 01-Oct-2026 | 23-Sep-2026 15:15:33 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 26-Sep-2026 05:31:48 | APPR | Approved | Jumpol Sudjitjul | 05-Oct-2026 | 26-Sep-2026 14:22:39 | 26-Sep-2026 08:07:00 | 0 |  |  | Approver | Locate
AO-001076 | MM-ZTK-1F-IP20-PLR-RPT-9006 | IP20 AT ZWP16 : RISER AND TIE-IN SPOOL STRESS ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 12-Jul-2026 11:42:46 | 26002z1fdcc@thoresen-jutal.com | 12-Jul-2026 12:11:43 | Jumpol Sudjitjul | 17-Jul-2026 |  | Akkarapat Suntornsuttiwat | 21-Jul-2026 | 13-Jul-2026 15:56:00 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 20-Jul-2026 02:58:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 20-Jul-2026 09:06:30 | 20-Jul-2026 03:19:41 | 0 |  |  | Approver | Locate
AO-001640 | MM-ZTK-1F-IP20-PLR-RPT-9006 | IP20 AT ZWP16 : RISER AND TIE-IN SPOOL STRESS ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 21-Aug-2026 09:42:52 | 26002z1fdcc@thoresen-jutal.com | 21-Aug-2026 10:47:02 | Jumpol Sudjitjul | 28-Aug-2026 |  | Akkarapat Suntornsuttiwat | 01-Sep-2026 | 24-Aug-2026 16:39:41 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 30-Aug-2026 00:01:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Sep-2026 | 30-Aug-2026 16:58:59 | 30-Aug-2026 10:56:31 | 0 |  |  | Approver | Locate
AO-002206 | MM-ZTK-1F-IP20-PLR-RPT-9006 | IP20 AT ZWP16 : RISER AND TIE-IN SPOOL STRESS ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 22-Sep-2026 11:59:12 | 26002z1fdcc@thoresen-jutal.com | 22-Sep-2026 16:01:16 | Jumpol Sudjitjul | 29-Sep-2026 |  | Akkarapat Suntornsuttiwat | 01-Oct-2026 | 23-Sep-2026 15:29:10 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 26-Sep-2026 05:31:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Oct-2026 | 26-Sep-2026 14:23:22 | 26-Sep-2026 08:09:23 | 0 |  |  | Approver | Locate
AO-002340 | MM-ZTK-1F-IP20-PLR-RPT-9006 | IP20 AT ZWP16 : RISER AND TIE-IN SPOOL STRESS ANALYSIS |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 02-Oct-2026 15:01:13 | 26002z1fdcc@thoresen-jutal.com | 02-Oct-2026 17:52:50 | Jumpol Sudjitjul | 12-Oct-2026 |  | Akkarapat Suntornsuttiwat | 15-Oct-2026 | 06-Oct-2026 08:36:15 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 02:00:18 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 10-Oct-2026 17:45:29 | 10-Oct-2026 11:20:07 | 0 |  |  | Approver | Locate
AO-001884 | MM-ZTK-1F-IP20-PLR-RPT-9007 | IP20 AT ZWP20 : RISER AND TIE-IN SPOOL SEISMIC ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 04-Sep-2026 16:18:11 | 26002z1fdcc@thoresen-jutal.com | 07-Sep-2026 17:08:59 | Jumpol Sudjitjul | 15-Sep-2026 |  | Akkarapat Suntornsuttiwat | 17-Sep-2026 | 08-Sep-2026 11:17:14 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 13-Sep-2026 17:15:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 23:13:45 | 13-Sep-2026 17:23:00 | 0 |  |  | Approver | Locate
AO-002532 | MM-ZTK-1F-IP20-PLR-RPT-9007 | IP20 AT ZWP20 : RISER AND TIE-IN SPOOL SEISMIC ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 15-Oct-2026 14:40:14 | 26002z1fdcc@thoresen-jutal.com | 15-Oct-2026 17:34:21 | Jumpol Sudjitjul | 26-Oct-2026 |  | Akkarapat Suntornsuttiwat | 28-Oct-2026 | 16-Oct-2026 13:32:47 | Pornlert Wanaphattharaphan | 29-Oct-2026 | 16-Oct-2026 22:47:23 | APPR | Approved | Jumpol Sudjitjul | 30-Oct-2026 | 18-Oct-2026 09:20:56 | 18-Oct-2026 05:15:11 | 0 |  |  | Approver | Locate
AO-001884 | MM-ZTK-1F-IP20-PLR-RPT-9008 | IP20 AT ZWP16 : RISER AND TIE-IN SPOOL SEISMIC ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 04-Sep-2026 16:18:43 | 26002z1fdcc@thoresen-jutal.com | 07-Sep-2026 17:09:28 | Jumpol Sudjitjul | 15-Sep-2026 |  | Akkarapat Suntornsuttiwat | 17-Sep-2026 | 08-Sep-2026 11:17:52 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 13-Sep-2026 17:16:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 23:14:09 | 13-Sep-2026 17:24:15 | 0 |  |  | Approver | Locate
AO-002443 | MM-ZTK-1F-IP20-PLR-RPT-9008 | IP20 AT ZWP16 : RISER AND TIE-IN SPOOL SEISMIC ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 08-Oct-2026 15:38:21 | 26002z1fdcc@thoresen-jutal.com | 08-Oct-2026 15:45:05 | Jumpol Sudjitjul | 16-Oct-2026 |  | Akkarapat Suntornsuttiwat | 20-Oct-2026 | 09-Oct-2026 15:10:03 | Pornlert Wanaphattharaphan | 21-Oct-2026 | 11-Oct-2026 00:32:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Oct-2026 | 11-Oct-2026 10:00:31 | 11-Oct-2026 03:18:16 | 0 |  |  | Approver | Locate
AO-001147 | MM-ZTK-1F-IP20-PLR-RPT-9009 | IP20 PIPELINE ON-BOTTOM STABILITY AND STRESS ANALYSIS (SEISMIC) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 16-Jul-2026 21:15:37 | 26002z1fdcc@thoresen-jutal.com | 17-Jul-2026 10:34:48 | Jumpol Sudjitjul | 24-Jul-2026 |  | Akkarapat Suntornsuttiwat | 30-Jul-2026 | 20-Jul-2026 16:00:53 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 26-Jul-2026 10:05:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 14:58:05 | 27-Jul-2026 08:54:55 | 0 |  |  | Approver | Locate
AO-001648 | MM-ZTK-1F-IP20-PLR-RPT-9009 | IP20 PIPELINE ON-BOTTOM STABILITY AND STRESS ANALYSIS (SEISMIC) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 21-Aug-2026 13:58:51 | 26002z1fdcc@thoresen-jutal.com | 21-Aug-2026 14:37:51 | Jumpol Sudjitjul | 28-Aug-2026 |  | Akkarapat Suntornsuttiwat | 01-Sep-2026 | 21-Aug-2026 16:18:31 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 22-Aug-2026 13:21:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Sep-2026 | 24-Aug-2026 19:42:55 | 24-Aug-2026 13:59:21 | 0 |  |  | Approver | Locate
AO-001758 | MM-ZTK-1F-IP20-PLR-RPT-9009 | IP20 PIPELINE ON-BOTTOM STABILITY AND STRESS ANALYSIS (SEISMIC) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 16:51:56 | 26002z1fdcc@thoresen-jutal.com | 28-Aug-2026 17:53:50 | Jumpol Sudjitjul | 07-Sep-2026 |  | Akkarapat Suntornsuttiwat | 09-Sep-2026 | 03-Sep-2026 13:43:45 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 07-Sep-2026 00:28:33 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 07-Sep-2026 12:01:40 | 07-Sep-2026 05:30:46 | 0 |  |  | Approver | Locate
AO-002305 | MM-ZTK-1F-IP20-PLR-RPT-9010 | IP20 PIPELINE LATERAL BUCKLING ANALYSIS LEVEL-2 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 29-Sep-2026 12:02:05 | 26002z1fdcc@thoresen-jutal.com | 29-Sep-2026 15:06:22 | Jumpol Sudjitjul | 06-Oct-2026 |  | Akkarapat Suntornsuttiwat | 08-Oct-2026 | 01-Oct-2026 10:40:32 | Pornlert Wanaphattharaphan | 09-Oct-2026 | 01-Oct-2026 23:17:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-Oct-2026 | 02-Oct-2026 13:22:07 | 02-Oct-2026 07:35:11 | 0 |  |  | Approver | Locate
AO-002536 | MM-ZTK-1F-IP20-PLR-RPT-9010 | IP20 PIPELINE LATERAL BUCKLING ANALYSIS LEVEL-2 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP20 |  |  | PLR | Pipeline | RPT | Report | 0 | In Review | IFA | Issued for Approval |  | 15-Oct-2026 18:05:45 | 26002z1fdcc@thoresen-jutal.com | 16-Oct-2026 15:49:00 | Jumpol Sudjitjul | 26-Oct-2026 |  | Akkarapat Suntornsuttiwat | 28-Oct-2026 |  | Pornlert Wanaphattharaphan | 29-Oct-2026 |  |  |  |  | 30-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000312 | MM-ZTK-1F-IP21-PLR-DWG-9001 | IP21 PIPELINE ROUTE DRAWING FROM ZWP21 TO PLEM14 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 06-May-2026 08:28:39 | 26002z1fdcc@thoresen-jutal.com | 06-May-2026 10:36:23 | Jumpol Sudjitjul | 13-May-2026 |  | Akkarapat Suntornsuttiwat | 15-May-2026 | 08-May-2026 16:01:09 | Pornlert Wanaphattharaphan | 18-May-2026 | 22-May-2026 01:39:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 22-May-2026 08:23:55 | 22-May-2026 02:01:29 | 0 |  |  | Approver | Locate
AO-000881 | MM-ZTK-1F-IP21-PLR-DWG-9001 | IP21 PIPELINE ROUTE DRAWING FROM ZWP21 TO PLEM14 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jun-2026 16:45:17 | 26002z1fdcc@thoresen-jutal.com | 23-Jun-2026 18:00:35 | Jumpol Sudjitjul | 01-Jul-2026 |  | Akkarapat Suntornsuttiwat | 03-Jul-2026 | 25-Jun-2026 10:31:20 | Pornlert Wanaphattharaphan | 06-Jul-2026 | 29-Jun-2026 01:20:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Jul-2026 | 30-Jun-2026 09:41:30 | 30-Jun-2026 03:23:28 | 0 |  |  | Approver | Locate
AO-001062 | MM-ZTK-1F-IP21-PLR-DWG-9001 | IP21 PIPELINE ROUTE DRAWING FROM ZWP21 TO PLEM14 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 16:56:34 | 26002z1fdcc@thoresen-jutal.com | 10-Jul-2026 17:54:44 | Jumpol Sudjitjul | 20-Jul-2026 |  | Akkarapat Suntornsuttiwat | 22-Jul-2026 | 13-Jul-2026 09:35:52 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 20-Jul-2026 02:51:09 | APPR | Approved | Jumpol Sudjitjul | 24-Jul-2026 | 20-Jul-2026 09:06:05 | 20-Jul-2026 03:18:20 | 0 |  |  | Approver | Locate
AO-001559 | MM-ZTK-1F-IP21-PLR-DWG-9002 | IP21 PIPELINE ALIGNMENT SHEETS: ZWP21 TO PLEM14 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 17-Aug-2026 14:44:36 | 26002z1fdcc@thoresen-jutal.com | 17-Aug-2026 15:36:38 | Jumpol Sudjitjul | 24-Aug-2026 |  | Akkarapat Suntornsuttiwat | 26-Aug-2026 | 19-Aug-2026 15:48:28 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:10:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 19:41:35 | 24-Aug-2026 13:57:53 | 0 |  |  | Approver | Locate
AO-001799 | MM-ZTK-1F-IP21-PLR-DWG-9002 | IP21 PIPELINE ALIGNMENT SHEETS: ZWP21 TO PLEM14 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 14:02:16 | 26002z1fdcc@thoresen-jutal.com | 31-Aug-2026 14:28:04 | Jumpol Sudjitjul | 07-Sep-2026 |  | Akkarapat Suntornsuttiwat | 09-Sep-2026 | 03-Sep-2026 11:34:45 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 04-Sep-2026 23:47:49 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 05-Sep-2026 18:02:55 | 05-Sep-2026 11:35:35 | 0 |  |  | Approver | Locate
AO-002016 | MM-ZTK-1F-IP21-PLR-DWG-9002 | IP21 PIPELINE ALIGNMENT SHEETS: ZWP21 TO PLEM14 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 21:01:14 | 26002z1fdcc@thoresen-jutal.com | 11-Sep-2026 21:07:46 | Jumpol Sudjitjul | 21-Sep-2026 |  | Akkarapat Suntornsuttiwat | 23-Sep-2026 | 14-Sep-2026 10:58:45 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 19-Sep-2026 21:16:37 | APPR | Approved | Jumpol Sudjitjul | 25-Sep-2026 | 20-Sep-2026 17:53:20 | 20-Sep-2026 11:41:53 | 0 |  |  | Approver | Locate
AO-001658 | MM-ZTK-1F-IP21-PLR-DWG-9003 | IP21 PIPELINE SCHEMATIC DIAGRAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 11:04:47 | 26002z1fdcc@thoresen-jutal.com | 25-Aug-2026 14:32:38 | Jumpol Sudjitjul | 01-Sep-2026 |  | Akkarapat Suntornsuttiwat | 03-Sep-2026 | 27-Aug-2026 15:48:03 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 23:23:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 15:55:05 | 31-Aug-2026 10:27:48 | 0 |  |  | Approver | Locate
AO-002016 | MM-ZTK-1F-IP21-PLR-DWG-9003 | IP21 PIPELINE SCHEMATIC DIAGRAM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 11-Sep-2026 21:01:49 | 26002z1fdcc@thoresen-jutal.com | 11-Sep-2026 21:08:13 | Jumpol Sudjitjul | 21-Sep-2026 |  | Akkarapat Suntornsuttiwat | 23-Sep-2026 | 14-Sep-2026 10:51:48 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 19-Sep-2026 21:14:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Sep-2026 | 20-Sep-2026 17:53:55 | 20-Sep-2026 11:43:10 | 0 |  |  | Approver | Locate
AO-002267 | MM-ZTK-1F-IP21-PLR-DWG-9003 | IP21 PIPELINE SCHEMATIC DIAGRAM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 25-Sep-2026 16:15:58 | 26002z1fdcc@thoresen-jutal.com | 25-Sep-2026 16:22:17 | Jumpol Sudjitjul | 02-Oct-2026 |  | Akkarapat Suntornsuttiwat | 06-Oct-2026 | 28-Sep-2026 15:27:19 | Pornlert Wanaphattharaphan | 07-Oct-2026 | 28-Sep-2026 23:00:58 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 29-Sep-2026 14:21:20 | 29-Sep-2026 08:30:45 | 0 |  |  | Approver | Locate
AO-000539 | MM-ZTK-1F-IP21-PLR-DWG-9004 | IP21 PIPELINE PLATFORM APPROACH AT ZWP21 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 09:41:20 | 26002z1fdcc@thoresen-jutal.com | 21-May-2026 14:11:59 | Jumpol Sudjitjul | 28-May-2026 |  | Akkarapat Suntornsuttiwat | 02-Jun-2026 | 25-May-2026 14:26:15 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:42:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 20:54:13 | 31-May-2026 14:33:00 | 0 |  |  | Approver | Locate
AO-000915 | MM-ZTK-1F-IP21-PLR-DWG-9004 | IP21 PIPELINE PLATFORM APPROACH AT ZWP21 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Jun-2026 20:35:12 | 26002z1fdcc@thoresen-jutal.com | 27-Jun-2026 18:50:02 | Jumpol Sudjitjul | 06-Jul-2026 |  | Akkarapat Suntornsuttiwat | 08-Jul-2026 | 29-Jun-2026 15:08:26 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 02-Jul-2026 00:40:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 02-Jul-2026 10:21:35 | 02-Jul-2026 04:00:19 | 0 |  |  | Approver | Locate
AO-001058 | MM-ZTK-1F-IP21-PLR-DWG-9004 | IP21 PIPELINE PLATFORM APPROACH AT ZWP21 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 12:19:23 | 26002z1fdcc@thoresen-jutal.com | 10-Jul-2026 13:03:29 | Jumpol Sudjitjul | 17-Jul-2026 |  | Akkarapat Suntornsuttiwat | 21-Jul-2026 | 10-Jul-2026 15:17:25 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 11-Jul-2026 12:14:21 | APPR | Approved | Jumpol Sudjitjul | 23-Jul-2026 | 12-Jul-2026 11:42:02 | 12-Jul-2026 05:41:34 | 0 |  |  | Approver | Locate
AO-000540 | MM-ZTK-1F-IP21-PLR-DWG-9005 | IP21 PIPELINE PLATFORM APPROACH AT PLEM14 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 09:41:59 | 26002z1fdcc@thoresen-jutal.com | 21-May-2026 14:12:38 | Jumpol Sudjitjul | 28-May-2026 |  | Akkarapat Suntornsuttiwat | 02-Jun-2026 | 25-May-2026 14:27:54 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 31-May-2026 16:11:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 31-May-2026 20:54:40 | 31-May-2026 14:34:16 | 0 |  |  | Approver | Locate
AO-000915 | MM-ZTK-1F-IP21-PLR-DWG-9005 | IP21 PIPELINE PLATFORM APPROACH AT PLEM14 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Jun-2026 20:35:37 | 26002z1fdcc@thoresen-jutal.com | 27-Jun-2026 18:50:02 | Jumpol Sudjitjul | 06-Jul-2026 |  | Akkarapat Suntornsuttiwat | 08-Jul-2026 | 29-Jun-2026 15:09:44 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 02-Jul-2026 00:41:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 02-Jul-2026 10:22:27 | 02-Jul-2026 04:03:10 | 0 |  |  | Approver | Locate
AO-001058 | MM-ZTK-1F-IP21-PLR-DWG-9005 | IP21 PIPELINE PLATFORM APPROACH AT PLEM14 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 12:19:47 | 26002z1fdcc@thoresen-jutal.com | 10-Jul-2026 13:03:30 | Jumpol Sudjitjul | 17-Jul-2026 |  | Akkarapat Suntornsuttiwat | 21-Jul-2026 | 10-Jul-2026 15:20:18 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 11-Jul-2026 10:01:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 12-Jul-2026 11:32:14 | 12-Jul-2026 04:56:41 | 0 |  |  | Approver | Locate
AO-001264 | MM-ZTK-1F-IP21-PLR-DWG-9005 | IP21 PIPELINE PLATFORM APPROACH AT PLEM14 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 14:11:56 | 26002z1fdcc@thoresen-jutal.com | 26-Jul-2026 22:02:00 | Jumpol Sudjitjul | 05-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 27-Jul-2026 15:59:52 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 29-Jul-2026 09:04:54 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 30-Jul-2026 09:42:43 | 30-Jul-2026 03:52:03 | 0 |  |  | Approver | Locate
AO-000521 | MM-ZTK-1F-IP21-PLR-GA-9001 | RISER GA DRAWING AT ZWP21 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 12:48:36 | 26002z1fdcc@thoresen-jutal.com | 20-May-2026 16:04:54 | Jumpol Sudjitjul | 27-May-2026 |  | Akkarapat Suntornsuttiwat | 29-May-2026 | 25-May-2026 09:18:33 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 09-Jun-2026 00:44:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Jun-2026 | 09-Jun-2026 07:50:33 | 09-Jun-2026 01:19:02 | 0 |  |  | Approver | Locate
AO-001075 | MM-ZTK-1F-IP21-PLR-GA-9001 | RISER GA DRAWING AT ZWP21 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:43:11 | 26002z1fdcc@thoresen-jutal.com | 12-Jul-2026 12:12:27 | Jumpol Sudjitjul | 17-Jul-2026 |  | Akkarapat Suntornsuttiwat | 21-Jul-2026 | 13-Jul-2026 10:01:39 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 20-Jul-2026 02:58:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 20-Jul-2026 09:05:39 | 20-Jul-2026 03:17:11 | 0 |  |  | Approver | Locate
AO-001375 | MM-ZTK-1F-IP21-PLR-GA-9001 | RISER GA DRAWING AT ZWP21 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 11:02:06 | 26002z1fdcc@thoresen-jutal.com | 03-Aug-2026 14:13:09 | Jumpol Sudjitjul | 10-Aug-2026 |  | Akkarapat Suntornsuttiwat | 13-Aug-2026 | 04-Aug-2026 10:23:02 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 22:49:21 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 14:11:28 | 17-Aug-2026 08:39:45 | 0 |  |  | Approver | Locate
AO-002463 | MM-ZTK-1F-IP21-PLR-GA-9001 | RISER GA DRAWING AT ZWP21 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | AFC | Approved for Construction |  | 09-Oct-2026 16:46:22 | 26002z1fdcc@thoresen-jutal.com | 09-Oct-2026 17:32:42 | Jumpol Sudjitjul | 20-Oct-2026 |  | Akkarapat Suntornsuttiwat | 22-Oct-2026 | 12-Oct-2026 10:01:15 | Pornlert Wanaphattharaphan | 26-Oct-2026 | 13-Oct-2026 14:46:26 | APPR | Approved | Jumpol Sudjitjul | 27-Oct-2026 | 14-Oct-2026 16:41:29 | 14-Oct-2026 10:03:47 | 0 |  |  | Approver | Locate
AO-001266 | MM-ZTK-1F-IP21-PLR-GA-9002 | IP21 TIE-IN SPOOL GA DRAWING AT ZWP21 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 17:08:04 | 26002z1fdcc@thoresen-jutal.com | 26-Jul-2026 23:48:19 | Jumpol Sudjitjul | 05-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 30-Jul-2026 15:07:26 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 06-Aug-2026 00:09:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 06-Aug-2026 09:36:31 | 06-Aug-2026 03:34:33 | 0 |  |  | Approver | Locate
AO-001616 | MM-ZTK-1F-IP21-PLR-GA-9002 | IP21 TIE-IN SPOOL GA DRAWING AT ZWP21 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 09:37:06 | 26002z1fdcc@thoresen-jutal.com | 20-Aug-2026 09:41:57 | Jumpol Sudjitjul | 27-Aug-2026 |  | Akkarapat Suntornsuttiwat | 31-Aug-2026 | 20-Aug-2026 11:14:58 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 22-Aug-2026 15:12:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Sep-2026 | 24-Aug-2026 19:41:12 | 24-Aug-2026 13:56:36 | 0 |  |  | Approver | Locate
AO-001764 | MM-ZTK-1F-IP21-PLR-GA-9002 | IP21 TIE-IN SPOOL GA DRAWING AT ZWP21 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | AFC | Approved for Construction |  | 29-Aug-2026 14:07:16 | 26002z1fdcc@thoresen-jutal.com | 29-Aug-2026 14:14:23 | Jumpol Sudjitjul | 04-Sep-2026 | 01-Sep-2026 10:27:14 | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 08:56:50 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 00:29:28 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 16:11:45 | 07-Sep-2026 10:20:20 | 0 |  |  | Approver | Locate
AO-001266 | MM-ZTK-1F-IP21-PLR-GA-9003 | IP21 TIE-IN SPOOL GA DRAWING AT PLEM14 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 17:08:30 | 26002z1fdcc@thoresen-jutal.com | 26-Jul-2026 23:48:20 | Jumpol Sudjitjul | 05-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 30-Jul-2026 15:08:19 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 06-Aug-2026 00:43:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 06-Aug-2026 09:37:59 | 06-Aug-2026 03:39:40 | 0 |  |  | Approver | Locate
AO-001616 | MM-ZTK-1F-IP21-PLR-GA-9003 | IP21 TIE-IN SPOOL GA DRAWING AT PLEM14 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 09:37:56 | 26002z1fdcc@thoresen-jutal.com | 20-Aug-2026 09:41:57 | Jumpol Sudjitjul | 27-Aug-2026 |  | Akkarapat Suntornsuttiwat | 31-Aug-2026 | 20-Aug-2026 11:16:15 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 22-Aug-2026 15:08:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Sep-2026 | 24-Aug-2026 19:40:48 | 24-Aug-2026 13:55:18 | 0 |  |  | Approver | Locate
AO-001764 | MM-ZTK-1F-IP21-PLR-GA-9003 | IP21 TIE-IN SPOOL GA DRAWING AT PLEM14 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | AFC | Approved for Construction |  | 29-Aug-2026 14:07:41 | 26002z1fdcc@thoresen-jutal.com | 29-Aug-2026 14:14:24 | Jumpol Sudjitjul | 04-Sep-2026 | 01-Sep-2026 10:32:17 | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 08:57:18 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 00:30:36 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 12:02:14 | 07-Sep-2026 05:38:41 | 0 |  |  | Approver | Locate
AO-000915 | MM-ZTK-1F-IP21-PLR-ISO-9001 | IP21 RISER ISOMETRIC AT ZWP21 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 20:36:04 | 26002z1fdcc@thoresen-jutal.com | 27-Jun-2026 18:55:33 | Jumpol Sudjitjul | 06-Jul-2026 |  | Akkarapat Suntornsuttiwat | 08-Jul-2026 | 29-Jun-2026 16:54:26 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 02-Jul-2026 00:54:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 02-Jul-2026 10:10:43 | 02-Jul-2026 03:51:08 | 0 |  |  | Approver | Locate
AO-001075 | MM-ZTK-1F-IP21-PLR-ISO-9001 | IP21 RISER ISOMETRIC AT ZWP21 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:43:37 | 26002z1fdcc@thoresen-jutal.com | 12-Jul-2026 12:13:01 | Jumpol Sudjitjul | 17-Jul-2026 |  | Akkarapat Suntornsuttiwat | 21-Jul-2026 | 13-Jul-2026 10:53:06 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 20-Jul-2026 02:58:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 20-Jul-2026 09:05:07 | 20-Jul-2026 03:15:51 | 0 |  |  | Approver | Locate
AO-001323 | MM-ZTK-1F-IP21-PLR-ISO-9001 | IP21 RISER ISOMETRIC AT ZWP21 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Jul-2026 09:14:59 | 26002z1fdcc@thoresen-jutal.com | 28-Jul-2026 20:31:13 | Jumpol Sudjitjul | 06-Aug-2026 |  | Akkarapat Suntornsuttiwat | 10-Aug-2026 | 30-Jul-2026 15:49:53 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 12-Aug-2026 09:33:50 | APPR | Approved | Jumpol Sudjitjul | 13-Aug-2026 | 13-Aug-2026 11:28:57 | 13-Aug-2026 05:27:23 | 0 |  |  | Approver | Locate
AO-001900 | MM-ZTK-1F-IP21-PLR-ISO-9001 | IP21 RISER ISOMETRIC AT ZWP21 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 10:30:17 | 26002z1fdcc@thoresen-jutal.com | 08-Sep-2026 09:18:29 | Jumpol Sudjitjul | 15-Sep-2026 |  | Akkarapat Suntornsuttiwat | 17-Sep-2026 | 08-Sep-2026 11:20:40 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 13-Sep-2026 17:19:32 | APPR | Approved | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 23:14:31 | 13-Sep-2026 16:42:25 | 0 |  |  | Approver | Locate
AO-000996 | MM-ZTK-1F-IP21-PLR-ISO-9002 | IP21 TIE-IN SPOOL ISOMETRIC AT ZWP21 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 13:27:34 | 26002z1fdcc@thoresen-jutal.com | 03-Jul-2026 14:15:32 | Jumpol Sudjitjul | 10-Jul-2026 |  | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 06-Jul-2026 14:19:12 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 22:28:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 11:08:55 | 15-Jul-2026 04:58:29 | 0 |  |  | Approver | Locate
AO-001560 | MM-ZTK-1F-IP21-PLR-ISO-9002 | IP21 TIE-IN SPOOL ISOMETRIC AT ZWP21 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:45:07 | 26002z1fdcc@thoresen-jutal.com | 17-Aug-2026 15:34:23 | Jumpol Sudjitjul | 24-Aug-2026 |  | Akkarapat Suntornsuttiwat | 26-Aug-2026 | 17-Aug-2026 16:26:59 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 17:54:24 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 19:40:18 | 24-Aug-2026 13:53:59 | 0 |  |  | Approver | Locate
AO-001763 | MM-ZTK-1F-IP21-PLR-ISO-9002 | IP21 TIE-IN SPOOL ISOMETRIC AT ZWP21 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 18:12:15 | 26002z1fdcc@thoresen-jutal.com | 29-Aug-2026 13:27:41 | Jumpol Sudjitjul | 04-Sep-2026 | 31-Aug-2026 16:31:48 | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 09:16:35 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 00:31:58 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 17:33:32 | 07-Sep-2026 11:38:05 | 0 |  |  | Approver | Locate
AO-000996 | MM-ZTK-1F-IP21-PLR-ISO-9003 | IP21 TIE-IN SPOOL ISOMETRIC AT PLEM14 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 13:29:06 | 26002z1fdcc@thoresen-jutal.com | 03-Jul-2026 14:15:33 | Jumpol Sudjitjul | 10-Jul-2026 |  | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 06-Jul-2026 14:21:01 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 22:29:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 11:09:56 | 15-Jul-2026 05:11:48 | 0 |  |  | Approver | Locate
AO-001560 | MM-ZTK-1F-IP21-PLR-ISO-9003 | IP21 TIE-IN SPOOL ISOMETRIC AT PLEM14 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:45:40 | 26002z1fdcc@thoresen-jutal.com | 17-Aug-2026 15:34:17 | Jumpol Sudjitjul | 24-Aug-2026 |  | Akkarapat Suntornsuttiwat | 26-Aug-2026 | 17-Aug-2026 16:27:20 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 17:55:23 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 19:39:55 | 24-Aug-2026 13:52:51 | 0 |  |  | Approver | Locate
AO-001763 | MM-ZTK-1F-IP21-PLR-ISO-9003 | IP21 TIE-IN SPOOL ISOMETRIC AT PLEM14 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP21 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 18:12:41 | 26002z1fdcc@thoresen-jutal.com | 29-Aug-2026 13:27:42 | Jumpol Sudjitjul | 04-Sep-2026 | 31-Aug-2026 16:32:08 | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 09:21:42 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 00:32:57 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 17:28:15 | 07-Sep-2026 11:36:57 | 0 |  |  | Approver | Locate
AO-000229 | MM-ZTK-1F-IP21-PLR-RPT-9001 | IP21 PIPELINE ROUTING STUDY AND DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 27-Apr-2026 10:33:03 | 26002z1fdcc@thoresen-jutal.com | 27-Apr-2026 16:50:15 | Jumpol Sudjitjul | 06-May-2026 |  | Akkarapat Suntornsuttiwat | 08-May-2026 | 05-May-2026 08:52:55 | Pornlert Wanaphattharaphan | 11-May-2026 | 09-May-2026 23:01:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 12-May-2026 | 10-May-2026 23:25:50 | 10-May-2026 17:21:19 | 0 |  |  | Approver | Locate
AO-000892 | MM-ZTK-1F-IP21-PLR-RPT-9001 | IP21 PIPELINE ROUTING STUDY AND DESIGN |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 14:27:25 | 26002z1fdcc@thoresen-jutal.com | 25-Jun-2026 15:14:25 | Jumpol Sudjitjul | 02-Jul-2026 |  | Akkarapat Suntornsuttiwat | 06-Jul-2026 | 26-Jun-2026 16:11:39 | Pornlert Wanaphattharaphan | 07-Jul-2026 | 29-Jun-2026 01:25:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jul-2026 | 30-Jun-2026 09:40:39 | 30-Jun-2026 03:18:08 | 0 |  |  | Approver | Locate
AO-001219 | MM-ZTK-1F-IP21-PLR-RPT-9001 | IP21 PIPELINE ROUTING STUDY AND DESIGN |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 21-Jul-2026 12:37:33 | 26002z1fdcc@thoresen-jutal.com | 21-Jul-2026 13:12:25 | Jumpol Sudjitjul | 30-Jul-2026 |  | Akkarapat Suntornsuttiwat | 03-Aug-2026 | 21-Jul-2026 14:22:03 | Pornlert Wanaphattharaphan | 04-Aug-2026 | 29-Jul-2026 08:45:39 | APPR | Approved | Jumpol Sudjitjul | 05-Aug-2026 | 30-Jul-2026 09:43:29 | 30-Jul-2026 03:53:16 | 0 |  |  | Approver | Locate
AO-001430 | MM-ZTK-1F-IP21-PLR-RPT-9002 | P21 PIPELINE ON-BOTTOM ROUGHNESS AND IN-PLACE STRESS ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 06-Aug-2026 12:10:46 | 26002z1fdcc@thoresen-jutal.com | 06-Aug-2026 14:45:18 | Jumpol Sudjitjul | 14-Aug-2026 |  | Akkarapat Suntornsuttiwat | 18-Aug-2026 | 07-Aug-2026 14:53:25 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 20-Aug-2026 22:58:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Aug-2026 | 21-Aug-2026 10:20:55 | 21-Aug-2026 04:19:09 | 0 |  |  | Approver | Locate
AO-001735 | MM-ZTK-1F-IP21-PLR-RPT-9002 | P21 PIPELINE ON-BOTTOM ROUGHNESS AND IN-PLACE STRESS ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 27-Aug-2026 12:03:14 | 26002z1fdcc@thoresen-jutal.com | 27-Aug-2026 13:08:27 | Jumpol Sudjitjul | 03-Sep-2026 |  | Akkarapat Suntornsuttiwat | 07-Sep-2026 | 03-Sep-2026 15:38:53 | Pornlert Wanaphattharaphan | 08-Sep-2026 | 07-Sep-2026 00:33:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Sep-2026 | 07-Sep-2026 17:27:04 | 07-Sep-2026 11:10:35 | 0 |  |  | Approver | Locate
AO-002013 | MM-ZTK-1F-IP21-PLR-RPT-9002 | P21 PIPELINE ON-BOTTOM ROUGHNESS AND IN-PLACE STRESS ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 21:02:48 | 26002z1fdcc@thoresen-jutal.com | 11-Sep-2026 21:06:45 | Jumpol Sudjitjul | 21-Sep-2026 |  | Akkarapat Suntornsuttiwat | 23-Sep-2026 | 14-Sep-2026 11:20:22 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 19-Sep-2026 21:10:47 | APPR | Approved | Jumpol Sudjitjul | 25-Sep-2026 | 20-Sep-2026 17:54:38 | 20-Sep-2026 11:44:21 | 0 |  |  | Approver | Locate
AO-001076 | MM-ZTK-1F-IP21-PLR-RPT-9003 | IP21 PIPELINE LATERAL BUCLKING ANALYSIS LEVEL 1 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 12-Jul-2026 11:44:02 | 26002z1fdcc@thoresen-jutal.com | 13-Jul-2026 09:26:45 | Jumpol Sudjitjul | 20-Jul-2026 |  | Akkarapat Suntornsuttiwat | 22-Jul-2026 | 15-Jul-2026 11:25:36 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 20-Jul-2026 02:41:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 20-Jul-2026 09:02:48 | 20-Jul-2026 03:11:00 | 0 |  |  | Approver | Locate
AO-001556 | MM-ZTK-1F-IP21-PLR-RPT-9003 | IP21 PIPELINE LATERAL BUCLKING ANALYSIS LEVEL 1 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:46:17 | 26002z1fdcc@thoresen-jutal.com | 17-Aug-2026 15:39:21 | Jumpol Sudjitjul | 24-Aug-2026 |  | Akkarapat Suntornsuttiwat | 26-Aug-2026 | 20-Aug-2026 09:52:15 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:14:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 19:38:38 | 24-Aug-2026 13:51:46 | 0 |  |  | Approver | Locate
AO-001816 | MM-ZTK-1F-IP21-PLR-RPT-9003 | IP21 PIPELINE LATERAL BUCLKING ANALYSIS LEVEL 1 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 18:24:50 | 26002z1fdcc@thoresen-jutal.com | 03-Sep-2026 11:14:40 | Jumpol Sudjitjul | 10-Sep-2026 |  | Akkarapat Suntornsuttiwat | 14-Sep-2026 | 03-Sep-2026 13:35:18 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 07-Sep-2026 00:33:54 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 07-Sep-2026 17:34:12 | 07-Sep-2026 11:05:41 | 0 |  |  | Approver | Locate
AO-001579 | MM-ZTK-1F-IP21-PLR-RPT-9004 | IP21 PIPELINE WALKING ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 17-Aug-2026 18:41:09 | 26002z1fdcc@thoresen-jutal.com | 18-Aug-2026 08:59:21 | Jumpol Sudjitjul | 25-Aug-2026 |  | Akkarapat Suntornsuttiwat | 27-Aug-2026 | 20-Aug-2026 14:47:11 | Pornlert Wanaphattharaphan | 28-Aug-2026 | 23-Aug-2026 23:34:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Aug-2026 | 24-Aug-2026 19:38:10 | 24-Aug-2026 13:29:01 | 0 |  |  | Approver | Locate
AO-001846 | MM-ZTK-1F-IP21-PLR-RPT-9004 | IP21 PIPELINE WALKING ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 03-Sep-2026 16:49:48 | 26002z1fdcc@thoresen-jutal.com | 04-Sep-2026 08:07:16 | Jumpol Sudjitjul | 11-Sep-2026 |  | Akkarapat Suntornsuttiwat | 15-Sep-2026 | 04-Sep-2026 13:43:06 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 07-Sep-2026 00:34:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 07-Sep-2026 17:27:41 | 07-Sep-2026 11:12:58 | 0 |  |  | Approver | Locate
AO-002129 | MM-ZTK-1F-IP21-PLR-RPT-9004 | IP21 PIPELINE WALKING ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 17-Sep-2026 13:35:45 | 26002z1fdcc@thoresen-jutal.com | 17-Sep-2026 14:45:44 | Jumpol Sudjitjul | 24-Sep-2026 |  | Akkarapat Suntornsuttiwat | 28-Sep-2026 | 18-Sep-2026 16:42:07 | Pornlert Wanaphattharaphan | 29-Sep-2026 | 19-Sep-2026 16:16:08 | APPR | Approved | Jumpol Sudjitjul | 30-Sep-2026 | 20-Sep-2026 17:55:21 | 20-Sep-2026 11:45:30 | 0 |  |  | Approver | Locate
AO-001076 | MM-ZTK-1F-IP21-PLR-RPT-9005 | IP21 AT ZWP21 : RISER AND TIE-IN SPOOL STRESS ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 12-Jul-2026 11:44:27 | 26002z1fdcc@thoresen-jutal.com | 12-Jul-2026 12:11:56 | Jumpol Sudjitjul | 17-Jul-2026 |  | Akkarapat Suntornsuttiwat | 21-Jul-2026 | 13-Jul-2026 15:57:45 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 20-Jul-2026 02:59:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 20-Jul-2026 09:04:39 | 20-Jul-2026 03:14:33 | 0 |  |  | Approver | Locate
AO-001667 | MM-ZTK-1F-IP21-PLR-RPT-9005 | IP21 AT ZWP21 : RISER AND TIE-IN SPOOL STRESS ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 11:05:19 | 26002z1fdcc@thoresen-jutal.com | 25-Aug-2026 13:09:31 | Jumpol Sudjitjul | 01-Sep-2026 |  | Akkarapat Suntornsuttiwat | 03-Sep-2026 | 26-Aug-2026 15:24:36 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 23:27:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 15:53:15 | 31-Aug-2026 10:25:17 | 0 |  |  | Approver | Locate
AO-001840 | MM-ZTK-1F-IP21-PLR-RPT-9005 | IP21 AT ZWP21 : RISER AND TIE-IN SPOOL STRESS ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 16:50:20 | 26002z1fdcc@thoresen-jutal.com | 04-Sep-2026 08:07:50 | Jumpol Sudjitjul | 11-Sep-2026 |  | Akkarapat Suntornsuttiwat | 15-Sep-2026 | 04-Sep-2026 14:45:32 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 07-Sep-2026 00:34:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 07-Sep-2026 17:38:21 | 07-Sep-2026 11:15:32 | 0 |  |  | Approver | Locate
AO-002068 | MM-ZTK-1F-IP21-PLR-RPT-9005 | IP21 AT ZWP21 : RISER AND TIE-IN SPOOL STRESS ANALYSIS |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:43:21 | 26002z1fdcc@thoresen-jutal.com | 15-Sep-2026 15:46:45 | Jumpol Sudjitjul | 22-Sep-2026 |  | Akkarapat Suntornsuttiwat | 24-Sep-2026 | 16-Sep-2026 11:27:25 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 19-Sep-2026 16:03:30 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 20-Sep-2026 17:56:31 | 20-Sep-2026 11:13:55 | 0 |  |  | Approver | Locate
AO-002527 | MM-ZTK-1F-IP21-PLR-RPT-9005 | IP21 AT ZWP21 : RISER AND TIE-IN SPOOL STRESS ANALYSIS |  | C3 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 15-Oct-2026 09:27:52 | 26002z1fdcc@thoresen-jutal.com | 15-Oct-2026 11:31:17 | Jumpol Sudjitjul | 22-Oct-2026 |  | Akkarapat Suntornsuttiwat | 27-Oct-2026 | 16-Oct-2026 13:22:12 | Pornlert Wanaphattharaphan | 28-Oct-2026 | 16-Oct-2026 22:53:37 | APPR | Approved | Jumpol Sudjitjul | 29-Oct-2026 | 18-Oct-2026 09:20:27 | 18-Oct-2026 05:06:50 | 0 |  |  | Approver | Locate
AO-001120 | MM-ZTK-1F-IP21-PLR-RPT-9006 | IP21 AT PLEM14 : TIE-IN SPOOL STRESS ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 15-Jul-2026 18:45:33 | 26002z1fdcc@thoresen-jutal.com | 15-Jul-2026 21:36:01 | Jumpol Sudjitjul | 23-Jul-2026 |  | Akkarapat Suntornsuttiwat | 27-Jul-2026 | 16-Jul-2026 11:25:18 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 20-Jul-2026 00:22:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Jul-2026 | 20-Jul-2026 09:03:58 | 20-Jul-2026 02:50:47 | 0 |  |  | Approver | Locate
AO-001632 | MM-ZTK-1F-IP21-PLR-RPT-9006 | IP21 AT PLEM14 : TIE-IN SPOOL STRESS ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 17:25:13 | 26002z1fdcc@thoresen-jutal.com | 21-Aug-2026 10:47:28 | Jumpol Sudjitjul | 28-Aug-2026 |  | Akkarapat Suntornsuttiwat | 01-Sep-2026 | 24-Aug-2026 16:40:51 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 30-Aug-2026 00:02:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Sep-2026 | 30-Aug-2026 16:45:05 | 30-Aug-2026 10:31:06 | 0 |  |  | Approver | Locate
AO-001855 | MM-ZTK-1F-IP21-PLR-RPT-9006 | IP21 AT PLEM14 : TIE-IN SPOOL STRESS ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 18:18:56 | 26002z1fdcc@thoresen-jutal.com | 04-Sep-2026 08:08:08 | Jumpol Sudjitjul | 11-Sep-2026 |  | Akkarapat Suntornsuttiwat | 15-Sep-2026 | 04-Sep-2026 14:27:33 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 07-Sep-2026 00:35:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 07-Sep-2026 17:38:52 | 07-Sep-2026 11:16:58 | 0 |  |  | Approver | Locate
AO-002017 | MM-ZTK-1F-IP21-PLR-RPT-9006 | IP21 AT PLEM14 : TIE-IN SPOOL STRESS ANALYSIS |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 21:03:33 | 26002z1fdcc@thoresen-jutal.com | 11-Sep-2026 21:07:24 | Jumpol Sudjitjul | 21-Sep-2026 |  | Akkarapat Suntornsuttiwat | 23-Sep-2026 | 16-Sep-2026 14:03:21 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 19-Sep-2026 21:08:59 | APPR | Approved | Jumpol Sudjitjul | 25-Sep-2026 | 20-Sep-2026 17:57:13 | 20-Sep-2026 11:46:43 | 0 |  |  | Approver | Locate
AO-001939 | MM-ZTK-1F-IP21-PLR-RPT-9007 | IP21 AT ZWP21 : RISER AND TIE-IN SPOOL SEISMIC ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 08-Sep-2026 18:34:44 | 26002z1fdcc@thoresen-jutal.com | 09-Sep-2026 08:51:33 | Jumpol Sudjitjul | 16-Sep-2026 |  | Akkarapat Suntornsuttiwat | 18-Sep-2026 | 10-Sep-2026 10:30:42 | Pornlert Wanaphattharaphan | 21-Sep-2026 | 13-Sep-2026 17:22:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Sep-2026 | 13-Sep-2026 23:15:00 | 13-Sep-2026 16:43:42 | 0 |  |  | Approver | Locate
AO-002386 | MM-ZTK-1F-IP21-PLR-RPT-9007 | IP21 AT ZWP21 : RISER AND TIE-IN SPOOL SEISMIC ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 06-Oct-2026 09:29:03 | 26002z1fdcc@thoresen-jutal.com | 06-Oct-2026 09:45:20 | Jumpol Sudjitjul | 14-Oct-2026 |  | Akkarapat Suntornsuttiwat | 16-Oct-2026 | 09-Oct-2026 15:11:58 | Pornlert Wanaphattharaphan | 19-Oct-2026 | 11-Oct-2026 00:14:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-Oct-2026 | 11-Oct-2026 10:01:26 | 11-Oct-2026 03:19:42 | 0 |  |  | Approver | Locate
AO-001375 | MM-ZTK-1F-IP21-PLR-RPT-9009 | IP21 PIPELINE ON-BOTTOM STABILITY AND STRESS ANALYSIS (SEISMIC) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 11:02:32 | 26002z1fdcc@thoresen-jutal.com | 03-Aug-2026 15:47:05 | Jumpol Sudjitjul | 10-Aug-2026 |  | Akkarapat Suntornsuttiwat | 13-Aug-2026 | 04-Aug-2026 14:46:01 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 23:04:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 14:01:15 | 17-Aug-2026 08:29:36 | 0 |  |  | Approver | Locate
AO-001714 | MM-ZTK-1F-IP21-PLR-RPT-9009 | IP21 PIPELINE ON-BOTTOM STABILITY AND STRESS ANALYSIS (SEISMIC) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 26-Aug-2026 08:45:27 | 26002z1fdcc@thoresen-jutal.com | 26-Aug-2026 12:22:50 | Jumpol Sudjitjul | 02-Sep-2026 |  | Akkarapat Suntornsuttiwat | 04-Sep-2026 | 27-Aug-2026 08:58:24 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 30-Aug-2026 23:30:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Sep-2026 | 31-Aug-2026 15:55:34 | 31-Aug-2026 10:31:07 | 0 |  |  | Approver | Locate
AO-001926 | MM-ZTK-1F-IP21-PLR-RPT-9009 | IP21 PIPELINE ON-BOTTOM STABILITY AND STRESS ANALYSIS (SEISMIC) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 08-Sep-2026 12:36:01 | 26002z1fdcc@thoresen-jutal.com | 08-Sep-2026 14:22:12 | Jumpol Sudjitjul | 15-Sep-2026 |  | Akkarapat Suntornsuttiwat | 17-Sep-2026 | 09-Sep-2026 11:11:03 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 12-Sep-2026 23:30:37 | APPR | Approved | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 08:20:20 | 13-Sep-2026 01:49:31 | 0 |  |  | Approver | Locate
AO-002267 | MM-ZTK-1F-IP21-PLR-RPT-9010 | IP21 PIPELINE LATERAL BUCKLING ANALYSIS LEVEL-2 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 16:16:47 | 26002z1fdcc@thoresen-jutal.com | 25-Sep-2026 17:27:08 | Jumpol Sudjitjul | 05-Oct-2026 |  | Akkarapat Suntornsuttiwat | 07-Oct-2026 | 01-Oct-2026 10:41:43 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 01-Oct-2026 23:16:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 02-Oct-2026 13:24:40 | 02-Oct-2026 07:18:37 | 0 |  |  | Approver | Locate
AO-002553 | MM-ZTK-1F-IP21-PLR-RPT-9010 | IP21 PIPELINE LATERAL BUCKLING ANALYSIS LEVEL-2 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP21 |  |  | PLR | Pipeline | RPT | Report | 0 | In Review | IFA | Issued for Approval |  | 16-Oct-2026 17:37:16 | 26002z1fdcc@thoresen-jutal.com | 18-Oct-2026 16:40:42 | Jumpol Sudjitjul | 26-Oct-2026 |  | Akkarapat Suntornsuttiwat | 28-Oct-2026 |  | Pornlert Wanaphattharaphan | 29-Oct-2026 |  |  |  |  | 30-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000304 | MM-ZTK-1F-IP22-PLR-DWG-9001 | IP22 PIPELINE ROUTE DRAWING FROM ZWP22 TO ZWP8 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 05-May-2026 15:12:34 | 26002z1fdcc@thoresen-jutal.com | 05-May-2026 16:29:43 | Jumpol Sudjitjul | 12-May-2026 |  | Akkarapat Suntornsuttiwat | 14-May-2026 | 08-May-2026 16:02:09 | Pornlert Wanaphattharaphan | 15-May-2026 | 20-May-2026 16:42:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-May-2026 | 20-May-2026 18:55:45 | 20-May-2026 12:16:52 | 0 |  |  | Approver | Locate
AO-000882 | MM-ZTK-1F-IP22-PLR-DWG-9001 | IP22 PIPELINE ROUTE DRAWING FROM ZWP22 TO ZWP8 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jun-2026 16:45:47 | 26002z1fdcc@thoresen-jutal.com | 23-Jun-2026 18:00:58 | Jumpol Sudjitjul | 01-Jul-2026 |  | Akkarapat Suntornsuttiwat | 03-Jul-2026 | 25-Jun-2026 10:33:48 | Pornlert Wanaphattharaphan | 06-Jul-2026 | 29-Jun-2026 01:20:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Jul-2026 | 30-Jun-2026 09:39:21 | 30-Jun-2026 03:24:59 | 0 |  |  | Approver | Locate
AO-001062 | MM-ZTK-1F-IP22-PLR-DWG-9001 | IP22 PIPELINE ROUTE DRAWING FROM ZWP22 TO ZWP8 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 16:57:00 | 26002z1fdcc@thoresen-jutal.com | 10-Jul-2026 17:54:59 | Jumpol Sudjitjul | 20-Jul-2026 |  | Akkarapat Suntornsuttiwat | 22-Jul-2026 | 13-Jul-2026 09:32:07 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 20-Jul-2026 02:51:36 | APPR | Approved | Jumpol Sudjitjul | 24-Jul-2026 | 20-Jul-2026 09:03:23 | 20-Jul-2026 03:12:12 | 0 |  |  | Approver | Locate
AO-001658 | MM-ZTK-1F-IP22-PLR-DWG-9002 | IP22 PIPELINE ALIGNMENT SHEETS: ZWP22 TO ZWP8 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 11:05:47 | 26002z1fdcc@thoresen-jutal.com | 25-Aug-2026 14:42:20 | Jumpol Sudjitjul | 01-Sep-2026 |  | Akkarapat Suntornsuttiwat | 03-Sep-2026 | 27-Aug-2026 10:00:34 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 23:33:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 15:56:43 | 31-Aug-2026 09:38:49 | 0 |  |  | Approver | Locate
AO-001900 | MM-ZTK-1F-IP22-PLR-DWG-9002 | IP22 PIPELINE ALIGNMENT SHEETS: ZWP22 TO ZWP8 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:30:51 | 26002z1fdcc@thoresen-jutal.com | 08-Sep-2026 09:34:15 | Jumpol Sudjitjul | 15-Sep-2026 |  | Akkarapat Suntornsuttiwat | 17-Sep-2026 | 08-Sep-2026 11:49:20 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 13-Sep-2026 17:24:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 23:15:32 | 13-Sep-2026 16:46:15 | 0 |  |  | Approver | Locate
AO-002241 | MM-ZTK-1F-IP22-PLR-DWG-9002 | IP22 PIPELINE ALIGNMENT SHEETS: ZWP22 TO ZWP8 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 10:54:31 | 26002z1fdcc@thoresen-jutal.com | 24-Sep-2026 13:59:02 | Jumpol Sudjitjul | 01-Oct-2026 |  | Akkarapat Suntornsuttiwat | 05-Oct-2026 | 28-Sep-2026 15:34:52 | Pornlert Wanaphattharaphan | 06-Oct-2026 | 28-Sep-2026 22:57:13 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 29-Sep-2026 14:20:30 | 29-Sep-2026 08:13:44 | 0 |  |  | Approver | Locate
AO-001666 | MM-ZTK-1F-IP22-PLR-DWG-9003 | IP22 PIPELINE SCHEMATIC DIAGRAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 11:06:12 | 26002z1fdcc@thoresen-jutal.com | 25-Aug-2026 14:32:54 | Jumpol Sudjitjul | 01-Sep-2026 |  | Akkarapat Suntornsuttiwat | 03-Sep-2026 | 27-Aug-2026 15:49:05 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 23:37:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 15:56:19 | 31-Aug-2026 09:37:28 | 0 |  |  | Approver | Locate
AO-001925 | MM-ZTK-1F-IP22-PLR-DWG-9003 | IP22 PIPELINE SCHEMATIC DIAGRAM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 08-Sep-2026 12:36:30 | 26002z1fdcc@thoresen-jutal.com | 08-Sep-2026 14:19:46 | Jumpol Sudjitjul | 15-Sep-2026 |  | Akkarapat Suntornsuttiwat | 17-Sep-2026 | 09-Sep-2026 10:50:40 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 12-Sep-2026 23:51:13 | APPR | Approved | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 08:12:59 | 13-Sep-2026 01:16:51 | 0 |  |  | Approver | Locate
AO-002267 | MM-ZTK-1F-IP22-PLR-DWG-9003 | IP22 PIPELINE SCHEMATIC DIAGRAM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 25-Sep-2026 16:17:25 | 26002z1fdcc@thoresen-jutal.com | 25-Sep-2026 16:22:48 | Jumpol Sudjitjul | 02-Oct-2026 |  | Akkarapat Suntornsuttiwat | 06-Oct-2026 | 28-Sep-2026 15:28:09 | Pornlert Wanaphattharaphan | 07-Oct-2026 | 28-Sep-2026 23:01:27 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 29-Sep-2026 14:19:59 | 29-Sep-2026 08:29:19 | 0 |  |  | Approver | Locate
AO-000917 | MM-ZTK-1F-IP22-PLR-DWG-9004 | IP22 PIPELINE PLATFORM APPROACH AT ZWP22 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 19:11:46 | 26002z1fdcc@thoresen-jutal.com | 27-Jun-2026 19:25:40 | Jumpol Sudjitjul | 06-Jul-2026 |  | Akkarapat Suntornsuttiwat | 08-Jul-2026 | 29-Jun-2026 15:11:23 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 02-Jul-2026 00:41:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 02-Jul-2026 10:22:19 | 02-Jul-2026 04:01:46 | 0 |  |  | Approver | Locate
AO-001058 | MM-ZTK-1F-IP22-PLR-DWG-9004 | IP22 PIPELINE PLATFORM APPROACH AT ZWP22 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Jul-2026 12:20:15 | 26002z1fdcc@thoresen-jutal.com | 10-Jul-2026 13:03:29 | Jumpol Sudjitjul | 17-Jul-2026 |  | Akkarapat Suntornsuttiwat | 21-Jul-2026 | 10-Jul-2026 15:18:31 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 11-Jul-2026 12:08:06 | APPR | Approved | Jumpol Sudjitjul | 23-Jul-2026 | 12-Jul-2026 11:40:57 | 12-Jul-2026 05:40:28 | 0 |  |  | Approver | Locate
AO-001264 | MM-ZTK-1F-IP22-PLR-DWG-9004 | IP22 PIPELINE PLATFORM APPROACH AT ZWP22 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 12:07:02 | 26002z1fdcc@thoresen-jutal.com | 26-Jul-2026 22:01:54 | Jumpol Sudjitjul | 05-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 27-Jul-2026 16:05:10 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 29-Jul-2026 09:08:03 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 30-Jul-2026 09:42:02 | 30-Jul-2026 03:35:19 | 0 |  |  | Approver | Locate
AO-000605 | MM-ZTK-1F-IP22-PLR-DWG-9005 | IP22 PIPELINE PLATFORM APPROACH AT ZWP8 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-May-2026 16:49:47 | 26002z1fdcc@thoresen-jutal.com | 27-May-2026 09:24:15 | Jumpol Sudjitjul | 05-Jun-2026 |  | Akkarapat Suntornsuttiwat | 09-Jun-2026 | 28-May-2026 11:34:19 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 10-Jun-2026 21:27:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Jun-2026 | 11-Jun-2026 11:15:12 | 11-Jun-2026 05:02:03 | 0 |  |  | Approver | Locate
AO-000915 | MM-ZTK-1F-IP22-PLR-DWG-9005 | IP22 PIPELINE PLATFORM APPROACH AT ZWP8 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Jun-2026 20:36:32 | 26002z1fdcc@thoresen-jutal.com | 27-Jun-2026 18:50:05 | Jumpol Sudjitjul | 06-Jul-2026 |  | Akkarapat Suntornsuttiwat | 08-Jul-2026 | 29-Jun-2026 15:12:30 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 02-Jul-2026 00:44:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 02-Jul-2026 10:21:21 | 02-Jul-2026 03:58:55 | 0 |  |  | Approver | Locate
AO-001058 | MM-ZTK-1F-IP22-PLR-DWG-9005 | IP22 PIPELINE PLATFORM APPROACH AT ZWP8 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 12:20:39 | 26002z1fdcc@thoresen-jutal.com | 10-Jul-2026 13:03:24 | Jumpol Sudjitjul | 17-Jul-2026 |  | Akkarapat Suntornsuttiwat | 21-Jul-2026 | 10-Jul-2026 15:21:36 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 11-Jul-2026 10:00:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 12-Jul-2026 11:40:27 | 12-Jul-2026 05:39:19 | 0 |  |  | Approver | Locate
AO-001264 | MM-ZTK-1F-IP22-PLR-DWG-9005 | IP22 PIPELINE PLATFORM APPROACH AT ZWP8 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 12:35:55 | 26002z1fdcc@thoresen-jutal.com | 26-Jul-2026 22:02:00 | Jumpol Sudjitjul | 05-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 27-Jul-2026 16:06:36 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 29-Jul-2026 09:43:24 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 30-Jul-2026 09:44:04 | 30-Jul-2026 03:36:38 | 0 |  |  | Approver | Locate
AO-000605 | MM-ZTK-1F-IP22-PLR-GA-9001 | RISER GA DRAWINGS AT ZWP22 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFR | Issued for Review |  | 26-May-2026 16:50:20 | 26002z1fdcc@thoresen-jutal.com | 27-May-2026 09:33:18 | Jumpol Sudjitjul | 05-Jun-2026 |  | Akkarapat Suntornsuttiwat | 09-Jun-2026 | 27-May-2026 14:01:48 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 10-Jun-2026 21:26:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Jun-2026 | 11-Jun-2026 11:16:56 | 11-Jun-2026 05:04:43 | 0 |  |  | Approver | Locate
AO-001075 | MM-ZTK-1F-IP22-PLR-GA-9001 | RISER GA DRAWINGS AT ZWP22 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:44:53 | 26002z1fdcc@thoresen-jutal.com | 12-Jul-2026 12:12:41 | Jumpol Sudjitjul | 17-Jul-2026 |  | Akkarapat Suntornsuttiwat | 21-Jul-2026 | 13-Jul-2026 10:34:18 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 20-Jul-2026 02:58:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 20-Jul-2026 09:01:26 | 20-Jul-2026 03:09:46 | 0 |  |  | Approver | Locate
AO-001375 | MM-ZTK-1F-IP22-PLR-GA-9001 | RISER GA DRAWINGS AT ZWP22 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 11:03:04 | 26002z1fdcc@thoresen-jutal.com | 03-Aug-2026 14:13:25 | Jumpol Sudjitjul | 10-Aug-2026 |  | Akkarapat Suntornsuttiwat | 13-Aug-2026 | 04-Aug-2026 10:26:18 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 22:51:07 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 14:13:28 | 17-Aug-2026 08:40:59 | 0 |  |  | Approver | Locate
AO-002463 | MM-ZTK-1F-IP22-PLR-GA-9001 | RISER GA DRAWINGS AT ZWP22 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | AFC | Approved for Construction |  | 09-Oct-2026 16:46:51 | 26002z1fdcc@thoresen-jutal.com | 09-Oct-2026 17:32:57 | Jumpol Sudjitjul | 20-Oct-2026 |  | Akkarapat Suntornsuttiwat | 22-Oct-2026 | 12-Oct-2026 10:01:31 | Pornlert Wanaphattharaphan | 26-Oct-2026 | 13-Oct-2026 14:47:20 | APPR | Approved | Jumpol Sudjitjul | 27-Oct-2026 | 14-Oct-2026 16:42:29 | 14-Oct-2026 10:05:10 | 0 |  |  | Approver | Locate
AO-001266 | MM-ZTK-1F-IP22-PLR-GA-9002 | IP22 TIE-IN SPOOL GA DRAWING AT ZWP22 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 17:08:55 | 26002z1fdcc@thoresen-jutal.com | 26-Jul-2026 23:48:20 | Jumpol Sudjitjul | 05-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 30-Jul-2026 15:09:26 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 06-Aug-2026 00:44:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 06-Aug-2026 09:38:24 | 06-Aug-2026 03:40:56 | 0 |  |  | Approver | Locate
AO-001616 | MM-ZTK-1F-IP22-PLR-GA-9002 | IP22 TIE-IN SPOOL GA DRAWING AT ZWP22 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 09:38:36 | 26002z1fdcc@thoresen-jutal.com | 20-Aug-2026 09:41:57 | Jumpol Sudjitjul | 27-Aug-2026 |  | Akkarapat Suntornsuttiwat | 31-Aug-2026 | 20-Aug-2026 11:17:25 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 22-Aug-2026 15:06:55 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 24-Aug-2026 19:37:33 | 24-Aug-2026 13:50:23 | 0 |  |  | Approver | Locate
AO-001764 | MM-ZTK-1F-IP22-PLR-GA-9002 | IP22 TIE-IN SPOOL GA DRAWING AT ZWP22 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | AFC | Approved for Construction |  | 29-Aug-2026 14:08:08 | 26002z1fdcc@thoresen-jutal.com | 29-Aug-2026 14:14:26 | Jumpol Sudjitjul | 04-Sep-2026 | 01-Sep-2026 10:35:03 | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 09:03:33 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 00:35:22 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 17:37:48 | 07-Sep-2026 11:14:07 | 0 |  |  | Approver | Locate
AO-001266 | MM-ZTK-1F-IP22-PLR-GA-9003 | IP22 TIE-IN SPOOL GA DRAWING AT ZWP8 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 17:09:20 | 26002z1fdcc@thoresen-jutal.com | 26-Jul-2026 23:48:26 | Jumpol Sudjitjul | 05-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 30-Jul-2026 15:10:44 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 06-Aug-2026 00:47:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 06-Aug-2026 09:39:02 | 06-Aug-2026 03:43:33 | 0 |  |  | Approver | Locate
AO-001616 | MM-ZTK-1F-IP22-PLR-GA-9003 | IP22 TIE-IN SPOOL GA DRAWING AT ZWP8 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 09:39:23 | 26002z1fdcc@thoresen-jutal.com | 20-Aug-2026 09:41:58 | Jumpol Sudjitjul | 27-Aug-2026 |  | Akkarapat Suntornsuttiwat | 31-Aug-2026 | 20-Aug-2026 11:17:45 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 22-Aug-2026 15:06:28 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 24-Aug-2026 19:30:14 | 24-Aug-2026 12:39:31 | 0 |  |  | Approver | Locate
AO-001764 | MM-ZTK-1F-IP22-PLR-GA-9003 | IP22 TIE-IN SPOOL GA DRAWING AT ZWP8 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | AFC | Approved for Construction |  | 29-Aug-2026 14:08:34 | 26002z1fdcc@thoresen-jutal.com | 29-Aug-2026 14:14:26 | Jumpol Sudjitjul | 04-Sep-2026 | 01-Sep-2026 10:36:17 | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 09:03:55 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 00:35:41 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 17:39:23 | 07-Sep-2026 11:18:06 | 0 |  |  | Approver | Locate
AO-001375 | MM-ZTK-1F-IP22-PLR-ISO-9001 | IP22 RISER ISOMETRIC AT ZWP22 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 11:03:32 | 26002z1fdcc@thoresen-jutal.com | 03-Aug-2026 14:14:40 | Jumpol Sudjitjul | 10-Aug-2026 |  | Akkarapat Suntornsuttiwat | 13-Aug-2026 | 04-Aug-2026 10:50:48 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 22:52:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 14:00:04 | 17-Aug-2026 07:23:53 | 0 |  |  | Approver | Locate
AO-001658 | MM-ZTK-1F-IP22-PLR-ISO-9001 | IP22 RISER ISOMETRIC AT ZWP22 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 11:06:43 | 26002z1fdcc@thoresen-jutal.com | 25-Aug-2026 14:44:54 | Jumpol Sudjitjul | 01-Sep-2026 |  | Akkarapat Suntornsuttiwat | 03-Sep-2026 | 26-Aug-2026 14:32:29 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 23:52:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 15:57:14 | 31-Aug-2026 09:40:12 | 0 |  |  | Approver | Locate
AO-001900 | MM-ZTK-1F-IP22-PLR-ISO-9001 | IP22 RISER ISOMETRIC AT ZWP22 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 10:31:27 | 26002z1fdcc@thoresen-jutal.com | 08-Sep-2026 09:19:29 | Jumpol Sudjitjul | 15-Sep-2026 |  | Akkarapat Suntornsuttiwat | 17-Sep-2026 | 08-Sep-2026 11:23:37 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 13-Sep-2026 17:20:39 | APPR | Approved | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 23:16:05 | 13-Sep-2026 16:47:21 | 0 |  |  | Approver | Locate
AO-000996 | MM-ZTK-1F-IP22-PLR-ISO-9002 | IP22 TIE-IN SPOOL ISOMETRIC AT ZWP22 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 13:30:40 | 26002z1fdcc@thoresen-jutal.com | 03-Jul-2026 14:15:38 | Jumpol Sudjitjul | 10-Jul-2026 |  | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 06-Jul-2026 14:22:47 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 22:30:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 11:11:09 | 15-Jul-2026 05:13:08 | 0 |  |  | Approver | Locate
AO-001560 | MM-ZTK-1F-IP22-PLR-ISO-9002 | IP22 TIE-IN SPOOL ISOMETRIC AT ZWP22 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:46:43 | 26002z1fdcc@thoresen-jutal.com | 17-Aug-2026 15:34:20 | Jumpol Sudjitjul | 24-Aug-2026 |  | Akkarapat Suntornsuttiwat | 26-Aug-2026 | 17-Aug-2026 16:34:59 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 17:56:07 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 19:37:06 | 24-Aug-2026 13:49:16 | 0 |  |  | Approver | Locate
AO-001763 | MM-ZTK-1F-IP22-PLR-ISO-9002 | IP22 TIE-IN SPOOL ISOMETRIC AT ZWP22 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 18:13:06 | 26002z1fdcc@thoresen-jutal.com | 29-Aug-2026 13:27:49 | Jumpol Sudjitjul | 04-Sep-2026 | 31-Aug-2026 16:32:57 | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 09:24:30 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 00:36:53 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 17:39:50 | 07-Sep-2026 11:40:24 | 0 |  |  | Approver | Locate
AO-000996 | MM-ZTK-1F-IP22-PLR-ISO-9003 | IP22 TIE-IN SPOOL ISOMETRIC AT ZWP8 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 13:31:43 | 26002z1fdcc@thoresen-jutal.com | 03-Jul-2026 14:15:32 | Jumpol Sudjitjul | 10-Jul-2026 |  | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 06-Jul-2026 14:56:57 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 22:31:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 11:16:24 | 15-Jul-2026 05:14:37 | 0 |  |  | Approver | Locate
AO-001560 | MM-ZTK-1F-IP22-PLR-ISO-9003 | IP22 TIE-IN SPOOL ISOMETRIC AT ZWP8 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:47:11 | 26002z1fdcc@thoresen-jutal.com | 17-Aug-2026 15:34:16 | Jumpol Sudjitjul | 24-Aug-2026 |  | Akkarapat Suntornsuttiwat | 26-Aug-2026 | 17-Aug-2026 16:35:22 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 17:56:50 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 19:36:41 | 24-Aug-2026 13:48:10 | 0 |  |  | Approver | Locate
AO-001763 | MM-ZTK-1F-IP22-PLR-ISO-9003 | IP22 TIE-IN SPOOL ISOMETRIC AT ZWP8 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP22 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 18:13:31 | 26002z1fdcc@thoresen-jutal.com | 29-Aug-2026 13:27:47 | Jumpol Sudjitjul | 04-Sep-2026 | 31-Aug-2026 16:32:41 | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 09:25:10 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 00:37:48 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 17:40:51 | 07-Sep-2026 11:41:31 | 0 |  |  | Approver | Locate
AO-000901 | MM-ZTK-1F-IP22-PLR-RPT-9001 | IP22 PIPELINE ROUTING STUDY AND DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP22 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 09:58:53 | 26002z1fdcc@thoresen-jutal.com | 26-Jun-2026 10:15:23 | Jumpol Sudjitjul | 03-Jul-2026 |  | Akkarapat Suntornsuttiwat | 07-Jul-2026 | 01-Jul-2026 13:33:08 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 02-Jul-2026 00:32:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 02-Jul-2026 10:20:25 | 02-Jul-2026 03:57:21 | 0 |  |  | Approver | Locate
AO-001282 | MM-ZTK-1F-IP22-PLR-RPT-9001 | IP22 PIPELINE ROUTING STUDY AND DESIGN |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP22 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 08:49:02 | 26002z1fdcc@thoresen-jutal.com | 27-Jul-2026 16:02:51 | Jumpol Sudjitjul | 05-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 30-Jul-2026 16:22:37 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 06-Aug-2026 00:57:51 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 06-Aug-2026 09:40:20 | 06-Aug-2026 03:48:55 | 0 |  |  | Approver | Locate
AO-001616 | MM-ZTK-1F-IP22-PLR-RPT-9001 | IP22 PIPELINE ROUTING STUDY AND DESIGN |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP22 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 09:40:31 | 26002z1fdcc@thoresen-jutal.com | 20-Aug-2026 09:48:59 | Jumpol Sudjitjul | 27-Aug-2026 |  | Akkarapat Suntornsuttiwat | 31-Aug-2026 | 20-Aug-2026 10:04:36 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 23-Aug-2026 23:44:23 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 24-Aug-2026 19:29:36 | 24-Aug-2026 12:38:18 | 0 |  |  | Approver | Locate
AO-001120 | MM-ZTK-1F-IP22-PLR-RPT-9002 | IP22 PIPELINE ON-BOTTOM ROUGHNESS AND IN-PLACE STRESS ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP22 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 15-Jul-2026 18:46:05 | 26002z1fdcc@thoresen-jutal.com | 15-Jul-2026 21:36:53 | Jumpol Sudjitjul | 23-Jul-2026 | 15-Jul-2026 23:21:31 | Akkarapat Suntornsuttiwat | 27-Jul-2026 | 16-Jul-2026 14:56:29 | Pornlert Wanaphattharaphan | 30-Jul-2026 | 19-Jul-2026 23:49:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Jul-2026 | 20-Jul-2026 09:00:54 | 20-Jul-2026 02:48:19 | 0 |  |  | Approver | Locate
AO-001539 | MM-ZTK-1F-IP22-PLR-RPT-9002 | IP22 PIPELINE ON-BOTTOM ROUGHNESS AND IN-PLACE STRESS ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP22 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 18:13:14 | 26002z1fdcc@thoresen-jutal.com | 15-Aug-2026 15:01:44 | Jumpol Sudjitjul | 21-Aug-2026 |  | Akkarapat Suntornsuttiwat | 25-Aug-2026 | 17-Aug-2026 10:43:46 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 23-Aug-2026 08:02:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 19:35:03 | 24-Aug-2026 14:17:51 | 0 |  |  | Approver | Locate
AO-001763 | MM-ZTK-1F-IP22-PLR-RPT-9002 | IP22 PIPELINE ON-BOTTOM ROUGHNESS AND IN-PLACE STRESS ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP22 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 18:14:08 | 26002z1fdcc@thoresen-jutal.com | 29-Aug-2026 13:29:50 | Jumpol Sudjitjul | 04-Sep-2026 |  | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 15:39:51 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 00:38:28 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 17:41:15 | 07-Sep-2026 11:42:51 | 0 |  |  | Approver | Locate
AO-001557 | MM-ZTK-1F-IP22-PLR-RPT-9003 | IP22 PIPELINE LATERAL BUCKLING ANALYSIS LEVEL 1 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP22 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 17-Aug-2026 14:47:43 | 26002z1fdcc@thoresen-jutal.com | 17-Aug-2026 15:39:49 | Jumpol Sudjitjul | 24-Aug-2026 |  | Akkarapat Suntornsuttiwat | 26-Aug-2026 | 20-Aug-2026 09:53:20 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:15:52 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 19:34:20 | 24-Aug-2026 12:41:57 | 0 |  |  | Approver | Locate
AO-001816 | MM-ZTK-1F-IP22-PLR-RPT-9003 | IP22 PIPELINE LATERAL BUCKLING ANALYSIS LEVEL 1 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP22 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 18:25:27 | 26002z1fdcc@thoresen-jutal.com | 03-Sep-2026 11:15:06 | Jumpol Sudjitjul | 10-Sep-2026 |  | Akkarapat Suntornsuttiwat | 14-Sep-2026 | 03-Sep-2026 13:35:40 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 07-Sep-2026 00:39:14 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 07-Sep-2026 17:41:39 | 07-Sep-2026 11:06:52 | 0 |  |  | Approver | Locate
AO-001667 | MM-ZTK-1F-IP22-PLR-RPT-9004 | IP22 PIPELINE WALKING ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP22 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 11:07:13 | 26002z1fdcc@thoresen-jutal.com | 25-Aug-2026 13:12:55 | Jumpol Sudjitjul | 01-Sep-2026 |  | Akkarapat Suntornsuttiwat | 03-Sep-2026 | 27-Aug-2026 10:35:29 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 23:59:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 15:57:46 | 31-Aug-2026 09:41:29 | 0 |  |  | Approver | Locate
AO-001884 | MM-ZTK-1F-IP22-PLR-RPT-9004 | IP22 PIPELINE WALKING ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP22 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 16:19:12 | 26002z1fdcc@thoresen-jutal.com | 05-Sep-2026 19:32:10 | Jumpol Sudjitjul | 14-Sep-2026 |  | Akkarapat Suntornsuttiwat | 16-Sep-2026 | 07-Sep-2026 10:05:38 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 13-Sep-2026 17:07:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 13-Sep-2026 23:16:37 | 13-Sep-2026 17:29:27 | 0 |  |  | Approver | Locate
AO-002257 | MM-ZTK-1F-IP22-PLR-RPT-9004 | IP22 PIPELINE WALKING ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP22 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 25-Sep-2026 13:29:24 | 26002z1fdcc@thoresen-jutal.com | 25-Sep-2026 14:01:34 | Jumpol Sudjitjul | 02-Oct-2026 |  | Akkarapat Suntornsuttiwat | 06-Oct-2026 | 29-Sep-2026 09:25:40 | Pornlert Wanaphattharaphan | 07-Oct-2026 | 30-Sep-2026 00:49:53 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 30-Sep-2026 13:16:38 | 30-Sep-2026 06:44:46 | 0 |  |  | Approver | Locate
AO-001282 | MM-ZTK-1F-IP22-PLR-RPT-9005 | IP22 AT ZWP22 : RISER AND TIE-IN SPOOL STRESS ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP22 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 27-Jul-2026 08:49:32 | 26002z1fdcc@thoresen-jutal.com | 27-Jul-2026 16:05:18 | Jumpol Sudjitjul | 05-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 03-Aug-2026 13:07:59 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 08-Aug-2026 07:39:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:18:02 | 08-Aug-2026 04:13:43 | 0 |  |  | Approver | Locate
AO-001667 | MM-ZTK-1F-IP22-PLR-RPT-9005 | IP22 AT ZWP22 : RISER AND TIE-IN SPOOL STRESS ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP22 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 10:04:08 | 26002z1fdcc@thoresen-jutal.com | 25-Aug-2026 13:09:49 | Jumpol Sudjitjul | 01-Sep-2026 |  | Akkarapat Suntornsuttiwat | 03-Sep-2026 | 26-Aug-2026 15:22:53 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 31-Aug-2026 00:02:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 15:58:15 | 31-Aug-2026 09:56:41 | 0 |  |  | Approver | Locate
AO-001962 | MM-ZTK-1F-IP22-PLR-RPT-9005 | IP22 AT ZWP22 : RISER AND TIE-IN SPOOL STRESS ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP22 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 09-Sep-2026 18:44:53 | 26002z1fdcc@thoresen-jutal.com | 10-Sep-2026 10:34:23 | Jumpol Sudjitjul | 17-Sep-2026 |  | Akkarapat Suntornsuttiwat | 21-Sep-2026 | 16-Sep-2026 14:15:44 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 21:01:21 | APPR | Approved | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 17:58:10 | 20-Sep-2026 11:15:09 | 0 |  |  | Approver | Locate
AO-000957 | MM-ZTK-1F-IP22-PLR-RPT-9006 | IP22 AT ZWP8 FOR RISER AND TIE-IN SPOOL STRESS ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP22 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 30-Jun-2026 12:05:30 | 26002z1fdcc@thoresen-jutal.com | 30-Jun-2026 14:16:52 | Jumpol Sudjitjul | 07-Jul-2026 |  | Akkarapat Suntornsuttiwat | 09-Jul-2026 | 07-Jul-2026 13:17:00 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 13-Jul-2026 23:24:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 14-Jul-2026 08:50:48 | 14-Jul-2026 02:34:16 | 0 |  |  | Approver | Locate
AO-001460 | MM-ZTK-1F-IP22-PLR-RPT-9006 | IP22 AT ZWP8 FOR RISER AND TIE-IN SPOOL STRESS ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP22 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 18:04:55 | 26002z1fdcc@thoresen-jutal.com | 08-Aug-2026 10:37:58 | Jumpol Sudjitjul | 17-Aug-2026 |  | Akkarapat Suntornsuttiwat | 19-Aug-2026 | 10-Aug-2026 13:08:08 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:29:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 08:40:29 | 21-Aug-2026 01:53:38 | 0 |  |  | Approver | Locate
AO-001900 | MM-ZTK-1F-IP22-PLR-RPT-9006 | IP22 AT ZWP8 FOR RISER AND TIE-IN SPOOL STRESS ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP22 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 10:32:06 | 26002z1fdcc@thoresen-jutal.com | 07-Sep-2026 17:09:48 | Jumpol Sudjitjul | 15-Sep-2026 |  | Akkarapat Suntornsuttiwat | 17-Sep-2026 | 08-Sep-2026 13:43:58 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 13-Sep-2026 17:46:32 | APPR | Approved | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 23:17:24 | 13-Sep-2026 16:49:39 | 0 |  |  | Approver | Locate
AO-001640 | MM-ZTK-1F-IP22-PLR-RPT-9009 | IP22 PIPELINE ON-BOTTOM STABILITY AND STRESS ANALYSIS (SEISMIC) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP22 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 21-Aug-2026 09:43:26 | 26002z1fdcc@thoresen-jutal.com | 21-Aug-2026 14:38:15 | Jumpol Sudjitjul | 28-Aug-2026 |  | Akkarapat Suntornsuttiwat | 01-Sep-2026 | 21-Aug-2026 16:19:58 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 22-Aug-2026 13:21:04 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 03-Sep-2026 | 24-Aug-2026 19:33:47 | 24-Aug-2026 12:49:43 | 0 |  |  | Approver | Locate
AO-001764 | MM-ZTK-1F-IP22-PLR-RPT-9009 | IP22 PIPELINE ON-BOTTOM STABILITY AND STRESS ANALYSIS (SEISMIC) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP22 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 29-Aug-2026 14:09:02 | 26002z1fdcc@thoresen-jutal.com | 29-Aug-2026 14:15:39 | Jumpol Sudjitjul | 04-Sep-2026 |  | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 13:44:06 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 00:39:43 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 17:42:30 | 07-Sep-2026 11:19:12 | 0 |  |  | Approver | Locate
AO-000414 | MM-ZTK-1F-IP23-PLR-DWG-9001 | IP23 PIPELINE ROUTE DRAWING FROM ZWP23 TO PLEM7 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 17:48:11 | 26002z1fdcc@thoresen-jutal.com | 15-May-2026 18:19:07 | Jumpol Sudjitjul | 25-May-2026 |  | Akkarapat Suntornsuttiwat | 27-May-2026 | 20-May-2026 08:28:59 | Pornlert Wanaphattharaphan | 28-May-2026 | 31-May-2026 01:37:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 31-May-2026 20:55:23 | 31-May-2026 14:21:36 | 0 |  |  | Approver | Locate
AO-000987 | MM-ZTK-1F-IP23-PLR-DWG-9001 | IP23 PIPELINE ROUTE DRAWING FROM ZWP23 TO PLEM7 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 09:49:56 | 26002z1fdcc@thoresen-jutal.com | 03-Jul-2026 14:10:37 | Jumpol Sudjitjul | 10-Jul-2026 |  | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 06-Jul-2026 15:32:32 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 22:40:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 11:07:56 | 15-Jul-2026 05:02:13 | 0 |  |  | Approver | Locate
AO-001266 | MM-ZTK-1F-IP23-PLR-DWG-9001 | IP23 PIPELINE ROUTE DRAWING FROM ZWP23 TO PLEM7 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 17:09:48 | 26002z1fdcc@thoresen-jutal.com | 26-Jul-2026 22:01:54 | Jumpol Sudjitjul | 05-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 27-Jul-2026 16:11:05 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 29-Jul-2026 09:43:38 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 30-Jul-2026 09:44:31 | 30-Jul-2026 03:54:32 | 0 |  |  | Approver | Locate
AO-001923 | MM-ZTK-1F-IP23-PLR-DWG-9002 | IP23 PIPELINE ALIGNMENT SHEETS: ZWP23 TO PLEM7 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Sep-2026 12:36:59 | 26002z1fdcc@thoresen-jutal.com | 08-Sep-2026 14:20:08 | Jumpol Sudjitjul | 15-Sep-2026 |  | Akkarapat Suntornsuttiwat | 17-Sep-2026 | 09-Sep-2026 09:39:34 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 13-Sep-2026 17:37:05 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 23:16:58 | 13-Sep-2026 16:31:10 | 0 |  |  | Approver | Locate
AO-002242 | MM-ZTK-1F-IP23-PLR-DWG-9002 | IP23 PIPELINE ALIGNMENT SHEETS: ZWP23 TO PLEM7 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 10:54:58 | 26002z1fdcc@thoresen-jutal.com | 24-Sep-2026 13:59:29 | Jumpol Sudjitjul | 01-Oct-2026 |  | Akkarapat Suntornsuttiwat | 05-Oct-2026 | 28-Sep-2026 15:37:31 | Pornlert Wanaphattharaphan | 06-Oct-2026 | 28-Sep-2026 22:57:55 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 29-Sep-2026 14:18:20 | 29-Sep-2026 08:12:19 | 0 |  |  | Approver | Locate
AO-001658 | MM-ZTK-1F-IP23-PLR-DWG-9003 | IP23 PIPELINE SCHEMATIC DIAGRAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 11:07:40 | 26002z1fdcc@thoresen-jutal.com | 25-Aug-2026 14:33:13 | Jumpol Sudjitjul | 01-Sep-2026 |  | Akkarapat Suntornsuttiwat | 03-Sep-2026 | 27-Aug-2026 15:50:14 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 31-Aug-2026 00:03:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 15:58:43 | 31-Aug-2026 09:42:44 | 0 |  |  | Approver | Locate
AO-002016 | MM-ZTK-1F-IP23-PLR-DWG-9003 | IP23 PIPELINE SCHEMATIC DIAGRAM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 11-Sep-2026 21:04:15 | 26002z1fdcc@thoresen-jutal.com | 11-Sep-2026 21:08:26 | Jumpol Sudjitjul | 21-Sep-2026 |  | Akkarapat Suntornsuttiwat | 23-Sep-2026 | 14-Sep-2026 10:52:49 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 19-Sep-2026 20:58:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Sep-2026 | 20-Sep-2026 17:59:07 | 20-Sep-2026 11:48:04 | 0 |  |  | Approver | Locate
AO-002267 | MM-ZTK-1F-IP23-PLR-DWG-9003 | IP23 PIPELINE SCHEMATIC DIAGRAM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 25-Sep-2026 16:17:56 | 26002z1fdcc@thoresen-jutal.com | 25-Sep-2026 16:23:15 | Jumpol Sudjitjul | 02-Oct-2026 |  | Akkarapat Suntornsuttiwat | 06-Oct-2026 | 28-Sep-2026 15:28:56 | Pornlert Wanaphattharaphan | 07-Oct-2026 | 28-Sep-2026 23:01:55 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 29-Sep-2026 10:46:20 | 29-Sep-2026 04:43:24 | 0 |  |  | Approver | Locate
AO-000605 | MM-ZTK-1F-IP23-PLR-DWG-9004 | IP23 PIPELINE PLATFORM APPROACH AT ZWP23 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-May-2026 16:50:47 | 26002z1fdcc@thoresen-jutal.com | 27-May-2026 09:24:52 | Jumpol Sudjitjul | 05-Jun-2026 |  | Akkarapat Suntornsuttiwat | 09-Jun-2026 | 27-May-2026 15:28:27 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 10-Jun-2026 21:26:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Jun-2026 | 11-Jun-2026 11:19:53 | 11-Jun-2026 05:06:01 | 0 |  |  | Approver | Locate
AO-000987 | MM-ZTK-1F-IP23-PLR-DWG-9004 | IP23 PIPELINE PLATFORM APPROACH AT ZWP23 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 09:50:27 | 26002z1fdcc@thoresen-jutal.com | 03-Jul-2026 14:11:15 | Jumpol Sudjitjul | 10-Jul-2026 |  | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 06-Jul-2026 15:04:46 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 22:37:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 11:18:13 | 15-Jul-2026 05:04:56 | 0 |  |  | Approver | Locate
AO-001264 | MM-ZTK-1F-IP23-PLR-DWG-9004 | IP23 PIPELINE PLATFORM APPROACH AT ZWP23 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 12:36:21 | 26002z1fdcc@thoresen-jutal.com | 26-Jul-2026 22:02:00 | Jumpol Sudjitjul | 05-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 27-Jul-2026 16:17:26 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 29-Jul-2026 09:49:52 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 30-Jul-2026 09:44:52 | 30-Jul-2026 03:37:49 | 0 |  |  | Approver | Locate
AO-000605 | MM-ZTK-1F-IP23-PLR-DWG-9005 | IP23 PIPELINE PLATFORM APPROACH AT PLEM7 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-May-2026 16:51:13 | 26002z1fdcc@thoresen-jutal.com | 27-May-2026 09:25:09 | Jumpol Sudjitjul | 05-Jun-2026 |  | Akkarapat Suntornsuttiwat | 09-Jun-2026 | 27-May-2026 15:29:36 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 10-Jun-2026 21:26:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Jun-2026 | 11-Jun-2026 11:26:14 | 11-Jun-2026 05:07:15 | 0 |  |  | Approver | Locate
AO-000987 | MM-ZTK-1F-IP23-PLR-DWG-9005 | IP23 PIPELINE PLATFORM APPROACH AT PLEM7 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 09:50:56 | 26002z1fdcc@thoresen-jutal.com | 03-Jul-2026 14:11:42 | Jumpol Sudjitjul | 10-Jul-2026 |  | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 06-Jul-2026 15:05:55 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 22:39:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 10:58:52 | 15-Jul-2026 04:11:13 | 0 |  |  | Approver | Locate
AO-001266 | MM-ZTK-1F-IP23-PLR-DWG-9005 | IP23 PIPELINE PLATFORM APPROACH AT PLEM7 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 17:10:15 | 26002z1fdcc@thoresen-jutal.com | 26-Jul-2026 22:02:00 | Jumpol Sudjitjul | 05-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 27-Jul-2026 16:15:35 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 30-Jul-2026 18:17:12 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 30-Jul-2026 19:16:13 | 30-Jul-2026 12:27:16 | 0 |  |  | Approver | Locate
AO-000915 | MM-ZTK-1F-IP23-PLR-GA-9001 | RISER GA DRAWING AT ZWP23 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 20:36:59 | 26002z1fdcc@thoresen-jutal.com | 27-Jun-2026 18:59:48 | Jumpol Sudjitjul | 06-Jul-2026 |  | Akkarapat Suntornsuttiwat | 08-Jul-2026 | 01-Jul-2026 14:31:58 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 02-Jul-2026 00:49:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 02-Jul-2026 10:17:37 | 02-Jul-2026 03:55:57 | 0 |  |  | Approver | Locate
AO-001210 | MM-ZTK-1F-IP23-PLR-GA-9001 | RISER GA DRAWING AT ZWP23 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFA | Issued for Approval |  | 21-Jul-2026 08:37:42 | 26002z1fdcc@thoresen-jutal.com | 21-Jul-2026 09:10:52 | Jumpol Sudjitjul | 30-Jul-2026 |  | Akkarapat Suntornsuttiwat | 03-Aug-2026 | 21-Jul-2026 14:05:41 | Pornlert Wanaphattharaphan | 04-Aug-2026 | 29-Jul-2026 08:34:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Aug-2026 | 30-Jul-2026 09:45:45 | 30-Jul-2026 03:55:54 | 0 |  |  | Approver | Locate
AO-001469 | MM-ZTK-1F-IP23-PLR-GA-9001 | RISER GA DRAWING AT ZWP23 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | AFC | Approved for Construction |  | 10-Aug-2026 12:03:25 | 26002z1fdcc@thoresen-jutal.com | 10-Aug-2026 15:08:40 | Jumpol Sudjitjul | 18-Aug-2026 |  | Akkarapat Suntornsuttiwat | 20-Aug-2026 | 10-Aug-2026 15:31:41 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 17:02:32 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 19:32:38 | 24-Aug-2026 13:12:46 | 0 |  |  | Approver | Locate
AO-002500 | MM-ZTK-1F-IP23-PLR-GA-9001 | RISER GA DRAWING AT ZWP23 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | AFC | Approved for Construction |  | 12-Oct-2026 17:06:56 | 26002z1fdcc@thoresen-jutal.com | 12-Oct-2026 17:16:57 | Jumpol Sudjitjul | 21-Oct-2026 |  | Akkarapat Suntornsuttiwat | 26-Oct-2026 | 14-Oct-2026 08:44:12 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:04:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 14:49:58 | 16-Oct-2026 08:14:52 | 0 |  |  | Approver | Locate
AO-001266 | MM-ZTK-1F-IP23-PLR-GA-9002 | IP23 TIE-IN SPOOL GA DRAWING AT ZWP23 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 17:10:41 | 26002z1fdcc@thoresen-jutal.com | 26-Jul-2026 23:48:21 | Jumpol Sudjitjul | 05-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 30-Jul-2026 15:11:50 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 06-Aug-2026 00:49:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 06-Aug-2026 09:38:20 | 06-Aug-2026 03:42:16 | 0 |  |  | Approver | Locate
AO-001616 | MM-ZTK-1F-IP23-PLR-GA-9002 | IP23 TIE-IN SPOOL GA DRAWING AT ZWP23 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 07:53:39 | 26002z1fdcc@thoresen-jutal.com | 20-Aug-2026 09:19:23 | Jumpol Sudjitjul | 27-Aug-2026 |  | Akkarapat Suntornsuttiwat | 31-Aug-2026 | 20-Aug-2026 11:18:30 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 22-Aug-2026 15:02:49 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 24-Aug-2026 19:32:08 | 24-Aug-2026 13:11:32 | 0 |  |  | Approver | Locate
AO-001764 | MM-ZTK-1F-IP23-PLR-GA-9002 | IP23 TIE-IN SPOOL GA DRAWING AT ZWP23 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | AFC | Approved for Construction |  | 29-Aug-2026 14:09:28 | 26002z1fdcc@thoresen-jutal.com | 29-Aug-2026 14:14:23 | Jumpol Sudjitjul | 04-Sep-2026 | 01-Sep-2026 09:02:24 | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 09:04:22 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 00:40:14 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 17:43:01 | 07-Sep-2026 11:20:21 | 0 |  |  | Approver | Locate
AO-001266 | MM-ZTK-1F-IP23-PLR-GA-9003 | IP23 TIE-IN SPOOL GA DRAWING AT PLEM7 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 17:11:05 | 26002z1fdcc@thoresen-jutal.com | 26-Jul-2026 23:48:22 | Jumpol Sudjitjul | 05-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 30-Jul-2026 15:12:38 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 06-Aug-2026 00:51:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 06-Aug-2026 09:37:54 | 06-Aug-2026 03:38:22 | 0 |  |  | Approver | Locate
AO-001616 | MM-ZTK-1F-IP23-PLR-GA-9003 | IP23 TIE-IN SPOOL GA DRAWING AT PLEM7 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | IFA | Issued for Approval |  | 20-Aug-2026 07:54:09 | 26002z1fdcc@thoresen-jutal.com | 20-Aug-2026 09:20:26 | Jumpol Sudjitjul | 27-Aug-2026 |  | Akkarapat Suntornsuttiwat | 31-Aug-2026 | 20-Aug-2026 11:18:49 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 22-Aug-2026 15:00:48 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 24-Aug-2026 19:31:38 | 24-Aug-2026 13:10:19 | 0 |  |  | Approver | Locate
AO-001764 | MM-ZTK-1F-IP23-PLR-GA-9003 | IP23 TIE-IN SPOOL GA DRAWING AT PLEM7 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | GA | General Arrangement | 0 | Submitted | AFC | Approved for Construction |  | 29-Aug-2026 14:09:55 | 26002z1fdcc@thoresen-jutal.com | 29-Aug-2026 14:14:25 | Jumpol Sudjitjul | 04-Sep-2026 | 01-Sep-2026 10:33:44 | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 09:04:40 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 00:40:37 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 17:43:34 | 07-Sep-2026 11:21:27 | 0 |  |  | Approver | Locate
AO-000605 | MM-ZTK-1F-IP23-PLR-ISO-9001 | IP23 RISER ISOMETRIC AT ZWP23 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-May-2026 16:51:49 | 26002z1fdcc@thoresen-jutal.com | 27-May-2026 09:36:12 | Jumpol Sudjitjul | 05-Jun-2026 |  | Akkarapat Suntornsuttiwat | 09-Jun-2026 | 27-May-2026 14:20:19 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 07-Jun-2026 21:15:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Jun-2026 | 07-Jun-2026 21:18:27 | 07-Jun-2026 15:01:48 | 0 |  |  | Approver | Locate
AO-001325 | MM-ZTK-1F-IP23-PLR-ISO-9001 | IP23 RISER ISOMETRIC AT ZWP23 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFA | Issued for Approval |  | 28-Jul-2026 09:15:26 | 26002z1fdcc@thoresen-jutal.com | 28-Jul-2026 20:31:29 | Jumpol Sudjitjul | 06-Aug-2026 |  | Akkarapat Suntornsuttiwat | 10-Aug-2026 | 30-Jul-2026 16:02:52 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 12-Aug-2026 09:38:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Aug-2026 | 13-Aug-2026 11:32:32 | 13-Aug-2026 05:28:38 | 0 |  |  | Approver | Locate
AO-001692 | MM-ZTK-1F-IP23-PLR-ISO-9001 | IP23 RISER ISOMETRIC AT ZWP23 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 17:16:57 | 26002z1fdcc@thoresen-jutal.com | 25-Aug-2026 14:45:19 | Jumpol Sudjitjul | 01-Sep-2026 |  | Akkarapat Suntornsuttiwat | 03-Sep-2026 | 26-Aug-2026 14:34:17 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 31-Aug-2026 00:10:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 15:59:12 | 31-Aug-2026 10:43:34 | 0 |  |  | Approver | Locate
AO-001900 | MM-ZTK-1F-IP23-PLR-ISO-9001 | IP23 RISER ISOMETRIC AT ZWP23 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 10:32:42 | 26002z1fdcc@thoresen-jutal.com | 08-Sep-2026 09:20:03 | Jumpol Sudjitjul | 15-Sep-2026 |  | Akkarapat Suntornsuttiwat | 17-Sep-2026 | 08-Sep-2026 11:25:25 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 13-Sep-2026 17:21:30 | APPR | Approved | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 23:16:29 | 13-Sep-2026 16:48:28 | 0 |  |  | Approver | Locate
AO-000996 | MM-ZTK-1F-IP23-PLR-ISO-9002 | IP23 TIE-IN SPOOL ISOMETRIC AT ZWP23 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 13:32:51 | 26002z1fdcc@thoresen-jutal.com | 03-Jul-2026 14:15:38 | Jumpol Sudjitjul | 10-Jul-2026 |  | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 06-Jul-2026 15:00:09 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 22:31:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 11:18:58 | 15-Jul-2026 05:16:01 | 0 |  |  | Approver | Locate
AO-001560 | MM-ZTK-1F-IP23-PLR-ISO-9002 | IP23 TIE-IN SPOOL ISOMETRIC AT ZWP23 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:48:24 | 26002z1fdcc@thoresen-jutal.com | 17-Aug-2026 15:34:20 | Jumpol Sudjitjul | 24-Aug-2026 |  | Akkarapat Suntornsuttiwat | 26-Aug-2026 | 17-Aug-2026 16:40:56 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 17:57:27 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 19:31:15 | 24-Aug-2026 12:40:40 | 0 |  |  | Approver | Locate
AO-001763 | MM-ZTK-1F-IP23-PLR-ISO-9002 | IP23 TIE-IN SPOOL ISOMETRIC AT ZWP23 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 18:14:34 | 26002z1fdcc@thoresen-jutal.com | 29-Aug-2026 13:27:50 | Jumpol Sudjitjul | 04-Sep-2026 | 31-Aug-2026 16:31:08 | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 09:25:55 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 00:41:12 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 17:44:06 | 07-Sep-2026 11:43:57 | 0 |  |  | Approver | Locate
AO-000996 | MM-ZTK-1F-IP23-PLR-ISO-9003 | IP23 TIE-IN SPOOL ISOMETRIC AT PLEM7 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 13:34:16 | 26002z1fdcc@thoresen-jutal.com | 03-Jul-2026 14:15:43 | Jumpol Sudjitjul | 10-Jul-2026 |  | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 06-Jul-2026 15:01:10 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 22:32:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 11:20:36 | 15-Jul-2026 05:18:56 | 0 |  |  | Approver | Locate
AO-001560 | MM-ZTK-1F-IP23-PLR-ISO-9003 | IP23 TIE-IN SPOOL ISOMETRIC AT PLEM7 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:49:00 | 26002z1fdcc@thoresen-jutal.com | 17-Aug-2026 15:34:18 | Jumpol Sudjitjul | 24-Aug-2026 |  | Akkarapat Suntornsuttiwat | 26-Aug-2026 | 17-Aug-2026 16:41:12 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 17:58:22 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 19:30:45 | 24-Aug-2026 13:09:09 | 0 |  |  | Approver | Locate
AO-001763 | MM-ZTK-1F-IP23-PLR-ISO-9003 | IP23 TIE-IN SPOOL ISOMETRIC AT PLEM7 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IP23 |  |  | PLR | Pipeline | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 18:14:59 | 26002z1fdcc@thoresen-jutal.com | 29-Aug-2026 13:27:48 | Jumpol Sudjitjul | 04-Sep-2026 | 31-Aug-2026 16:32:25 | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 09:26:34 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 00:41:34 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 17:44:31 | 07-Sep-2026 11:45:05 | 0 |  |  | Approver | Locate
AO-001282 | MM-ZTK-1F-IP23-PLR-RPT-9001 | IP23 PIPELINE ROUTING STUDY AND DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP23 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 27-Jul-2026 08:49:57 | 26002z1fdcc@thoresen-jutal.com | 27-Jul-2026 16:04:10 | Jumpol Sudjitjul | 05-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 30-Jul-2026 16:34:28 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 06-Aug-2026 01:07:15 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-Aug-2026 | 06-Aug-2026 09:39:50 | 06-Aug-2026 03:47:39 | 0 |  |  | Approver | Locate
AO-001616 | MM-ZTK-1F-IP23-PLR-RPT-9001 | IP23 PIPELINE ROUTING STUDY AND DESIGN |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP23 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 07:54:41 | 26002z1fdcc@thoresen-jutal.com | 20-Aug-2026 09:17:22 | Jumpol Sudjitjul | 27-Aug-2026 |  | Akkarapat Suntornsuttiwat | 31-Aug-2026 | 20-Aug-2026 10:05:08 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 23-Aug-2026 23:45:20 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 24-Aug-2026 19:30:06 | 24-Aug-2026 13:08:01 | 0 |  |  | Approver | Locate
AO-001362 | MM-ZTK-1F-IP23-PLR-RPT-9002 | IP23 PIPELINE ON-BOTTOM ROUGHNESS AND IN-PLACE STRESS ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP23 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 31-Jul-2026 18:15:58 | 26002z1fdcc@thoresen-jutal.com | 31-Jul-2026 21:40:30 | Jumpol Sudjitjul | 10-Aug-2026 |  | Akkarapat Suntornsuttiwat | 13-Aug-2026 | 03-Aug-2026 13:33:22 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 22:43:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 17:05:56 | 17-Aug-2026 11:00:31 | 0 |  |  | Approver | Locate
AO-001648 | MM-ZTK-1F-IP23-PLR-RPT-9002 | IP23 PIPELINE ON-BOTTOM ROUGHNESS AND IN-PLACE STRESS ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP23 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 21-Aug-2026 13:59:29 | 26002z1fdcc@thoresen-jutal.com | 21-Aug-2026 14:38:32 | Jumpol Sudjitjul | 28-Aug-2026 |  | Akkarapat Suntornsuttiwat | 01-Sep-2026 | 25-Aug-2026 11:00:04 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 30-Aug-2026 00:05:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Sep-2026 | 30-Aug-2026 17:00:33 | 30-Aug-2026 11:28:09 | 0 |  |  | Approver | Locate
AO-002002 | MM-ZTK-1F-IP23-PLR-RPT-9002 | IP23 PIPELINE ON-BOTTOM ROUGHNESS AND IN-PLACE STRESS ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP23 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 12:48:20 | 26002z1fdcc@thoresen-jutal.com | 11-Sep-2026 19:22:11 | Jumpol Sudjitjul | 21-Sep-2026 |  | Akkarapat Suntornsuttiwat | 23-Sep-2026 | 14-Sep-2026 11:24:22 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 19-Sep-2026 20:35:04 | APPR | Approved | Jumpol Sudjitjul | 25-Sep-2026 | 20-Sep-2026 17:59:49 | 20-Sep-2026 11:16:23 | 0 |  |  | Approver | Locate
AO-001558 | MM-ZTK-1F-IP23-PLR-RPT-9003 | IP23 PIPELINE LATERAL BUCKLING ANALYSIS LEVEL 1 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP23 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 17-Aug-2026 14:49:35 | 26002z1fdcc@thoresen-jutal.com | 17-Aug-2026 15:40:06 | Jumpol Sudjitjul | 24-Aug-2026 |  | Akkarapat Suntornsuttiwat | 26-Aug-2026 | 20-Aug-2026 09:54:26 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:16:39 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 19:29:33 | 24-Aug-2026 13:06:47 | 0 |  |  | Approver | Locate
AO-001816 | MM-ZTK-1F-IP23-PLR-RPT-9003 | IP23 PIPELINE LATERAL BUCKLING ANALYSIS LEVEL 1 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP23 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 02-Sep-2026 18:26:01 | 26002z1fdcc@thoresen-jutal.com | 03-Sep-2026 11:15:28 | Jumpol Sudjitjul | 10-Sep-2026 |  | Akkarapat Suntornsuttiwat | 14-Sep-2026 | 03-Sep-2026 13:36:25 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 07-Sep-2026 00:42:49 | APPR | Approved | Jumpol Sudjitjul | 16-Sep-2026 | 07-Sep-2026 17:45:00 | 07-Sep-2026 11:08:01 | 0 |  |  | Approver | Locate
AO-001884 | MM-ZTK-1F-IP23-PLR-RPT-9004 | IP23 PIPELINE WALKING ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP23 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 04-Sep-2026 16:19:40 | 26002z1fdcc@thoresen-jutal.com | 05-Sep-2026 19:32:47 | Jumpol Sudjitjul | 14-Sep-2026 |  | Akkarapat Suntornsuttiwat | 16-Sep-2026 | 07-Sep-2026 10:03:25 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 13-Sep-2026 17:06:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 13-Sep-2026 23:16:01 | 13-Sep-2026 17:27:59 | 0 |  |  | Approver | Locate
AO-002155 | MM-ZTK-1F-IP23-PLR-RPT-9004 | IP23 PIPELINE WALKING ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP23 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 18-Sep-2026 17:29:00 | 26002z1fdcc@thoresen-jutal.com | 18-Sep-2026 17:48:42 | Jumpol Sudjitjul | 28-Sep-2026 |  | Akkarapat Suntornsuttiwat | 30-Sep-2026 | 23-Sep-2026 15:02:40 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 26-Sep-2026 05:46:28 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 26-Sep-2026 14:23:55 | 26-Sep-2026 07:59:43 | 0 |  |  | Approver | Locate
AO-002411 | MM-ZTK-1F-IP23-PLR-RPT-9004 | IP23 PIPELINE WALKING ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP23 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 07-Oct-2026 17:13:10 | 26002z1fdcc@thoresen-jutal.com | 08-Oct-2026 10:37:18 | Jumpol Sudjitjul | 16-Oct-2026 |  | Akkarapat Suntornsuttiwat | 20-Oct-2026 | 09-Oct-2026 11:26:59 | Pornlert Wanaphattharaphan | 21-Oct-2026 | 11-Oct-2026 00:32:24 | APPR | Approved | Jumpol Sudjitjul | 22-Oct-2026 | 11-Oct-2026 10:02:19 | 11-Oct-2026 03:20:54 | 0 |  |  | Approver | Locate
AO-001076 | MM-ZTK-1F-IP23-PLR-RPT-9005 | IP23 AT ZWP23 FOR RISER AND TIE-IN SPOOL STRESS ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP23 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 12-Jul-2026 11:45:21 | 26002z1fdcc@thoresen-jutal.com | 12-Jul-2026 12:12:10 | Jumpol Sudjitjul | 17-Jul-2026 |  | Akkarapat Suntornsuttiwat | 21-Jul-2026 | 13-Jul-2026 15:59:13 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 20-Jul-2026 02:59:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 20-Jul-2026 09:00:21 | 20-Jul-2026 03:08:26 | 0 |  |  | Approver | Locate
AO-001648 | MM-ZTK-1F-IP23-PLR-RPT-9005 | IP23 AT ZWP23 FOR RISER AND TIE-IN SPOOL STRESS ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP23 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 21-Aug-2026 14:00:13 | 26002z1fdcc@thoresen-jutal.com | 21-Aug-2026 14:38:48 | Jumpol Sudjitjul | 28-Aug-2026 |  | Akkarapat Suntornsuttiwat | 01-Sep-2026 | 24-Aug-2026 16:42:44 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 30-Aug-2026 00:02:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Sep-2026 | 30-Aug-2026 17:02:09 | 30-Aug-2026 11:54:16 | 0 |  |  | Approver | Locate
AO-002130 | MM-ZTK-1F-IP23-PLR-RPT-9005 | IP23 AT ZWP23 FOR RISER AND TIE-IN SPOOL STRESS ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP23 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 17-Sep-2026 13:36:24 | 26002z1fdcc@thoresen-jutal.com | 17-Sep-2026 14:46:10 | Jumpol Sudjitjul | 24-Sep-2026 |  | Akkarapat Suntornsuttiwat | 28-Sep-2026 | 24-Sep-2026 10:10:07 | Pornlert Wanaphattharaphan | 29-Sep-2026 | 26-Sep-2026 05:52:27 | APPR | Approved | Jumpol Sudjitjul | 30-Sep-2026 | 26-Sep-2026 14:24:21 | 26-Sep-2026 08:03:20 | 0 |  |  | Approver | Locate
AO-001375 | MM-ZTK-1F-IP23-PLR-RPT-9006 | IP23 AT PLEM7 : TIE-IN SPOOL STRESS ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP23 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 11:03:57 | 26002z1fdcc@thoresen-jutal.com | 03-Aug-2026 14:08:53 | Jumpol Sudjitjul | 10-Aug-2026 |  | Akkarapat Suntornsuttiwat | 13-Aug-2026 | 04-Aug-2026 14:13:09 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 22:55:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 14:15:28 | 17-Aug-2026 08:42:28 | 0 |  |  | Approver | Locate
AO-001640 | MM-ZTK-1F-IP23-PLR-RPT-9006 | IP23 AT PLEM7 : TIE-IN SPOOL STRESS ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP23 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 21-Aug-2026 09:44:06 | 26002z1fdcc@thoresen-jutal.com | 21-Aug-2026 10:47:46 | Jumpol Sudjitjul | 28-Aug-2026 |  | Akkarapat Suntornsuttiwat | 01-Sep-2026 | 24-Aug-2026 16:44:27 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 30-Aug-2026 00:03:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Sep-2026 | 30-Aug-2026 17:02:55 | 30-Aug-2026 11:32:27 | 0 |  |  | Approver | Locate
AO-002206 | MM-ZTK-1F-IP23-PLR-RPT-9006 | IP23 AT PLEM7 : TIE-IN SPOOL STRESS ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP23 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 22-Sep-2026 11:59:39 | 26002z1fdcc@thoresen-jutal.com | 22-Sep-2026 16:01:31 | Jumpol Sudjitjul | 29-Sep-2026 |  | Akkarapat Suntornsuttiwat | 01-Oct-2026 | 24-Sep-2026 10:09:04 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 26-Sep-2026 05:30:57 | APPR | Approved | Jumpol Sudjitjul | 05-Oct-2026 | 26-Sep-2026 14:07:16 | 26-Sep-2026 07:48:37 | 0 |  |  | Approver | Locate
AO-001586 | MM-ZTK-1F-IP23-PLR-RPT-9009 | IP23 PIPELINE ON-BOTTOM STABILITY AND STRESS ANALYSIS (SEISMIC) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP23 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 18-Aug-2026 10:57:49 | 26002z1fdcc@thoresen-jutal.com | 18-Aug-2026 12:42:11 | Jumpol Sudjitjul | 25-Aug-2026 |  | Akkarapat Suntornsuttiwat | 27-Aug-2026 | 21-Aug-2026 16:21:50 | Pornlert Wanaphattharaphan | 28-Aug-2026 | 23-Aug-2026 23:35:36 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 31-Aug-2026 | 24-Aug-2026 19:29:05 | 24-Aug-2026 13:05:20 | 0 |  |  | Approver | Locate
AO-001840 | MM-ZTK-1F-IP23-PLR-RPT-9009 | IP23 PIPELINE ON-BOTTOM STABILITY AND STRESS ANALYSIS (SEISMIC) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IP23 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 16:50:53 | 26002z1fdcc@thoresen-jutal.com | 04-Sep-2026 08:08:32 | Jumpol Sudjitjul | 11-Sep-2026 |  | Akkarapat Suntornsuttiwat | 15-Sep-2026 | 04-Sep-2026 14:09:45 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 07-Sep-2026 00:43:38 | APPR | Approved | Jumpol Sudjitjul | 17-Sep-2026 | 07-Sep-2026 17:45:36 | 07-Sep-2026 11:24:59 | 0 |  |  | Approver | Locate
AO-002267 | MM-ZTK-1F-IP23-PLR-RPT-9010 | IP23 PIPELINE LATERAL BUCKLING ANALYSIS LEVEL-2 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IP23 |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 16:18:31 | 26002z1fdcc@thoresen-jutal.com | 25-Sep-2026 17:27:26 | Jumpol Sudjitjul | 05-Oct-2026 |  | Akkarapat Suntornsuttiwat | 07-Oct-2026 | 01-Oct-2026 10:43:54 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 01-Oct-2026 23:16:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 02-Oct-2026 13:25:23 | 02-Oct-2026 07:21:22 | 0 |  |  | Approver | Locate
AO-002537 | MM-ZTK-1F-IP23-PLR-RPT-9010 | IP23 PIPELINE LATERAL BUCKLING ANALYSIS LEVEL-2 |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IP23 |  |  | PLR | Pipeline | RPT | Report | 0 | In Review | IFA | Issued for Approval |  | 15-Oct-2026 18:06:13 | 26002z1fdcc@thoresen-jutal.com | 16-Oct-2026 15:49:29 | Jumpol Sudjitjul | 26-Oct-2026 |  | Akkarapat Suntornsuttiwat | 28-Oct-2026 |  | Pornlert Wanaphattharaphan | 29-Oct-2026 |  |  |  |  | 30-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000272 | MM-ZTK-1F-IPX-PLR-BOD-9001 | PIPELINE AND RISER DESIGN BASIS AND DESIGN CRITERIA |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | BOD | Basis of Design | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 19:02:47 | kanokon.i@mermaid-group.com | 30-Apr-2026 10:21:38 | Jumpol Sudjitjul | 11-May-2026 | 30-Apr-2026 12:39:54 | Akkarapat Suntornsuttiwat | 13-May-2026 | 11-May-2026 08:35:56 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:13:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 14:59:36 | 19-May-2026 15:51:20 | 0 |  |  | Approver | Locate
AO-000836 | MM-ZTK-1F-IPX-PLR-BOD-9001 | PIPELINE AND RISER DESIGN BASIS AND DESIGN CRITERIA |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | BOD | Basis of Design | 0 | Submitted | IFA | Issued for Approval |  | 19-Jun-2026 16:41:03 | 26002z1fdcc@thoresen-jutal.com | 19-Jun-2026 16:52:26 | Jumpol Sudjitjul | 26-Jun-2026 |  | Akkarapat Suntornsuttiwat | 30-Jun-2026 | 25-Jun-2026 13:11:28 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 28-Jun-2026 23:21:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 30-Jun-2026 09:38:08 | 30-Jun-2026 04:06:10 | 0 |  |  | Approver | Locate
AO-001196 | MM-ZTK-1F-IPX-PLR-BOD-9001 | PIPELINE AND RISER DESIGN BASIS AND DESIGN CRITERIA |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 12:12:38 | 26002z1fdcc@thoresen-jutal.com | 20-Jul-2026 15:05:25 | Jumpol Sudjitjul | 27-Jul-2026 |  | Akkarapat Suntornsuttiwat | 31-Jul-2026 | 21-Jul-2026 13:10:12 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 12:26:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:59:36 | 27-Jul-2026 08:57:39 | 0 |  |  | Approver | Locate
AO-001759 | MM-ZTK-1F-IPX-PLR-BOD-9001 | PIPELINE AND RISER DESIGN BASIS AND DESIGN CRITERIA |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 16:52:27 | 26002z1fdcc@thoresen-jutal.com | 28-Aug-2026 17:51:16 | Jumpol Sudjitjul | 07-Sep-2026 |  | Akkarapat Suntornsuttiwat | 09-Sep-2026 | 03-Sep-2026 10:33:00 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 07-Sep-2026 00:44:53 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 07-Sep-2026 17:46:49 | 07-Sep-2026 11:34:27 | 0 |  |  | Approver | Locate
AO-000273 | MM-ZTK-1F-IPX-PLR-BOD-9002 | SEISMIC CONSIDERATION FOR SUBSEA PIPELINE IN SEISMIC HAZARDOUS AREA |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | BOD | Basis of Design | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 19:03:14 | kanokon.i@mermaid-group.com | 30-Apr-2026 10:21:53 | Jumpol Sudjitjul | 11-May-2026 | 30-Apr-2026 12:42:54 | Akkarapat Suntornsuttiwat | 13-May-2026 | 11-May-2026 08:37:00 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:14:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 14:35:51 | 19-May-2026 08:01:09 | 0 |  |  | Approver | Locate
AO-000941 | MM-ZTK-1F-IPX-PLR-BOD-9002 | SEISMIC CONSIDERATION FOR SUBSEA PIPELINE IN SEISMIC HAZARDOUS AREA |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | BOD | Basis of Design | 0 | Submitted | IFA | Issued for Approval |  | 29-Jun-2026 22:07:17 | 26002z1fdcc@thoresen-jutal.com | 30-Jun-2026 11:07:42 | Jumpol Sudjitjul | 07-Jul-2026 |  | Akkarapat Suntornsuttiwat | 09-Jul-2026 | 01-Jul-2026 15:50:24 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 02-Jul-2026 00:52:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 02-Jul-2026 10:11:48 | 02-Jul-2026 03:39:15 | 0 |  |  | Approver | Locate
AO-001226 | MM-ZTK-1F-IPX-PLR-BOD-9002 | SEISMIC CONSIDERATION FOR SUBSEA PIPELINE IN SEISMIC HAZARDOUS AREA |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 23-Jul-2026 09:33:12 | 26002z1fdcc@thoresen-jutal.com | 23-Jul-2026 10:06:29 | Jumpol Sudjitjul | 03-Aug-2026 |  | Akkarapat Suntornsuttiwat | 05-Aug-2026 | 23-Jul-2026 14:32:32 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 29-Jul-2026 09:03:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 30-Jul-2026 09:37:03 | 30-Jul-2026 03:44:21 | 0 |  |  | Approver | Locate
AO-001840 | MM-ZTK-1F-IPX-PLR-BOD-9002 | SEISMIC CONSIDERATION FOR SUBSEA PIPELINE IN SEISMIC HAZARDOUS AREA |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 15:19:40 | 26002z1fdcc@thoresen-jutal.com | 04-Sep-2026 11:42:08 | Jumpol Sudjitjul | 11-Sep-2026 |  | Akkarapat Suntornsuttiwat | 15-Sep-2026 | 04-Sep-2026 15:19:03 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 07-Sep-2026 00:45:27 | APPR | Approved | Jumpol Sudjitjul | 17-Sep-2026 | 07-Sep-2026 17:38:12 | 07-Sep-2026 11:39:16 | 0 |  |  | Approver | Locate
AO-000915 | MM-ZTK-1F-IPX-PLR-DWG-9000 | PIPELINE DRAWING INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 20:37:23 | 26002z1fdcc@thoresen-jutal.com | 27-Jun-2026 19:26:49 | Jumpol Sudjitjul | 06-Jul-2026 |  | Akkarapat Suntornsuttiwat | 08-Jul-2026 | 29-Jun-2026 17:04:35 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 01-Jul-2026 22:17:19 | APPR | Approved | Jumpol Sudjitjul | 10-Jul-2026 | 02-Jul-2026 10:10:27 | 02-Jul-2026 03:49:42 | 0 |  |  | Approver | Locate
AO-001158 | MM-ZTK-1F-IPX-PLR-DWG-9000 | PIPELINE DRAWING INDEX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Jul-2026 20:47:08 | 26002z1fdcc@thoresen-jutal.com | 17-Jul-2026 22:17:55 | Jumpol Sudjitjul | 27-Jul-2026 |  | Akkarapat Suntornsuttiwat | 31-Jul-2026 | 20-Jul-2026 08:55:21 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 11:17:44 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 14:58:47 | 27-Jul-2026 08:56:07 | 0 |  |  | Approver | Locate
AO-001469 | MM-ZTK-1F-IPX-PLR-DWG-9000 | PIPELINE DRAWING INDEX |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Aug-2026 12:03:58 | 26002z1fdcc@thoresen-jutal.com | 10-Aug-2026 15:04:49 | Jumpol Sudjitjul | 18-Aug-2026 |  | Akkarapat Suntornsuttiwat | 20-Aug-2026 | 10-Aug-2026 15:25:11 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 17:01:25 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 19:28:35 | 24-Aug-2026 13:03:56 | 0 |  |  | Approver | Locate
AO-000915 | MM-ZTK-1F-IPX-PLR-DWG-9001 | OVERALL FIELD LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 20:37:48 | 26002z1fdcc@thoresen-jutal.com | 27-Jun-2026 18:52:13 | Jumpol Sudjitjul | 06-Jul-2026 |  | Akkarapat Suntornsuttiwat | 08-Jul-2026 | 30-Jun-2026 11:36:13 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 02-Jul-2026 00:53:11 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 10-Jul-2026 | 02-Jul-2026 10:11:17 | 02-Jul-2026 03:53:17 | 0 |  |  | Approver | Locate
AO-001159 | MM-ZTK-1F-IPX-PLR-DWG-9001 | OVERALL FIELD LAYOUT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 20:47:32 | 26002z1fdcc@thoresen-jutal.com | 17-Jul-2026 22:18:19 | Jumpol Sudjitjul | 27-Jul-2026 |  | Akkarapat Suntornsuttiwat | 31-Jul-2026 | 20-Jul-2026 09:02:55 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 11:28:08 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 15:01:19 | 27-Jul-2026 10:07:08 | 0 |  |  | Approver | Locate
AO-000524 | MM-ZTK-1F-IPX-PLR-DWG-9002 | PIPELINE FIELD JOINT COATING DETAILS DRAWING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 12:49:07 | 26002z1fdcc@thoresen-jutal.com | 20-May-2026 16:06:56 | Jumpol Sudjitjul | 27-May-2026 |  | Akkarapat Suntornsuttiwat | 29-May-2026 | 29-May-2026 08:15:35 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 09-Jun-2026 00:12:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Jun-2026 | 09-Jun-2026 07:51:04 | 09-Jun-2026 01:20:19 | 0 |  |  | Approver | Locate
AO-000915 | MM-ZTK-1F-IPX-PLR-DWG-9002 | PIPELINE FIELD JOINT COATING DETAILS DRAWING |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Jun-2026 20:38:14 | 26002z1fdcc@thoresen-jutal.com | 27-Jun-2026 18:50:07 | Jumpol Sudjitjul | 06-Jul-2026 |  | Akkarapat Suntornsuttiwat | 08-Jul-2026 | 03-Jul-2026 13:10:04 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 04-Jul-2026 21:04:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 05-Jul-2026 10:40:08 | 05-Jul-2026 04:14:25 | 0 |  |  | Approver | Locate
AO-001469 | MM-ZTK-1F-IPX-PLR-DWG-9002 | PIPELINE FIELD JOINT COATING DETAILS DRAWING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Aug-2026 12:04:29 | 26002z1fdcc@thoresen-jutal.com | 10-Aug-2026 15:05:19 | Jumpol Sudjitjul | 18-Aug-2026 |  | Akkarapat Suntornsuttiwat | 20-Aug-2026 | 10-Aug-2026 15:28:14 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 17:01:57 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 19:28:12 | 24-Aug-2026 13:02:47 | 0 |  |  | Approver | Locate
AO-000605 | MM-ZTK-1F-IPX-PLR-DWG-9003 | PIPELINE BODY DETAILS DRAWING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-May-2026 16:52:17 | 26002z1fdcc@thoresen-jutal.com | 27-May-2026 10:11:22 | Jumpol Sudjitjul | 05-Jun-2026 |  | Akkarapat Suntornsuttiwat | 09-Jun-2026 | 28-May-2026 15:14:21 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 10-Jun-2026 21:27:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Jun-2026 | 11-Jun-2026 11:27:48 | 11-Jun-2026 05:08:32 | 0 |  |  | Approver | Locate
AO-000892 | MM-ZTK-1F-IPX-PLR-DWG-9003 | PIPELINE BODY DETAILS DRAWING |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 14:28:21 | 26002z1fdcc@thoresen-jutal.com | 25-Jun-2026 15:12:42 | Jumpol Sudjitjul | 02-Jul-2026 |  | Akkarapat Suntornsuttiwat | 06-Jul-2026 | 26-Jun-2026 14:12:00 | Pornlert Wanaphattharaphan | 07-Jul-2026 | 29-Jun-2026 01:23:36 | APPR | Approved | Jumpol Sudjitjul | 08-Jul-2026 | 30-Jun-2026 09:36:25 | 30-Jun-2026 03:16:44 | 0 |  |  | Approver | Locate
AO-001037 | MM-ZTK-1F-IPX-PLR-DWG-9003 | PIPELINE BODY DETAILS DRAWING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 08-Jul-2026 17:27:39 | 26002z1fdcc@thoresen-jutal.com | 09-Jul-2026 10:29:37 | Jumpol Sudjitjul | 16-Jul-2026 |  | Akkarapat Suntornsuttiwat | 20-Jul-2026 | 09-Jul-2026 15:28:15 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 20-Jul-2026 03:00:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jul-2026 | 20-Jul-2026 08:59:26 | 20-Jul-2026 02:46:59 | 0 |  |  | Approver | Locate
AO-001375 | MM-ZTK-1F-IPX-PLR-DWG-9003 | PIPELINE BODY DETAILS DRAWING |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 11:04:24 | 26002z1fdcc@thoresen-jutal.com | 03-Aug-2026 14:11:10 | Jumpol Sudjitjul | 10-Aug-2026 |  | Akkarapat Suntornsuttiwat | 13-Aug-2026 | 03-Aug-2026 16:28:15 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 22:48:19 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 14:09:18 | 17-Aug-2026 08:35:30 | 0 |  |  | Approver | Locate
AO-000605 | MM-ZTK-1F-IPX-PLR-DWG-9004 | PIPELINE HOT INDUCTION BEND DETAILS DRAWING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-May-2026 16:52:43 | 26002z1fdcc@thoresen-jutal.com | 27-May-2026 10:11:42 | Jumpol Sudjitjul | 05-Jun-2026 |  | Akkarapat Suntornsuttiwat | 09-Jun-2026 | 28-May-2026 15:15:35 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 10-Jun-2026 21:27:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Jun-2026 | 11-Jun-2026 11:29:01 | 11-Jun-2026 05:09:52 | 0 |  |  | Approver | Locate
AO-000880 | MM-ZTK-1F-IPX-PLR-DWG-9004 | PIPELINE HOT INDUCTION BEND DETAILS DRAWING |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jun-2026 16:46:15 | 26002z1fdcc@thoresen-jutal.com | 23-Jun-2026 17:45:38 | Jumpol Sudjitjul | 01-Jul-2026 |  | Akkarapat Suntornsuttiwat | 03-Jul-2026 | 25-Jun-2026 10:26:51 | Pornlert Wanaphattharaphan | 06-Jul-2026 | 29-Jun-2026 01:19:49 | APPR | Approved | Jumpol Sudjitjul | 07-Jul-2026 | 30-Jun-2026 09:35:06 | 30-Jun-2026 03:14:26 | 0 |  |  | Approver | Locate
AO-001037 | MM-ZTK-1F-IPX-PLR-DWG-9004 | PIPELINE HOT INDUCTION BEND DETAILS DRAWING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 08-Jul-2026 17:28:14 | 26002z1fdcc@thoresen-jutal.com | 09-Jul-2026 10:30:01 | Jumpol Sudjitjul | 16-Jul-2026 |  | Akkarapat Suntornsuttiwat | 20-Jul-2026 | 09-Jul-2026 15:42:48 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 20-Jul-2026 02:57:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jul-2026 | 20-Jul-2026 08:58:51 | 20-Jul-2026 02:45:43 | 0 |  |  | Approver | Locate
AO-001324 | MM-ZTK-1F-IPX-PLR-DWG-9004 | PIPELINE HOT INDUCTION BEND DETAILS DRAWING |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Jul-2026 09:15:55 | 26002z1fdcc@thoresen-jutal.com | 28-Jul-2026 20:32:56 | Jumpol Sudjitjul | 06-Aug-2026 |  | Akkarapat Suntornsuttiwat | 10-Aug-2026 | 30-Jul-2026 15:28:02 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 12-Aug-2026 09:15:59 | APPR | Approved | Jumpol Sudjitjul | 13-Aug-2026 | 13-Aug-2026 11:34:02 | 13-Aug-2026 05:29:45 | 0 |  |  | Approver | Locate
AO-000605 | MM-ZTK-1F-IPX-PLR-DWG-9005 | PIPELINE ANODE DETAILS DRAWING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 26-May-2026 16:53:10 | 26002z1fdcc@thoresen-jutal.com | 27-May-2026 09:31:00 | Jumpol Sudjitjul | 05-Jun-2026 | 02-Jun-2026 16:22:45 | Akkarapat Suntornsuttiwat | 09-Jun-2026 | 11-Jun-2026 08:43:22 | Pornlert Wanaphattharaphan | 10-Jun-2026 | 11-Jun-2026 15:43:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Jun-2026 | 11-Jun-2026 16:15:03 | 11-Jun-2026 09:33:19 | 0 |  |  | Approver | Locate
AO-000987 | MM-ZTK-1F-IPX-PLR-DWG-9005 | PIPELINE ANODE DETAILS DRAWING |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 09:51:25 | 26002z1fdcc@thoresen-jutal.com | 03-Jul-2026 14:12:06 | Jumpol Sudjitjul | 10-Jul-2026 |  | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 06-Jul-2026 16:06:27 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 22:41:01 | APPR | Approved | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 10:59:28 | 15-Jul-2026 04:12:21 | 0 |  |  | Approver | Locate
AO-001264 | MM-ZTK-1F-IPX-PLR-DWG-9005 | PIPELINE ANODE DETAILS DRAWING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 12:07:28 | 26002z1fdcc@thoresen-jutal.com | 26-Jul-2026 22:02:00 | Jumpol Sudjitjul | 05-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 27-Jul-2026 16:26:19 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 29-Jul-2026 09:37:59 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 30-Jul-2026 09:46:16 | 30-Jul-2026 03:39:05 | 0 |  |  | Approver | Locate
AO-001568 | MM-ZTK-1F-IPX-PLR-DWG-9006 | RISER HANGER FLANGE DRAWING (NPS18) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 17-Aug-2026 17:18:35 | 26002z1fdcc@thoresen-jutal.com | 18-Aug-2026 09:13:20 | Jumpol Sudjitjul | 25-Aug-2026 |  | Akkarapat Suntornsuttiwat | 27-Aug-2026 | 19-Aug-2026 14:58:17 | Pornlert Wanaphattharaphan | 28-Aug-2026 | 23-Aug-2026 23:31:57 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 31-Aug-2026 | 24-Aug-2026 19:27:40 | 24-Aug-2026 12:48:28 | 0 |  |  | Approver | Locate
AO-001763 | MM-ZTK-1F-IPX-PLR-DWG-9006 | RISER HANGER FLANGE DRAWING (NPS18) |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 18:15:26 | 26002z1fdcc@thoresen-jutal.com | 29-Aug-2026 13:28:27 | Jumpol Sudjitjul | 04-Sep-2026 |  | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 09:33:47 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 00:45:48 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 17:50:54 | 07-Sep-2026 11:47:17 | 0 |  |  | Approver | Locate
AO-002463 | MM-ZTK-1F-IPX-PLR-DWG-9006 | RISER HANGER FLANGE DRAWING (NPS18) |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 09-Oct-2026 16:47:19 | 26002z1fdcc@thoresen-jutal.com | 09-Oct-2026 17:36:33 | Jumpol Sudjitjul | 20-Oct-2026 |  | Akkarapat Suntornsuttiwat | 22-Oct-2026 | 12-Oct-2026 10:52:59 | Pornlert Wanaphattharaphan | 26-Oct-2026 | 13-Oct-2026 14:48:36 | APPR | Approved | Jumpol Sudjitjul | 27-Oct-2026 | 14-Oct-2026 16:43:13 | 14-Oct-2026 10:08:09 | 0 |  |  | Approver | Locate
AO-001568 | MM-ZTK-1F-IPX-PLR-DWG-9007 | RISER HANGER FLANGE DRAWING (NPS10) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 17-Aug-2026 17:19:02 | 26002z1fdcc@thoresen-jutal.com | 18-Aug-2026 09:14:09 | Jumpol Sudjitjul | 25-Aug-2026 |  | Akkarapat Suntornsuttiwat | 27-Aug-2026 | 19-Aug-2026 14:59:35 | Pornlert Wanaphattharaphan | 28-Aug-2026 | 23-Aug-2026 23:32:56 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 31-Aug-2026 | 24-Aug-2026 19:26:56 | 24-Aug-2026 12:47:21 | 0 |  |  | Approver | Locate
AO-001763 | MM-ZTK-1F-IPX-PLR-DWG-9007 | RISER HANGER FLANGE DRAWING (NPS10) |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 18:15:52 | 26002z1fdcc@thoresen-jutal.com | 29-Aug-2026 13:28:48 | Jumpol Sudjitjul | 04-Sep-2026 |  | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 09:34:49 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 00:46:09 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 17:49:32 | 07-Sep-2026 11:46:11 | 0 |  |  | Approver | Locate
AO-002463 | MM-ZTK-1F-IPX-PLR-DWG-9007 | RISER HANGER FLANGE DRAWING (NPS10) |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 09-Oct-2026 16:48:09 | 26002z1fdcc@thoresen-jutal.com | 09-Oct-2026 17:36:50 | Jumpol Sudjitjul | 20-Oct-2026 |  | Akkarapat Suntornsuttiwat | 22-Oct-2026 | 12-Oct-2026 10:53:40 | Pornlert Wanaphattharaphan | 26-Oct-2026 | 13-Oct-2026 14:49:45 | APPR | Approved | Jumpol Sudjitjul | 27-Oct-2026 | 14-Oct-2026 16:44:16 | 14-Oct-2026 10:09:39 | 0 |  |  | Approver | Locate
AO-002016 | MM-ZTK-1F-IPX-PLR-DWG-9008 | FLANGE PROTECTOR DETAILS DRAWING (NPS18) |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Sep-2026 21:04:56 | 26002z1fdcc@thoresen-jutal.com | 11-Sep-2026 21:11:13 | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 21:55:09 | Akkarapat Suntornsuttiwat | 23-Sep-2026 | 28-Sep-2026 15:20:40 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 28-Sep-2026 21:55:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Sep-2026 | 29-Sep-2026 14:17:50 | 29-Sep-2026 07:42:47 | 0 |  |  | Approver | Locate
AO-002468 | MM-ZTK-1F-IPX-PLR-DWG-9008 | FLANGE PROTECTOR DETAILS DRAWING (NPS18) |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | IPX |  |  | PLR | Pipeline | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 09-Oct-2026 17:16:36 | 26002z1fdcc@thoresen-jutal.com | 09-Oct-2026 17:37:06 | Jumpol Sudjitjul | 20-Oct-2026 |  | Akkarapat Suntornsuttiwat | 22-Oct-2026 | 12-Oct-2026 10:11:43 | Pornlert Wanaphattharaphan | 26-Oct-2026 | 13-Oct-2026 14:50:44 | APPR | Approved | Jumpol Sudjitjul | 27-Oct-2026 | 14-Oct-2026 16:45:36 | 14-Oct-2026 10:12:39 | 0 |  |  | Approver | Locate
AO-000913 | MM-ZTK-1F-IPX-PLR-MR-9001 | MATERIAL REQUISITION FOR 18" LSAW LINE PIPE, BEND MOTHER PIPE AND HOT INDUCTION BEND |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 19:50:31 | 26002z1fdcc@thoresen-jutal.com | 26-Jun-2026 19:54:41 | Jumpol Sudjitjul | 06-Jul-2026 | 04-Jul-2026 07:26:04 | Akkarapat Suntornsuttiwat | 08-Jul-2026 | 08-Jul-2026 08:59:59 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 09-Jul-2026 08:44:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 09-Jul-2026 10:12:17 | 09-Jul-2026 03:54:33 | 0 |  |  | Approver | Locate
AO-001083 | MM-ZTK-1F-IPX-PLR-MR-9001 | MATERIAL REQUISITION FOR 18" LSAW LINE PIPE, BEND MOTHER PIPE AND HOT INDUCTION BEND |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 12-Jul-2026 11:45:51 | 26002z1fdcc@thoresen-jutal.com | 12-Jul-2026 12:16:23 | Jumpol Sudjitjul | 17-Jul-2026 | 15-Jul-2026 10:44:01 | Akkarapat Suntornsuttiwat | 21-Jul-2026 | 15-Jul-2026 14:16:43 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 17-Jul-2026 00:18:16 | APPR | Approved | Jumpol Sudjitjul | 23-Jul-2026 | 17-Jul-2026 09:28:01 | 17-Jul-2026 03:26:18 | 0 |  |  | Approver | Locate
AO-001950 | MM-ZTK-1F-IPX-PLR-MR-9001 | MATERIAL REQUISITION FOR 18" LSAW LINE PIPE, BEND MOTHER PIPE AND HOT INDUCTION BEND |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 09-Sep-2026 17:33:10 | 26002z1fdcc@thoresen-jutal.com | 09-Sep-2026 17:46:28 | Jumpol Sudjitjul | 17-Sep-2026 |  | Akkarapat Suntornsuttiwat | 21-Sep-2026 | 10-Sep-2026 10:46:28 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 13-Sep-2026 17:42:35 | APPR | Approved | Jumpol Sudjitjul | 23-Sep-2026 | 13-Sep-2026 23:15:37 | 13-Sep-2026 17:01:12 | 0 |  |  | Approver | Locate
AO-000914 | MM-ZTK-1F-IPX-PLR-MR-9002 | MATERIAL REQUISITION FOR 10” SMLS LINE PIPE, BEND MOTHER PIPE AND HOT INDUCTION BEND |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 19:51:01 | 26002z1fdcc@thoresen-jutal.com | 27-Jun-2026 19:03:47 | Jumpol Sudjitjul | 06-Jul-2026 | 04-Jul-2026 07:23:46 | Akkarapat Suntornsuttiwat | 08-Jul-2026 | 08-Jul-2026 09:00:51 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 09-Jul-2026 08:45:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 09-Jul-2026 10:12:19 | 09-Jul-2026 03:53:17 | 0 |  |  | Approver | Locate
AO-001086 | MM-ZTK-1F-IPX-PLR-MR-9002 | MATERIAL REQUISITION FOR 10” SMLS LINE PIPE, BEND MOTHER PIPE AND HOT INDUCTION BEND |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 12-Jul-2026 11:46:27 | 26002z1fdcc@thoresen-jutal.com | 12-Jul-2026 12:16:38 | Jumpol Sudjitjul | 17-Jul-2026 |  | Akkarapat Suntornsuttiwat | 21-Jul-2026 | 15-Jul-2026 14:18:57 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 19-Jul-2026 17:07:03 | APPR | Approved | Jumpol Sudjitjul | 23-Jul-2026 | 20-Jul-2026 08:58:19 | 20-Jul-2026 03:05:26 | 0 |  |  | Approver | Locate
AO-001951 | MM-ZTK-1F-IPX-PLR-MR-9002 | MATERIAL REQUISITION FOR 10” SMLS LINE PIPE, BEND MOTHER PIPE AND HOT INDUCTION BEND |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 09-Sep-2026 15:27:17 | 26002z1fdcc@thoresen-jutal.com | 09-Sep-2026 16:44:49 | Jumpol Sudjitjul | 16-Sep-2026 |  | Akkarapat Suntornsuttiwat | 18-Sep-2026 | 10-Sep-2026 10:46:43 | Pornlert Wanaphattharaphan | 21-Sep-2026 | 13-Sep-2026 17:44:08 | APPR | Approved | Jumpol Sudjitjul | 22-Sep-2026 | 13-Sep-2026 23:11:47 | 13-Sep-2026 16:28:34 | 0 |  |  | Approver | Locate
AO-001071 | MM-ZTK-1F-IPX-PLR-MR-9003 | MATERIAL REQUISITION FOR PIPELINE EXTERNAL ANTICORROSION COATING & CONCRETE WEIGHT COATING, BEND EXTERNAL ANTICORROSION COATING, AND RISER/SPOOL EXTERNAL ANTICORROSION COATING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 10-Jul-2026 18:47:26 | 26002z1fdcc@thoresen-jutal.com | 10-Jul-2026 20:27:39 | Jumpol Sudjitjul | 20-Jul-2026 | 11-Jul-2026 06:21:14 | Akkarapat Suntornsuttiwat | 22-Jul-2026 | 16-Jul-2026 09:10:05 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 17-Jul-2026 00:20:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 17-Jul-2026 09:28:06 | 17-Jul-2026 03:27:32 | 0 |  |  | Approver | Locate
AO-001260 | MM-ZTK-1F-IPX-PLR-MR-9003 | MATERIAL REQUISITION FOR PIPELINE EXTERNAL ANTICORROSION COATING & CONCRETE WEIGHT COATING, BEND EXTERNAL ANTICORROSION COATING, AND RISER/SPOOL EXTERNAL ANTICORROSION COATING |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 09:59:37 | 26002z1fdcc@thoresen-jutal.com | 24-Jul-2026 11:17:49 | Jumpol Sudjitjul | 04-Aug-2026 | 25-Jul-2026 07:53:06 | Akkarapat Suntornsuttiwat | 06-Aug-2026 | 31-Jul-2026 16:24:12 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 03-Aug-2026 00:18:17 | APPR | Approved | Jumpol Sudjitjul | 10-Aug-2026 | 03-Aug-2026 09:02:47 | 03-Aug-2026 02:18:39 | 0 |  |  | Approver | Locate
AO-001116 | MM-ZTK-1F-IPX-PLR-MR-9004 | MATERIAL REQUISITION FOR NEOPRENE COATING FOR RISER SPLASH ZONE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 14-Jul-2026 18:12:24 | 26002z1fdcc@thoresen-jutal.com | 14-Jul-2026 20:05:16 | Jumpol Sudjitjul | 22-Jul-2026 | 15-Jul-2026 22:57:50 | Akkarapat Suntornsuttiwat | 24-Jul-2026 | 23-Jul-2026 08:29:11 | Pornlert Wanaphattharaphan | 27-Jul-2026 | 23-Jul-2026 10:12:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 30-Jul-2026 | 23-Jul-2026 10:14:25 | 23-Jul-2026 03:28:07 | 0 |  |  | Approver | Locate
AO-001273 | MM-ZTK-1F-IPX-PLR-MR-9004 | MATERIAL REQUISITION FOR NEOPRENE COATING FOR RISER SPLASH ZONE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 25-Jul-2026 09:17:17 | 26002z1fdcc@thoresen-jutal.com | 26-Jul-2026 23:52:01 | Jumpol Sudjitjul | 05-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 31-Jul-2026 16:32:08 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 03-Aug-2026 00:17:52 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 03-Aug-2026 09:00:24 | 03-Aug-2026 02:16:09 | 0 |  |  | Approver | Locate
AO-001004 | MM-ZTK-1F-IPX-PLR-MR-9005 | MATERIAL REQUISITION FOR SACRIFICIAL BRACELET ANODES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR |  | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:24:58 | 26002z1fdcc@thoresen-jutal.com | 03-Jul-2026 19:04:21 | Jumpol Sudjitjul | 13-Jul-2026 | 15-Jul-2026 13:12:58 | Akkarapat Suntornsuttiwat | 15-Jul-2026 | 16-Jul-2026 09:15:33 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 17-Jul-2026 00:14:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 17-Jul-2026 09:26:52 | 17-Jul-2026 03:05:36 | 0 |  |  | Approver | Locate
AO-001269 | MM-ZTK-1F-IPX-PLR-MR-9005 | MATERIAL REQUISITION FOR SACRIFICIAL BRACELET ANODES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR |  | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 17:38:38 | 26002z1fdcc@thoresen-jutal.com | 26-Jul-2026 23:51:46 | Jumpol Sudjitjul | 05-Aug-2026 | 28-Jul-2026 07:08:52 | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 31-Jul-2026 16:39:26 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 03-Aug-2026 00:18:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 03-Aug-2026 08:59:52 | 03-Aug-2026 02:14:54 | 0 |  |  | Approver | Locate
AO-001746 | MM-ZTK-1F-IPX-PLR-MR-9005 | MATERIAL REQUISITION FOR SACRIFICIAL BRACELET ANODES |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR |  | 0 | Submitted | AFC | Approved for Construction |  | 28-Aug-2026 10:33:25 | 26002z1fdcc@thoresen-jutal.com | 28-Aug-2026 14:03:19 | Jumpol Sudjitjul | 04-Sep-2026 | 31-Aug-2026 15:54:45 | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 09:46:02 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 01:14:46 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 17:48:39 | 07-Sep-2026 11:09:13 | 0 |  |  | Approver | Locate
AO-001004 | MM-ZTK-1F-IPX-PLR-MR-9006 | MATERIAL REQUISITION FOR FLANGES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR |  | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:25:24 | 26002z1fdcc@thoresen-jutal.com | 03-Jul-2026 19:04:35 | Jumpol Sudjitjul | 13-Jul-2026 | 15-Jul-2026 13:14:09 | Akkarapat Suntornsuttiwat | 15-Jul-2026 | 16-Jul-2026 09:21:10 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 17-Jul-2026 00:14:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 17-Jul-2026 09:26:13 | 17-Jul-2026 03:04:22 | 0 |  |  | Approver | Locate
AO-001450 | MM-ZTK-1F-IPX-PLR-MR-9006 | MATERIAL REQUISITION FOR FLANGES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR |  | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 17:33:47 | 26002z1fdcc@thoresen-jutal.com | 07-Aug-2026 17:37:59 | Jumpol Sudjitjul | 18-Aug-2026 | 08-Aug-2026 07:13:07 | Akkarapat Suntornsuttiwat | 20-Aug-2026 | 10-Aug-2026 13:11:12 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 16-Aug-2026 23:58:20 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 17-Aug-2026 14:16:05 | 17-Aug-2026 08:59:58 | 0 |  |  | Approver | Locate
AO-002549 | MM-ZTK-1F-IPX-PLR-MR-9006 | MATERIAL REQUISITION FOR FLANGES |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR |  | 0 | In Review | AFC | Approved for Construction |  | 16-Oct-2026 14:50:55 | 26002z1fdcc@thoresen-jutal.com | 16-Oct-2026 16:25:56 | Jumpol Sudjitjul | 26-Oct-2026 |  | Akkarapat Suntornsuttiwat | 28-Oct-2026 |  | Pornlert Wanaphattharaphan | 29-Oct-2026 |  |  |  |  | 30-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001004 | MM-ZTK-1F-IPX-PLR-MR-9007 | MATERIAL REQUISITION FOR FITTINGS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:25:50 | 26002z1fdcc@thoresen-jutal.com | 03-Jul-2026 19:04:50 | Jumpol Sudjitjul | 13-Jul-2026 | 15-Jul-2026 13:22:43 | Akkarapat Suntornsuttiwat | 15-Jul-2026 | 16-Jul-2026 09:23:30 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 17-Jul-2026 00:15:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 17-Jul-2026 09:25:48 | 17-Jul-2026 03:03:04 | 0 |  |  | Approver | Locate
AO-001451 | MM-ZTK-1F-IPX-PLR-MR-9007 | MATERIAL REQUISITION FOR FITTINGS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 17:34:25 | 26002z1fdcc@thoresen-jutal.com | 07-Aug-2026 17:38:20 | Jumpol Sudjitjul | 18-Aug-2026 | 12-Aug-2026 08:13:46 | Akkarapat Suntornsuttiwat | 20-Aug-2026 | 18-Aug-2026 09:21:19 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:24:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 19:26:28 | 24-Aug-2026 12:37:05 | 0 |  |  | Approver | Locate
AO-002550 | MM-ZTK-1F-IPX-PLR-MR-9007 | MATERIAL REQUISITION FOR FITTINGS |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR | Material Requisition | 0 | In Review | AFC | Approved for Construction |  | 16-Oct-2026 14:51:48 | 26002z1fdcc@thoresen-jutal.com | 16-Oct-2026 16:26:14 | Jumpol Sudjitjul | 26-Oct-2026 |  | Akkarapat Suntornsuttiwat | 28-Oct-2026 |  | Pornlert Wanaphattharaphan | 29-Oct-2026 |  |  |  |  | 30-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001004 | MM-ZTK-1F-IPX-PLR-MR-9008 | MATERIAL REQUISITION FOR GASKETS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:26:16 | 26002z1fdcc@thoresen-jutal.com | 03-Jul-2026 19:05:03 | Jumpol Sudjitjul | 13-Jul-2026 | 15-Jul-2026 13:23:07 | Akkarapat Suntornsuttiwat | 15-Jul-2026 | 16-Jul-2026 09:25:32 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 17-Jul-2026 00:15:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 17-Jul-2026 09:23:51 | 17-Jul-2026 03:01:48 | 0 |  |  | Approver | Locate
AO-001514 | MM-ZTK-1F-IPX-PLR-MR-9008 | MATERIAL REQUISITION FOR GASKETS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 13-Aug-2026 12:37:16 | 26002z1fdcc@thoresen-jutal.com | 13-Aug-2026 16:33:10 | Jumpol Sudjitjul | 20-Aug-2026 |  | Akkarapat Suntornsuttiwat | 24-Aug-2026 | 14-Aug-2026 14:03:24 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 16-Aug-2026 23:58:42 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 17-Aug-2026 14:17:21 | 17-Aug-2026 08:45:09 | 0 |  |  | Approver | Locate
AO-001004 | MM-ZTK-1F-IPX-PLR-MR-9009 | MATERIAL REQUISITION FOR FASTENERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 18:26:44 | 26002z1fdcc@thoresen-jutal.com | 03-Jul-2026 19:05:19 | Jumpol Sudjitjul | 13-Jul-2026 | 15-Jul-2026 13:23:31 | Akkarapat Suntornsuttiwat | 15-Jul-2026 | 16-Jul-2026 09:27:49 | Pornlert Wanaphattharaphan | 16-Jul-2026 | 17-Jul-2026 00:16:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jul-2026 | 17-Jul-2026 09:21:48 | 17-Jul-2026 03:00:31 | 0 |  |  | Approver | Locate
AO-001458 | MM-ZTK-1F-IPX-PLR-MR-9009 | MATERIAL REQUISITION FOR FASTENERS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 17:35:33 | 26002z1fdcc@thoresen-jutal.com | 07-Aug-2026 17:38:51 | Jumpol Sudjitjul | 18-Aug-2026 |  | Akkarapat Suntornsuttiwat | 20-Aug-2026 | 10-Aug-2026 09:21:33 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 16-Aug-2026 23:57:52 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 17-Aug-2026 14:10:13 | 17-Aug-2026 08:55:01 | 0 |  |  | Approver | Locate
AO-001144 | MM-ZTK-1F-IPX-PLR-MR-9010 | MATERIAL REQUISITION FOR FIELD JOINT COATING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 16-Jul-2026 18:48:03 | 26002z1fdcc@thoresen-jutal.com | 16-Jul-2026 20:58:10 | Jumpol Sudjitjul | 24-Jul-2026 | 18-Jul-2026 08:56:58 | Akkarapat Suntornsuttiwat | 30-Jul-2026 | 23-Jul-2026 08:32:15 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 23-Jul-2026 10:14:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 23-Jul-2026 10:16:52 | 23-Jul-2026 03:30:29 | 0 |  |  | Approver | Locate
AO-001400 | MM-ZTK-1F-IPX-PLR-MR-9010 | MATERIAL REQUISITION FOR FIELD JOINT COATING |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 16:54:50 | 26002z1fdcc@thoresen-jutal.com | 04-Aug-2026 08:23:59 | Jumpol Sudjitjul | 11-Aug-2026 |  | Akkarapat Suntornsuttiwat | 14-Aug-2026 | 05-Aug-2026 14:08:34 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 12-Aug-2026 21:13:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 13-Aug-2026 11:34:59 | 13-Aug-2026 05:40:25 | 0 |  |  | Approver | Locate
AO-000727 | MM-ZTK-1F-IPX-PLR-MTO-9001 | MATERIAL TAKE OFF FOR 18" LSAW LINE PIPE AND BEND MOTHER-PIPE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 17:23:16 | 26002z1fdcc@thoresen-jutal.com | 10-Jun-2026 08:29:51 | Jumpol Sudjitjul | 17-Jun-2026 | 10-Jun-2026 12:03:17 | Akkarapat Suntornsuttiwat | 19-Jun-2026 | 15-Jun-2026 09:25:23 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 21-Jun-2026 00:26:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 22-Jun-2026 12:58:06 | 22-Jun-2026 06:52:18 | 0 |  |  | Approver | Locate
AO-000945 | MM-ZTK-1F-IPX-PLR-MTO-9001 | MATERIAL TAKE OFF FOR 18" LSAW LINE PIPE AND BEND MOTHER-PIPE |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | IFA | Issued for Approval |  | 29-Jun-2026 22:07:48 | 26002z1fdcc@thoresen-jutal.com | 30-Jun-2026 11:09:07 | Jumpol Sudjitjul | 07-Jul-2026 |  | Akkarapat Suntornsuttiwat | 09-Jul-2026 | 30-Jun-2026 14:10:30 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 02-Jul-2026 00:44:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 02-Jul-2026 10:09:36 | 02-Jul-2026 03:37:43 | 0 |  |  | Approver | Locate
AO-001096 | MM-ZTK-1F-IPX-PLR-MTO-9001 | MATERIAL TAKE OFF FOR 18" LSAW LINE PIPE AND BEND MOTHER-PIPE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | AFC | Approved for Construction |  | 13-Jul-2026 13:24:22 | 26002z1fdcc@thoresen-jutal.com | 13-Jul-2026 14:51:12 | Jumpol Sudjitjul | 20-Jul-2026 | 14-Jul-2026 10:15:59 | Akkarapat Suntornsuttiwat | 22-Jul-2026 | 14-Jul-2026 16:21:02 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 20-Jul-2026 02:47:52 | APPR | Approved | Jumpol Sudjitjul | 24-Jul-2026 | 20-Jul-2026 08:57:49 | 20-Jul-2026 02:06:07 | 0 |  |  | Approver | Locate
AO-001651 | MM-ZTK-1F-IPX-PLR-MTO-9001 | MATERIAL TAKE OFF FOR 18" LSAW LINE PIPE AND BEND MOTHER-PIPE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 18:45:35 | 26002z1fdcc@thoresen-jutal.com | 24-Aug-2026 18:40:43 | Jumpol Sudjitjul | 01-Sep-2026 | 25-Aug-2026 08:39:32 | Akkarapat Suntornsuttiwat | 03-Sep-2026 | 25-Aug-2026 09:57:08 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 15:39:43 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 16:46:27 | 30-Aug-2026 10:32:15 | 0 |  |  | Approver | Locate
AO-000712 | MM-ZTK-1F-IPX-PLR-MTO-9002 | MATERIAL TAKE OFF FOR 10" SEAMLESS LINE PIPE AND BEND MOTHER-PIPE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 14:32:21 | 26002z1fdcc@thoresen-jutal.com | 08-Jun-2026 17:21:15 | Jumpol Sudjitjul | 16-Jun-2026 |  | Akkarapat Suntornsuttiwat | 18-Jun-2026 | 15-Jun-2026 09:23:48 | Pornlert Wanaphattharaphan | 19-Jun-2026 | 20-Jun-2026 21:44:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jun-2026 | 22-Jun-2026 12:58:30 | 22-Jun-2026 06:55:40 | 0 |  |  | Approver | Locate
AO-000916 | MM-ZTK-1F-IPX-PLR-MTO-9002 | MATERIAL TAKE OFF FOR 10" SEAMLESS LINE PIPE AND BEND MOTHER-PIPE |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | IFA | Issued for Approval |  | 26-Jun-2026 20:38:42 | 26002z1fdcc@thoresen-jutal.com | 27-Jun-2026 18:54:06 | Jumpol Sudjitjul | 06-Jul-2026 |  | Akkarapat Suntornsuttiwat | 08-Jul-2026 | 30-Jun-2026 14:24:18 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 02-Jul-2026 00:52:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 02-Jul-2026 10:05:59 | 02-Jul-2026 03:46:56 | 0 |  |  | Approver | Locate
AO-001097 | MM-ZTK-1F-IPX-PLR-MTO-9002 | MATERIAL TAKE OFF FOR 10" SEAMLESS LINE PIPE AND BEND MOTHER-PIPE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | AFC | Approved for Construction |  | 13-Jul-2026 13:24:52 | 26002z1fdcc@thoresen-jutal.com | 13-Jul-2026 14:51:33 | Jumpol Sudjitjul | 20-Jul-2026 |  | Akkarapat Suntornsuttiwat | 22-Jul-2026 | 14-Jul-2026 16:24:04 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 20-Jul-2026 02:47:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 20-Jul-2026 08:57:13 | 20-Jul-2026 02:04:51 | 0 |  |  | Approver | Locate
AO-001567 | MM-ZTK-1F-IPX-PLR-MTO-9002 | MATERIAL TAKE OFF FOR 10" SEAMLESS LINE PIPE AND BEND MOTHER-PIPE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 14:50:10 | 26002z1fdcc@thoresen-jutal.com | 17-Aug-2026 15:41:22 | Jumpol Sudjitjul | 24-Aug-2026 |  | Akkarapat Suntornsuttiwat | 26-Aug-2026 | 19-Aug-2026 15:10:19 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:09:05 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 19:25:53 | 24-Aug-2026 13:01:34 | 0 |  |  | Approver | Locate
AO-000887 | MM-ZTK-1F-IPX-PLR-MTO-9003 | MATERIAL TAKE OFF FOR CONCRETE WEIGHT COATING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 24-Jun-2026 13:20:27 | 26002z1fdcc@thoresen-jutal.com | 24-Jun-2026 14:57:45 | Jumpol Sudjitjul | 01-Jul-2026 | 26-Jun-2026 09:58:00 | Akkarapat Suntornsuttiwat | 03-Jul-2026 | 26-Jun-2026 14:11:14 | Pornlert Wanaphattharaphan | 06-Jul-2026 | 29-Jun-2026 01:22:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Jul-2026 | 30-Jun-2026 09:34:11 | 30-Jun-2026 03:47:09 | 0 |  |  | Approver | Locate
AO-001040 | MM-ZTK-1F-IPX-PLR-MTO-9003 | MATERIAL TAKE OFF FOR CONCRETE WEIGHT COATING |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | IFA | Issued for Approval |  | 09-Jul-2026 14:58:45 | 26002z1fdcc@thoresen-jutal.com | 09-Jul-2026 15:05:57 | Jumpol Sudjitjul | 16-Jul-2026 |  | Akkarapat Suntornsuttiwat | 20-Jul-2026 | 10-Jul-2026 15:36:10 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 11-Jul-2026 09:48:26 | APPR | Approved | Jumpol Sudjitjul | 22-Jul-2026 | 12-Jul-2026 11:37:12 | 12-Jul-2026 04:51:48 | 0 |  |  | Approver | Locate
AO-001155 | MM-ZTK-1F-IPX-PLR-MTO-9003 | MATERIAL TAKE OFF FOR CONCRETE WEIGHT COATING |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 17:58:17 | 26002z1fdcc@thoresen-jutal.com | 17-Jul-2026 20:13:30 | Jumpol Sudjitjul | 27-Jul-2026 | 18-Jul-2026 08:45:10 | Akkarapat Suntornsuttiwat | 31-Jul-2026 | 20-Jul-2026 09:19:29 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 11:35:18 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 15:02:05 | 27-Jul-2026 09:33:27 | 0 |  |  | Approver | Locate
AO-001736 | MM-ZTK-1F-IPX-PLR-MTO-9003 | MATERIAL TAKE OFF FOR CONCRETE WEIGHT COATING |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | AFC | Approved for Construction |  | 27-Aug-2026 12:03:46 | 26002z1fdcc@thoresen-jutal.com | 27-Aug-2026 13:10:00 | Jumpol Sudjitjul | 03-Sep-2026 | 28-Aug-2026 10:15:29 | Akkarapat Suntornsuttiwat | 07-Sep-2026 | 03-Sep-2026 09:50:19 | Pornlert Wanaphattharaphan | 08-Sep-2026 | 07-Sep-2026 01:09:53 | APPR | Approved | Jumpol Sudjitjul | 09-Sep-2026 | 07-Sep-2026 17:50:21 | 07-Sep-2026 11:26:08 | 0 |  |  | Approver | Locate
AO-000906 | MM-ZTK-1F-IPX-PLR-MTO-9004 | MATERIAL TAKE OFF FOR HOT INDUCTION BENDS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 16:40:57 | 26002z1fdcc@thoresen-jutal.com | 27-Jun-2026 19:00:50 | Jumpol Sudjitjul | 06-Jul-2026 |  | Akkarapat Suntornsuttiwat | 08-Jul-2026 | 02-Jul-2026 09:07:01 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 04-Jul-2026 20:02:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 05-Jul-2026 10:40:57 | 05-Jul-2026 04:20:29 | 0 |  |  | Approver | Locate
AO-001102 | MM-ZTK-1F-IPX-PLR-MTO-9004 | MATERIAL TAKE OFF FOR HOT INDUCTION BENDS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | IFA | Issued for Approval |  | 14-Jul-2026 12:49:47 | 26002z1fdcc@thoresen-jutal.com | 14-Jul-2026 13:45:31 | Jumpol Sudjitjul | 21-Jul-2026 | 15-Jul-2026 22:13:36 | Akkarapat Suntornsuttiwat | 23-Jul-2026 | 16-Jul-2026 10:10:56 | Pornlert Wanaphattharaphan | 24-Jul-2026 | 20-Jul-2026 02:07:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Jul-2026 | 20-Jul-2026 08:55:41 | 20-Jul-2026 02:03:30 | 0 |  |  | Approver | Locate
AO-001278 | MM-ZTK-1F-IPX-PLR-MTO-9004 | MATERIAL TAKE OFF FOR HOT INDUCTION BENDS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | AFC | Approved for Construction |  | 25-Jul-2026 09:17:43 | 26002z1fdcc@thoresen-jutal.com | 26-Jul-2026 23:53:12 | Jumpol Sudjitjul | 05-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 27-Jul-2026 16:35:52 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 30-Jul-2026 10:43:34 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 30-Jul-2026 10:49:57 | 30-Jul-2026 04:33:09 | 0 |  |  | Approver | Locate
AO-000971 | MM-ZTK-1F-IPX-PLR-MTO-9005 | MATERIAL TAKE OFF FOR PIPELINE /RISER EXTERNAL ANTI-CORROSION COATING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 01-Jul-2026 18:00:09 | 26002z1fdcc@thoresen-jutal.com | 02-Jul-2026 14:00:04 | Jumpol Sudjitjul | 09-Jul-2026 | 02-Jul-2026 14:33:17 | Akkarapat Suntornsuttiwat | 13-Jul-2026 | 02-Jul-2026 16:48:31 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 02-Jul-2026 22:39:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jul-2026 | 03-Jul-2026 11:29:56 | 03-Jul-2026 04:59:22 | 0 |  |  | Approver | Locate
AO-001156 | MM-ZTK-1F-IPX-PLR-MTO-9005 | MATERIAL TAKE OFF FOR PIPELINE /RISER EXTERNAL ANTI-CORROSION COATING |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | IFA | Issued for Approval |  | 17-Jul-2026 17:58:46 | 26002z1fdcc@thoresen-jutal.com | 17-Jul-2026 20:13:53 | Jumpol Sudjitjul | 27-Jul-2026 | 18-Jul-2026 08:46:29 | Akkarapat Suntornsuttiwat | 31-Jul-2026 | 20-Jul-2026 11:07:20 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 12:10:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 15:00:11 | 27-Jul-2026 08:59:09 | 0 |  |  | Approver | Locate
AO-001628 | MM-ZTK-1F-IPX-PLR-MTO-9005 | MATERIAL TAKE OFF FOR PIPELINE /RISER EXTERNAL ANTI-CORROSION COATING |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 14:25:40 | 26002z1fdcc@thoresen-jutal.com | 20-Aug-2026 14:39:15 | Jumpol Sudjitjul | 27-Aug-2026 |  | Akkarapat Suntornsuttiwat | 31-Aug-2026 | 21-Aug-2026 15:08:39 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 22-Aug-2026 13:24:02 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 24-Aug-2026 19:24:57 | 24-Aug-2026 13:00:19 | 0 |  |  | Approver | Locate
AO-000681 | MM-ZTK-1F-IPX-PLR-MTO-9006 | MATERIAL TAKE OFF FOR SACRIFICIAL BRACELET ANODE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 13:52:48 | 26002z1fdcc@thoresen-jutal.com | 05-Jun-2026 14:24:56 | Jumpol Sudjitjul | 12-Jun-2026 |  | Akkarapat Suntornsuttiwat | 16-Jun-2026 | 15-Jun-2026 09:22:35 | Pornlert Wanaphattharaphan | 17-Jun-2026 | 18-Jun-2026 09:56:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Jun-2026 | 18-Jun-2026 10:25:35 | 18-Jun-2026 04:19:32 | 0 |  |  | Approver | Locate
AO-000989 | MM-ZTK-1F-IPX-PLR-MTO-9006 | MATERIAL TAKE OFF FOR SACRIFICIAL BRACELET ANODE |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 09:51:55 | 26002z1fdcc@thoresen-jutal.com | 03-Jul-2026 14:16:35 | Jumpol Sudjitjul | 10-Jul-2026 |  | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 07-Jul-2026 14:07:17 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 22:41:11 | APPR | Approved | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 11:21:15 | 15-Jul-2026 05:06:05 | 0 |  |  | Approver | Locate
AO-001200 | MM-ZTK-1F-IPX-PLR-MTO-9006 | MATERIAL TAKE OFF FOR SACRIFICIAL BRACELET ANODE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 13:15:16 | 26002z1fdcc@thoresen-jutal.com | 20-Jul-2026 15:30:28 | Jumpol Sudjitjul | 27-Jul-2026 |  | Akkarapat Suntornsuttiwat | 31-Jul-2026 | 20-Jul-2026 16:30:10 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 12:25:15 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 15:03:13 | 27-Jul-2026 09:35:58 | 0 |  |  | Approver | Locate
AO-001647 | MM-ZTK-1F-IPX-PLR-MTO-9006 | MATERIAL TAKE OFF FOR SACRIFICIAL BRACELET ANODE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 14:00:56 | 26002z1fdcc@thoresen-jutal.com | 21-Aug-2026 14:41:42 | Jumpol Sudjitjul | 28-Aug-2026 |  | Akkarapat Suntornsuttiwat | 01-Sep-2026 | 21-Aug-2026 15:15:11 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 22-Aug-2026 13:23:07 | APPR | Approved | Jumpol Sudjitjul | 03-Sep-2026 | 24-Aug-2026 19:24:30 | 24-Aug-2026 12:44:15 | 0 |  |  | Approver | Locate
AO-000905 | MM-ZTK-1F-IPX-PLR-MTO-9007 | MATERIAL TAKE OFF FOR FLANGES, FITTINGS, GASKETS AND FASTENERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 16:41:32 | 26002z1fdcc@thoresen-jutal.com | 26-Jun-2026 17:10:56 | Jumpol Sudjitjul | 06-Jul-2026 | 27-Jun-2026 06:56:33 | Akkarapat Suntornsuttiwat | 08-Jul-2026 | 02-Jul-2026 15:53:46 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 04-Jul-2026 22:07:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 05-Jul-2026 10:41:58 | 05-Jul-2026 04:24:21 | 0 |  |  | Approver | Locate
AO-001157 | MM-ZTK-1F-IPX-PLR-MTO-9007 | MATERIAL TAKE OFF FOR FLANGES, FITTINGS, GASKETS AND FASTENERS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | IFA | Issued for Approval |  | 17-Jul-2026 17:59:14 | 26002z1fdcc@thoresen-jutal.com | 17-Jul-2026 20:14:08 | Jumpol Sudjitjul | 27-Jul-2026 | 18-Jul-2026 08:29:44 | Akkarapat Suntornsuttiwat | 31-Jul-2026 | 20-Jul-2026 11:01:10 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 11:59:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 15:02:39 | 27-Jul-2026 09:34:48 | 0 |  |  | Approver | Locate
AO-001656 | MM-ZTK-1F-IPX-PLR-MTO-9007 | MATERIAL TAKE OFF FOR FLANGES, FITTINGS, GASKETS AND FASTENERS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 18:46:08 | 26002z1fdcc@thoresen-jutal.com | 24-Aug-2026 18:41:02 | Jumpol Sudjitjul | 01-Sep-2026 | 25-Aug-2026 08:26:40 | Akkarapat Suntornsuttiwat | 03-Sep-2026 | 25-Aug-2026 10:28:59 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 16:21:06 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 16:49:29 | 30-Aug-2026 10:33:27 | 0 |  |  | Approver | Locate
AO-002327 | MM-ZTK-1F-IPX-PLR-MTO-9007 | MATERIAL TAKE OFF FOR FLANGES, FITTINGS, GASKETS AND FASTENERS |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | AFC | Approved for Construction |  | 01-Oct-2026 17:24:15 | 26002z1fdcc@thoresen-jutal.com | 02-Oct-2026 14:20:39 | Jumpol Sudjitjul | 09-Oct-2026 | 03-Oct-2026 06:37:18 | Akkarapat Suntornsuttiwat | 14-Oct-2026 | 05-Oct-2026 08:42:22 | Pornlert Wanaphattharaphan | 15-Oct-2026 | 10-Oct-2026 01:51:58 | APPR | Approved | Jumpol Sudjitjul | 16-Oct-2026 | 10-Oct-2026 17:42:07 | 10-Oct-2026 11:40:24 | 0 |  |  | Approver | Locate
AO-000995 | MM-ZTK-1F-IPX-PLR-MTO-9008 | MATERIAL TAKE OFF FOR FIELD JOINT COATING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 13:35:31 | 26002z1fdcc@thoresen-jutal.com | 03-Jul-2026 14:18:37 | Jumpol Sudjitjul | 10-Jul-2026 | 03-Jul-2026 16:14:57 | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 07-Jul-2026 15:43:43 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 13:46:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 14-Jul-2026 14:18:33 | 14-Jul-2026 08:23:59 | 0 |  |  | Approver | Locate
AO-001756 | MM-ZTK-1F-IPX-PLR-MTO-9008 | MATERIAL TAKE OFF FOR FIELD JOINT COATING |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | IFA | Issued for Approval |  | 28-Aug-2026 14:49:35 | 26002z1fdcc@thoresen-jutal.com | 29-Aug-2026 13:41:05 | Jumpol Sudjitjul | 04-Sep-2026 | 01-Sep-2026 11:01:08 | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 03-Sep-2026 10:21:47 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 01:16:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 17:51:36 | 07-Sep-2026 11:27:27 | 0 |  |  | Approver | Locate
AO-002323 | MM-ZTK-1F-IPX-PLR-MTO-9008 | MATERIAL TAKE OFF FOR FIELD JOINT COATING |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | MTO | Material Take Off | 0 | Submitted | AFC | Approved for Construction |  | 01-Oct-2026 12:03:45 | 26002z1fdcc@thoresen-jutal.com | 01-Oct-2026 13:12:28 | Jumpol Sudjitjul | 08-Oct-2026 | 03-Oct-2026 06:35:58 | Akkarapat Suntornsuttiwat | 12-Oct-2026 | 05-Oct-2026 08:29:35 | Pornlert Wanaphattharaphan | 14-Oct-2026 | 10-Oct-2026 01:48:42 | APPR | Approved | Jumpol Sudjitjul | 15-Oct-2026 | 10-Oct-2026 17:41:30 | 10-Oct-2026 11:35:54 | 0 |  |  | Approver | Locate
AO-000405 | MM-ZTK-1F-IPX-PLR-RPT-9001 | PIPELINE WALL THICKNESS ANALYSIS REPORT (IP20, IP21, IP22, IP23) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 10:53:22 | 26002z1fdcc@thoresen-jutal.com | 15-May-2026 18:17:11 | Jumpol Sudjitjul | 25-May-2026 |  | Akkarapat Suntornsuttiwat | 27-May-2026 | 20-May-2026 08:31:00 | Pornlert Wanaphattharaphan | 28-May-2026 | 31-May-2026 01:50:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 31-May-2026 20:54:45 | 31-May-2026 14:41:04 | 0 |  |  | Approver | Locate
AO-000907 | MM-ZTK-1F-IPX-PLR-RPT-9001 | PIPELINE WALL THICKNESS ANALYSIS REPORT (IP20, IP21, IP22, IP23) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 26-Jun-2026 18:08:54 | 26002z1fdcc@thoresen-jutal.com | 26-Jun-2026 19:50:39 | Jumpol Sudjitjul | 06-Jul-2026 |  | Akkarapat Suntornsuttiwat | 08-Jul-2026 | 30-Jun-2026 14:49:40 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 02-Jul-2026 00:42:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 02-Jul-2026 10:06:34 | 02-Jul-2026 04:34:26 | 0 |  |  | Approver | Locate
AO-001152 | MM-ZTK-1F-IPX-PLR-RPT-9001 | PIPELINE WALL THICKNESS ANALYSIS REPORT (IP20, IP21, IP22, IP23) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 13:24:13 | 26002z1fdcc@thoresen-jutal.com | 17-Jul-2026 13:32:31 | Jumpol Sudjitjul | 24-Jul-2026 |  | Akkarapat Suntornsuttiwat | 30-Jul-2026 | 20-Jul-2026 14:37:15 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 26-Jul-2026 10:04:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 15:04:19 | 27-Jul-2026 10:46:22 | 0 |  |  | Approver | Locate
AO-001435 | MM-ZTK-1F-IPX-PLR-RPT-9001 | PIPELINE WALL THICKNESS ANALYSIS REPORT (IP20, IP21, IP22, IP23) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 06-Aug-2026 16:11:37 | 26002z1fdcc@thoresen-jutal.com | 06-Aug-2026 16:14:43 | Jumpol Sudjitjul | 14-Aug-2026 |  | Akkarapat Suntornsuttiwat | 18-Aug-2026 | 07-Aug-2026 09:29:24 | Pornlert Wanaphattharaphan | 19-Aug-2026 | 16-Aug-2026 23:23:44 | APPR | Approved | Jumpol Sudjitjul | 20-Aug-2026 | 17-Aug-2026 14:17:51 | 17-Aug-2026 08:26:12 | 0 |  |  | Approver | Locate
AO-000568 | MM-ZTK-1F-IPX-PLR-RPT-9002 | PIPELINE ON-BOTTOM STABILITY ANALYSIS (IP20, IP21,IP22, IP23) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 22-May-2026 10:58:00 | 26002z1fdcc@thoresen-jutal.com | 22-May-2026 12:45:36 | Jumpol Sudjitjul | 29-May-2026 |  | Akkarapat Suntornsuttiwat | 04-Jun-2026 | 27-May-2026 08:37:10 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 08-Jun-2026 23:55:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 09-Jun-2026 07:51:29 | 09-Jun-2026 01:21:47 | 0 |  |  | Approver | Locate
AO-000920 | MM-ZTK-1F-IPX-PLR-RPT-9002 | PIPELINE ON-BOTTOM STABILITY ANALYSIS (IP20, IP21,IP22, IP23) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 27-Jun-2026 19:26:25 | 26002z1fdcc@thoresen-jutal.com | 27-Jun-2026 19:31:09 | Jumpol Sudjitjul | 06-Jul-2026 |  | Akkarapat Suntornsuttiwat | 08-Jul-2026 | 01-Jul-2026 09:08:59 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 02-Jul-2026 00:42:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 02-Jul-2026 10:05:10 | 02-Jul-2026 04:31:31 | 0 |  |  | Approver | Locate
AO-001264 | MM-ZTK-1F-IPX-PLR-RPT-9002 | PIPELINE ON-BOTTOM STABILITY ANALYSIS (IP20, IP21,IP22, IP23) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 24-Jul-2026 12:07:57 | 26002z1fdcc@thoresen-jutal.com | 26-Jul-2026 23:49:00 | Jumpol Sudjitjul | 05-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 03-Aug-2026 10:55:00 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 22:02:36 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:20:44 | 08-Aug-2026 04:11:05 | 0 |  |  | Approver | Locate
AO-000738 | MM-ZTK-1F-IPX-PLR-RPT-9003 | PIPELINE FAULT CROSSING ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 15:27:02 | 26002z1fdcc@thoresen-jutal.com | 11-Jun-2026 15:35:35 | Jumpol Sudjitjul | 18-Jun-2026 |  | Akkarapat Suntornsuttiwat | 22-Jun-2026 | 18-Jun-2026 08:35:50 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 21-Jun-2026 08:15:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 22-Jun-2026 12:59:20 | 22-Jun-2026 06:57:20 | 0 |  |  | Approver | Locate
AO-001062 | MM-ZTK-1F-IPX-PLR-RPT-9003 | PIPELINE FAULT CROSSING ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 10-Jul-2026 16:57:27 | 26002z1fdcc@thoresen-jutal.com | 10-Jul-2026 17:52:58 | Jumpol Sudjitjul | 20-Jul-2026 |  | Akkarapat Suntornsuttiwat | 22-Jul-2026 | 13-Jul-2026 13:55:37 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 20-Jul-2026 02:48:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 20-Jul-2026 08:55:08 | 20-Jul-2026 02:02:08 | 0 |  |  | Approver | Locate
AO-001415 | MM-ZTK-1F-IPX-PLR-RPT-9003 | PIPELINE FAULT CROSSING ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 04-Aug-2026 17:36:04 | 26002z1fdcc@thoresen-jutal.com | 05-Aug-2026 08:27:47 | Jumpol Sudjitjul | 13-Aug-2026 |  | Akkarapat Suntornsuttiwat | 17-Aug-2026 | 05-Aug-2026 14:21:31 | Pornlert Wanaphattharaphan | 18-Aug-2026 | 16-Aug-2026 23:23:19 | APPR | Approved | Jumpol Sudjitjul | 19-Aug-2026 | 17-Aug-2026 14:14:44 | 17-Aug-2026 08:56:21 | 0 |  |  | Approver | Locate
AO-000812 | MM-ZTK-1F-IPX-PLR-RPT-9004 | PIPELINE EXTERNAL ANTI-CORROSION COATING AND CATHODIC PROTECTION DESIGN (IP20, IP21, IP22, IP23) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 16-Jun-2026 09:35:32 | 26002z1fdcc@thoresen-jutal.com | 16-Jun-2026 11:06:26 | Jumpol Sudjitjul | 23-Jun-2026 |  | Akkarapat Suntornsuttiwat | 25-Jun-2026 | 19-Jun-2026 14:56:22 | Pornlert Wanaphattharaphan | 26-Jun-2026 | 21-Jun-2026 16:34:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-Jun-2026 | 22-Jun-2026 13:00:22 | 22-Jun-2026 07:01:28 | 0 |  |  | Approver | Locate
AO-000972 | MM-ZTK-1F-IPX-PLR-RPT-9004 | PIPELINE EXTERNAL ANTI-CORROSION COATING AND CATHODIC PROTECTION DESIGN (IP20, IP21, IP22, IP23) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 01-Jul-2026 18:00:45 | 26002z1fdcc@thoresen-jutal.com | 02-Jul-2026 13:56:53 | Jumpol Sudjitjul | 09-Jul-2026 |  | Akkarapat Suntornsuttiwat | 13-Jul-2026 | 06-Jul-2026 15:38:51 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 14-Jul-2026 20:48:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 11:02:57 | 15-Jul-2026 05:00:51 | 0 |  |  | Approver | Locate
AO-001201 | MM-ZTK-1F-IPX-PLR-RPT-9004 | PIPELINE EXTERNAL ANTI-CORROSION COATING AND CATHODIC PROTECTION DESIGN (IP20, IP21, IP22, IP23) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 20-Jul-2026 13:16:00 | 26002z1fdcc@thoresen-jutal.com | 20-Jul-2026 15:33:04 | Jumpol Sudjitjul | 27-Jul-2026 |  | Akkarapat Suntornsuttiwat | 31-Jul-2026 | 20-Jul-2026 16:27:11 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 26-Jul-2026 12:22:18 | APPR | Approved | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 15:04:56 | 27-Jul-2026 09:37:17 | 0 |  |  | Approver | Locate
AO-000594 | MM-ZTK-1F-IPX-PLR-RPT-9005 | PIPELINE END EXPANSION ANALYSIS REPORT (IP20, IP21, IP22, IP23) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 25-May-2026 12:01:31 | 26002z1fdcc@thoresen-jutal.com | 25-May-2026 13:04:19 | Jumpol Sudjitjul | 02-Jun-2026 |  | Akkarapat Suntornsuttiwat | 05-Jun-2026 | 29-May-2026 16:03:44 | Pornlert Wanaphattharaphan | 08-Jun-2026 | 10-Jun-2026 21:20:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jun-2026 | 11-Jun-2026 11:29:01 | 11-Jun-2026 04:57:28 | 0 |  |  | Approver | Locate
AO-000915 | MM-ZTK-1F-IPX-PLR-RPT-9005 | PIPELINE END EXPANSION ANALYSIS REPORT (IP20, IP21, IP22, IP23) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 26-Jun-2026 20:39:09 | 26002z1fdcc@thoresen-jutal.com | 27-Jun-2026 18:49:24 | Jumpol Sudjitjul | 06-Jul-2026 |  | Akkarapat Suntornsuttiwat | 08-Jul-2026 | 30-Jun-2026 16:45:35 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 02-Jul-2026 00:42:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 02-Jul-2026 10:04:26 | 02-Jul-2026 03:45:34 | 0 |  |  | Approver | Locate
AO-001153 | MM-ZTK-1F-IPX-PLR-RPT-9005 | PIPELINE END EXPANSION ANALYSIS REPORT (IP20, IP21, IP22, IP23) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 17-Jul-2026 13:24:44 | 26002z1fdcc@thoresen-jutal.com | 17-Jul-2026 13:32:56 | Jumpol Sudjitjul | 24-Jul-2026 |  | Akkarapat Suntornsuttiwat | 30-Jul-2026 | 20-Jul-2026 14:09:18 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 26-Jul-2026 10:03:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 15:05:37 | 27-Jul-2026 10:47:39 | 0 |  |  | Approver | Locate
AO-001633 | MM-ZTK-1F-IPX-PLR-RPT-9005 | PIPELINE END EXPANSION ANALYSIS REPORT (IP20, IP21, IP22, IP23) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 17:25:44 | 26002z1fdcc@thoresen-jutal.com | 21-Aug-2026 10:48:11 | Jumpol Sudjitjul | 28-Aug-2026 |  | Akkarapat Suntornsuttiwat | 01-Sep-2026 | 21-Aug-2026 15:18:28 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 22-Aug-2026 13:22:21 | APPR | Approved | Jumpol Sudjitjul | 03-Sep-2026 | 24-Aug-2026 19:23:53 | 24-Aug-2026 12:59:06 | 0 |  |  | Approver | Locate
AO-000739 | MM-ZTK-1F-IPX-PLR-RPT-9006 | PIPELINE ALLOWABLE FREE SPAN CALCULATION (IP20, IP21, IP22, IP23) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 15:27:29 | 26002z1fdcc@thoresen-jutal.com | 11-Jun-2026 15:41:00 | Jumpol Sudjitjul | 18-Jun-2026 |  | Akkarapat Suntornsuttiwat | 22-Jun-2026 | 18-Jun-2026 08:40:27 | Pornlert Wanaphattharaphan | 23-Jun-2026 | 21-Jun-2026 08:19:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jun-2026 | 22-Jun-2026 13:01:06 | 22-Jun-2026 07:03:26 | 0 |  |  | Approver | Locate
AO-001219 | MM-ZTK-1F-IPX-PLR-RPT-9006 | PIPELINE ALLOWABLE FREE SPAN CALCULATION (IP20, IP21, IP22, IP23) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 21-Jul-2026 12:38:02 | 26002z1fdcc@thoresen-jutal.com | 21-Jul-2026 13:11:59 | Jumpol Sudjitjul | 30-Jul-2026 |  | Akkarapat Suntornsuttiwat | 03-Aug-2026 | 22-Jul-2026 16:21:10 | Pornlert Wanaphattharaphan | 04-Aug-2026 | 29-Jul-2026 08:51:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Aug-2026 | 30-Jul-2026 09:47:24 | 30-Jul-2026 03:57:31 | 0 |  |  | Approver | Locate
AO-001536 | MM-ZTK-1F-IPX-PLR-RPT-9006 | PIPELINE ALLOWABLE FREE SPAN CALCULATION (IP20, IP21, IP22, IP23) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 14-Aug-2026 17:34:10 | 26002z1fdcc@thoresen-jutal.com | 14-Aug-2026 17:45:30 | Jumpol Sudjitjul | 24-Aug-2026 |  | Akkarapat Suntornsuttiwat | 26-Aug-2026 | 17-Aug-2026 08:46:20 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 17:44:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 19:23:16 | 24-Aug-2026 13:25:54 | 0 |  |  | Approver | Locate
AO-001801 | MM-ZTK-1F-IPX-PLR-RPT-9006 | PIPELINE ALLOWABLE FREE SPAN CALCULATION (IP20, IP21, IP22, IP23) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 31-Aug-2026 16:10:24 | 26002z1fdcc@thoresen-jutal.com | 31-Aug-2026 16:15:59 | Jumpol Sudjitjul | 07-Sep-2026 |  | Akkarapat Suntornsuttiwat | 09-Sep-2026 | 03-Sep-2026 09:42:57 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 07-Sep-2026 01:17:32 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 07-Sep-2026 17:52:29 | 07-Sep-2026 11:48:33 | 0 |  |  | Approver | Locate
AO-000278 | MM-ZTK-1F-IPX-PLR-RPT-9007 | PIPELINE SOIL INTERACTION STUDY (IP20, IP21, IP22, IP23) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 30-Apr-2026 13:22:37 | kanokon.i@mermaid-group.com | 30-Apr-2026 14:01:20 | Jumpol Sudjitjul | 11-May-2026 | 05-May-2026 09:33:16 | Akkarapat Suntornsuttiwat | 13-May-2026 | 13-May-2026 11:07:49 | Pornlert Wanaphattharaphan | 14-May-2026 | 20-May-2026 00:48:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 20-May-2026 11:11:41 | 20-May-2026 11:22:08 | 0 |  |  | Approver | Locate
AO-000837 | MM-ZTK-1F-IPX-PLR-RPT-9007 | PIPELINE SOIL INTERACTION STUDY (IP20, IP21, IP22, IP23) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 19-Jun-2026 16:41:42 | 26002z1fdcc@thoresen-jutal.com | 19-Jun-2026 16:56:40 | Jumpol Sudjitjul | 26-Jun-2026 |  | Akkarapat Suntornsuttiwat | 30-Jun-2026 | 25-Jun-2026 10:24:57 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 28-Jun-2026 23:10:29 | APPR | Approved | Jumpol Sudjitjul | 02-Jul-2026 | 30-Jun-2026 09:33:23 | 30-Jun-2026 04:03:57 | 0 |  |  | Approver | Locate
AO-001073 | MM-ZTK-1F-IPX-PLR-RPT-9007 | PIPELINE SOIL INTERACTION STUDY (IP20, IP21, IP22, IP23) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 18:47:54 | 26002z1fdcc@thoresen-jutal.com | 10-Jul-2026 20:26:23 | Jumpol Sudjitjul | 20-Jul-2026 |  | Akkarapat Suntornsuttiwat | 22-Jul-2026 | 13-Jul-2026 11:20:43 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 20-Jul-2026 02:49:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 20-Jul-2026 08:54:31 | 20-Jul-2026 02:23:10 | 0 |  |  | Approver | Locate
AO-001360 | MM-ZTK-1F-IPX-PLR-RPT-9007 | PIPELINE SOIL INTERACTION STUDY (IP20, IP21, IP22, IP23) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 31-Jul-2026 16:26:45 | 26002z1fdcc@thoresen-jutal.com | 31-Jul-2026 17:10:35 | Jumpol Sudjitjul | 10-Aug-2026 |  | Akkarapat Suntornsuttiwat | 13-Aug-2026 | 03-Aug-2026 10:51:24 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 22:43:28 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 14:21:36 | 17-Aug-2026 08:46:24 | 0 |  |  | Approver | Locate
AO-000507 | MM-ZTK-1F-IPX-PLR-RPT-9008 | RISER SPAN ANALYSIS REPORT (IP20, IP21, IP22, IP23) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 11:11:11 | 26002z1fdcc@thoresen-jutal.com | 19-May-2026 13:12:02 | Jumpol Sudjitjul | 26-May-2026 | 21-May-2026 09:52:41 | Akkarapat Suntornsuttiwat | 28-May-2026 | 25-May-2026 16:09:30 | Pornlert Wanaphattharaphan | 29-May-2026 | 08-Jun-2026 23:57:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 09-Jun-2026 07:51:57 | 09-Jun-2026 01:27:58 | 0 |  |  | Approver | Locate
AO-000915 | MM-ZTK-1F-IPX-PLR-RPT-9008 | RISER SPAN ANALYSIS REPORT (IP20, IP21, IP22, IP23) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 26-Jun-2026 20:39:40 | 26002z1fdcc@thoresen-jutal.com | 27-Jun-2026 18:50:05 | Jumpol Sudjitjul | 06-Jul-2026 |  | Akkarapat Suntornsuttiwat | 08-Jul-2026 | 01-Jul-2026 11:03:23 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 02-Jul-2026 00:43:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 02-Jul-2026 10:03:56 | 02-Jul-2026 04:29:50 | 0 |  |  | Approver | Locate
AO-001580 | MM-ZTK-1F-IPX-PLR-RPT-9008 | RISER SPAN ANALYSIS REPORT (IP20, IP21, IP22, IP23) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 18:41:55 | 26002z1fdcc@thoresen-jutal.com | 18-Aug-2026 08:53:15 | Jumpol Sudjitjul | 25-Aug-2026 |  | Akkarapat Suntornsuttiwat | 27-Aug-2026 | 18-Aug-2026 10:56:50 | Pornlert Wanaphattharaphan | 28-Aug-2026 | 21-Aug-2026 11:33:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Aug-2026 | 21-Aug-2026 13:09:28 | 21-Aug-2026 06:16:19 | 0 |  |  | Approver | Locate
AO-001737 | MM-ZTK-1F-IPX-PLR-RPT-9008 | RISER SPAN ANALYSIS REPORT (IP20, IP21, IP22, IP23) |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 27-Aug-2026 12:04:19 | 26002z1fdcc@thoresen-jutal.com | 27-Aug-2026 13:08:57 | Jumpol Sudjitjul | 03-Sep-2026 |  | Akkarapat Suntornsuttiwat | 07-Sep-2026 | 03-Sep-2026 09:39:32 | Pornlert Wanaphattharaphan | 08-Sep-2026 | 07-Sep-2026 01:09:20 | APPR | Approved | Jumpol Sudjitjul | 09-Sep-2026 | 07-Sep-2026 17:44:34 | 07-Sep-2026 11:23:50 | 0 |  |  | Approver | Locate
AO-002079 | MM-ZTK-1F-IPX-PLR-RPT-9009 | RISER HANGER FLANGE DESIGN REPORT (IP20, IP21, IP22, IP23) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 15-Sep-2026 16:14:55 | 26002z1fdcc@thoresen-jutal.com | 16-Sep-2026 08:15:06 | Jumpol Sudjitjul | 23-Sep-2026 |  | Akkarapat Suntornsuttiwat | 25-Sep-2026 | 28-Sep-2026 10:44:16 | Pornlert Wanaphattharaphan | 28-Sep-2026 | 28-Sep-2026 21:47:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-Sep-2026 | 29-Sep-2026 10:49:33 | 29-Sep-2026 04:23:15 | 0 |  |  | Approver | Locate
AO-001520 | MM-ZTK-1F-IPX-PLR-RPT-9010 | SEISMIC PIPELINE SOIL INTERACTION STUDY (IP20, IP21, IP22, IP23) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 08:42:45 | 26002z1fdcc@thoresen-jutal.com | 14-Aug-2026 08:56:22 | Jumpol Sudjitjul | 21-Aug-2026 |  | Akkarapat Suntornsuttiwat | 25-Aug-2026 | 20-Aug-2026 09:58:08 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 23-Aug-2026 17:17:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 19:22:36 | 24-Aug-2026 13:24:32 | 0 |  |  | Approver | Locate
AO-001900 | MM-ZTK-1F-IPX-PLR-RPT-9010 | SEISMIC PIPELINE SOIL INTERACTION STUDY (IP20, IP21, IP22, IP23) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:33:31 | 26002z1fdcc@thoresen-jutal.com | 07-Sep-2026 17:10:08 | Jumpol Sudjitjul | 15-Sep-2026 |  | Akkarapat Suntornsuttiwat | 17-Sep-2026 | 08-Sep-2026 09:11:20 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 13-Sep-2026 17:50:06 | APPR | Approved | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 23:10:58 | 13-Sep-2026 17:19:25 | 0 |  |  | Approver | Locate
AO-002119 | MM-ZTK-1F-IPX-PLR-RPT-9010 | SEISMIC PIPELINE SOIL INTERACTION STUDY (IP20, IP21, IP22, IP23) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 17-Sep-2026 12:16:58 | 26002z1fdcc@thoresen-jutal.com | 17-Sep-2026 14:46:24 | Jumpol Sudjitjul | 24-Sep-2026 |  | Akkarapat Suntornsuttiwat | 28-Sep-2026 | 23-Sep-2026 15:08:28 | Pornlert Wanaphattharaphan | 29-Sep-2026 | 26-Sep-2026 05:52:54 | APPR | Approved | Jumpol Sudjitjul | 30-Sep-2026 | 26-Sep-2026 14:24:17 | 26-Sep-2026 08:00:53 | 0 |  |  | Approver | Locate
AO-000596 | MM-ZTK-1F-IPX-PLR-SPE-9001 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR 18" LSAW LINE PIPE AND BEND MOTHER-PIPE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 25-May-2026 12:01:59 | 26002z1fdcc@thoresen-jutal.com | 25-May-2026 13:08:14 | Jumpol Sudjitjul | 02-Jun-2026 |  | Akkarapat Suntornsuttiwat | 05-Jun-2026 | 08-Jun-2026 10:20:22 | Pornlert Wanaphattharaphan | 08-Jun-2026 | 10-Jun-2026 21:21:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jun-2026 | 11-Jun-2026 11:07:40 | 11-Jun-2026 04:53:28 | 0 |  |  | Approver | Locate
AO-000963 | MM-ZTK-1F-IPX-PLR-SPE-9001 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR 18" LSAW LINE PIPE AND BEND MOTHER-PIPE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 01-Jul-2026 08:43:59 | 26002z1fdcc@thoresen-jutal.com | 01-Jul-2026 10:10:02 | Jumpol Sudjitjul | 08-Jul-2026 |  | Akkarapat Suntornsuttiwat | 10-Jul-2026 | 13-Jul-2026 08:31:06 | Pornlert Wanaphattharaphan | 13-Jul-2026 | 14-Jul-2026 20:36:53 | APPR | Approved | Jumpol Sudjitjul | 14-Jul-2026 | 15-Jul-2026 11:21:41 | 15-Jul-2026 05:21:25 | 0 |  |  | Approver | Locate
AO-000597 | MM-ZTK-1F-IPX-PLR-SPE-9002 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR 10" SEAMLESS LINE PIPE AND BEND MOTHER-PIPE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 25-May-2026 12:02:26 | 26002z1fdcc@thoresen-jutal.com | 25-May-2026 13:28:39 | Jumpol Sudjitjul | 02-Jun-2026 | 02-Jun-2026 13:50:37 | Akkarapat Suntornsuttiwat | 05-Jun-2026 | 08-Jun-2026 10:21:15 | Pornlert Wanaphattharaphan | 08-Jun-2026 | 10-Jun-2026 21:21:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jun-2026 | 11-Jun-2026 11:28:26 | 11-Jun-2026 04:56:10 | 0 |  |  | Approver | Locate
AO-000959 | MM-ZTK-1F-IPX-PLR-SPE-9002 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR 10" SEAMLESS LINE PIPE AND BEND MOTHER-PIPE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 30-Jun-2026 18:40:13 | 26002z1fdcc@thoresen-jutal.com | 01-Jul-2026 10:10:20 | Jumpol Sudjitjul | 08-Jul-2026 |  | Akkarapat Suntornsuttiwat | 10-Jul-2026 | 13-Jul-2026 08:34:09 | Pornlert Wanaphattharaphan | 13-Jul-2026 | 14-Jul-2026 20:37:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Jul-2026 | 15-Jul-2026 11:22:26 | 15-Jul-2026 04:56:03 | 0 |  |  | Approver | Locate
AO-001219 | MM-ZTK-1F-IPX-PLR-SPE-9002 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR 10" SEAMLESS LINE PIPE AND BEND MOTHER-PIPE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 21-Jul-2026 12:38:30 | 26002z1fdcc@thoresen-jutal.com | 21-Jul-2026 13:14:30 | Jumpol Sudjitjul | 30-Jul-2026 |  | Akkarapat Suntornsuttiwat | 03-Aug-2026 | 21-Jul-2026 15:33:38 | Pornlert Wanaphattharaphan | 04-Aug-2026 | 29-Jul-2026 08:47:22 | APPR | Approved | Jumpol Sudjitjul | 05-Aug-2026 | 30-Jul-2026 09:48:58 | 30-Jul-2026 03:58:49 | 0 |  |  | Approver | Locate
AO-000812 | MM-ZTK-1F-IPX-PLR-SPE-9003 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR CONCRETE WEIGHT COATING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 16-Jun-2026 09:36:09 | 26002z1fdcc@thoresen-jutal.com | 16-Jun-2026 11:13:56 | Jumpol Sudjitjul | 23-Jun-2026 |  | Akkarapat Suntornsuttiwat | 25-Jun-2026 | 22-Jun-2026 09:15:34 | Pornlert Wanaphattharaphan | 26-Jun-2026 | 24-Jun-2026 23:22:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-Jun-2026 | 25-Jun-2026 13:44:43 | 25-Jun-2026 07:31:38 | 0 |  |  | Approver | Locate
AO-000970 | MM-ZTK-1F-IPX-PLR-SPE-9003 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR CONCRETE WEIGHT COATING |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 01-Jul-2026 18:01:19 | 26002z1fdcc@thoresen-jutal.com | 02-Jul-2026 13:55:19 | Jumpol Sudjitjul | 09-Jul-2026 |  | Akkarapat Suntornsuttiwat | 13-Jul-2026 | 13-Jul-2026 08:35:43 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 14-Jul-2026 20:49:07 | APPR | Approved | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 11:23:15 | 15-Jul-2026 05:08:53 | 0 |  |  | Approver | Locate
AO-000816 | MM-ZTK-1F-IPX-PLR-SPE-9004 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR HOT INDUCTION BENDS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 16-Jun-2026 18:43:02 | 26002z1fdcc@thoresen-jutal.com | 17-Jun-2026 08:55:36 | Jumpol Sudjitjul | 24-Jun-2026 | 19-Jun-2026 01:48:15 | Akkarapat Suntornsuttiwat | 26-Jun-2026 | 22-Jun-2026 09:17:13 | Pornlert Wanaphattharaphan | 29-Jun-2026 | 24-Jun-2026 23:23:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 30-Jun-2026 | 25-Jun-2026 13:48:42 | 25-Jun-2026 07:16:38 | 0 |  |  | Approver | Locate
AO-000970 | MM-ZTK-1F-IPX-PLR-SPE-9004 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR HOT INDUCTION BENDS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 01-Jul-2026 18:01:53 | 26002z1fdcc@thoresen-jutal.com | 02-Jul-2026 13:55:53 | Jumpol Sudjitjul | 09-Jul-2026 |  | Akkarapat Suntornsuttiwat | 13-Jul-2026 | 13-Jul-2026 08:37:02 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 14-Jul-2026 20:49:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jul-2026 | 15-Jul-2026 11:23:02 | 15-Jul-2026 05:10:22 | 0 |  |  | Approver | Locate
AO-001559 | MM-ZTK-1F-IPX-PLR-SPE-9004 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR HOT INDUCTION BENDS |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 14:50:48 | 26002z1fdcc@thoresen-jutal.com | 17-Aug-2026 15:40:50 | Jumpol Sudjitjul | 24-Aug-2026 | 18-Aug-2026 09:26:29 | Akkarapat Suntornsuttiwat | 26-Aug-2026 | 18-Aug-2026 10:03:25 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:03:13 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 19:22:02 | 24-Aug-2026 12:57:51 | 0 |  |  | Approver | Locate
AO-000901 | MM-ZTK-1F-IPX-PLR-SPE-9005 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR PIPELINE/RISER EXTERNAL ANTI-CORROSION COATING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 09:59:28 | 26002z1fdcc@thoresen-jutal.com | 26-Jun-2026 10:19:52 | Jumpol Sudjitjul | 03-Jul-2026 |  | Akkarapat Suntornsuttiwat | 07-Jul-2026 | 13-Jul-2026 08:38:35 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 13-Jul-2026 22:50:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 14-Jul-2026 08:50:10 | 14-Jul-2026 02:16:16 | 0 |  |  | Approver | Locate
AO-001282 | MM-ZTK-1F-IPX-PLR-SPE-9005 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR PIPELINE/RISER EXTERNAL ANTI-CORROSION COATING |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 27-Jul-2026 08:50:24 | 26002z1fdcc@thoresen-jutal.com | 27-Jul-2026 16:01:32 | Jumpol Sudjitjul | 05-Aug-2026 |  | Akkarapat Suntornsuttiwat | 07-Aug-2026 | 31-Jul-2026 11:23:45 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 06:04:58 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 07-Aug-2026 08:49:15 | 07-Aug-2026 02:17:22 | 0 |  |  | Approver | Locate
AO-000863 | MM-ZTK-1F-IPX-PLR-SPE-9006 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR SACRIFICIAL BRACELET ANODE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 22-Jun-2026 13:24:01 | 26002z1fdcc@thoresen-jutal.com | 22-Jun-2026 14:43:13 | Jumpol Sudjitjul | 29-Jun-2026 |  | Akkarapat Suntornsuttiwat | 01-Jul-2026 | 01-Jul-2026 08:14:50 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 01-Jul-2026 15:05:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 01-Jul-2026 15:26:51 | 01-Jul-2026 08:56:42 | 0 |  |  | Approver | Locate
AO-000987 | MM-ZTK-1F-IPX-PLR-SPE-9006 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR SACRIFICIAL BRACELET ANODE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Jul-2026 09:52:29 | 26002z1fdcc@thoresen-jutal.com | 03-Jul-2026 14:19:43 | Jumpol Sudjitjul | 10-Jul-2026 |  | Akkarapat Suntornsuttiwat | 14-Jul-2026 | 13-Jul-2026 08:55:04 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 23:24:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 11:21:35 | 15-Jul-2026 05:07:32 | 0 |  |  | Approver | Locate
AO-001469 | MM-ZTK-1F-IPX-PLR-SPE-9006 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR SACRIFICIAL BRACELET ANODE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 10-Aug-2026 12:04:58 | 26002z1fdcc@thoresen-jutal.com | 10-Aug-2026 15:11:58 | Jumpol Sudjitjul | 18-Aug-2026 |  | Akkarapat Suntornsuttiwat | 20-Aug-2026 | 18-Aug-2026 09:12:03 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 17:00:43 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 19:21:27 | 24-Aug-2026 12:56:42 | 0 |  |  | Approver | Locate
AO-000915 | MM-ZTK-1F-IPX-PLR-SPE-9007 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR FLANGES, FITTINGS, GASKETS AND FASTENERS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 20:40:07 | 26002z1fdcc@thoresen-jutal.com | 27-Jun-2026 18:58:09 | Jumpol Sudjitjul | 06-Jul-2026 |  | Akkarapat Suntornsuttiwat | 08-Jul-2026 | 13-Jul-2026 08:42:55 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 13-Jul-2026 23:18:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 14-Jul-2026 08:49:32 | 14-Jul-2026 02:14:53 | 0 |  |  | Approver | Locate
AO-001219 | MM-ZTK-1F-IPX-PLR-SPE-9007 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR FLANGES, FITTINGS, GASKETS AND FASTENERS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 21-Jul-2026 12:38:57 | 26002z1fdcc@thoresen-jutal.com | 21-Jul-2026 13:14:44 | Jumpol Sudjitjul | 30-Jul-2026 |  | Akkarapat Suntornsuttiwat | 03-Aug-2026 | 22-Jul-2026 11:01:57 | Pornlert Wanaphattharaphan | 04-Aug-2026 | 29-Jul-2026 08:48:51 | APPR | Approved | Jumpol Sudjitjul | 05-Aug-2026 | 30-Jul-2026 09:41:13 | 30-Jul-2026 03:50:52 | 0 |  |  | Approver | Locate
AO-000961 | MM-ZTK-1F-IPX-PLR-SPE-9008 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR FIELD JOINT COATING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 30-Jun-2026 18:40:42 | 26002z1fdcc@thoresen-jutal.com | 01-Jul-2026 10:10:40 | Jumpol Sudjitjul | 08-Jul-2026 |  | Akkarapat Suntornsuttiwat | 10-Jul-2026 | 13-Jul-2026 08:45:33 | Pornlert Wanaphattharaphan | 13-Jul-2026 | 14-Jul-2026 13:48:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Jul-2026 | 14-Jul-2026 15:02:17 | 14-Jul-2026 08:31:58 | 0 |  |  | Approver | Locate
AO-001219 | MM-ZTK-1F-IPX-PLR-SPE-9008 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR FIELD JOINT COATING |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 21-Jul-2026 12:39:24 | 26002z1fdcc@thoresen-jutal.com | 21-Jul-2026 13:14:59 | Jumpol Sudjitjul | 30-Jul-2026 |  | Akkarapat Suntornsuttiwat | 03-Aug-2026 | 22-Jul-2026 10:53:03 | Pornlert Wanaphattharaphan | 04-Aug-2026 | 29-Jul-2026 08:48:24 | APPR | Approved | Jumpol Sudjitjul | 05-Aug-2026 | 30-Jul-2026 09:40:31 | 30-Jul-2026 03:49:36 | 0 |  |  | Approver | Locate
AO-001635 | MM-ZTK-1F-IPX-PLR-SPE-9009 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR PRE-COMMISSIONING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 21-Aug-2026 10:32:03 | 26002z1fdcc@thoresen-jutal.com | 21-Aug-2026 11:04:59 | Jumpol Sudjitjul | 28-Aug-2026 | 02-Sep-2026 09:37:50 | Akkarapat Suntornsuttiwat | 01-Sep-2026 | 02-Sep-2026 15:31:58 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 02-Sep-2026 21:33:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Sep-2026 | 03-Sep-2026 09:52:57 | 03-Sep-2026 03:27:33 | 0 |  |  | Approver | Locate
AO-002303 | MM-ZTK-1F-IPX-PLR-SPE-9009 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR PRE-COMMISSIONING |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 15:21:44 | 26002z1fdcc@thoresen-jutal.com | 28-Sep-2026 15:58:13 | Jumpol Sudjitjul | 05-Oct-2026 | 05-Oct-2026 11:50:36 | Akkarapat Suntornsuttiwat | 07-Oct-2026 | 07-Oct-2026 13:13:48 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 10-Oct-2026 01:24:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 10-Oct-2026 17:32:55 | 10-Oct-2026 11:33:02 | 0 |  |  | Approver | Locate
AO-001037 | MM-ZTK-1F-IPX-PLR-SPE-9010 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR WELDING OF PIPELINE ACCORDING TO API 1104 |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 08-Jul-2026 17:28:53 | 26002z1fdcc@thoresen-jutal.com | 09-Jul-2026 10:33:02 | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 17:04:54 | Akkarapat Suntornsuttiwat | 20-Jul-2026 | 23-Jul-2026 08:25:55 | Pornlert Wanaphattharaphan | 21-Jul-2026 | 24-Jul-2026 00:00:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jul-2026 | 24-Jul-2026 08:23:26 | 24-Jul-2026 01:56:09 | 0 |  |  | Approver | Locate
AO-001375 | MM-ZTK-1F-IPX-PLR-SPE-9010 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR WELDING OF PIPELINE ACCORDING TO API 1104 |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 11:04:53 | 26002z1fdcc@thoresen-jutal.com | 03-Aug-2026 14:10:14 | Jumpol Sudjitjul | 10-Aug-2026 |  | Akkarapat Suntornsuttiwat | 13-Aug-2026 | 03-Aug-2026 16:32:38 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 22:48:53 | APPR | Approved | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 14:23:33 | 17-Aug-2026 08:48:55 | 0 |  |  | Approver | Locate
AO-000812 | MM-ZTK-1F-IPX-PLR-SPE-9011 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR BEND ANTI-CORROSION COATING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | IFR | Issued for Review |  | 16-Jun-2026 09:36:41 | 26002z1fdcc@thoresen-jutal.com | 16-Jun-2026 11:08:25 | Jumpol Sudjitjul | 23-Jun-2026 |  | Akkarapat Suntornsuttiwat | 25-Jun-2026 | 22-Jun-2026 09:19:28 | Pornlert Wanaphattharaphan | 26-Jun-2026 | 24-Jun-2026 23:22:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-Jun-2026 | 25-Jun-2026 13:51:56 | 25-Jun-2026 07:35:16 | 0 |  |  | Approver | Locate
AO-000970 | MM-ZTK-1F-IPX-PLR-SPE-9011 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR BEND ANTI-CORROSION COATING |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 01-Jul-2026 16:41:50 | 26002z1fdcc@thoresen-jutal.com | 01-Jul-2026 16:58:35 | Jumpol Sudjitjul | 08-Jul-2026 |  | Akkarapat Suntornsuttiwat | 10-Jul-2026 | 13-Jul-2026 08:48:52 | Pornlert Wanaphattharaphan | 13-Jul-2026 | 14-Jul-2026 20:48:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Jul-2026 | 15-Jul-2026 11:21:06 | 15-Jul-2026 05:20:15 | 0 |  |  | Approver | Locate
AO-001559 | MM-ZTK-1F-IPX-PLR-SPE-9011 | PROJECT PARTICULAR SPECIFICATION & DATASHEET FOR BEND ANTI-CORROSION COATING |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | SPE | Specification | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 14:51:22 | 26002z1fdcc@thoresen-jutal.com | 17-Aug-2026 15:41:29 | Jumpol Sudjitjul | 24-Aug-2026 | 18-Aug-2026 09:38:47 | Akkarapat Suntornsuttiwat | 26-Aug-2026 | 18-Aug-2026 10:09:41 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:06:19 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 19:20:43 | 24-Aug-2026 12:55:27 | 0 |  |  | Approver | Locate
AO-001331 | MM-ZTK-1F-IPX-PLR-TBE-9001 | TECHNICAL BID EVALUATION FOR 18" LSAW LINE PIPE AND BEND MOTHER-PIPE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | TBE | Technical Bid Evaluation | 0 | Submitted | IFR | Issued for Review |  | 30-Jul-2026 09:53:08 | 26002z1fdcc@thoresen-jutal.com | 30-Jul-2026 10:12:29 | Jumpol Sudjitjul | 06-Aug-2026 | 08-Aug-2026 07:04:06 | Akkarapat Suntornsuttiwat | 10-Aug-2026 | 11-Aug-2026 08:37:43 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 11-Aug-2026 17:33:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Aug-2026 | 11-Aug-2026 17:50:11 | 11-Aug-2026 11:26:43 | 0 |  |  | Approver | Locate
AO-001603 | MM-ZTK-1F-IPX-PLR-TBE-9001 | TECHNICAL BID EVALUATION FOR 18" LSAW LINE PIPE AND BEND MOTHER-PIPE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 10:09:25 | 26002z1fdcc@thoresen-jutal.com | 19-Aug-2026 11:10:16 | Jumpol Sudjitjul | 26-Aug-2026 | 21-Aug-2026 11:05:07 | Akkarapat Suntornsuttiwat | 28-Aug-2026 | 21-Aug-2026 14:28:22 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 22-Aug-2026 14:09:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Sep-2026 | 24-Aug-2026 19:20:08 | 24-Aug-2026 12:54:18 | 0 |  |  | Approver | Locate
AO-002159 | MM-ZTK-1F-IPX-PLR-TBE-9001 | TECHNICAL BID EVALUATION FOR 18" LSAW LINE PIPE AND BEND MOTHER-PIPE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 17:29:32 | 26002z1fdcc@thoresen-jutal.com | 18-Sep-2026 17:49:57 | Jumpol Sudjitjul | 28-Sep-2026 | 24-Sep-2026 14:29:10 | Akkarapat Suntornsuttiwat | 30-Sep-2026 | 28-Sep-2026 15:08:27 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 28-Sep-2026 22:46:00 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 29-Sep-2026 10:43:26 | 29-Sep-2026 04:21:55 | 0 |  |  | Approver | Locate
AO-001331 | MM-ZTK-1F-IPX-PLR-TBE-9002 | TECHNICAL BID EVALUATION FOR 10" SEAMLESS LINE PIPE AND BEND MOTHER-PIPE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | TBE | Technical Bid Evaluation | 0 | Submitted | IFR | Issued for Review |  | 30-Jul-2026 09:53:33 | 26002z1fdcc@thoresen-jutal.com | 30-Jul-2026 10:13:55 | Jumpol Sudjitjul | 06-Aug-2026 | 08-Aug-2026 07:15:24 | Akkarapat Suntornsuttiwat | 10-Aug-2026 | 11-Aug-2026 08:40:47 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 11-Aug-2026 16:53:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Aug-2026 | 11-Aug-2026 17:44:05 | 11-Aug-2026 11:24:01 | 0 |  |  | Approver | Locate
AO-002086 | MM-ZTK-1F-IPX-PLR-TBE-9002 | TECHNICAL BID EVALUATION FOR 10" SEAMLESS LINE PIPE AND BEND MOTHER-PIPE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 15-Sep-2026 16:15:29 | 26002z1fdcc@thoresen-jutal.com | 15-Sep-2026 17:18:14 | Jumpol Sudjitjul | 23-Sep-2026 |  | Akkarapat Suntornsuttiwat | 25-Sep-2026 | 17-Sep-2026 15:06:36 | Pornlert Wanaphattharaphan | 28-Sep-2026 | 19-Sep-2026 16:09:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-Sep-2026 | 20-Sep-2026 17:16:15 | 20-Sep-2026 11:11:31 | 0 |  |  | Approver | Locate
AO-002213 | MM-ZTK-1F-IPX-PLR-TBE-9002 | TECHNICAL BID EVALUATION FOR 10" SEAMLESS LINE PIPE AND BEND MOTHER-PIPE |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 22-Sep-2026 17:26:06 | 26002z1fdcc@thoresen-jutal.com | 22-Sep-2026 17:40:42 | Jumpol Sudjitjul | 30-Sep-2026 | 28-Sep-2026 14:29:57 | Akkarapat Suntornsuttiwat | 02-Oct-2026 | 28-Sep-2026 15:10:58 | Pornlert Wanaphattharaphan | 05-Oct-2026 | 28-Sep-2026 22:53:29 | APPR | Approved | Jumpol Sudjitjul | 06-Oct-2026 | 29-Sep-2026 10:37:31 | 29-Sep-2026 05:00:12 | 0 |  |  | Approver | Locate
AO-001401 | MM-ZTK-1F-IPX-PLR-TBE-9003 | TECHNICAL BID EVALUATION FOR PIPELINE EXTERNAL ANTI-CORROSION COATING & CONCRETE WEIGHT COATING & BEND COATING & RISER/SPOOL EXTERNAL ANTICORROSION COATING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Issued for Review |  | 03-Aug-2026 16:55:18 | 26002z1fdcc@thoresen-jutal.com | 04-Aug-2026 08:20:40 | Jumpol Sudjitjul | 11-Aug-2026 | 11-Aug-2026 09:40:22 | Akkarapat Suntornsuttiwat | 14-Aug-2026 | 18-Aug-2026 09:34:22 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 18-Aug-2026 22:33:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 19-Aug-2026 09:55:44 | 19-Aug-2026 03:01:34 | 0 |  |  | Approver | Locate
AO-002128 | MM-ZTK-1F-IPX-PLR-TBE-9003 | TECHNICAL BID EVALUATION FOR PIPELINE EXTERNAL ANTI-CORROSION COATING & CONCRETE WEIGHT COATING & BEND COATING & RISER/SPOOL EXTERNAL ANTICORROSION COATING |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 17-Sep-2026 16:09:19 | 26002z1fdcc@thoresen-jutal.com | 17-Sep-2026 16:12:48 | Jumpol Sudjitjul | 24-Sep-2026 | 22-Sep-2026 16:11:53 | Akkarapat Suntornsuttiwat | 28-Sep-2026 | 28-Sep-2026 14:59:19 | Pornlert Wanaphattharaphan | 29-Sep-2026 | 28-Sep-2026 22:06:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 30-Sep-2026 | 29-Sep-2026 10:35:12 | 29-Sep-2026 04:58:58 | 0 |  |  | Approver | Locate
AO-002538 | MM-ZTK-1F-IPX-PLR-TBE-9003 | TECHNICAL BID EVALUATION FOR PIPELINE EXTERNAL ANTI-CORROSION COATING & CONCRETE WEIGHT COATING & BEND COATING & RISER/SPOOL EXTERNAL ANTICORROSION COATING |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | TBE | Technical Bid Evaluation | 0 | In Review | AFC | Approved for Construction |  | 16-Oct-2026 10:54:05 | 26002z1fdcc@thoresen-jutal.com | 16-Oct-2026 17:29:46 | Jumpol Sudjitjul | 27-Oct-2026 |  | Akkarapat Suntornsuttiwat | 29-Oct-2026 |  | Pornlert Wanaphattharaphan | 30-Oct-2026 |  |  |  |  | 02-Nov-2026 |  |  | 0 |  |  | Approver | Locate
AO-001331 | MM-ZTK-1F-IPX-PLR-TBE-9004 | TECHNICAL BID EVALUATION FOR HOT INDUCTION BENDS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | TBE | Technical Bid Evaluation | 0 | Submitted | IFR | Issued for Review |  | 30-Jul-2026 09:54:00 | 26002z1fdcc@thoresen-jutal.com | 30-Jul-2026 10:15:17 | Jumpol Sudjitjul | 06-Aug-2026 |  | Akkarapat Suntornsuttiwat | 10-Aug-2026 | 11-Aug-2026 08:44:48 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 11-Aug-2026 16:43:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Aug-2026 | 11-Aug-2026 17:44:38 | 11-Aug-2026 11:25:23 | 0 |  |  | Approver | Locate
AO-001604 | MM-ZTK-1F-IPX-PLR-TBE-9004 | TECHNICAL BID EVALUATION FOR HOT INDUCTION BENDS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 10:09:54 | 26002z1fdcc@thoresen-jutal.com | 19-Aug-2026 11:10:39 | Jumpol Sudjitjul | 26-Aug-2026 | 21-Aug-2026 11:19:34 | Akkarapat Suntornsuttiwat | 28-Aug-2026 | 21-Aug-2026 14:30:07 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 22-Aug-2026 14:08:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Sep-2026 | 24-Aug-2026 19:18:53 | 24-Aug-2026 12:52:57 | 0 |  |  | Approver | Locate
AO-002195 | MM-ZTK-1F-IPX-PLR-TBE-9004 | TECHNICAL BID EVALUATION FOR HOT INDUCTION BENDS |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 09:40:17 | 26002z1fdcc@thoresen-jutal.com | 21-Sep-2026 09:55:13 | Jumpol Sudjitjul | 28-Sep-2026 | 25-Sep-2026 11:36:28 | Akkarapat Suntornsuttiwat | 30-Sep-2026 | 29-Sep-2026 08:51:30 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 30-Sep-2026 00:45:32 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 30-Sep-2026 13:15:29 | 30-Sep-2026 06:40:37 | 0 |  |  | Approver | Locate
AO-001402 | MM-ZTK-1F-IPX-PLR-TBE-9005 | TECHNICAL BID EVALUATION FOR PIPELINE/RISER EXTERNAL ANTI-CORROSION COATING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | TBE | Technical Bid Evaluation | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 15:21:25 | 26002z1fdcc@thoresen-jutal.com | 03-Aug-2026 15:41:44 | Jumpol Sudjitjul | 10-Aug-2026 | 11-Aug-2026 09:39:56 | Akkarapat Suntornsuttiwat | 13-Aug-2026 | 18-Aug-2026 09:45:26 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 18-Aug-2026 23:15:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 19-Aug-2026 09:56:17 | 19-Aug-2026 03:05:35 | 0 |  |  | Approver | Locate
AO-001719 | MM-ZTK-1F-IPX-PLR-TBE-9006 | TECHNICAL BID EVALUATION FOR SACRIFICIAL BRACELET ANODE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | TBE | Technical Bid Evaluation | 0 | Submitted | IFR | Issued for Review |  | 26-Aug-2026 18:38:21 | 26002z1fdcc@thoresen-jutal.com | 27-Aug-2026 09:00:37 | Jumpol Sudjitjul | 03-Sep-2026 | 02-Sep-2026 08:57:49 | Akkarapat Suntornsuttiwat | 07-Sep-2026 | 02-Sep-2026 15:48:00 | Pornlert Wanaphattharaphan | 08-Sep-2026 | 02-Sep-2026 21:24:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Sep-2026 | 03-Sep-2026 09:55:14 | 03-Sep-2026 03:10:32 | 0 |  |  | Approver | Locate
AO-001946 | MM-ZTK-1F-IPX-PLR-TBE-9006 | TECHNICAL BID EVALUATION FOR SACRIFICIAL BRACELET ANODE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 09-Sep-2026 10:17:21 | 26002z1fdcc@thoresen-jutal.com | 09-Sep-2026 16:47:36 | Jumpol Sudjitjul | 16-Sep-2026 | 14-Sep-2026 15:41:12 | Akkarapat Suntornsuttiwat | 18-Sep-2026 | 17-Sep-2026 09:52:40 | Pornlert Wanaphattharaphan | 21-Sep-2026 | 19-Sep-2026 15:06:11 | APPR | Approved | Jumpol Sudjitjul | 22-Sep-2026 | 20-Sep-2026 17:17:18 | 20-Sep-2026 11:35:49 | 0 |  |  | Approver | Locate
AO-001745 | MM-ZTK-1F-IPX-PLR-TBE-9007 | TECHNICAL BID EVALUATION FOR FLANGES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | TBE | Technical Bid Evaluation | 0 | Submitted | IFR | Issued for Review |  | 28-Aug-2026 10:33:53 | 26002z1fdcc@thoresen-jutal.com | 28-Aug-2026 14:07:39 | Jumpol Sudjitjul | 04-Sep-2026 | 01-Sep-2026 16:28:22 | Akkarapat Suntornsuttiwat | 08-Sep-2026 | 02-Sep-2026 15:59:07 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 02-Sep-2026 21:30:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 03-Sep-2026 09:57:40 | 03-Sep-2026 03:52:50 | 0 |  |  | Approver | Locate
AO-001921 | MM-ZTK-1F-IPX-PLR-TBE-9007 | TECHNICAL BID EVALUATION FOR FLANGES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 18:41:02 | 26002z1fdcc@thoresen-jutal.com | 08-Sep-2026 09:45:50 | Jumpol Sudjitjul | 15-Sep-2026 | 08-Sep-2026 15:41:40 | Akkarapat Suntornsuttiwat | 17-Sep-2026 | 10-Sep-2026 16:40:06 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 11-Sep-2026 00:31:18 | APPR | Approved | Jumpol Sudjitjul | 21-Sep-2026 | 11-Sep-2026 08:15:53 | 11-Sep-2026 01:55:25 | 0 |  |  | Approver | Locate
AO-001702 | MM-ZTK-1F-IPX-PLR-TBE-9011 | TECHNICAL BID EVALUATION FOR FIELD JOINT COATING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | TBE | Technical Bid Evaluation | 0 | Submitted | IFR | Issued for Review |  | 25-Aug-2026 11:58:20 | 26002z1fdcc@thoresen-jutal.com | 26-Aug-2026 09:00:49 | Jumpol Sudjitjul | 02-Sep-2026 | 02-Sep-2026 09:44:01 | Akkarapat Suntornsuttiwat | 04-Sep-2026 | 02-Sep-2026 16:27:39 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 02-Sep-2026 21:20:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Sep-2026 | 03-Sep-2026 09:58:58 | 03-Sep-2026 04:26:10 | 0 |  |  | Approver | Locate
AO-002157 | MM-ZTK-1F-IPX-PLR-TBE-9011 | TECHNICAL BID EVALUATION FOR FIELD JOINT COATING |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | TBE | Technical Bid Evaluation | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 17:30:02 | 26002z1fdcc@thoresen-jutal.com | 18-Sep-2026 17:50:13 | Jumpol Sudjitjul | 28-Sep-2026 | 24-Sep-2026 14:30:36 | Akkarapat Suntornsuttiwat | 30-Sep-2026 | 29-Sep-2026 08:46:56 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 30-Sep-2026 00:44:13 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 30-Sep-2026 13:14:50 | 30-Sep-2026 06:35:16 | 0 |  |  | Approver | Locate
AO-001922 | MM-ZTK-1F-IPX-PLR-TBE-9012 | TECHNICAL BID EVALUATION FOR SPLASH ZONE COATING |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PLR | Pipeline | TBE | Technical Bid Evaluation | 0 | Submitted | IFR | Issued for Review |  | 07-Sep-2026 18:41:28 | 26002z1fdcc@thoresen-jutal.com | 08-Sep-2026 09:47:39 | Jumpol Sudjitjul | 15-Sep-2026 | 10-Sep-2026 09:27:58 | Akkarapat Suntornsuttiwat | 17-Sep-2026 | 16-Sep-2026 11:14:05 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 00:26:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 17:16:34 | 20-Sep-2026 12:01:48 | 0 |  |  | Approver | Locate
AO-000569 | MM-ZTK-1F-IPX-PRO-BOD-9001 | DESIGN BASIS FOR PIPELINE AND RISER FLOW ASSURANCE STUDIES |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PRO | Process | BOD | Basis of Design | 0 | Submitted | IFR | Issued for Review |  | 22-May-2026 10:58:25 | 26002z1fdcc@thoresen-jutal.com | 22-May-2026 12:41:19 | Jumpol Sudjitjul | 29-May-2026 | 27-May-2026 09:40:50 | Chananun Rojanarungruengporn | 04-Jun-2026 | 02-Jun-2026 11:17:27 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 08-Jun-2026 23:53:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 09-Jun-2026 07:52:27 | 09-Jun-2026 01:23:08 | 0 |  |  | Approver | Locate
AO-000898 | MM-ZTK-1F-IPX-PRO-BOD-9001 | DESIGN BASIS FOR PIPELINE AND RISER FLOW ASSURANCE STUDIES |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PRO | Process | BOD | Basis of Design | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 23:17:58 | 26002z1fdcc@thoresen-jutal.com | 26-Jun-2026 08:45:13 | Jumpol Sudjitjul | 03-Jul-2026 | 01-Jul-2026 11:21:07 | Chananun Rojanarungruengporn | 07-Jul-2026 | 08-Jul-2026 17:07:43 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 11-Jul-2026 13:48:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 12-Jul-2026 11:36:28 | 12-Jul-2026 05:27:59 | 0 |  |  | Approver | Locate
AO-001147 | MM-ZTK-1F-IPX-PRO-BOD-9001 | DESIGN BASIS FOR PIPELINE AND RISER FLOW ASSURANCE STUDIES |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PRO | Process | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 16-Jul-2026 21:16:11 | 26002z1fdcc@thoresen-jutal.com | 17-Jul-2026 10:35:40 | Jumpol Sudjitjul | 24-Jul-2026 | 20-Jul-2026 14:41:26 | Chananun Rojanarungruengporn | 30-Jul-2026 | 24-Jul-2026 14:35:10 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 26-Jul-2026 11:19:15 | APPR | Approved | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 15:06:29 | 27-Jul-2026 10:30:52 | 0 |  |  | Approver | Locate
AO-001568 | MM-ZTK-1F-IPX-PRO-BOD-9001 | DESIGN BASIS FOR PIPELINE AND RISER FLOW ASSURANCE STUDIES |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PRO | Process | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 17:19:55 | 26002z1fdcc@thoresen-jutal.com | 18-Aug-2026 09:01:19 | Jumpol Sudjitjul | 25-Aug-2026 | 23-Aug-2026 23:13:33 | Chananun Rojanarungruengporn | 27-Aug-2026 | 24-Aug-2026 08:42:52 | Pornlert Wanaphattharaphan | 28-Aug-2026 | 29-Aug-2026 23:08:04 | APPR | Approved | Jumpol Sudjitjul | 31-Aug-2026 | 30-Aug-2026 16:48:29 | 30-Aug-2026 10:18:12 | 0 |  |  | Approver | Locate
AO-000901 | MM-ZTK-1F-IPX-PRO-RPT-9001 | PIPELINE FLOW ASSURANCE - STEADY STATE ANALYSIS (IP20, IP21, IP22, IP23) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PRO | Process | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 26-Jun-2026 10:00:01 | 26002z1fdcc@thoresen-jutal.com | 26-Jun-2026 10:13:00 | Jumpol Sudjitjul | 03-Jul-2026 | 01-Jul-2026 13:08:45 | Chananun Rojanarungruengporn | 07-Jul-2026 | 08-Jul-2026 22:54:08 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 11-Jul-2026 13:05:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 12-Jul-2026 11:35:01 | 12-Jul-2026 04:49:15 | 0 |  |  | Approver | Locate
AO-001147 | MM-ZTK-1F-IPX-PRO-RPT-9001 | PIPELINE FLOW ASSURANCE - STEADY STATE ANALYSIS (IP20, IP21, IP22, IP23) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PRO | Process | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 21:16:42 | 26002z1fdcc@thoresen-jutal.com | 17-Jul-2026 10:37:01 | Jumpol Sudjitjul | 24-Jul-2026 | 25-Jul-2026 23:56:23 | Chananun Rojanarungruengporn | 30-Jul-2026 | 04-Aug-2026 10:34:00 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 05-Aug-2026 20:40:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 06-Aug-2026 09:36:08 | 06-Aug-2026 03:33:13 | 0 |  |  | Approver | Locate
AO-001568 | MM-ZTK-1F-IPX-PRO-RPT-9001 | PIPELINE FLOW ASSURANCE - STEADY STATE ANALYSIS (IP20, IP21, IP22, IP23) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PRO | Process | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 17:20:32 | 26002z1fdcc@thoresen-jutal.com | 18-Aug-2026 09:03:07 | Jumpol Sudjitjul | 25-Aug-2026 | 24-Aug-2026 23:56:03 | Chananun Rojanarungruengporn | 27-Aug-2026 | 26-Aug-2026 07:53:20 | Pornlert Wanaphattharaphan | 28-Aug-2026 | 29-Aug-2026 23:09:24 | APPR | Approved | Jumpol Sudjitjul | 31-Aug-2026 | 30-Aug-2026 16:47:31 | 30-Aug-2026 10:15:52 | 0 |  |  | Approver | Locate
AO-001045 | MM-ZTK-1F-IPX-PRO-RPT-9002 | PIPELINE FLOW ASSURANCE -TRANSIENT ANALYSIS (IP20, IP21, IP22, IP23) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PRO | Process | RPT | Report | 0 | Submitted | IFR | Issued for Review |  | 09-Jul-2026 15:37:05 | 26002z1fdcc@thoresen-jutal.com | 09-Jul-2026 17:13:09 | Jumpol Sudjitjul | 17-Jul-2026 |  | Chananun Rojanarungruengporn | 21-Jul-2026 | 22-Jul-2026 10:14:00 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 24-Jul-2026 00:16:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 24-Jul-2026 08:22:20 | 24-Jul-2026 02:03:00 | 0 |  |  | Approver | Locate
AO-001501 | MM-ZTK-1F-IPX-PRO-RPT-9002 | PIPELINE FLOW ASSURANCE -TRANSIENT ANALYSIS (IP20, IP21, IP22, IP23) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PRO | Process | RPT | Report | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 12:59:46 | 26002z1fdcc@thoresen-jutal.com | 10-Aug-2026 15:13:27 | Jumpol Sudjitjul | 18-Aug-2026 | 18-Aug-2026 23:27:27 | Chananun Rojanarungruengporn | 20-Aug-2026 | 19-Aug-2026 09:30:29 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:39:41 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 18:41:51 | 24-Aug-2026 12:51:37 | 0 |  |  | Approver | Locate
AO-001738 | MM-ZTK-1F-IPX-PRO-RPT-9002 | PIPELINE FLOW ASSURANCE -TRANSIENT ANALYSIS (IP20, IP21, IP22, IP23) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | IPX |  |  | PRO | Process | RPT | Report | 0 | Submitted | AFC | Approved for Construction |  | 27-Aug-2026 12:04:48 | 26002z1fdcc@thoresen-jutal.com | 27-Aug-2026 13:06:57 | Jumpol Sudjitjul | 03-Sep-2026 | 03-Sep-2026 23:55:29 | Chananun Rojanarungruengporn | 07-Sep-2026 | 04-Sep-2026 13:59:10 | Pornlert Wanaphattharaphan | 08-Sep-2026 | 07-Sep-2026 01:10:13 | APPR | Approved | Jumpol Sudjitjul | 09-Sep-2026 | 07-Sep-2026 17:44:08 | 07-Sep-2026 11:22:35 | 0 |  |  | Approver | Locate
AO-001352 | MM-ZTK-1F-ZPQ-INS-MR-0001 | MATERIAL REQUISITION FOR SCADA SYSTEM |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZPQ |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 31-Jul-2026 11:27:06 | wisuda.c@jutal.com | 31-Jul-2026 13:49:01 | Jumpol Sudjitjul | 07-Aug-2026 | 05-Aug-2026 14:04:44 | Wichai Salee | 11-Aug-2026 | 09-Aug-2026 18:15:53 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 12-Aug-2026 10:04:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Aug-2026 | 13-Aug-2026 11:35:54 | 13-Aug-2026 05:30:58 | 0 |  |  | Approver | Locate
AO-002132 | MM-ZTK-1F-ZPQ-INS-MR-0001 | MATERIAL REQUISITION FOR SCADA SYSTEM |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZPQ |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 17-Sep-2026 16:06:22 | wisuda.c@jutal.com | 17-Sep-2026 16:15:29 | Jumpol Sudjitjul | 24-Sep-2026 |  | Wichai Salee | 28-Sep-2026 | 20-Sep-2026 17:03:47 | Pornlert Wanaphattharaphan | 29-Sep-2026 | 22-Sep-2026 20:07:48 | APPR | Approved | Jumpol Sudjitjul | 30-Sep-2026 | 23-Sep-2026 11:34:29 | 23-Sep-2026 04:54:43 | 0 |  |  | Approver | Locate
AO-002138 | MM-ZTK-1F-ZPQ-INS-TBE-0001 | TECHNICAL BID EVALUATION FOR SCADA SYSTEM |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZPQ |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 18-Sep-2026 09:44:06 | wisuda.c@jutal.com | 18-Sep-2026 17:13:15 | Jumpol Sudjitjul | 28-Sep-2026 |  | Wichai Salee | 30-Sep-2026 | 24-Sep-2026 15:51:42 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 24-Sep-2026 23:43:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Oct-2026 | 25-Sep-2026 08:19:01 | 25-Sep-2026 01:58:19 | 0 |  |  | Approver | Locate
AO-002391 | MM-ZTK-1F-ZPQ-INS-TBE-0001 | TECHNICAL BID EVALUATION FOR SCADA SYSTEM |  | C2 | Project Document | Engineering Document | Part B - Engineering Doc | ZPQ |  |  | INS | Instrumentation and Control | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 06-Oct-2026 08:32:26 | wisuda.c@jutal.com | 06-Oct-2026 08:51:59 | Jumpol Sudjitjul | 14-Oct-2026 |  | Wichai Salee | 16-Oct-2026 | 06-Oct-2026 13:37:16 | Pornlert Wanaphattharaphan | 19-Oct-2026 | 07-Oct-2026 00:30:33 | APPR | Approved | Jumpol Sudjitjul | 20-Oct-2026 | 07-Oct-2026 08:32:18 | 07-Oct-2026 02:02:36 | 0 |  |  | Approver | Locate
AO-000643 | MM-ZTK-1F-ZWP20-COR-CAL-0001 | ZWP20 CATHODIC PROTECTION CALCULATION |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | COR | Corrosion | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 02-Jun-2026 10:24:06 | wisuda.c@jutal.com | 02-Jun-2026 15:09:57 | Jumpol Sudjitjul | 10-Jun-2026 | 02-Jun-2026 15:48:00 | Sompop Singhatiraj | 12-Jun-2026 | 07-Jun-2026 11:36:48 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 10-Jun-2026 21:38:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 11-Jun-2026 10:57:47 | 11-Jun-2026 04:48:35 | 0 |  |  | Approver | Locate
AO-001765 | MM-ZTK-1F-ZWP20-COR-CAL-0001 | ZWP20 CATHODIC PROTECTION CALCULATION |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | COR | Corrosion | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 29-Aug-2026 14:03:28 | wisuda.c@jutal.com | 29-Aug-2026 14:17:46 | Jumpol Sudjitjul | 04-Sep-2026 |  | Sompop Singhatiraj | 08-Sep-2026 | 02-Sep-2026 10:49:04 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 01:12:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 17:53:35 | 07-Sep-2026 11:30:01 | 0 |  |  | Approver | Locate
AO-001896 | MM-ZTK-1F-ZWP20-NVA-CAL-2011 | ZWP20 JACKET BARGE MOTION ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 07-Sep-2026 10:29:00 | wisuda.c@jutal.com | 08-Sep-2026 09:30:51 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 21-Sep-2026 13:41:46 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 22-Sep-2026 20:07:14 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Sep-2026 | 23-Sep-2026 11:25:08 | 23-Sep-2026 04:58:27 | 0 |  |  | Approver | Locate
AO-000809 | MM-ZTK-1F-ZWP20-NVA-CAL-2012 | ZWP20 JACKET LAUNCH ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 15-Jun-2026 22:50:18 | wisuda.c@jutal.com | 16-Jun-2026 10:58:50 | Jumpol Sudjitjul | 23-Jun-2026 | 19-Jun-2026 01:14:52 | Sompop Singhatiraj | 25-Jun-2026 | 29-Jun-2026 17:30:54 | Pornlert Wanaphattharaphan | 26-Jun-2026 | 30-Jun-2026 22:05:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-Jun-2026 | 01-Jul-2026 08:30:28 | 01-Jul-2026 01:42:19 | 0 |  |  | Approver | Locate
AO-002029 | MM-ZTK-1F-ZWP20-NVA-CAL-2012 | ZWP20 JACKET LAUNCH ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 14-Sep-2026 10:33:51 | wisuda.c@jutal.com | 15-Sep-2026 15:23:59 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 28-Sep-2026 13:45:33 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 28-Sep-2026 22:03:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 29-Sep-2026 14:16:45 | 29-Sep-2026 07:41:22 | 0 |  |  | Approver | Locate
AO-001901 | MM-ZTK-1F-ZWP20-NVA-CAL-2013 | ZWP20 JACKET FLOATATION AND UPENDING ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 07-Sep-2026 10:29:39 | wisuda.c@jutal.com | 08-Sep-2026 09:31:12 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 21-Sep-2026 11:18:59 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 22-Sep-2026 20:06:52 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Sep-2026 | 23-Sep-2026 11:25:50 | 23-Sep-2026 05:01:06 | 0 |  |  | Approver | Locate
AO-000467 | MM-ZTK-1F-ZWP20-PIP-LAY-0005 | EQUIPMENT LAYOUT SUMP DECK PLAN T.O.S. EL.(+) 14.700 M. & BOAT LANDING PLAN T.O.S EL.(+) 5.000 M. |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 07:20:39 | wisuda.c@jutal.com | 18-May-2026 08:00:23 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 21:24:41 | Pornlert Wanaphattharaphan | 28-May-2026 | 04-Jun-2026 16:40:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 04-Jun-2026 18:27:47 | 04-Jun-2026 14:22:26 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWP20-PIP-LAY-0005 | EQUIPMENT LAYOUT SUMP DECK PLAN T.O.S. EL.(+) 14.700 M. & BOAT LANDING PLAN T.O.S EL.(+) 5.000 M. |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:31:07 | wisuda.c@jutal.com | 15-Sep-2026 09:55:42 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:26:23 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 21:16:57 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 23:03:12 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 08:45:24 | 08-Oct-2026 02:14:08 | 0 |  |  | Approver | Locate
AO-000468 | MM-ZTK-1F-ZWP20-PIP-LAY-0006 | EQUIPMENT LAYOUT ELEVATION LOOKING NORTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 07:21:05 | wisuda.c@jutal.com | 18-May-2026 08:01:10 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 21:27:51 | Pornlert Wanaphattharaphan | 28-May-2026 | 04-Jun-2026 16:41:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 04-Jun-2026 16:59:29 | 04-Jun-2026 14:23:49 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWP20-PIP-LAY-0006 | EQUIPMENT LAYOUT ELEVATION LOOKING NORTH |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:31:41 | wisuda.c@jutal.com | 15-Sep-2026 09:55:38 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:14:19 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 21:21:15 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 23:03:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 09:35:41 | 08-Oct-2026 04:17:47 | 0 |  |  | Approver | Locate
AO-000469 | MM-ZTK-1F-ZWP20-PIP-LAY-0007 | EQUIPMENT LAYOUT ELEVATION LOOKING EAST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 07:21:31 | wisuda.c@jutal.com | 18-May-2026 08:01:37 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 21:29:57 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 21:48:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:28:08 | 07-Jun-2026 11:34:13 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWP20-PIP-LAY-0007 | EQUIPMENT LAYOUT ELEVATION LOOKING EAST |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:32:19 | wisuda.c@jutal.com | 15-Sep-2026 09:55:37 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:13:10 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 21:25:19 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 23:04:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 09:37:16 | 08-Oct-2026 04:16:27 | 0 |  |  | Approver | Locate
AO-000470 | MM-ZTK-1F-ZWP20-PIP-LAY-0008 | EQUIPMENT LAYOUT ELEVATION LOOKING SOUTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 14:05:50 | wisuda.c@jutal.com | 18-May-2026 08:02:09 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 21:31:44 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 21:49:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:28:40 | 07-Jun-2026 10:52:57 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWP20-PIP-LAY-0008 | EQUIPMENT LAYOUT ELEVATION LOOKING SOUTH |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:32:59 | wisuda.c@jutal.com | 15-Sep-2026 09:55:42 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:19:33 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 21:32:44 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 23:04:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 09:37:55 | 08-Oct-2026 04:20:23 | 0 |  |  | Approver | Locate
AO-000471 | MM-ZTK-1F-ZWP20-PIP-LAY-0009 | EQUIPMENT LAYOUT ELEVATION LOOKING WEST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 14:06:15 | wisuda.c@jutal.com | 18-May-2026 08:02:28 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 21:33:36 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 21:53:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:29:34 | 07-Jun-2026 10:54:15 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWP20-PIP-LAY-0009 | EQUIPMENT LAYOUT ELEVATION LOOKING WEST |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:33:34 | wisuda.c@jutal.com | 15-Sep-2026 09:55:43 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:15:44 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 21:36:59 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 23:05:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 09:40:05 | 08-Oct-2026 04:19:05 | 0 |  |  | Approver | Locate
AO-001377 | MM-ZTK-1F-ZWP20-PRC-UPO-5001 | PRIMARY STEEL PLATES FOR ZWP20(CUT-OFF DATE 31-JUL-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | ZWP20 |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 03-Aug-2026 10:53:54 | zm169dc@jutal.com | 03-Aug-2026 14:04:54 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 12-Aug-2026 09:45:09 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 13-Aug-2026 11:36:39 | 13-Aug-2026 05:09:49 | 0 |  |  | For Info | Locate
AO-002501 | MM-ZTK-1F-ZWP20-PRC-UPO-5002 | UNPRICED PO FOR STEEL PLATES FOR ZWP20(CUT-OFF DATE 12-OCT-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | ZWP20 |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 12-Oct-2026 18:00:44 | zhaoli@jutal.com | 12-Oct-2026 18:16:03 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  |  | Prin Jitatisil | [8 empty] | 0 |  |  | For Info | Locate
AO-002524 | MM-ZTK-1F-ZWP20-PRC-UPO-5003 | UNPRICED PO FOR STEEL PLATES FOR ZWP20(CUT-OFF DATE 12-OCT-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | ZWP20 |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 14-Oct-2026 17:38:14 | zhaoli@jutal.com | 15-Oct-2026 11:17:33 | Jumpol Sudjitjul |  |  | Jirayu Pantito | [11 empty] | 0 |  |  | For Info | Locate
AO-002158 | MM-ZTK-1F-ZWP20-PRC-UPO-5100 | UNPRICED PO FOR ANODE FOR ZWP20 (CUT-OFF DATE 17-SEP-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | ZWP20 |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 18-Sep-2026 17:26:31 | zm169dc@jutal.com | 20-Sep-2026 12:58:18 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  |  | Prin Jitatisil | [8 empty] | 0 |  |  | For Info | Locate
AO-000550 | MM-ZTK-1F-ZWP20-STR-CAL-2001 | ZWP20 JACKET COMPUTER MODELING AND LOAD FORMULATION |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 17:50:02 | wisuda.c@jutal.com | 21-May-2026 17:57:22 | Jumpol Sudjitjul | 29-May-2026 |  | Sompop Singhatiraj | 04-Jun-2026 | 25-May-2026 14:36:18 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 25-May-2026 20:38:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 25-May-2026 21:16:25 | 25-May-2026 21:36:09 | 0 |  |  | Approver | Locate
AO-001391 | MM-ZTK-1F-ZWP20-STR-CAL-2011 | ZWP20 JACKET IN-PLACE ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 10:56:35 | wisuda.c@jutal.com | 03-Aug-2026 13:21:08 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 16-Aug-2026 18:00:37 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 23:21:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 14:24:10 | 17-Aug-2026 09:09:43 | 0 |  |  | Approver | Locate
AO-002020 | MM-ZTK-1F-ZWP20-STR-CAL-2011 | ZWP20 JACKET IN-PLACE ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 11-Sep-2026 20:40:54 | wisuda.c@jutal.com | 11-Sep-2026 20:51:18 | Jumpol Sudjitjul | 21-Sep-2026 |  | Sompop Singhatiraj | 23-Sep-2026 | 28-Sep-2026 17:13:06 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 28-Sep-2026 22:00:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Sep-2026 | 29-Sep-2026 14:15:44 | 29-Sep-2026 07:55:48 | 0 |  |  | Approver | Locate
AO-000659 | MM-ZTK-1F-ZWP20-STR-CAL-2012 | ZWP20 JACKET DYNAMIC ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 04-Jun-2026 09:35:45 | wisuda.c@jutal.com | 04-Jun-2026 13:33:36 | Jumpol Sudjitjul | 11-Jun-2026 |  | Sompop Singhatiraj | 15-Jun-2026 | 08-Jun-2026 08:40:22 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 10-Jun-2026 21:42:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 11-Jun-2026 11:16:15 | 11-Jun-2026 12:03:24 | 0 |  |  | Approver | Locate
AO-001776 | MM-ZTK-1F-ZWP20-STR-CAL-2012 | ZWP20 JACKET DYNAMIC ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:23:33 | wisuda.c@jutal.com | 31-Aug-2026 11:30:37 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 14-Sep-2026 15:09:19 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 15-Sep-2026 22:32:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 17-Sep-2026 12:04:49 | 17-Sep-2026 05:57:17 | 0 |  |  | Approver | Locate
AO-001892 | MM-ZTK-1F-ZWP20-STR-CAL-2013 | ZWP20 IN-SERVICE COMBINED TOPSIDES AND JACKET FATIGUE ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 07-Sep-2026 10:05:28 | wisuda.c@jutal.com | 08-Sep-2026 12:01:05 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 14-Sep-2026 14:30:00 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 15-Sep-2026 23:15:36 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Sep-2026 | 17-Sep-2026 12:04:09 | 17-Sep-2026 06:06:17 | 0 |  |  | Approver | Locate
AO-000660 | MM-ZTK-1F-ZWP20-STR-CAL-2014 | ZWP20 JACKET LOADOUT ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 04-Jun-2026 09:36:50 | wisuda.c@jutal.com | 04-Jun-2026 13:35:41 | Jumpol Sudjitjul | 11-Jun-2026 | 17-Jun-2026 16:25:40 | Sompop Singhatiraj | 15-Jun-2026 | 18-Jun-2026 11:04:42 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 18-Jun-2026 12:54:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 18-Jun-2026 14:26:10 | 18-Jun-2026 08:03:42 | 0 |  |  | Approver | Locate
AO-002363 | MM-ZTK-1F-ZWP20-STR-CAL-2014 | ZWP20 JACKET LOADOUT ANALYSIS REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 09:15:43 | wisuda.c@jutal.com | 05-Oct-2026 10:37:27 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 12-Oct-2026 12:35:26 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 13-Oct-2026 14:37:08 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 14-Oct-2026 16:46:46 | 14-Oct-2026 10:36:18 | 0 |  |  | Approver | Locate
AO-000553 | MM-ZTK-1F-ZWP20-STR-CAL-2015 | ZWP20 JACKET TRANSPORTATION ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 17:50:34 | wisuda.c@jutal.com | 21-May-2026 17:55:23 | Jumpol Sudjitjul | 29-May-2026 | 04-Jun-2026 15:25:22 | Sompop Singhatiraj | 04-Jun-2026 | 04-Jun-2026 16:34:55 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 06-Jun-2026 00:02:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 07-Jun-2026 17:30:09 | 07-Jun-2026 11:28:03 | 0 |  |  | Approver | Locate
AO-002055 | MM-ZTK-1F-ZWP20-STR-CAL-2015 | ZWP20 JACKET TRANSPORTATION ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 14-Sep-2026 20:03:37 | wisuda.c@jutal.com | 15-Sep-2026 15:16:11 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 28-Sep-2026 11:59:26 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 28-Sep-2026 22:03:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 29-Sep-2026 14:15:12 | 29-Sep-2026 07:57:47 | 0 |  |  | Approver | Locate
AO-001636 | MM-ZTK-1F-ZWP20-STR-CAL-2016 | ZWP20 JACKET TRANSPORTATION FATIGUE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 21-Aug-2026 10:21:04 | wisuda.c@jutal.com | 21-Aug-2026 11:02:10 | Jumpol Sudjitjul | 28-Aug-2026 |  | Sompop Singhatiraj | 01-Sep-2026 | 27-Aug-2026 16:15:14 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 30-Aug-2026 00:10:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Sep-2026 | 30-Aug-2026 17:03:49 | 30-Aug-2026 11:08:30 | 0 |  |  | Approver | Locate
AO-001682 | MM-ZTK-1F-ZWP20-STR-CAL-2017 | ZWP20 JACKET BOAT IMPACT ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 09:47:09 | wisuda.c@jutal.com | 25-Aug-2026 10:10:25 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 28-Aug-2026 08:55:22 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 31-Aug-2026 00:10:32 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 15:59:51 | 31-Aug-2026 10:44:49 | 0 |  |  | Approver | Locate
AO-001482 | MM-ZTK-1F-ZWP20-STR-CAL-2018 | ZWP20 JACKET ON-BOTTOM STABILITY ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 10-Aug-2026 11:43:59 | wisuda.c@jutal.com | 10-Aug-2026 14:40:37 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 13-Aug-2026 16:03:41 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 14-Aug-2026 00:10:19 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 24-Aug-2026 | 14-Aug-2026 08:29:52 | 14-Aug-2026 01:59:39 | 0 |  |  | Approver | Locate
AO-001485 | MM-ZTK-1F-ZWP20-STR-CAL-2019 | ZWP20 JACKET MISCELLANEOUS DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 10-Aug-2026 11:44:38 | wisuda.c@jutal.com | 10-Aug-2026 14:41:58 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 16-Sep-2026 18:33:53 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 17-Sep-2026 22:48:24 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 24-Aug-2026 | 18-Sep-2026 09:42:47 | 18-Sep-2026 03:38:02 | 0 |  |  | Approver | Locate
AO-002364 | MM-ZTK-1F-ZWP20-STR-CAL-2020 | ZWP20 JACKET LEVELLING ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 05-Oct-2026 09:16:18 | wisuda.c@jutal.com | 05-Oct-2026 10:37:24 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 12-Oct-2026 15:53:34 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 13-Oct-2026 14:37:32 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 19-Oct-2026 | 14-Oct-2026 16:40:29 | 14-Oct-2026 10:28:08 | 0 |  |  | Approver | Locate
AO-001685 | MM-ZTK-1F-ZWP20-STR-CAL-2021 | ZWP20 JACKET PILE HANDLING AND STICK-UP ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 09:47:49 | wisuda.c@jutal.com | 25-Aug-2026 10:12:24 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 28-Aug-2026 11:51:33 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 31-Aug-2026 00:14:33 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 16:00:33 | 31-Aug-2026 10:46:11 | 0 |  |  | Approver | Locate
AO-001683 | MM-ZTK-1F-ZWP20-STR-CAL-2022 | ZWP20 PILE DRIVEABILITY AND PILE FATIGUE ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 09:48:31 | wisuda.c@jutal.com | 25-Aug-2026 10:17:14 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 28-Aug-2026 11:17:33 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 31-Aug-2026 00:16:10 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 16:01:09 | 31-Aug-2026 10:47:26 | 0 |  |  | Approver | Locate
AO-001963 | MM-ZTK-1F-ZWP20-STR-CAL-2023 | ZWP20 JACKET PILE CLUSTER FEA REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 10-Sep-2026 10:29:06 | wisuda.c@jutal.com | 10-Sep-2026 13:09:00 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 21-Sep-2026 14:11:13 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 22-Sep-2026 20:06:18 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 23-Sep-2026 | 23-Sep-2026 11:24:30 | 23-Sep-2026 05:04:46 | 0 |  |  | Approver | Locate
AO-001637 | MM-ZTK-1F-ZWP20-STR-CAL-2024 | ZWP20 PILE GROUP EFFECT ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 21-Aug-2026 10:22:03 | wisuda.c@jutal.com | 21-Aug-2026 11:02:28 | Jumpol Sudjitjul | 28-Aug-2026 |  | Sompop Singhatiraj | 01-Sep-2026 | 26-Aug-2026 16:25:06 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 30-Aug-2026 00:08:39 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 03-Sep-2026 | 30-Aug-2026 17:04:42 | 30-Aug-2026 11:09:50 | 0 |  |  | Approver | Locate
AO-002108 | MM-ZTK-1F-ZWP20-STR-CAL-2025 | ZWP20 MUDMAT FEA ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 16-Sep-2026 19:11:19 | wisuda.c@jutal.com | 17-Sep-2026 09:23:10 | Jumpol Sudjitjul | 24-Sep-2026 |  | Sompop Singhatiraj | 28-Sep-2026 | 22-Sep-2026 11:04:51 |  |  |  | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 30-Sep-2026 | 22-Sep-2026 11:55:00 | 22-Sep-2026 05:22:55 | 0 |  |  | Focal Point | Locate
AO-000806 | MM-ZTK-1F-ZWP20-STR-CAL-2031 | ZWP20 TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (EXTREME LEVEL EARTHQUAKE - ELE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 15-Jun-2026 22:48:16 | wisuda.c@jutal.com | 16-Jun-2026 10:35:51 | Jumpol Sudjitjul | 23-Jun-2026 |  | Sompop Singhatiraj | 25-Jun-2026 | 19-Jun-2026 19:35:53 | Pornlert Wanaphattharaphan | 26-Jun-2026 | 20-Jun-2026 17:38:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-Jun-2026 | 21-Jun-2026 21:29:37 | 22-Jun-2026 01:05:55 | 0 |  |  | Approver | Locate
AO-001889 | MM-ZTK-1F-ZWP20-STR-CAL-2031 | ZWP20 TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (EXTREME LEVEL EARTHQUAKE - ELE) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 09:35:46 | wisuda.c@jutal.com | 08-Sep-2026 09:12:24 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 18-Sep-2026 14:03:47 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 15:13:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 17:45:48 | 20-Sep-2026 12:03:10 | 0 |  |  | Approver | Locate
AO-002365 | MM-ZTK-1F-ZWP20-STR-CAL-2031 | ZWP20 TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (EXTREME LEVEL EARTHQUAKE - ELE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 09:16:55 | wisuda.c@jutal.com | 05-Oct-2026 10:37:26 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 12-Oct-2026 09:35:29 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 13-Oct-2026 14:38:04 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 14-Oct-2026 16:41:52 | 14-Oct-2026 10:29:35 | 0 |  |  | Approver | Locate
AO-001778 | MM-ZTK-1F-ZWP20-STR-CAL-2032 | ZWP20 TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT(ABNORMAL LEVEL EARTHQUAKE-ALE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 31-Aug-2026 09:24:28 | wisuda.c@jutal.com | 31-Aug-2026 11:35:38 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 02-Sep-2026 18:20:06 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 04-Sep-2026 23:51:31 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-Sep-2026 | 05-Sep-2026 18:03:31 | 05-Sep-2026 11:55:22 | 0 |  |  | Approver | Locate
AO-002022 | MM-ZTK-1F-ZWP20-STR-CAL-2041 | ZWP20 JACKET PUSHOVER ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 11-Sep-2026 20:41:25 | wisuda.c@jutal.com | 11-Sep-2026 20:54:40 | Jumpol Sudjitjul | 21-Sep-2026 |  | Sompop Singhatiraj | 23-Sep-2026 | 22-Sep-2026 11:26:38 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 22-Sep-2026 20:05:43 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 25-Sep-2026 | 23-Sep-2026 11:35:15 | 23-Sep-2026 04:57:10 | 0 |  |  | Approver | Locate
AO-000560 | MM-ZTK-1F-ZWP20-STR-CAL-2050 | ZWP20 JACKET CONSTRUCTION MODEL REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 17:51:06 | wisuda.c@jutal.com | 21-May-2026 17:58:42 | Jumpol Sudjitjul | 29-May-2026 |  | Sompop Singhatiraj | 04-Jun-2026 | 25-May-2026 16:55:18 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 25-May-2026 20:40:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 25-May-2026 21:17:56 | 25-May-2026 21:37:42 | 0 |  |  | Approver | Locate
AO-002274 | MM-ZTK-1F-ZWP20-STR-CAL-2801 | ZWP20 RISER CLAMP DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | In Review | IFR | Issued for Review |  | 28-Sep-2026 09:44:45 | wisuda.c@jutal.com | 28-Sep-2026 10:00:04 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 |  | Pornlert Wanaphattharaphan | 08-Oct-2026 |  |  |  |  | 09-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP20-STR-DWG-2100 | ZWP20 JACKET - VERTICAL FRAMING ROW 'A' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:16:31 | wisuda.c@jutal.com | 22-Apr-2026 10:45:02 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 09:28:22 | Pornlert Wanaphattharaphan | 06-May-2026 | 24-Apr-2026 00:41:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 08:26:13 | 24-Apr-2026 01:48:30 | 0 |  |  | Approver | Locate
AO-001716 | MM-ZTK-1F-ZWP20-STR-DWG-2100 | ZWP20 JACKET - VERTICAL FRAMING ROW 'A' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Aug-2026 09:29:28 | wisuda.c@jutal.com | 26-Aug-2026 09:53:41 | Jumpol Sudjitjul | 02-Sep-2026 |  | Sompop Singhatiraj | 04-Sep-2026 | 27-Aug-2026 15:01:44 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 31-Aug-2026 00:17:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Sep-2026 | 31-Aug-2026 16:01:40 | 01-Sep-2026 07:10:24 | 0 |  |  | Approver | Locate
AO-002307 | MM-ZTK-1F-ZWP20-STR-DWG-2100 | ZWP20 JACKET - VERTICAL FRAMING ROW 'A' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 30-Sep-2026 09:20:34 | wisuda.c@jutal.com | 30-Sep-2026 16:04:35 | Jumpol Sudjitjul | 07-Oct-2026 |  | Sompop Singhatiraj | 09-Oct-2026 | 01-Oct-2026 15:25:49 | Pornlert Wanaphattharaphan | 12-Oct-2026 | 01-Oct-2026 22:56:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Oct-2026 | 02-Oct-2026 13:14:48 | 02-Oct-2026 06:33:13 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP20-STR-DWG-2101 | ZWP20 JACKET - VERTICAL FRAMING ROW 'B' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:49:44 | wisuda.c@jutal.com | 22-Apr-2026 10:45:25 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 11:21:50 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 23:59:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 08:31:09 | 24-Apr-2026 01:49:42 | 0 |  |  | Approver | Locate
AO-001716 | MM-ZTK-1F-ZWP20-STR-DWG-2101 | ZWP20 JACKET - VERTICAL FRAMING ROW 'B' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Aug-2026 09:29:58 | wisuda.c@jutal.com | 26-Aug-2026 09:53:41 | Jumpol Sudjitjul | 02-Sep-2026 |  | Sompop Singhatiraj | 04-Sep-2026 | 27-Aug-2026 15:03:03 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 31-Aug-2026 00:18:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Sep-2026 | 31-Aug-2026 16:02:09 | 01-Sep-2026 08:11:17 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWP20-STR-DWG-2101 | ZWP20 JACKET - VERTICAL FRAMING ROW 'B' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 10:20:54 | wisuda.c@jutal.com | 28-Sep-2026 10:27:34 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 14:06:00 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:07:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 13:51:06 | 30-Sep-2026 07:10:05 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP20-STR-DWG-2102 | ZWP20 JACKET - VERTICAL FRAMING ROW '1' & '1.1' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 20:48:43 | wisuda.c@jutal.com | 22-Apr-2026 10:45:42 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 11:00:58 | Pornlert Wanaphattharaphan | 06-May-2026 | 24-Apr-2026 00:34:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 08:32:34 | 24-Apr-2026 02:03:20 | 0 |  |  | Approver | Locate
AO-001716 | MM-ZTK-1F-ZWP20-STR-DWG-2102 | ZWP20 JACKET - VERTICAL FRAMING ROW '1' & '1.1' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Aug-2026 09:30:26 | wisuda.c@jutal.com | 26-Aug-2026 09:53:41 | Jumpol Sudjitjul | 02-Sep-2026 |  | Sompop Singhatiraj | 04-Sep-2026 | 03-Sep-2026 14:04:17 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 07-Sep-2026 01:03:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Sep-2026 | 07-Sep-2026 17:52:58 | 07-Sep-2026 11:28:42 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWP20-STR-DWG-2102 | ZWP20 JACKET - VERTICAL FRAMING ROW '1' & '1.1' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 10:21:29 | wisuda.c@jutal.com | 28-Sep-2026 10:27:37 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 14:10:24 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:10:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 13:51:54 | 30-Sep-2026 07:11:52 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP20-STR-DWG-2103 | ZWP20 JACKET - VERTICAL FRAMING ROW '2' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 20:49:06 | wisuda.c@jutal.com | 22-Apr-2026 10:46:00 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 12:32:00 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 23:38:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 08:23:06 | 24-Apr-2026 01:52:08 | 0 |  |  | Approver | Locate
AO-001716 | MM-ZTK-1F-ZWP20-STR-DWG-2103 | ZWP20 JACKET - VERTICAL FRAMING ROW '2' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Aug-2026 08:35:06 | wisuda.c@jutal.com | 26-Aug-2026 09:53:42 | Jumpol Sudjitjul | 02-Sep-2026 |  | Sompop Singhatiraj | 04-Sep-2026 | 27-Aug-2026 12:33:53 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 31-Aug-2026 00:18:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Sep-2026 | 31-Aug-2026 16:02:32 | 31-Aug-2026 10:32:26 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWP20-STR-DWG-2103 | ZWP20 JACKET - VERTICAL FRAMING ROW '2' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 10:22:01 | wisuda.c@jutal.com | 28-Sep-2026 10:27:42 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 14:08:06 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:08:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 13:53:29 | 30-Sep-2026 07:14:18 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP20-STR-DWG-2104 | ZWP20 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'AA' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 20:49:29 | wisuda.c@jutal.com | 22-Apr-2026 10:57:14 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 12:33:38 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 23:33:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 08:20:39 | 24-Apr-2026 01:50:57 | 0 |  |  | Approver | Locate
AO-001716 | MM-ZTK-1F-ZWP20-STR-DWG-2104 | ZWP20 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'AA' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Aug-2026 08:35:34 | wisuda.c@jutal.com | 26-Aug-2026 09:53:46 | Jumpol Sudjitjul | 02-Sep-2026 |  | Sompop Singhatiraj | 04-Sep-2026 | 27-Aug-2026 12:33:44 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 31-Aug-2026 00:19:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Sep-2026 | 31-Aug-2026 16:03:28 | 31-Aug-2026 10:17:07 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWP20-STR-DWG-2104 | ZWP20 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'AA' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 10:22:39 | wisuda.c@jutal.com | 28-Sep-2026 10:27:38 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 14:07:58 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:08:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 13:58:54 | 30-Sep-2026 07:34:07 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP20-STR-DWG-2105 | ZWP20 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'BB' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:50:10 | wisuda.c@jutal.com | 22-Apr-2026 10:57:31 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 12:35:02 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 23:29:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 08:21:33 | 24-Apr-2026 01:47:17 | 0 |  |  | Approver | Locate
AO-001716 | MM-ZTK-1F-ZWP20-STR-DWG-2105 | ZWP20 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'BB' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Aug-2026 08:36:02 | wisuda.c@jutal.com | 26-Aug-2026 09:53:41 | Jumpol Sudjitjul | 02-Sep-2026 |  | Sompop Singhatiraj | 04-Sep-2026 | 27-Aug-2026 12:33:36 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 31-Aug-2026 00:19:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Sep-2026 | 31-Aug-2026 16:08:39 | 31-Aug-2026 10:33:42 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWP20-STR-DWG-2105 | ZWP20 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'BB' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 10:23:07 | wisuda.c@jutal.com | 28-Sep-2026 10:27:35 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 14:08:24 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:09:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 14:00:14 | 30-Sep-2026 07:36:48 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP20-STR-DWG-2110 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(+) 8000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 20:49:51 | wisuda.c@jutal.com | 22-Apr-2026 10:58:05 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 13:58:48 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 22:45:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 08:42:11 | 24-Apr-2026 02:26:28 | 0 |  |  | Approver | Locate
AO-001716 | MM-ZTK-1F-ZWP20-STR-DWG-2110 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(+) 8000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Aug-2026 08:36:30 | wisuda.c@jutal.com | 26-Aug-2026 10:02:34 | Jumpol Sudjitjul | 02-Sep-2026 |  | Sompop Singhatiraj | 04-Sep-2026 | 03-Sep-2026 15:10:35 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 07-Sep-2026 01:04:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Sep-2026 | 07-Sep-2026 17:54:04 | 07-Sep-2026 11:49:52 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWP20-STR-DWG-2110 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(+) 8000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 10:23:39 | wisuda.c@jutal.com | 28-Sep-2026 10:27:40 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 11:57:23 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:04:09 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 14:02:27 | 30-Sep-2026 07:38:00 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP20-STR-DWG-2111 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 3000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 20:50:13 | wisuda.c@jutal.com | 22-Apr-2026 10:58:37 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 14:00:39 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 22:38:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 08:44:03 | 24-Apr-2026 02:27:40 | 0 |  |  | Approver | Locate
AO-001716 | MM-ZTK-1F-ZWP20-STR-DWG-2111 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 3000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Aug-2026 08:36:58 | wisuda.c@jutal.com | 26-Aug-2026 10:02:36 | Jumpol Sudjitjul | 02-Sep-2026 |  | Sompop Singhatiraj | 04-Sep-2026 | 03-Sep-2026 15:10:46 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 07-Sep-2026 01:04:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Sep-2026 | 07-Sep-2026 17:54:58 | 07-Sep-2026 11:51:13 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWP20-STR-DWG-2111 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 3000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 10:24:14 | wisuda.c@jutal.com | 28-Sep-2026 10:27:41 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 11:58:50 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:04:47 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 14:04:01 | 30-Sep-2026 07:39:12 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP20-STR-DWG-2112 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 14000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 20:50:37 | wisuda.c@jutal.com | 22-Apr-2026 11:19:17 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 14:51:46 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 22:16:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 08:29:21 | 24-Apr-2026 02:00:47 | 0 |  |  | Approver | Locate
AO-001716 | MM-ZTK-1F-ZWP20-STR-DWG-2112 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 14000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Aug-2026 08:37:34 | wisuda.c@jutal.com | 26-Aug-2026 10:02:31 | Jumpol Sudjitjul | 02-Sep-2026 |  | Sompop Singhatiraj | 04-Sep-2026 | 03-Sep-2026 15:10:53 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 07-Sep-2026 01:05:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Sep-2026 | 07-Sep-2026 17:55:18 | 07-Sep-2026 11:52:28 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWP20-STR-DWG-2112 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 14000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 10:24:48 | wisuda.c@jutal.com | 28-Sep-2026 10:27:42 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 14:29:59 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:12:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 14:07:43 | 30-Sep-2026 07:41:48 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP20-STR-DWG-2113 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 26000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 20:51:01 | wisuda.c@jutal.com | 22-Apr-2026 11:19:31 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 14:54:21 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 22:09:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 08:27:58 | 24-Apr-2026 01:59:29 | 0 |  |  | Approver | Locate
AO-001716 | MM-ZTK-1F-ZWP20-STR-DWG-2113 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 26000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Aug-2026 08:38:07 | wisuda.c@jutal.com | 26-Aug-2026 10:02:29 | Jumpol Sudjitjul | 02-Sep-2026 |  | Sompop Singhatiraj | 04-Sep-2026 | 03-Sep-2026 15:11:44 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 07-Sep-2026 01:05:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Sep-2026 | 07-Sep-2026 17:55:31 | 07-Sep-2026 11:53:44 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWP20-STR-DWG-2113 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 26000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 09:45:14 | wisuda.c@jutal.com | 28-Sep-2026 10:07:03 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 11:58:54 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:05:21 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 14:06:58 | 30-Sep-2026 07:40:22 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP20-STR-DWG-2114 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 38000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 20:51:23 | wisuda.c@jutal.com | 22-Apr-2026 11:19:43 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 14:54:11 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 22:11:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 08:44:58 | 24-Apr-2026 02:30:22 | 0 |  |  | Approver | Locate
AO-001716 | MM-ZTK-1F-ZWP20-STR-DWG-2114 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 38000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Aug-2026 08:38:44 | wisuda.c@jutal.com | 26-Aug-2026 10:02:29 | Jumpol Sudjitjul | 02-Sep-2026 |  | Sompop Singhatiraj | 04-Sep-2026 | 03-Sep-2026 15:13:29 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 07-Sep-2026 01:06:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Sep-2026 | 07-Sep-2026 17:56:06 | 07-Sep-2026 11:55:00 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWP20-STR-DWG-2114 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 38000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 10:25:21 | wisuda.c@jutal.com | 28-Sep-2026 10:27:37 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 14:29:45 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:12:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 14:08:41 | 30-Sep-2026 07:44:46 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP20-STR-DWG-2115 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 52000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 20:51:45 | wisuda.c@jutal.com | 22-Apr-2026 11:19:57 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 15:55:17 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 18:48:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 08:24:31 | 24-Apr-2026 01:54:36 | 0 |  |  | Approver | Locate
AO-001716 | MM-ZTK-1F-ZWP20-STR-DWG-2115 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 52000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Aug-2026 08:39:14 | wisuda.c@jutal.com | 26-Aug-2026 10:02:38 | Jumpol Sudjitjul | 02-Sep-2026 |  | Sompop Singhatiraj | 04-Sep-2026 | 03-Sep-2026 15:13:07 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 07-Sep-2026 01:05:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Sep-2026 | 07-Sep-2026 17:56:32 | 07-Sep-2026 11:56:12 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWP20-STR-DWG-2115 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 52000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 10:25:54 | wisuda.c@jutal.com | 28-Sep-2026 10:49:15 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 11:58:58 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:06:28 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 15:00:59 | 30-Sep-2026 08:58:36 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP20-STR-DWG-2116 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 66000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:50:34 | wisuda.c@jutal.com | 22-Apr-2026 11:07:33 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 15:52:01 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 19:13:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 08:45:56 | 24-Apr-2026 02:54:28 | 0 |  |  | Approver | Locate
AO-001716 | MM-ZTK-1F-ZWP20-STR-DWG-2116 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 66000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Aug-2026 08:39:49 | wisuda.c@jutal.com | 26-Aug-2026 10:02:31 | Jumpol Sudjitjul | 02-Sep-2026 |  | Sompop Singhatiraj | 04-Sep-2026 | 03-Sep-2026 15:13:14 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 07-Sep-2026 01:06:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Sep-2026 | 07-Sep-2026 17:56:59 | 07-Sep-2026 11:57:28 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWP20-STR-DWG-2116 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 66000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 10:26:24 | wisuda.c@jutal.com | 28-Sep-2026 10:49:17 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 14:34:19 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:17:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 14:09:57 | 30-Sep-2026 07:46:08 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP20-STR-DWG-2117 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 79500 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 20:52:11 | wisuda.c@jutal.com | 22-Apr-2026 11:07:15 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 15:54:11 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 18:50:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 08:47:26 | 24-Apr-2026 02:32:49 | 0 |  |  | Approver | Locate
AO-001716 | MM-ZTK-1F-ZWP20-STR-DWG-2117 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 79500 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Aug-2026 08:40:21 | wisuda.c@jutal.com | 26-Aug-2026 10:02:28 | Jumpol Sudjitjul | 02-Sep-2026 |  | Sompop Singhatiraj | 04-Sep-2026 | 03-Sep-2026 15:13:21 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 07-Sep-2026 01:06:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Sep-2026 | 07-Sep-2026 17:57:32 | 07-Sep-2026 11:58:42 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWP20-STR-DWG-2117 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 79500 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 10:26:58 | wisuda.c@jutal.com | 28-Sep-2026 10:49:12 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 11:59:02 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:05:57 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 15:27:06 | 30-Sep-2026 09:28:56 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP20-STR-DWG-2118 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 93000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 20:52:34 | wisuda.c@jutal.com | 22-Apr-2026 11:06:53 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 15:56:39 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 18:44:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 08:47:21 | 24-Apr-2026 02:31:35 | 0 |  |  | Approver | Locate
AO-001716 | MM-ZTK-1F-ZWP20-STR-DWG-2118 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 93000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Aug-2026 08:40:51 | wisuda.c@jutal.com | 26-Aug-2026 10:02:33 | Jumpol Sudjitjul | 02-Sep-2026 |  | Sompop Singhatiraj | 04-Sep-2026 | 03-Sep-2026 15:15:13 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 07-Sep-2026 01:07:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Sep-2026 | 07-Sep-2026 17:58:02 | 07-Sep-2026 11:59:57 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWP20-STR-DWG-2118 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 93000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 09:45:43 | wisuda.c@jutal.com | 28-Sep-2026 10:07:29 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 14:34:21 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:13:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 15:25:52 | 30-Sep-2026 10:01:54 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP20-STR-DWG-2119 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 103000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:50:57 | wisuda.c@jutal.com | 22-Apr-2026 11:06:29 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 15:59:00 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 18:34:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 08:45:10 | 24-Apr-2026 02:53:17 | 0 |  |  | Approver | Locate
AO-001716 | MM-ZTK-1F-ZWP20-STR-DWG-2119 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 103000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Aug-2026 08:41:18 | wisuda.c@jutal.com | 26-Aug-2026 10:02:27 | Jumpol Sudjitjul | 02-Sep-2026 |  | Sompop Singhatiraj | 04-Sep-2026 | 03-Sep-2026 15:15:18 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 07-Sep-2026 01:07:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Sep-2026 | 07-Sep-2026 17:58:26 | 07-Sep-2026 12:01:14 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWP20-STR-DWG-2119 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 103000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 10:27:40 | wisuda.c@jutal.com | 28-Sep-2026 10:49:15 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 11:59:05 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:07:00 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 15:29:12 | 30-Sep-2026 09:30:08 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP20-STR-DWG-2120 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 113000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 20:52:56 | wisuda.c@jutal.com | 22-Apr-2026 10:50:08 | Jumpol Sudjitjul | 29-Apr-2026 | 24-Apr-2026 10:41:27 | Sompop Singhatiraj | 05-May-2026 | 24-Apr-2026 17:40:20 | Pornlert Wanaphattharaphan | 06-May-2026 | 29-Apr-2026 22:30:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 30-Apr-2026 08:38:42 | 30-Apr-2026 01:48:56 | 0 |  |  | Approver | Locate
AO-001716 | MM-ZTK-1F-ZWP20-STR-DWG-2120 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 113000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Aug-2026 08:41:46 | wisuda.c@jutal.com | 26-Aug-2026 10:02:39 | Jumpol Sudjitjul | 02-Sep-2026 |  | Sompop Singhatiraj | 04-Sep-2026 | 03-Sep-2026 15:15:26 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 07-Sep-2026 01:07:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Sep-2026 | 07-Sep-2026 17:58:54 | 07-Sep-2026 12:02:27 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWP20-STR-DWG-2120 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 113000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 10:28:24 | wisuda.c@jutal.com | 28-Sep-2026 10:49:12 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 14:29:36 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:10:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 14:11:17 | 30-Sep-2026 07:47:34 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP20-STR-DWG-2121 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 124000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:51:20 | wisuda.c@jutal.com | 22-Apr-2026 10:49:54 | Jumpol Sudjitjul | 29-Apr-2026 | 24-Apr-2026 10:42:12 | Sompop Singhatiraj | 05-May-2026 | 24-Apr-2026 17:39:01 | Pornlert Wanaphattharaphan | 06-May-2026 | 29-Apr-2026 22:31:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 30-Apr-2026 08:40:13 | 30-Apr-2026 01:59:58 | 0 |  |  | Approver | Locate
AO-001716 | MM-ZTK-1F-ZWP20-STR-DWG-2121 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 124000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Aug-2026 08:42:10 | wisuda.c@jutal.com | 26-Aug-2026 10:02:30 | Jumpol Sudjitjul | 02-Sep-2026 |  | Sompop Singhatiraj | 04-Sep-2026 | 03-Sep-2026 15:15:35 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 07-Sep-2026 01:08:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Sep-2026 | 07-Sep-2026 17:59:31 | 07-Sep-2026 12:03:44 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWP20-STR-DWG-2121 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 124000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 10:29:01 | wisuda.c@jutal.com | 28-Sep-2026 10:49:17 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 11:56:15 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:03:45 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 15:26:25 | 30-Sep-2026 09:27:16 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP20-STR-DWG-2122 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 135000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:51:41 | wisuda.c@jutal.com | 22-Apr-2026 10:49:40 | Jumpol Sudjitjul | 29-Apr-2026 | 24-Apr-2026 10:43:07 | Sompop Singhatiraj | 05-May-2026 | 24-Apr-2026 17:38:45 | Pornlert Wanaphattharaphan | 06-May-2026 | 29-Apr-2026 22:50:12 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 07-May-2026 | 30-Apr-2026 08:34:22 | 30-Apr-2026 01:58:47 | 0 |  |  | Approver | Locate
AO-001716 | MM-ZTK-1F-ZWP20-STR-DWG-2122 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 135000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Aug-2026 08:42:36 | wisuda.c@jutal.com | 26-Aug-2026 10:02:34 | Jumpol Sudjitjul | 02-Sep-2026 |  | Sompop Singhatiraj | 04-Sep-2026 | 03-Sep-2026 15:17:02 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 07-Sep-2026 01:08:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Sep-2026 | 07-Sep-2026 18:00:49 | 07-Sep-2026 12:04:58 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWP20-STR-DWG-2122 | ZWP20 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 135000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 10:29:27 | wisuda.c@jutal.com | 28-Sep-2026 10:49:16 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 14:34:33 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:18:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 15:32:46 | 30-Sep-2026 09:33:15 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP20-STR-DWG-2123 | ZWP20 JACKET - FRAMING SECTIONS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 20:53:19 | wisuda.c@jutal.com | 22-Apr-2026 10:49:26 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 16:12:08 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 18:41:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 08:44:18 | 24-Apr-2026 02:28:58 | 0 |  |  | Approver | Locate
AO-001716 | MM-ZTK-1F-ZWP20-STR-DWG-2123 | ZWP20 JACKET - FRAMING SECTIONS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 26-Aug-2026 08:43:03 | wisuda.c@jutal.com | 26-Aug-2026 10:02:28 | Jumpol Sudjitjul | 02-Sep-2026 |  | Sompop Singhatiraj | 04-Sep-2026 | 03-Sep-2026 15:17:10 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 04-Sep-2026 23:53:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Sep-2026 | 05-Sep-2026 18:03:34 | 05-Sep-2026 11:36:54 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWP20-STR-DWG-2123 | ZWP20 JACKET - FRAMING SECTIONS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 10:29:56 | wisuda.c@jutal.com | 28-Sep-2026 11:06:30 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 10:52:58 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:03:21 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 15:33:17 | 30-Sep-2026 09:34:24 | 0 |  |  | Approver | Locate
AO-000371 | MM-ZTK-1F-ZWP20-STR-DWG-2130 | ZWP20 JACKET - LAUNCH CRADLE GENERAL ARRANGEMENT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 18:44:32 | wisuda.c@jutal.com | 12-May-2026 11:11:21 | Jumpol Sudjitjul | 19-May-2026 |  | Sompop Singhatiraj | 21-May-2026 | 18-May-2026 10:45:00 | Pornlert Wanaphattharaphan | 22-May-2026 | 22-May-2026 00:07:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-May-2026 | 22-May-2026 08:25:11 | 22-May-2026 01:35:18 | 0 |  |  | Approver | Locate
AO-000985 | MM-ZTK-1F-ZWP20-STR-DWG-2130 | ZWP20 JACKET - LAUNCH CRADLE GENERAL ARRANGEMENT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 10:46:36 | wisuda.c@jutal.com | 03-Jul-2026 14:06:36 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 03-Jul-2026 17:25:38 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 04-Jul-2026 20:09:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 05-Jul-2026 10:45:08 | 05-Jul-2026 04:15:43 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP20-STR-DWG-2130 | ZWP20 JACKET - LAUNCH CRADLE GENERAL ARRANGEMENT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:12:44 | wisuda.c@jutal.com | 21-Sep-2026 18:02:13 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 22-Sep-2026 14:08:51 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 22-Sep-2026 20:05:25 | APPR | Approved | Jumpol Sudjitjul | 05-Oct-2026 | 23-Sep-2026 11:35:50 | 23-Sep-2026 05:12:11 | 0 |  |  | Approver | Locate
AO-000371 | MM-ZTK-1F-ZWP20-STR-DWG-2131 | ZWP20 JACKET - LAUNCH CRADLE DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 18:44:55 | wisuda.c@jutal.com | 12-May-2026 11:11:41 | Jumpol Sudjitjul | 19-May-2026 |  | Sompop Singhatiraj | 21-May-2026 | 18-May-2026 10:42:33 | Pornlert Wanaphattharaphan | 22-May-2026 | 22-May-2026 00:03:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-May-2026 | 22-May-2026 08:27:34 | 22-May-2026 02:30:54 | 0 |  |  | Approver | Locate
AO-000985 | MM-ZTK-1F-ZWP20-STR-DWG-2131 | ZWP20 JACKET - LAUNCH CRADLE DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 10:47:27 | wisuda.c@jutal.com | 03-Jul-2026 14:06:33 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 03-Jul-2026 17:27:01 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 04-Jul-2026 20:09:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 05-Jul-2026 10:46:41 | 05-Jul-2026 04:41:37 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP20-STR-DWG-2131 | ZWP20 JACKET - LAUNCH CRADLE DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:13:11 | wisuda.c@jutal.com | 21-Sep-2026 18:02:12 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 22-Sep-2026 14:06:52 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 22-Sep-2026 20:04:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Oct-2026 | 23-Sep-2026 11:36:30 | 23-Sep-2026 05:13:24 | 0 |  |  | Approver | Locate
AO-000371 | MM-ZTK-1F-ZWP20-STR-DWG-2132 | ZWP20 JACKET - LAUNCH CRADLE DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 18:45:20 | wisuda.c@jutal.com | 12-May-2026 11:11:53 | Jumpol Sudjitjul | 19-May-2026 |  | Sompop Singhatiraj | 21-May-2026 | 18-May-2026 10:45:12 | Pornlert Wanaphattharaphan | 22-May-2026 | 22-May-2026 00:21:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-May-2026 | 22-May-2026 08:29:54 | 22-May-2026 02:32:07 | 0 |  |  | Approver | Locate
AO-000985 | MM-ZTK-1F-ZWP20-STR-DWG-2132 | ZWP20 JACKET - LAUNCH CRADLE DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 10:48:05 | wisuda.c@jutal.com | 03-Jul-2026 14:06:35 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 03-Jul-2026 17:27:10 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 04-Jul-2026 20:09:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 05-Jul-2026 10:47:34 | 05-Jul-2026 04:42:53 | 0 |  |  | Approver | Locate
AO-001552 | MM-ZTK-1F-ZWP20-STR-DWG-2132 | ZWP20 JACKET - LAUNCH CRADLE DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 14:23:58 | wisuda.c@jutal.com | 17-Aug-2026 15:21:57 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 20-Aug-2026 13:51:40 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:22:04 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 18:20:53 | 24-Aug-2026 12:44:06 | 0 |  |  | Approver | Locate
AO-000518 | MM-ZTK-1F-ZWP20-STR-DWG-2133 | ZWP20 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 18:14:21 | wisuda.c@jutal.com | 19-May-2026 18:23:46 | Jumpol Sudjitjul | 27-May-2026 |  | Sompop Singhatiraj | 29-May-2026 | 20-May-2026 10:10:45 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 22-May-2026 01:03:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Jun-2026 | 22-May-2026 08:41:03 | 22-May-2026 02:47:37 | 0 |  |  | Approver | Locate
AO-001821 | MM-ZTK-1F-ZWP20-STR-DWG-2133 | ZWP20 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:07:03 | wisuda.c@jutal.com | 03-Sep-2026 11:06:05 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 08-Sep-2026 10:41:18 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 16:39:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 08:22:17 | 13-Sep-2026 01:58:42 | 0 |  |  | Approver | Locate
AO-000518 | MM-ZTK-1F-ZWP20-STR-DWG-2134 | ZWP20 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 18:14:47 | wisuda.c@jutal.com | 19-May-2026 18:24:08 | Jumpol Sudjitjul | 27-May-2026 |  | Sompop Singhatiraj | 29-May-2026 | 20-May-2026 10:13:21 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 22-May-2026 01:04:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Jun-2026 | 22-May-2026 08:43:05 | 22-May-2026 02:48:47 | 0 |  |  | Approver | Locate
AO-001821 | MM-ZTK-1F-ZWP20-STR-DWG-2134 | ZWP20 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:43:02 | wisuda.c@jutal.com | 03-Sep-2026 11:06:10 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 08-Sep-2026 10:42:34 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 16:40:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 08:24:03 | 13-Sep-2026 01:59:58 | 0 |  |  | Approver | Locate
AO-000518 | MM-ZTK-1F-ZWP20-STR-DWG-2135 | ZWP20 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 18:15:16 | wisuda.c@jutal.com | 19-May-2026 18:24:22 | Jumpol Sudjitjul | 27-May-2026 |  | Sompop Singhatiraj | 29-May-2026 | 20-May-2026 10:16:22 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 22-May-2026 01:05:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Jun-2026 | 22-May-2026 08:44:31 | 22-May-2026 02:49:58 | 0 |  |  | Approver | Locate
AO-001821 | MM-ZTK-1F-ZWP20-STR-DWG-2135 | ZWP20 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:43:35 | wisuda.c@jutal.com | 03-Sep-2026 11:06:07 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 08-Sep-2026 10:42:57 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 16:40:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 08:24:46 | 13-Sep-2026 02:01:14 | 0 |  |  | Approver | Locate
AO-000518 | MM-ZTK-1F-ZWP20-STR-DWG-2136 | ZWP20 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 18:15:45 | wisuda.c@jutal.com | 19-May-2026 18:24:35 | Jumpol Sudjitjul | 27-May-2026 |  | Sompop Singhatiraj | 29-May-2026 | 20-May-2026 10:13:10 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 22-May-2026 01:03:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Jun-2026 | 22-May-2026 08:46:48 | 22-May-2026 02:51:11 | 0 |  |  | Approver | Locate
AO-000985 | MM-ZTK-1F-ZWP20-STR-DWG-2136 | ZWP20 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 4 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 10:48:39 | wisuda.c@jutal.com | 03-Jul-2026 14:06:28 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 03-Jul-2026 17:52:13 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 04-Jul-2026 20:15:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 05-Jul-2026 10:35:58 | 05-Jul-2026 04:10:33 | 0 |  |  | Approver | Locate
AO-000400 | MM-ZTK-1F-ZWP20-STR-DWG-2141 | ZWP20 JACKET - PILE CLUSTER ARRANGEMENT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 09:29:52 | wisuda.c@jutal.com | 15-May-2026 11:55:44 | Jumpol Sudjitjul | 22-May-2026 |  | Sompop Singhatiraj | 26-May-2026 | 20-May-2026 11:49:07 | Pornlert Wanaphattharaphan | 27-May-2026 | 22-May-2026 00:17:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 22-May-2026 08:48:39 | 22-May-2026 02:42:52 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP20-STR-DWG-2141 | ZWP20 JACKET - PILE CLUSTER ARRANGEMENT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Sep-2026 16:13:43 | wisuda.c@jutal.com | 21-Sep-2026 18:02:14 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 22-Sep-2026 17:16:55 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 22-Sep-2026 20:04:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Oct-2026 | 23-Sep-2026 13:23:04 | 23-Sep-2026 07:01:00 | 0 |  |  | Approver | Locate
AO-002310 | MM-ZTK-1F-ZWP20-STR-DWG-2141 | ZWP20 JACKET - PILE CLUSTER ARRANGEMENT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 30-Sep-2026 09:21:26 | wisuda.c@jutal.com | 30-Sep-2026 16:04:35 | Jumpol Sudjitjul | 07-Oct-2026 |  | Sompop Singhatiraj | 09-Oct-2026 | 01-Oct-2026 15:53:45 | Pornlert Wanaphattharaphan | 12-Oct-2026 | 01-Oct-2026 22:56:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Oct-2026 | 02-Oct-2026 13:15:19 | 02-Oct-2026 06:34:36 | 0 |  |  | Approver | Locate
AO-000400 | MM-ZTK-1F-ZWP20-STR-DWG-2142 | ZWP20 JACKET - PILE SLEEVE DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 09:30:15 | wisuda.c@jutal.com | 15-May-2026 11:55:44 | Jumpol Sudjitjul | 22-May-2026 |  | Sompop Singhatiraj | 26-May-2026 | 20-May-2026 11:51:30 | Pornlert Wanaphattharaphan | 27-May-2026 | 22-May-2026 00:22:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 22-May-2026 08:49:43 | 22-May-2026 02:44:02 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP20-STR-DWG-2142 | ZWP20 JACKET - PILE SLEEVE DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Sep-2026 16:14:14 | wisuda.c@jutal.com | 21-Sep-2026 18:02:13 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 22-Sep-2026 17:08:59 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 22-Sep-2026 20:03:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Oct-2026 | 23-Sep-2026 11:26:24 | 23-Sep-2026 05:07:15 | 0 |  |  | Approver | Locate
AO-002310 | MM-ZTK-1F-ZWP20-STR-DWG-2142 | ZWP20 JACKET - PILE SLEEVE DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 30-Sep-2026 09:22:16 | wisuda.c@jutal.com | 30-Sep-2026 16:04:35 | Jumpol Sudjitjul | 07-Oct-2026 |  | Sompop Singhatiraj | 09-Oct-2026 | 01-Oct-2026 17:37:41 | Pornlert Wanaphattharaphan | 12-Oct-2026 | 01-Oct-2026 22:55:24 | APPR | Approved | Jumpol Sudjitjul | 14-Oct-2026 | 02-Oct-2026 13:16:53 | 02-Oct-2026 07:13:30 | 0 |  |  | Approver | Locate
AO-000400 | MM-ZTK-1F-ZWP20-STR-DWG-2143 | ZWP20 JACKET - SKIRT SLEEVE MARKING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 09:30:40 | wisuda.c@jutal.com | 15-May-2026 11:55:48 | Jumpol Sudjitjul | 22-May-2026 |  | Sompop Singhatiraj | 26-May-2026 | 20-May-2026 11:52:57 | Pornlert Wanaphattharaphan | 27-May-2026 | 22-May-2026 00:23:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 22-May-2026 08:50:57 | 22-May-2026 02:45:12 | 0 |  |  | Approver | Locate
AO-000698 | MM-ZTK-1F-ZWP20-STR-DWG-2144 | ZWP20 JACKET - PILE MAKE-UP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 08:39:58 | wisuda.c@jutal.com | 08-Jun-2026 15:54:19 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 12-Jun-2026 13:38:44 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 13-Jun-2026 00:47:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 13-Jun-2026 07:02:47 | 13-Jun-2026 00:17:35 | 0 |  |  | Approver | Locate
AO-001821 | MM-ZTK-1F-ZWP20-STR-DWG-2144 | ZWP20 JACKET - PILE MAKE-UP |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:44:07 | wisuda.c@jutal.com | 03-Sep-2026 11:06:13 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 07-Sep-2026 13:45:05 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 15:50:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 08:32:13 | 13-Sep-2026 02:02:31 | 0 |  |  | Approver | Locate
AO-002308 | MM-ZTK-1F-ZWP20-STR-DWG-2144 | ZWP20 JACKET - PILE MAKE-UP |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 30-Sep-2026 09:23:24 | wisuda.c@jutal.com | 30-Sep-2026 16:04:37 | Jumpol Sudjitjul | 07-Oct-2026 |  | Sompop Singhatiraj | 09-Oct-2026 | 01-Oct-2026 15:42:39 | Pornlert Wanaphattharaphan | 12-Oct-2026 | 01-Oct-2026 22:48:19 | APPR | Approved | Jumpol Sudjitjul | 14-Oct-2026 | 02-Oct-2026 13:26:23 | 02-Oct-2026 07:23:47 | 0 |  |  | Approver | Locate
AO-000984 | MM-ZTK-1F-ZWP20-STR-DWG-2200 | ZWP20 JACKET - HYDROSTATIC RING DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 10:49:09 | wisuda.c@jutal.com | 03-Jul-2026 14:09:02 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 03-Jul-2026 17:52:26 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 04-Jul-2026 20:16:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 05-Jul-2026 10:36:38 | 05-Jul-2026 04:11:48 | 0 |  |  | Approver | Locate
AO-002164 | MM-ZTK-1F-ZWP20-STR-DWG-2200 | ZWP20 JACKET - HYDROSTATIC RING DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 18-Sep-2026 18:59:09 | wisuda.c@jutal.com | 20-Sep-2026 12:44:36 | Jumpol Sudjitjul | 25-Sep-2026 |  | Sompop Singhatiraj | 29-Sep-2026 | 28-Sep-2026 09:51:02 | Pornlert Wanaphattharaphan | 30-Sep-2026 | 28-Sep-2026 22:07:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Oct-2026 | 29-Sep-2026 11:07:51 | 29-Sep-2026 04:50:04 | 0 |  |  | Approver | Locate
AO-000984 | MM-ZTK-1F-ZWP20-STR-DWG-2201 | ZWP20 JACKET - HYDROSTATIC RING DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 10:49:54 | wisuda.c@jutal.com | 03-Jul-2026 14:09:49 | Jumpol Sudjitjul | 10-Jul-2026 | 15-Jul-2026 22:56:39 | Sompop Singhatiraj | 14-Jul-2026 | 03-Jul-2026 17:55:17 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 04-Jul-2026 20:57:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 05-Jul-2026 10:35:02 | 05-Jul-2026 04:09:10 | 0 |  |  | Approver | Locate
AO-002164 | MM-ZTK-1F-ZWP20-STR-DWG-2201 | ZWP20 JACKET - HYDROSTATIC RING DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 18-Sep-2026 18:59:37 | wisuda.c@jutal.com | 22-Sep-2026 09:06:13 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 28-Sep-2026 10:18:17 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 28-Sep-2026 22:52:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Oct-2026 | 29-Sep-2026 11:06:20 | 29-Sep-2026 04:47:34 | 0 |  |  | Approver | Locate
AO-000740 | MM-ZTK-1F-ZWP20-STR-DWG-2241 | ZWP20 JACKET - RISER PROTECTOR |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 18:11:26 | wisuda.c@jutal.com | 12-Jun-2026 09:48:32 | Jumpol Sudjitjul | 19-Jun-2026 |  | Sompop Singhatiraj | 23-Jun-2026 | 15-Jun-2026 15:59:22 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 18-Jun-2026 20:19:29 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 25-Jun-2026 | 19-Jun-2026 08:55:36 | 19-Jun-2026 02:34:06 | 0 |  |  | Approver | Locate
AO-001845 | MM-ZTK-1F-ZWP20-STR-DWG-2300 | ZWP20 JACKET - CASING GUIDE ARRANGEMENT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Sep-2026 16:45:37 | wisuda.c@jutal.com | 03-Sep-2026 17:37:42 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 07-Sep-2026 13:58:24 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 16:47:24 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 08:29:05 | 13-Sep-2026 02:13:32 | 0 |  |  | Approver | Locate
AO-002217 | MM-ZTK-1F-ZWP20-STR-DWG-2300 | ZWP20 JACKET - CASING GUIDE ARRANGEMENT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 23-Sep-2026 09:27:10 | wisuda.c@jutal.com | 23-Sep-2026 13:57:04 | Jumpol Sudjitjul | 30-Sep-2026 |  | Sompop Singhatiraj | 02-Oct-2026 | 25-Sep-2026 16:53:06 | Pornlert Wanaphattharaphan | 05-Oct-2026 | 26-Sep-2026 05:21:05 | APPR | Approved | Jumpol Sudjitjul | 06-Oct-2026 | 26-Sep-2026 15:57:48 | 26-Sep-2026 09:35:30 | 0 |  |  | Approver | Locate
AO-001845 | MM-ZTK-1F-ZWP20-STR-DWG-2301 | ZWP20 JACKET - CASING GUIDE DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Sep-2026 17:28:45 | wisuda.c@jutal.com | 03-Sep-2026 17:37:42 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 07-Sep-2026 14:09:07 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 16:51:36 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 08:37:32 | 13-Sep-2026 02:07:28 | 0 |  |  | Approver | Locate
AO-002217 | MM-ZTK-1F-ZWP20-STR-DWG-2301 | ZWP20 JACKET - CASING GUIDE DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 23-Sep-2026 09:27:56 | wisuda.c@jutal.com | 23-Sep-2026 13:57:11 | Jumpol Sudjitjul | 30-Sep-2026 |  | Sompop Singhatiraj | 02-Oct-2026 | 25-Sep-2026 16:52:51 | Pornlert Wanaphattharaphan | 05-Oct-2026 | 26-Sep-2026 05:21:26 | APPR | Approved | Jumpol Sudjitjul | 06-Oct-2026 | 26-Sep-2026 16:04:20 | 26-Sep-2026 09:37:51 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP20-STR-DWG-2311 | ZWP20 JACKET - ANODE STRUCTURE AND INSTALLATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 01:57:41 | wisuda.c@jutal.com | 04-May-2026 11:00:48 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 11:45:34 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 15:11:50 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:40:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:56:09 | 19-May-2026 05:02:47 | 0 |  |  | Approver | Locate
AO-001893 | MM-ZTK-1F-ZWP20-STR-DWG-2311 | ZWP20 JACKET - ANODE STRUCTURE AND INSTALLATION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:06:03 | wisuda.c@jutal.com | 08-Sep-2026 08:34:21 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 10-Sep-2026 16:05:24 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 13-Sep-2026 10:50:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 11:05:14 | 13-Sep-2026 04:31:31 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP20-STR-DWG-2312 | ZWP20 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'A' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 01:58:03 | wisuda.c@jutal.com | 04-May-2026 11:01:06 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 11:47:30 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 15:26:18 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:41:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:58:26 | 19-May-2026 05:07:19 | 0 |  |  | Approver | Locate
AO-001893 | MM-ZTK-1F-ZWP20-STR-DWG-2312 | ZWP20 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'A' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:06:36 | wisuda.c@jutal.com | 08-Sep-2026 08:34:20 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 10-Sep-2026 16:03:46 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 13-Sep-2026 10:49:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 11:06:21 | 13-Sep-2026 04:32:45 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP20-STR-DWG-2313 | ZWP20 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'B' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:02:01 | wisuda.c@jutal.com | 04-May-2026 11:01:18 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 13:04:49 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 15:27:32 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:42:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 14:58:36 | 19-May-2026 08:39:47 | 0 |  |  | Approver | Locate
AO-001893 | MM-ZTK-1F-ZWP20-STR-DWG-2313 | ZWP20 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'B' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:07:11 | wisuda.c@jutal.com | 08-Sep-2026 08:34:21 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 14:43:24 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 17-Sep-2026 22:59:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 18-Sep-2026 09:37:47 | 18-Sep-2026 03:16:57 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP20-STR-DWG-2314 | ZWP20 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '1' & '1.1' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 01:58:25 | wisuda.c@jutal.com | 04-May-2026 11:01:30 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 13:09:16 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 15:28:51 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:42:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:50:06 | 19-May-2026 04:56:13 | 0 |  |  | Approver | Locate
AO-001893 | MM-ZTK-1F-ZWP20-STR-DWG-2314 | ZWP20 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '1' & '1.1' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:07:46 | wisuda.c@jutal.com | 08-Sep-2026 08:34:23 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 14:44:19 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 13:00:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:02:41 | 20-Sep-2026 11:17:37 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP20-STR-DWG-2315 | ZWP20 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '2' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 01:58:48 | wisuda.c@jutal.com | 04-May-2026 11:03:46 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 13:18:04 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 15:32:23 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:43:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:51:51 | 19-May-2026 04:58:44 | 0 |  |  | Approver | Locate
AO-001893 | MM-ZTK-1F-ZWP20-STR-DWG-2315 | ZWP20 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '2' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:08:30 | wisuda.c@jutal.com | 08-Sep-2026 08:34:20 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 14:44:30 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 13:02:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:03:30 | 20-Sep-2026 11:18:51 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP20-STR-DWG-2316 | ZWP20 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'AA' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:02:25 | wisuda.c@jutal.com | 04-May-2026 11:03:58 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 13:27:48 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 15:33:14 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:44:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 14:56:11 | 19-May-2026 08:38:17 | 0 |  |  | Approver | Locate
AO-001893 | MM-ZTK-1F-ZWP20-STR-DWG-2316 | ZWP20 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'AA' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:09:12 | wisuda.c@jutal.com | 08-Sep-2026 08:34:20 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 10-Sep-2026 16:06:38 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 13-Sep-2026 10:51:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 11:07:14 | 13-Sep-2026 04:35:27 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP20-STR-DWG-2317 | ZWP20 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'BB' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:02:46 | wisuda.c@jutal.com | 04-May-2026 11:04:11 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 13:30:16 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 15:24:58 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:41:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 14:55:21 | 19-May-2026 08:36:51 | 0 |  |  | Approver | Locate
AO-001893 | MM-ZTK-1F-ZWP20-STR-DWG-2317 | ZWP20 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'BB' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:09:52 | wisuda.c@jutal.com | 08-Sep-2026 08:34:21 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 10-Sep-2026 16:07:29 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 13-Sep-2026 10:51:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 11:06:47 | 13-Sep-2026 04:34:04 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP20-STR-DWG-2321 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 14000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 01:59:11 | wisuda.c@jutal.com | 04-May-2026 11:04:24 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 13:32:25 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:12:20 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:52:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 14:35:09 | 19-May-2026 07:58:14 | 0 |  |  | Approver | Locate
AO-001893 | MM-ZTK-1F-ZWP20-STR-DWG-2321 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 14000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:10:30 | wisuda.c@jutal.com | 08-Sep-2026 08:34:20 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 14:46:14 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 13:03:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:04:04 | 20-Sep-2026 11:20:12 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP20-STR-DWG-2322 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 26000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 01:59:33 | wisuda.c@jutal.com | 04-May-2026 11:06:12 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 13:35:08 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:13:13 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:53:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 14:51:55 | 19-May-2026 08:28:40 | 0 |  |  | Approver | Locate
AO-001893 | MM-ZTK-1F-ZWP20-STR-DWG-2322 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 26000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:11:00 | wisuda.c@jutal.com | 08-Sep-2026 08:34:21 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 14:46:46 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 13:04:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:05:55 | 20-Sep-2026 12:57:36 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP20-STR-DWG-2323 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 38000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 01:59:58 | wisuda.c@jutal.com | 04-May-2026 11:06:28 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 13:37:48 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:13:21 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:54:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 14:49:07 | 19-May-2026 08:23:23 | 0 |  |  | Approver | Locate
AO-001893 | MM-ZTK-1F-ZWP20-STR-DWG-2323 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 38000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:11:30 | wisuda.c@jutal.com | 08-Sep-2026 08:34:25 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 14:46:54 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 13:05:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:06:57 | 20-Sep-2026 12:58:49 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP20-STR-DWG-2324 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 52000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:03:10 | wisuda.c@jutal.com | 04-May-2026 11:06:40 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 13:43:39 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:14:35 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:54:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 14:47:53 | 19-May-2026 08:20:41 | 0 |  |  | Approver | Locate
AO-001893 | MM-ZTK-1F-ZWP20-STR-DWG-2324 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 52000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:12:08 | wisuda.c@jutal.com | 08-Sep-2026 08:34:26 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 10-Sep-2026 16:10:32 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 13-Sep-2026 10:55:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 11:08:24 | 13-Sep-2026 04:38:02 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP20-STR-DWG-2325 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 66000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 02:00:22 | wisuda.c@jutal.com | 04-May-2026 11:06:52 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 13:46:42 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:14:41 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:55:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 14:44:32 | 19-May-2026 08:17:36 | 0 |  |  | Approver | Locate
AO-001893 | MM-ZTK-1F-ZWP20-STR-DWG-2325 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 66000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:12:50 | wisuda.c@jutal.com | 08-Sep-2026 08:34:26 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 14:47:56 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 13:06:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:07:45 | 20-Sep-2026 13:00:00 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP20-STR-DWG-2326 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 79500 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:03:34 | wisuda.c@jutal.com | 04-May-2026 11:09:33 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 13:48:23 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:14:48 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:55:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 14:41:34 | 19-May-2026 08:14:51 | 0 |  |  | Approver | Locate
AO-001893 | MM-ZTK-1F-ZWP20-STR-DWG-2326 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 79500 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:13:23 | wisuda.c@jutal.com | 08-Sep-2026 08:34:25 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 14:48:55 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 13:07:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:08:25 | 20-Sep-2026 13:01:15 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP20-STR-DWG-2327 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 93000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 02:00:46 | wisuda.c@jutal.com | 04-May-2026 11:09:45 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 13:50:23 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:18:42 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:57:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 14:40:22 | 19-May-2026 08:13:35 | 0 |  |  | Approver | Locate
AO-001893 | MM-ZTK-1F-ZWP20-STR-DWG-2327 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 93000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:13:54 | wisuda.c@jutal.com | 08-Sep-2026 08:34:22 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 14:48:59 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 13:14:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:09:02 | 20-Sep-2026 13:02:27 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP20-STR-DWG-2328 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 103000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:03:56 | wisuda.c@jutal.com | 04-May-2026 11:09:58 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 13:52:18 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:16:05 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:56:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 14:39:44 | 19-May-2026 08:11:05 | 0 |  |  | Approver | Locate
AO-001893 | MM-ZTK-1F-ZWP20-STR-DWG-2328 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 103000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 09:36:14 | wisuda.c@jutal.com | 08-Sep-2026 08:34:25 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 10-Sep-2026 16:15:08 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 13-Sep-2026 10:59:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 11:13:19 | 13-Sep-2026 04:23:49 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP20-STR-DWG-2329 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 113000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:04:21 | wisuda.c@jutal.com | 04-May-2026 11:10:11 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 13:54:01 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:16:13 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:56:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:59:14 | 19-May-2026 05:08:33 | 0 |  |  | Approver | Locate
AO-001893 | MM-ZTK-1F-ZWP20-STR-DWG-2329 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 113000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:14:24 | wisuda.c@jutal.com | 08-Sep-2026 08:34:26 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 10-Sep-2026 16:15:15 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 13-Sep-2026 11:00:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 11:14:08 | 13-Sep-2026 04:40:33 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP20-STR-DWG-2330 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 124000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 02:01:09 | wisuda.c@jutal.com | 04-May-2026 11:21:09 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 13:55:56 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:18:29 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:57:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:58:03 | 19-May-2026 05:06:07 | 0 |  |  | Approver | Locate
AO-001893 | MM-ZTK-1F-ZWP20-STR-DWG-2330 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 124000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:14:52 | wisuda.c@jutal.com | 08-Sep-2026 08:34:24 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 14:50:20 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 13:15:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:10:23 | 20-Sep-2026 13:03:39 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP20-STR-DWG-2331 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 135000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:04:44 | wisuda.c@jutal.com | 04-May-2026 11:21:21 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 13:58:22 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:19:44 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:58:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:56:02 | 19-May-2026 05:01:25 | 0 |  |  | Approver | Locate
AO-001893 | MM-ZTK-1F-ZWP20-STR-DWG-2331 | ZWP20 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 135000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:15:25 | wisuda.c@jutal.com | 08-Sep-2026 08:34:33 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 14:51:17 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 16:27:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:11:19 | 20-Sep-2026 13:04:55 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP20-STR-DWG-2332 | ZWP20 JACKET - ANODE DISTRIBUTION OF PILE CLUSTER |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:05:07 | wisuda.c@jutal.com | 04-May-2026 11:21:33 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 14:00:31 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:10:30 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:52:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:52:21 | 19-May-2026 05:00:01 | 0 |  |  | Approver | Locate
AO-001893 | MM-ZTK-1F-ZWP20-STR-DWG-2332 | ZWP20 JACKET - ANODE DISTRIBUTION OF PILE CLUSTER |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:15:58 | wisuda.c@jutal.com | 08-Sep-2026 08:34:27 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 14:50:47 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 13:22:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:11:54 | 20-Sep-2026 13:06:09 | 0 |  |  | Approver | Locate
AO-000822 | MM-ZTK-1F-ZWP20-STR-DWG-2801 | ZWP20 JACKET RISER AND RISER SUPPORT LOCATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 10:02:20 | wisuda.c@jutal.com | 18-Jun-2026 10:05:38 | Jumpol Sudjitjul | 25-Jun-2026 | 18-Jun-2026 15:55:02 | Sompop Singhatiraj | 29-Jun-2026 | 19-Jun-2026 17:02:31 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 20-Jun-2026 17:28:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 21-Jun-2026 21:29:58 | 22-Jun-2026 00:52:29 | 0 |  |  | Approver | Locate
AO-002031 | MM-ZTK-1F-ZWP20-STR-DWG-2801 | ZWP20 JACKET RISER AND RISER SUPPORT LOCATION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 14-Sep-2026 09:46:49 | wisuda.c@jutal.com | 15-Sep-2026 14:21:31 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 17-Sep-2026 18:17:50 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 19-Sep-2026 16:02:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 20-Sep-2026 18:13:13 | 20-Sep-2026 13:07:23 | 0 |  |  | Approver | Locate
AO-002033 | MM-ZTK-1F-ZWP20-STR-DWG-2802 | ZWP20 JACKET 18" RISER CLAMP DETAILS - HANGER CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Sep-2026 10:18:19 | wisuda.c@jutal.com | 15-Sep-2026 14:52:28 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 17-Sep-2026 18:17:58 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 19-Sep-2026 16:04:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 20-Sep-2026 18:15:56 | 20-Sep-2026 12:08:21 | 0 |  |  | Approver | Locate
AO-002033 | MM-ZTK-1F-ZWP20-STR-DWG-2803 | ZWP20 JACKET 18" RISER CLAMP DETAILS - SLIDING CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Sep-2026 09:47:26 | wisuda.c@jutal.com | 15-Sep-2026 14:52:27 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 17-Sep-2026 18:18:06 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 19-Sep-2026 16:04:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 20-Sep-2026 18:17:23 | 20-Sep-2026 13:08:34 | 0 |  |  | Approver | Locate
AO-002033 | MM-ZTK-1F-ZWP20-STR-DWG-2804 | ZWP20 JACKET 18" RISER CLAMP DETAILS - SLIDING CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Sep-2026 10:19:09 | wisuda.c@jutal.com | 15-Sep-2026 14:52:25 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 17-Sep-2026 18:18:15 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 19-Sep-2026 16:05:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 20-Sep-2026 18:17:53 | 20-Sep-2026 12:09:30 | 0 |  |  | Approver | Locate
AO-002033 | MM-ZTK-1F-ZWP20-STR-DWG-2805 | ZWP20 JACKET 18" RISER CLAMP DETAILS - TEMPORARY CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Sep-2026 09:47:56 | wisuda.c@jutal.com | 15-Sep-2026 14:52:27 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 17-Sep-2026 18:19:23 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 19-Sep-2026 16:10:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 20-Sep-2026 18:19:10 | 20-Sep-2026 13:09:48 | 0 |  |  | Approver | Locate
AO-000740 | MM-ZTK-1F-ZWP20-STR-DWG-2900 | ZWP20 JACKET - CLOSURE PLATE DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 18:11:51 | wisuda.c@jutal.com | 12-Jun-2026 10:08:58 | Jumpol Sudjitjul | 19-Jun-2026 |  | Sompop Singhatiraj | 23-Jun-2026 | 15-Jun-2026 16:54:24 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 18-Jun-2026 20:22:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 19-Jun-2026 08:56:03 | 19-Jun-2026 02:36:36 | 0 |  |  | Approver | Locate
AO-001895 | MM-ZTK-1F-ZWP20-STR-DWG-2900 | ZWP20 JACKET - CLOSURE PLATE DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:16:26 | wisuda.c@jutal.com | 08-Sep-2026 08:36:49 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 15:56:19 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 13:20:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:20:02 | 20-Sep-2026 13:09:16 | 0 |  |  | Approver | Locate
AO-002361 | MM-ZTK-1F-ZWP20-STR-DWG-2900 | ZWP20 JACKET - CLOSURE PLATE DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 10:05:48 | wisuda.c@jutal.com | 05-Oct-2026 10:25:13 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 08-Oct-2026 14:58:49 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 23:00:51 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 11-Oct-2026 10:04:13 | 11-Oct-2026 03:28:43 | 0 |  |  | Approver | Locate
AO-000740 | MM-ZTK-1F-ZWP20-STR-DWG-2901 | ZWP20 JACKET - CLOSURE PLATE DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 18:12:17 | wisuda.c@jutal.com | 12-Jun-2026 10:09:19 | Jumpol Sudjitjul | 19-Jun-2026 |  | Sompop Singhatiraj | 23-Jun-2026 | 15-Jun-2026 16:54:24 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 18-Jun-2026 20:23:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 19-Jun-2026 08:56:31 | 19-Jun-2026 02:40:26 | 0 |  |  | Approver | Locate
AO-001895 | MM-ZTK-1F-ZWP20-STR-DWG-2901 | ZWP20 JACKET - CLOSURE PLATE DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:16:56 | wisuda.c@jutal.com | 08-Sep-2026 08:37:07 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 15:52:46 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 13:13:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:20:31 | 20-Sep-2026 13:10:30 | 0 |  |  | Approver | Locate
AO-002361 | MM-ZTK-1F-ZWP20-STR-DWG-2901 | ZWP20 JACKET - CLOSURE PLATE DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 10:06:20 | wisuda.c@jutal.com | 05-Oct-2026 10:25:14 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 08-Oct-2026 15:18:24 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 23:52:43 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 11-Oct-2026 10:04:44 | 11-Oct-2026 03:29:54 | 0 |  |  | Approver | Locate
AO-000741 | MM-ZTK-1F-ZWP20-STR-DWG-2902 | ZWP20 JACKET - LEG PARTITION DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 12-Jun-2026 08:39:01 | wisuda.c@jutal.com | 12-Jun-2026 10:09:34 | Jumpol Sudjitjul | 19-Jun-2026 |  | Sompop Singhatiraj | 23-Jun-2026 | 15-Jun-2026 16:55:37 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 18-Jun-2026 20:25:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 19-Jun-2026 08:56:57 | 19-Jun-2026 02:31:30 | 0 |  |  | Approver | Locate
AO-001774 | MM-ZTK-1F-ZWP20-STR-DWG-2902 | ZWP20 JACKET - LEG PARTITION DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:25:02 | wisuda.c@jutal.com | 31-Aug-2026 11:08:05 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 03-Sep-2026 09:24:19 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 04-Sep-2026 23:47:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 05-Sep-2026 18:03:58 | 05-Sep-2026 11:53:46 | 0 |  |  | Approver | Locate
AO-002361 | MM-ZTK-1F-ZWP20-STR-DWG-2902 | ZWP20 JACKET - LEG PARTITION DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 10:06:58 | wisuda.c@jutal.com | 05-Oct-2026 10:25:13 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 08-Oct-2026 15:24:17 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 23:55:32 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 11-Oct-2026 10:05:14 | 11-Oct-2026 03:31:06 | 0 |  |  | Approver | Locate
AO-002301 | MM-ZTK-1F-ZWP20-STR-DWG-2911 | ZWP20 JACKET - UPENDING ARRANGEMENT AND DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-Sep-2026 17:59:19 | wisuda.c@jutal.com | 29-Sep-2026 14:26:09 | Jumpol Sudjitjul | 06-Oct-2026 |  | Sompop Singhatiraj | 08-Oct-2026 | 06-Oct-2026 09:32:25 | Pornlert Wanaphattharaphan | 09-Oct-2026 | 10-Oct-2026 01:37:04 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 12-Oct-2026 | 10-Oct-2026 17:33:58 | 10-Oct-2026 10:53:55 | 0 |  |  | Approver | Locate
AO-000308 | MM-ZTK-1F-ZWP20-STR-DWG-2931 | ZWP20 JACKET - BALLAST / DEBASSAST SCHEMATIC |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 05-May-2026 19:04:28 | wisuda.c@jutal.com | 06-May-2026 10:08:42 | Jumpol Sudjitjul | 13-May-2026 |  | Sompop Singhatiraj | 15-May-2026 | 16-May-2026 11:43:45 | Pornlert Wanaphattharaphan | 18-May-2026 | 18-May-2026 23:20:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 19-May-2026 10:51:01 | 19-May-2026 04:57:29 | 0 |  |  | Approver | Locate
AO-001660 | MM-ZTK-1F-ZWP20-STR-DWG-2931 | ZWP20 JACKET - BALLAST / DEBASSAST SCHEMATIC |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 10:47:54 | wisuda.c@jutal.com | 24-Aug-2026 20:32:51 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 03-Sep-2026 12:43:57 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 01:02:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:01:12 | 07-Sep-2026 12:07:14 | 0 |  |  | Approver | Locate
AO-000308 | MM-ZTK-1F-ZWP20-STR-DWG-2932 | ZWP20 JACKET - GROUTING SCHEMATIC |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 05-May-2026 19:04:53 | wisuda.c@jutal.com | 06-May-2026 10:08:57 | Jumpol Sudjitjul | 13-May-2026 |  | Sompop Singhatiraj | 15-May-2026 | 16-May-2026 11:45:35 | Pornlert Wanaphattharaphan | 18-May-2026 | 18-May-2026 23:23:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 19-May-2026 10:49:34 | 19-May-2026 04:54:58 | 0 |  |  | Approver | Locate
AO-001660 | MM-ZTK-1F-ZWP20-STR-DWG-2932 | ZWP20 JACKET - GROUTING SCHEMATIC |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:49:18 | wisuda.c@jutal.com | 24-Aug-2026 20:32:52 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 03-Sep-2026 11:30:15 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:57:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:01:43 | 07-Sep-2026 12:15:51 | 0 |  |  | Approver | Locate
AO-001775 | MM-ZTK-1F-ZWP20-STR-DWG-2933 | ZWP20 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT ROW A ELEVATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 31-Aug-2026 09:25:36 | wisuda.c@jutal.com | 31-Aug-2026 11:26:23 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 03-Sep-2026 13:52:20 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 04-Sep-2026 23:31:55 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-Sep-2026 | 05-Sep-2026 18:04:28 | 05-Sep-2026 11:56:44 | 0 |  |  | Approver | Locate
AO-001775 | MM-ZTK-1F-ZWP20-STR-DWG-2934 | ZWP20 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT ROW B ELEVATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 31-Aug-2026 09:26:09 | wisuda.c@jutal.com | 31-Aug-2026 11:26:47 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 03-Sep-2026 13:53:52 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 04-Sep-2026 23:31:17 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-Sep-2026 | 05-Sep-2026 18:04:55 | 05-Sep-2026 11:58:02 | 0 |  |  | Approver | Locate
AO-002030 | MM-ZTK-1F-ZWP20-STR-DWG-2935 | ZWP20 JACKET - BALLAST AND GROUTING SYSTEM SUPPORT DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Sep-2026 10:19:54 | wisuda.c@jutal.com | 15-Sep-2026 14:59:01 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 22-Sep-2026 12:23:14 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 22-Sep-2026 20:02:54 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 28-Sep-2026 | 23-Sep-2026 13:24:28 | 23-Sep-2026 07:22:02 | 0 |  |  | Approver | Locate
AO-002030 | MM-ZTK-1F-ZWP20-STR-DWG-2936 | ZWP20 JACKET - BALLAST AND GROUTING SYSTEM SUPPORT DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Sep-2026 10:20:59 | wisuda.c@jutal.com | 15-Sep-2026 14:58:58 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 22-Sep-2026 12:23:22 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 22-Sep-2026 20:03:14 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 28-Sep-2026 | 23-Sep-2026 13:21:46 | 23-Sep-2026 07:19:30 | 0 |  |  | Approver | Locate
AO-002030 | MM-ZTK-1F-ZWP20-STR-DWG-2937 | ZWP20 JACKET - BALLAST SYSTEM VALVE DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Sep-2026 10:22:04 | wisuda.c@jutal.com | 15-Sep-2026 14:59:01 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 22-Sep-2026 12:23:29 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 22-Sep-2026 20:02:36 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 28-Sep-2026 | 23-Sep-2026 13:25:26 | 23-Sep-2026 07:23:14 | 0 |  |  | Approver | Locate
AO-002030 | MM-ZTK-1F-ZWP20-STR-DWG-2938 | ZWP20 JACKET -GROUT, SKIRT SLEEVE VENT AND FLOODING DETAILS AT SKIRT PILE SLEEVE SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Sep-2026 10:22:56 | wisuda.c@jutal.com | 15-Sep-2026 14:59:04 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 22-Sep-2026 12:25:07 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 22-Sep-2026 20:01:53 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 28-Sep-2026 | 23-Sep-2026 13:26:26 | 23-Sep-2026 07:24:29 | 0 |  |  | Approver | Locate
AO-002030 | MM-ZTK-1F-ZWP20-STR-DWG-2939 | ZWP20 JACKET -GROUT, SKIRT SLEEVE VENT AND FLOODING DETAILS AT SKIRT PILE SLEEVE SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Sep-2026 10:23:53 | wisuda.c@jutal.com | 15-Sep-2026 14:59:02 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 22-Sep-2026 12:25:13 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 22-Sep-2026 19:59:39 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 28-Sep-2026 | 23-Sep-2026 11:23:31 | 23-Sep-2026 04:26:53 | 0 |  |  | Approver | Locate
AO-002030 | MM-ZTK-1F-ZWP20-STR-DWG-2940 | ZWP20 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT EL(+) 8000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Sep-2026 10:24:50 | wisuda.c@jutal.com | 15-Sep-2026 14:58:59 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 22-Sep-2026 12:25:20 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 22-Sep-2026 19:58:52 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 28-Sep-2026 | 23-Sep-2026 13:27:02 | 23-Sep-2026 07:25:50 | 0 |  |  | Approver | Locate
AO-002030 | MM-ZTK-1F-ZWP20-STR-DWG-2941 | ZWP20 JACKET - GROUT SYSTEM DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Sep-2026 10:25:56 | wisuda.c@jutal.com | 15-Sep-2026 14:58:58 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 22-Sep-2026 12:25:29 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 22-Sep-2026 19:57:48 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 28-Sep-2026 | 23-Sep-2026 13:27:51 | 23-Sep-2026 07:27:10 | 0 |  |  | Approver | Locate
AO-001903 | MM-ZTK-1F-ZWP20-STR-DWG-2971 | ZWP20 JACKET - WELD PROFILE CONTROL SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Sep-2026 10:17:31 | wisuda.c@jutal.com | 08-Sep-2026 08:55:42 | Jumpol Sudjitjul | 15-Sep-2026 | 09-Sep-2026 10:37:09 | Sompop Singhatiraj | 17-Sep-2026 | 10-Sep-2026 11:36:02 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 12-Sep-2026 23:27:12 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 08:40:06 | 13-Sep-2026 02:08:43 | 0 |  |  | Approver | Locate
AO-001903 | MM-ZTK-1F-ZWP20-STR-DWG-2972 | ZWP20 JACKET - WELD PROFILE CONTROL SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Sep-2026 10:18:03 | wisuda.c@jutal.com | 08-Sep-2026 08:55:40 | Jumpol Sudjitjul | 15-Sep-2026 | 09-Sep-2026 10:31:42 | Sompop Singhatiraj | 17-Sep-2026 | 10-Sep-2026 11:34:24 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 12-Sep-2026 23:17:14 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 08:43:43 | 13-Sep-2026 02:11:14 | 0 |  |  | Approver | Locate
AO-001903 | MM-ZTK-1F-ZWP20-STR-DWG-2973 | ZWP20 JACKET - WELD PROFILE CONTROL SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Sep-2026 10:18:39 | wisuda.c@jutal.com | 08-Sep-2026 08:55:40 | Jumpol Sudjitjul | 15-Sep-2026 | 09-Sep-2026 10:25:52 | Sompop Singhatiraj | 17-Sep-2026 | 10-Sep-2026 13:58:13 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 12-Sep-2026 23:29:15 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 08:33:56 | 13-Sep-2026 02:03:45 | 0 |  |  | Approver | Locate
AO-001903 | MM-ZTK-1F-ZWP20-STR-DWG-2974 | ZWP20 JACKET - WELD PROFILE CONTROL SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Sep-2026 10:19:16 | wisuda.c@jutal.com | 08-Sep-2026 08:55:36 | Jumpol Sudjitjul | 15-Sep-2026 | 09-Sep-2026 10:24:57 | Sompop Singhatiraj | 17-Sep-2026 | 10-Sep-2026 13:59:12 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 12-Sep-2026 23:32:45 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 08:34:41 | 13-Sep-2026 02:05:02 | 0 |  |  | Approver | Locate
AO-001903 | MM-ZTK-1F-ZWP20-STR-DWG-2975 | ZWP20 JACKET - WELD PROFILE CONTROL SHEET 5 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Sep-2026 10:19:58 | wisuda.c@jutal.com | 08-Sep-2026 08:55:41 | Jumpol Sudjitjul | 15-Sep-2026 | 09-Sep-2026 10:34:35 | Sompop Singhatiraj | 17-Sep-2026 | 10-Sep-2026 13:59:24 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 12-Sep-2026 23:32:08 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 08:35:58 | 13-Sep-2026 02:06:19 | 0 |  |  | Approver | Locate
AO-001903 | MM-ZTK-1F-ZWP20-STR-DWG-2976 | ZWP20 JACKET - WELD PROFILE CONTROL SHEET 6 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Sep-2026 10:20:32 | wisuda.c@jutal.com | 08-Sep-2026 08:55:42 | Jumpol Sudjitjul | 15-Sep-2026 | 09-Sep-2026 10:42:43 | Sompop Singhatiraj | 17-Sep-2026 | 10-Sep-2026 13:58:25 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 12-Sep-2026 23:31:02 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 08:49:06 | 13-Sep-2026 02:28:50 | 0 |  |  | Approver | Locate
AO-002030 | MM-ZTK-1F-ZWP20-STR-DWG-2991 | ZWP20 JACKET - JACKET TRANSPORTATION ARRANGEMENT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Sep-2026 09:48:26 | wisuda.c@jutal.com | 15-Sep-2026 15:02:16 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 18-Sep-2026 08:36:29 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 19-Sep-2026 16:11:14 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 28-Sep-2026 | 20-Sep-2026 18:21:31 | 20-Sep-2026 13:12:56 | 0 |  |  | Approver | Locate
AO-002544 | MM-ZTK-1F-ZWP20-STR-DWG-2991 | ZWP20 JACKET - JACKET TRANSPORTATION ARRANGEMENT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP20 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 16-Oct-2026 10:12:13 | wisuda.c@jutal.com | 16-Oct-2026 16:06:01 | Jumpol Sudjitjul | 26-Oct-2026 |  | Sompop Singhatiraj | 28-Oct-2026 |  | Pornlert Wanaphattharaphan | 29-Oct-2026 |  |  |  |  | 30-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000293 | MM-ZTK-1F-ZWP20-STR-MR-2001 | MATERIAL REǪUISITION FOR ZWP20 JACKET PRIMARY TUBULAR STEEL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 02:01:40 | wisuda.c@jutal.com | 04-May-2026 13:11:09 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 08:18:01 | Sompop Singhatiraj | 13-May-2026 | 15-May-2026 15:59:41 | Pornlert Wanaphattharaphan | 14-May-2026 | 15-May-2026 22:45:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 17-May-2026 10:30:12 | 17-May-2026 11:32:15 | 0 |  |  | Approver | Locate
AO-000317 | MM-ZTK-1F-ZWP20-STR-MR-2002 | MATERIAL REǪUISITION FOR ZWP20 JACKET PRIMARY STEEL (PLATE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 06-May-2026 09:48:38 | wisuda.c@jutal.com | 06-May-2026 10:31:53 | Jumpol Sudjitjul | 13-May-2026 | 15-May-2026 07:37:27 | Sompop Singhatiraj | 15-May-2026 | 15-May-2026 16:46:46 | Pornlert Wanaphattharaphan | 18-May-2026 | 15-May-2026 23:20:12 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 19-May-2026 | 17-May-2026 09:58:14 | 17-May-2026 03:32:05 | 0 |  |  | Approver | Locate
AO-001771 | MM-ZTK-1F-ZWP20-STR-MTO-2001 | ZWP20 JACKET PRIMARY STEEL MTO REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 31-Aug-2026 09:26:39 | wisuda.c@jutal.com | 31-Aug-2026 11:33:56 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 10-Sep-2026 18:53:37 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 12-Sep-2026 15:13:22 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-Sep-2026 | 13-Sep-2026 08:42:33 | 13-Sep-2026 02:19:05 | 0 |  |  | Approver | Locate
AO-001772 | MM-ZTK-1F-ZWP20-STR-MTO-2002 | ZWP20 JACKET SECONDARY STEEL MTO REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 31-Aug-2026 09:27:10 | wisuda.c@jutal.com | 31-Aug-2026 11:34:21 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 10-Sep-2026 18:53:45 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 12-Sep-2026 15:20:00 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-Sep-2026 | 13-Sep-2026 08:47:37 | 13-Sep-2026 01:57:26 | 0 |  |  | Approver | Locate
AO-001309 | MM-ZTK-1F-ZWP20-STR-TBE-1001 | TECHNICAL BID EVALUATION FOR ZWP20 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 27-Jul-2026 08:45:02 | wisuda.c@jutal.com | 27-Jul-2026 16:10:46 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 30-Jul-2026 12:25:55 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 30-Jul-2026 18:08:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 30-Jul-2026 19:08:53 | 30-Jul-2026 12:23:00 | 0 |  |  | Approver | Locate
AO-000201 | MM-ZTK-1F-ZWP20-STR-WCR-2001 | ZWP20 JACKET WEIGHT CONTROL REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | WCR | Weight Control Report | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:35:14 | wisuda.c@jutal.com | 22-Apr-2026 10:38:27 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 24-Apr-2026 10:24:17 | Pornlert Wanaphattharaphan | 06-May-2026 | 24-Apr-2026 12:03:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 14:19:35 | 24-Apr-2026 07:37:29 | 0 |  |  | Approver | Locate
AO-001931 | MM-ZTK-1F-ZWP20-STR-WCR-2001 | ZWP20 JACKET WEIGHT CONTROL REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | WCR | Weight Control Report | 0 | Submitted | IFA | Issued for Approval |  | 08-Sep-2026 12:35:03 | wisuda.c@jutal.com | 08-Sep-2026 14:23:52 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 21-Sep-2026 09:51:58 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 22-Sep-2026 19:55:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 23-Sep-2026 13:29:16 | 23-Sep-2026 06:51:18 | 0 |  |  | Approver | Locate
AO-002295 | MM-ZTK-1F-ZWP20-STR-WCR-2001 | ZWP20 JACKET WEIGHT CONTROL REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP20 |  |  | STR | Structural | WCR | Weight Control Report | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 09:46:32 | wisuda.c@jutal.com | 28-Sep-2026 10:08:53 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 01-Oct-2026 11:21:55 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 01-Oct-2026 22:54:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 02-Oct-2026 13:30:17 | 02-Oct-2026 07:04:25 | 0 |  |  | Approver | Locate
AO-000645 | MM-ZTK-1F-ZWP21-COR-CAL-0001 | ZWP21 CATHODIC PROTECTION CALCULATION |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | COR | Corrosion | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 02-Jun-2026 10:24:40 | wisuda.c@jutal.com | 02-Jun-2026 15:10:21 | Jumpol Sudjitjul | 10-Jun-2026 |  | Sompop Singhatiraj | 12-Jun-2026 | 07-Jun-2026 11:56:43 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 10-Jun-2026 21:38:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 11-Jun-2026 11:14:44 | 11-Jun-2026 04:51:12 | 0 |  |  | Approver | Locate
AO-001449 | MM-ZTK-1F-ZWP21-COR-CAL-0001 | ZWP21 CATHODIC PROTECTION CALCULATION |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | COR | Corrosion | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:38:39 | wisuda.c@jutal.com | 07-Aug-2026 17:16:55 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 02-Sep-2026 16:04:23 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 02-Sep-2026 22:47:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 03-Sep-2026 10:02:35 | 03-Sep-2026 04:14:33 | 0 |  |  | Approver | Locate
AO-000513 | MM-ZTK-1F-ZWP21-NVA-CAL-2011 | ZWP21 JACKET BARGE MOTION ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 13:33:56 | wisuda.c@jutal.com | 19-May-2026 13:46:45 | Jumpol Sudjitjul | 26-May-2026 | 04-Jun-2026 08:33:19 | Sompop Singhatiraj | 28-May-2026 | 07-Jun-2026 16:15:51 | Pornlert Wanaphattharaphan | 29-May-2026 | 10-Jun-2026 21:00:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 11-Jun-2026 13:51:20 | 11-Jun-2026 07:35:55 | 0 |  |  | Approver | Locate
AO-001140 | MM-ZTK-1F-ZWP21-NVA-CAL-2011 | ZWP21 JACKET BARGE MOTION ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 18:47:03 | wisuda.c@jutal.com | 16-Jul-2026 20:36:32 | Jumpol Sudjitjul | 24-Jul-2026 | 10-Aug-2026 11:49:31 | Sompop Singhatiraj | 30-Jul-2026 | 13-Aug-2026 10:05:42 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 15-Aug-2026 06:33:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 15-Aug-2026 14:44:23 | 15-Aug-2026 08:20:08 | 0 |  |  | Approver | Locate
AO-001776 | MM-ZTK-1F-ZWP21-NVA-CAL-2011 | ZWP21 JACKET BARGE MOTION ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 31-Aug-2026 09:44:08 | wisuda.c@jutal.com | 31-Aug-2026 13:27:59 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 21-Sep-2026 13:39:34 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 22-Sep-2026 19:55:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 23-Sep-2026 13:29:56 | 23-Sep-2026 06:53:46 | 0 |  |  | Approver | Locate
AO-000617 | MM-ZTK-1F-ZWP21-NVA-CAL-2012 | ZWP21 JACKET LAUNCH ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 16:08:21 | wisuda.c@jutal.com | 28-May-2026 21:00:08 | Jumpol Sudjitjul | 09-Jun-2026 | 01-Jun-2026 14:53:58 | Sompop Singhatiraj | 11-Jun-2026 | 05-Jun-2026 19:37:51 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 10-Jun-2026 21:30:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 11-Jun-2026 13:50:52 | 11-Jun-2026 07:34:25 | 0 |  |  | Approver | Locate
AO-001585 | MM-ZTK-1F-ZWP21-NVA-CAL-2012 | ZWP21 JACKET LAUNCH ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 18-Aug-2026 08:56:30 | wisuda.c@jutal.com | 18-Aug-2026 09:18:19 | Jumpol Sudjitjul | 25-Aug-2026 |  | Sompop Singhatiraj | 27-Aug-2026 | 28-Aug-2026 15:58:33 | Pornlert Wanaphattharaphan | 28-Aug-2026 | 29-Aug-2026 23:21:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Aug-2026 | 30-Aug-2026 17:05:50 | 30-Aug-2026 11:57:24 | 0 |  |  | Approver | Locate
AO-002021 | MM-ZTK-1F-ZWP21-NVA-CAL-2012 | ZWP21 JACKET LAUNCH ANALYSIS REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 11-Sep-2026 20:58:24 | wisuda.c@jutal.com | 11-Sep-2026 21:11:47 | Jumpol Sudjitjul | 21-Sep-2026 |  | Sompop Singhatiraj | 23-Sep-2026 | 28-Sep-2026 13:45:23 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 28-Sep-2026 21:59:39 | APPR | Approved | Jumpol Sudjitjul | 25-Sep-2026 | 29-Sep-2026 10:33:01 | 29-Sep-2026 04:56:11 | 0 |  |  | Approver | Locate
AO-000856 | MM-ZTK-1F-ZWP21-NVA-CAL-2013 | ZWP21 JACKET FLOATATION AND UPENDING ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Review |  | 21-Jun-2026 22:40:20 | wisuda.c@jutal.com | 22-Jun-2026 14:01:27 | Jumpol Sudjitjul | 29-Jun-2026 |  | Sompop Singhatiraj | 01-Jul-2026 | 01-Jul-2026 18:45:32 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 03-Jul-2026 00:45:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 03-Jul-2026 11:32:20 | 03-Jul-2026 05:03:22 | 0 |  |  | Approver | Locate
AO-001186 | MM-ZTK-1F-ZWP21-NVA-CAL-2013 | ZWP21 JACKET FLOATATION AND UPENDING ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 10:38:19 | wisuda.c@jutal.com | 20-Jul-2026 15:00:53 | Jumpol Sudjitjul | 27-Jul-2026 | 13-Aug-2026 12:45:22 | Sompop Singhatiraj | 31-Jul-2026 | 16-Aug-2026 16:17:26 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 16-Aug-2026 16:58:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 17-Aug-2026 14:23:58 | 17-Aug-2026 08:50:24 | 0 |  |  | Approver | Locate
AO-001964 | MM-ZTK-1F-ZWP21-NVA-CAL-2013 | ZWP21 JACKET FLOATATION AND UPENDING ANALYSIS REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 10:41:24 | wisuda.c@jutal.com | 10-Sep-2026 12:01:46 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 21-Sep-2026 11:12:39 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 22-Sep-2026 19:54:34 | APPR | Approved | Jumpol Sudjitjul | 23-Sep-2026 | 23-Sep-2026 13:31:11 | 23-Sep-2026 07:28:35 | 0 |  |  | Approver | Locate
AO-000472 | MM-ZTK-1F-ZWP21-PIP-LAY-0005 | EQUIPMENT LAYOUT SUMP DECK PLAN T.O.S. EL.(+) 14.700 M. & BOAT LANDING PLAN T.O.S EL.(+) 5.000 M. |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 14:06:39 | wisuda.c@jutal.com | 18-May-2026 08:10:16 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 21:35:04 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 22:00:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:30:54 | 07-Jun-2026 10:55:31 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWP21-PIP-LAY-0005 | EQUIPMENT LAYOUT SUMP DECK PLAN T.O.S. EL.(+) 14.700 M. & BOAT LANDING PLAN T.O.S EL.(+) 5.000 M. |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:34:18 | wisuda.c@jutal.com | 15-Sep-2026 09:55:42 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:26:32 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 21:38:35 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 23:06:16 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 09:48:58 | 08-Oct-2026 04:09:49 | 0 |  |  | Approver | Locate
AO-000473 | MM-ZTK-1F-ZWP21-PIP-LAY-0006 | EQUIPMENT LAYOUT ELEVATION LOOKING NORTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 14:07:04 | wisuda.c@jutal.com | 18-May-2026 08:10:49 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 21:40:22 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 22:01:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:31:24 | 07-Jun-2026 10:56:47 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWP21-PIP-LAY-0006 | EQUIPMENT LAYOUT ELEVATION LOOKING NORTH |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:35:01 | wisuda.c@jutal.com | 15-Sep-2026 09:55:39 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:14:26 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 21:41:57 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 23:09:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 09:50:34 | 08-Oct-2026 04:12:32 | 0 |  |  | Approver | Locate
AO-000474 | MM-ZTK-1F-ZWP21-PIP-LAY-0007 | EQUIPMENT LAYOUT ELEVATION LOOKING EAST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 14:07:27 | wisuda.c@jutal.com | 18-May-2026 08:11:26 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 21:42:09 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 22:02:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:31:54 | 07-Jun-2026 10:58:05 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWP21-PIP-LAY-0007 | EQUIPMENT LAYOUT ELEVATION LOOKING EAST |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:35:34 | wisuda.c@jutal.com | 15-Sep-2026 09:55:40 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:13:19 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 21:46:22 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 23:09:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 09:52:11 | 08-Oct-2026 04:11:11 | 0 |  |  | Approver | Locate
AO-000475 | MM-ZTK-1F-ZWP21-PIP-LAY-0008 | EQUIPMENT LAYOUT ELEVATION LOOKING SOUTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 14:07:52 | wisuda.c@jutal.com | 18-May-2026 08:12:01 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 21:44:43 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 22:03:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:32:52 | 07-Jun-2026 10:59:22 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWP21-PIP-LAY-0008 | EQUIPMENT LAYOUT ELEVATION LOOKING SOUTH |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:36:08 | wisuda.c@jutal.com | 15-Sep-2026 09:55:39 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:20:01 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 21:51:07 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 23:10:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 10:08:28 | 08-Oct-2026 04:21:40 | 0 |  |  | Approver | Locate
AO-000476 | MM-ZTK-1F-ZWP21-PIP-LAY-0009 | EQUIPMENT LAYOUT ELEVATION LOOKING WEST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 14:08:16 | wisuda.c@jutal.com | 18-May-2026 08:12:40 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 21:46:40 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 22:04:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:33:21 | 07-Jun-2026 11:00:41 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWP21-PIP-LAY-0009 | EQUIPMENT LAYOUT ELEVATION LOOKING WEST |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:36:41 | wisuda.c@jutal.com | 15-Sep-2026 09:55:40 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:15:22 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 21:53:49 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 23:11:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 10:09:57 | 08-Oct-2026 04:22:55 | 0 |  |  | Approver | Locate
AO-000976 | MM-ZTK-1F-ZWP21-PRC-UPO-5001 | UNPRICED PO FOR PRIMARY STEEL PLATES FOR ZWP21 |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | ZWP21 |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 02-Jul-2026 17:21:23 | zm169dc@jutal.com | 02-Jul-2026 17:45:30 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 12-Aug-2026 09:31:30 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 13-Aug-2026 11:37:58 | 13-Aug-2026 06:00:00 | 0 |  |  | For Info | Locate
AO-001035 | MM-ZTK-1F-ZWP21-PRC-UPO-5002 | UNPRICED PO FOR PRIMARY STEEL PLATES FOR ZWP21 (CUT-OFF DATE 6-JUL-2026) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | ZWP21 |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 08-Jul-2026 10:13:27 | zm169dc@jutal.com | 08-Jul-2026 14:34:14 | Jumpol Sudjitjul | 15-Jul-2026 |  | Jirayu Pantito | 17-Jul-2026 | 18-Jul-2026 08:48:25 |  |  |  | REC | Received | Jumpol Sudjitjul | 21-Jul-2026 | 20-Jul-2026 08:54:03 | 20-Jul-2026 02:20:52 | 0 |  |  | Focal Point | Locate
AO-001343 | MM-ZTK-1F-ZWP21-PRC-UPO-5003 | UNPRICED PO FOR PRIMARY STEEL PLATES FOR ZWP21(CUT-OFF DATE 27-JUL-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | ZWP21 |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 30-Jul-2026 17:23:34 | zm169dc@jutal.com | 30-Jul-2026 19:18:52 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 12-Aug-2026 09:34:59 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 13-Aug-2026 11:38:31 | 13-Aug-2026 06:01:17 | 0 |  |  | For Info | Locate
AO-002121 | MM-ZTK-1F-ZWP21-PRC-UPO-5004 | UNPRICED PO FOR STEEL PLATES FOR ZWP21(CUT-OFF DATE 15-SEP-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | ZWP21 |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 17-Sep-2026 13:33:49 | zm169dc@jutal.com | 18-Sep-2026 16:24:03 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  |  | Prin Jitatisil | [8 empty] | 0 |  |  | For Info | Locate
AO-002121 | MM-ZTK-1F-ZWP21-PRC-UPO-5100 | UNPRICED PO FOR ANODE FOR ZWP21 (CUT-OFF DATE 15-SEP-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | ZWP21 |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 17-Sep-2026 13:34:22 | zm169dc@jutal.com | 18-Sep-2026 16:24:51 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  |  | Prin Jitatisil | [8 empty] | 0 |  |  | For Info | Locate
AO-000326 | MM-ZTK-1F-ZWP21-STR-CAL-2001 | ZWP21 JACKET COMPUTER MODELING AND LOAD FORMULATION |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 06-May-2026 15:57:24 | wisuda.c@jutal.com | 06-May-2026 17:20:18 | Jumpol Sudjitjul | 14-May-2026 | 17-May-2026 07:37:09 | Sompop Singhatiraj | 18-May-2026 | 25-May-2026 14:33:32 | Pornlert Wanaphattharaphan | 19-May-2026 | 25-May-2026 20:18:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-May-2026 | 25-May-2026 21:19:21 | 25-May-2026 14:33:54 | 0 |  |  | Approver | Locate
AO-001014 | MM-ZTK-1F-ZWP21-STR-CAL-2001 | ZWP21 JACKET COMPUTER MODELING AND LOAD FORMULATION |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 23:35:01 | wisuda.c@jutal.com | 04-Jul-2026 14:38:40 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 10-Jul-2026 14:44:49 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 14-Jul-2026 23:25:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 15-Jul-2026 11:20:23 | 15-Jul-2026 04:54:45 | 0 |  |  | Approver | Locate
AO-002270 | MM-ZTK-1F-ZWP21-STR-CAL-2001 | ZWP21 JACKET COMPUTER MODELING AND LOAD FORMULATION |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 18:38:43 | wisuda.c@jutal.com | 26-Sep-2026 16:29:49 | Jumpol Sudjitjul | 02-Oct-2026 |  | Sompop Singhatiraj | 06-Oct-2026 | 06-Oct-2026 14:23:27 | Pornlert Wanaphattharaphan | 07-Oct-2026 | 10-Oct-2026 00:49:43 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 10-Oct-2026 17:45:53 | 10-Oct-2026 11:21:28 | 0 |  |  | Approver | Locate
AO-000599 | MM-ZTK-1F-ZWP21-STR-CAL-2011 | ZWP21 JACKET IN-PLACE ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 25-May-2026 21:27:36 | wisuda.c@jutal.com | 25-May-2026 22:17:53 | Jumpol Sudjitjul | 04-Jun-2026 | 04-Jun-2026 16:07:21 | Sompop Singhatiraj | 08-Jun-2026 | 12-Jun-2026 13:17:20 | Pornlert Wanaphattharaphan | 09-Jun-2026 | 13-Jun-2026 00:39:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jun-2026 | 13-Jun-2026 07:01:26 | 13-Jun-2026 00:16:16 | 0 |  |  | Approver | Locate
AO-001015 | MM-ZTK-1F-ZWP21-STR-CAL-2011 | ZWP21 JACKET IN-PLACE ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 23:35:38 | wisuda.c@jutal.com | 04-Jul-2026 14:38:58 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 10-Jul-2026 15:32:47 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 11-Jul-2026 09:52:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 12-Jul-2026 11:34:34 | 12-Jul-2026 04:59:18 | 0 |  |  | Approver | Locate
AO-001965 | MM-ZTK-1F-ZWP21-STR-CAL-2011 | ZWP21 JACKET IN-PLACE ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 10:30:06 | wisuda.c@jutal.com | 10-Sep-2026 12:03:30 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 21-Sep-2026 18:08:21 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 22-Sep-2026 19:53:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Sep-2026 | 23-Sep-2026 13:31:49 | 23-Sep-2026 07:04:58 | 0 |  |  | Approver | Locate
AO-000534 | MM-ZTK-1F-ZWP21-STR-CAL-2012 | ZWP21 JACKET DYNAMIC ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 20-May-2026 17:44:53 | wisuda.c@jutal.com | 20-May-2026 18:18:45 | Jumpol Sudjitjul | 28-May-2026 | 04-Jun-2026 15:05:57 | Sompop Singhatiraj | 02-Jun-2026 | 08-Jun-2026 08:39:07 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 10-Jun-2026 21:03:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Jun-2026 | 11-Jun-2026 13:50:09 | 11-Jun-2026 07:29:14 | 0 |  |  | Approver | Locate
AO-000949 | MM-ZTK-1F-ZWP21-STR-CAL-2012 | ZWP21 JACKET DYNAMIC ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 30-Jun-2026 09:23:07 | wisuda.c@jutal.com | 30-Jun-2026 11:27:01 | Jumpol Sudjitjul | 07-Jul-2026 | 06-Jul-2026 13:57:39 | Sompop Singhatiraj | 09-Jul-2026 | 08-Jul-2026 15:55:43 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 10-Jul-2026 00:55:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 10-Jul-2026 08:07:08 | 10-Jul-2026 02:20:26 | 0 |  |  | Approver | Locate
AO-001776 | MM-ZTK-1F-ZWP21-STR-CAL-2012 | ZWP21 JACKET DYNAMIC ANALYSIS REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 31-Aug-2026 09:27:52 | wisuda.c@jutal.com | 31-Aug-2026 11:31:00 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 14-Sep-2026 15:07:10 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 15-Sep-2026 22:31:26 | APPR | Approved | Jumpol Sudjitjul | 11-Sep-2026 | 17-Sep-2026 12:02:36 | 17-Sep-2026 05:53:01 | 0 |  |  | Approver | Locate
AO-000806 | MM-ZTK-1F-ZWP21-STR-CAL-2013 | ZWP21 IN-SERVICE COMBINED TOPSIDES AND JACKET FATIGUE ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Review |  | 15-Jun-2026 22:48:48 | wisuda.c@jutal.com | 16-Jun-2026 10:38:00 | Jumpol Sudjitjul | 23-Jun-2026 | 19-Jun-2026 00:59:39 | Sompop Singhatiraj | 25-Jun-2026 | 29-Jun-2026 15:14:10 | Pornlert Wanaphattharaphan | 26-Jun-2026 | 30-Jun-2026 22:03:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-Jun-2026 | 01-Jul-2026 08:29:11 | 01-Jul-2026 01:40:45 | 0 |  |  | Approver | Locate
AO-001214 | MM-ZTK-1F-ZWP21-STR-CAL-2013 | ZWP21 IN-SERVICE COMBINED TOPSIDES AND JACKET FATIGUE ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 21-Jul-2026 07:51:15 | wisuda.c@jutal.com | 21-Jul-2026 08:10:00 | Jumpol Sudjitjul | 30-Jul-2026 | 14-Aug-2026 13:06:51 | Sompop Singhatiraj | 03-Aug-2026 | 31-Aug-2026 17:22:46 | Pornlert Wanaphattharaphan | 04-Aug-2026 | 01-Sep-2026 22:52:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Aug-2026 | 02-Sep-2026 09:36:43 | 02-Sep-2026 03:21:27 | 0 |  |  | Approver | Locate
AO-002058 | MM-ZTK-1F-ZWP21-STR-CAL-2013 | ZWP21 IN-SERVICE COMBINED TOPSIDES AND JACKET FATIGUE ANALYSIS REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:25:05 | wisuda.c@jutal.com | 15-Sep-2026 15:16:28 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 28-Sep-2026 14:50:53 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 28-Sep-2026 22:04:36 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 29-Sep-2026 11:03:02 | 29-Sep-2026 04:33:35 | 0 |  |  | Approver | Locate
AO-000327 | MM-ZTK-1F-ZWP21-STR-CAL-2014 | ZWP21 JACKET LOADOUT ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 06-May-2026 15:57:55 | wisuda.c@jutal.com | 06-May-2026 17:20:43 | Jumpol Sudjitjul | 14-May-2026 | 25-May-2026 10:25:12 | Sompop Singhatiraj | 18-May-2026 | 04-Jun-2026 13:34:37 | Pornlert Wanaphattharaphan | 19-May-2026 | 05-Jun-2026 23:23:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-May-2026 | 07-Jun-2026 17:33:55 | 07-Jun-2026 11:02:05 | 0 |  |  | Approver | Locate
AO-001088 | MM-ZTK-1F-ZWP21-STR-CAL-2014 | ZWP21 JACKET LOADOUT ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 13-Jul-2026 08:30:59 | wisuda.c@jutal.com | 13-Jul-2026 09:08:38 | Jumpol Sudjitjul | 20-Jul-2026 |  | Sompop Singhatiraj | 22-Jul-2026 | 14-Jul-2026 14:23:55 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 20-Jul-2026 02:48:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 20-Jul-2026 08:53:09 | 20-Jul-2026 02:19:42 | 0 |  |  | Approver | Locate
AO-001897 | MM-ZTK-1F-ZWP21-STR-CAL-2014 | ZWP21 JACKET LOADOUT ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 10:21:11 | wisuda.c@jutal.com | 08-Sep-2026 09:12:58 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 21-Sep-2026 15:54:35 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 22-Sep-2026 19:52:39 | APPR | Approved | Jumpol Sudjitjul | 21-Sep-2026 | 23-Sep-2026 13:32:19 | 23-Sep-2026 07:07:31 | 0 |  |  | Approver | Locate
AO-000390 | MM-ZTK-1F-ZWP21-STR-CAL-2015 | ZWP21 JACKET TRANSPORTATION ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 13-May-2026 15:30:13 | wisuda.c@jutal.com | 13-May-2026 15:49:31 | Jumpol Sudjitjul | 20-May-2026 | 25-May-2026 14:49:27 | Sompop Singhatiraj | 22-May-2026 | 04-Jun-2026 16:28:24 | Pornlert Wanaphattharaphan | 25-May-2026 | 05-Jun-2026 23:46:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-May-2026 | 07-Jun-2026 17:35:46 | 07-Jun-2026 11:41:50 | 0 |  |  | Approver | Locate
AO-001103 | MM-ZTK-1F-ZWP21-STR-CAL-2015 | ZWP21 JACKET TRANSPORTATION ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 14-Jul-2026 12:46:04 | wisuda.c@jutal.com | 14-Jul-2026 13:50:17 | Jumpol Sudjitjul | 21-Jul-2026 | 15-Jul-2026 22:50:46 | Sompop Singhatiraj | 23-Jul-2026 | 13-Aug-2026 11:00:40 | Pornlert Wanaphattharaphan | 24-Jul-2026 | 13-Aug-2026 23:23:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Jul-2026 | 14-Aug-2026 08:28:21 | 14-Aug-2026 02:15:17 | 0 |  |  | Approver | Locate
AO-001898 | MM-ZTK-1F-ZWP21-STR-CAL-2015 | ZWP21 JACKET TRANSPORTATION ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 10:21:52 | wisuda.c@jutal.com | 08-Sep-2026 09:13:27 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 21-Sep-2026 15:16:51 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 22-Sep-2026 19:51:43 | APPR | Approved | Jumpol Sudjitjul | 21-Sep-2026 | 23-Sep-2026 13:33:11 | 23-Sep-2026 07:09:48 | 0 |  |  | Approver | Locate
AO-000701 | MM-ZTK-1F-ZWP21-STR-CAL-2016 | ZWP21 JACKET TRANSPORTATION FATIGUE ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 08:40:26 | wisuda.c@jutal.com | 08-Jun-2026 12:00:03 | Jumpol Sudjitjul | 15-Jun-2026 | 17-Jun-2026 22:54:09 | Sompop Singhatiraj | 17-Jun-2026 | 21-Jun-2026 15:59:05 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 22-Jun-2026 11:48:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 22-Jun-2026 13:02:05 | 22-Jun-2026 07:05:24 | 0 |  |  | Approver | Locate
AO-001257 | MM-ZTK-1F-ZWP21-STR-CAL-2016 | ZWP21 JACKET TRANSPORTATION FATIGUE ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 24-Jul-2026 08:41:30 | wisuda.c@jutal.com | 24-Jul-2026 10:58:15 | Jumpol Sudjitjul | 04-Aug-2026 |  | Sompop Singhatiraj | 06-Aug-2026 | 17-Aug-2026 16:00:05 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 17-Aug-2026 20:49:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Aug-2026 | 18-Aug-2026 08:15:22 | 18-Aug-2026 01:40:22 | 0 |  |  | Approver | Locate
AO-002027 | MM-ZTK-1F-ZWP21-STR-CAL-2016 | ZWP21 JACKET TRANSPORTATION FATIGUE ANALYSIS REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 10:26:55 | wisuda.c@jutal.com | 15-Sep-2026 15:16:49 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 28-Sep-2026 16:20:25 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 28-Sep-2026 22:05:05 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 29-Sep-2026 10:51:49 | 29-Sep-2026 04:46:12 | 0 |  |  | Approver | Locate
AO-001012 | MM-ZTK-1F-ZWP21-STR-CAL-2017 | ZWP21 JACKET BOAT IMPACT ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 23:36:13 | wisuda.c@jutal.com | 04-Jul-2026 14:37:22 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 07-Jul-2026 18:35:15 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 08-Jul-2026 01:18:05 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 16-Jul-2026 | 08-Jul-2026 09:45:28 | 08-Jul-2026 03:24:00 | 0 |  |  | Approver | Locate
AO-002366 | MM-ZTK-1F-ZWP21-STR-CAL-2017 | ZWP21 JACKET BOAT IMPACT ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 10:07:38 | wisuda.c@jutal.com | 05-Oct-2026 10:37:24 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 07-Oct-2026 15:26:58 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 22:49:48 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 11-Oct-2026 10:05:41 | 11-Oct-2026 03:32:20 | 0 |  |  | Approver | Locate
AO-000622 | MM-ZTK-1F-ZWP21-STR-CAL-2018 | ZWP21 JACKET ON-BOTTOM STABILITY ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 14:49:33 | wisuda.c@jutal.com | 29-May-2026 15:14:26 | Jumpol Sudjitjul | 09-Jun-2026 |  | Sompop Singhatiraj | 11-Jun-2026 | 08-Jun-2026 11:55:48 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 10-Jun-2026 21:31:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 11-Jun-2026 13:49:36 | 11-Jun-2026 07:32:56 | 0 |  |  | Approver | Locate
AO-001103 | MM-ZTK-1F-ZWP21-STR-CAL-2018 | ZWP21 JACKET ON-BOTTOM STABILITY ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 14-Jul-2026 12:46:34 | wisuda.c@jutal.com | 14-Jul-2026 13:51:02 | Jumpol Sudjitjul | 21-Jul-2026 | 15-Jul-2026 22:53:20 | Sompop Singhatiraj | 23-Jul-2026 | 13-Aug-2026 16:03:13 | Pornlert Wanaphattharaphan | 24-Jul-2026 | 13-Aug-2026 23:44:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Jul-2026 | 14-Aug-2026 08:30:25 | 14-Aug-2026 02:17:58 | 0 |  |  | Approver | Locate
AO-002270 | MM-ZTK-1F-ZWP21-STR-CAL-2018 | ZWP21 JACKET ON-BOTTOM STABILITY ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 18:17:38 | wisuda.c@jutal.com | 26-Sep-2026 16:29:51 | Jumpol Sudjitjul | 02-Oct-2026 |  | Sompop Singhatiraj | 06-Oct-2026 | 06-Oct-2026 17:25:55 | Pornlert Wanaphattharaphan | 07-Oct-2026 | 10-Oct-2026 00:50:21 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 10-Oct-2026 17:46:49 | 10-Oct-2026 11:44:14 | 0 |  |  | Approver | Locate
AO-000857 | MM-ZTK-1F-ZWP21-STR-CAL-2019 | ZWP21 JACKET MISCELLANEOUS DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 22:39:22 | wisuda.c@jutal.com | 22-Jun-2026 13:56:49 | Jumpol Sudjitjul | 29-Jun-2026 |  | Sompop Singhatiraj | 01-Jul-2026 | 08-Jul-2026 17:36:37 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 09-Jul-2026 23:33:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 10-Jul-2026 08:02:37 | 10-Jul-2026 02:18:51 | 0 |  |  | Approver | Locate
AO-001042 | MM-ZTK-1F-ZWP21-STR-CAL-2020 | ZWP21 JACKET LEVELLING ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 09-Jul-2026 15:36:04 | wisuda.c@jutal.com | 09-Jul-2026 17:14:51 | Jumpol Sudjitjul | 17-Jul-2026 |  | Sompop Singhatiraj | 21-Jul-2026 | 10-Jul-2026 10:08:01 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 14-Jul-2026 23:32:12 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 23-Jul-2026 | 15-Jul-2026 11:16:24 | 15-Jul-2026 05:03:33 | 0 |  |  | Approver | Locate
AO-002028 | MM-ZTK-1F-ZWP21-STR-CAL-2020 | ZWP21 JACKET LEVELLING ANALYSIS REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 10:27:49 | wisuda.c@jutal.com | 15-Sep-2026 15:17:26 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 |  | Pornlert Wanaphattharaphan | 25-Sep-2026 |  | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 26-Sep-2026 14:23:51 | 26-Sep-2026 08:02:06 | 0 |  |  | Approver | Locate
AO-001016 | MM-ZTK-1F-ZWP21-STR-CAL-2021 | ZWP21 JACKET PILE HANDLING AND STICK-UP ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 23:36:46 | wisuda.c@jutal.com | 04-Jul-2026 14:36:00 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 07-Jul-2026 14:16:07 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 08-Jul-2026 01:17:15 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 16-Jul-2026 | 08-Jul-2026 09:46:32 | 08-Jul-2026 03:25:24 | 0 |  |  | Approver | Locate
AO-002298 | MM-ZTK-1F-ZWP21-STR-CAL-2021 | ZWP21 JACKET PILE HANDLING AND STICK-UP ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 08:35:55 | wisuda.c@jutal.com | 28-Sep-2026 09:53:42 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 07-Oct-2026 09:13:37 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 10-Oct-2026 01:24:02 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 10-Oct-2026 17:47:27 | 10-Oct-2026 11:45:33 | 0 |  |  | Approver | Locate
AO-000515 | MM-ZTK-1F-ZWP21-STR-CAL-2022 | ZWP21 PILE DRIVEABILITY AND PILE FATIGUE ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 16:15:08 | wisuda.c@jutal.com | 19-May-2026 16:37:58 | Jumpol Sudjitjul | 26-May-2026 | 04-Jun-2026 10:58:55 | Sompop Singhatiraj | 28-May-2026 | 07-Jun-2026 14:52:18 | Pornlert Wanaphattharaphan | 29-May-2026 | 07-Jun-2026 22:48:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 08-Jun-2026 09:06:04 | 08-Jun-2026 02:45:58 | 0 |  |  | Approver | Locate
AO-001139 | MM-ZTK-1F-ZWP21-STR-CAL-2022 | ZWP21 PILE DRIVEABILITY AND PILE FATIGUE ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 17:52:31 | wisuda.c@jutal.com | 16-Jul-2026 20:34:17 | Jumpol Sudjitjul | 24-Jul-2026 | 07-Aug-2026 15:25:06 | Sompop Singhatiraj | 30-Jul-2026 | 14-Aug-2026 12:49:05 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 15-Aug-2026 06:36:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 15-Aug-2026 14:46:28 | 15-Aug-2026 08:41:17 | 0 |  |  | Approver | Locate
AO-002311 | MM-ZTK-1F-ZWP21-STR-CAL-2022 | ZWP21 PILE DRIVEABILITY AND PILE FATIGUE ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 30-Sep-2026 09:24:30 | wisuda.c@jutal.com | 30-Sep-2026 16:05:24 | Jumpol Sudjitjul | 07-Oct-2026 |  | Sompop Singhatiraj | 09-Oct-2026 | 07-Oct-2026 12:20:48 | Pornlert Wanaphattharaphan | 12-Oct-2026 | 10-Oct-2026 01:43:05 | APPR | Approved | Jumpol Sudjitjul | 14-Oct-2026 | 10-Oct-2026 17:47:49 | 10-Oct-2026 11:46:52 | 0 |  |  | Approver | Locate
AO-001392 | MM-ZTK-1F-ZWP21-STR-CAL-2023 | ZWP21 JACKET PILE CLUSTER FEA REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 10:57:04 | wisuda.c@jutal.com | 03-Aug-2026 13:23:35 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 12-Aug-2026 16:20:01 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 12-Aug-2026 21:10:57 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 17-Aug-2026 | 13-Aug-2026 11:41:43 | 13-Aug-2026 05:11:10 | 0 |  |  | Approver | Locate
AO-000696 | MM-ZTK-1F-ZWP21-STR-CAL-2024 | ZWP21 PILE GROUP EFFECT ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 07-Jun-2026 17:49:01 | wisuda.c@jutal.com | 07-Jun-2026 18:19:48 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 18-Jun-2026 13:10:40 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 18-Jun-2026 19:56:28 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 19-Jun-2026 | 19-Jun-2026 08:57:21 | 19-Jun-2026 02:43:00 | 0 |  |  | Approver | Locate
AO-001456 | MM-ZTK-1F-ZWP21-STR-CAL-2025 | ZWP21 MUDMAT FEA ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 07-Aug-2026 17:31:21 | wisuda.c@jutal.com | 07-Aug-2026 17:45:50 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 12-Aug-2026 14:43:08 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 12-Aug-2026 21:11:26 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 24-Aug-2026 | 13-Aug-2026 11:43:31 | 13-Aug-2026 05:41:42 | 0 |  |  | Approver | Locate
AO-002486 | MM-ZTK-1F-ZWP21-STR-CAL-2026 | ZWP21 JACKET PILE TRANSPORTATION FATIGUE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | In Review | IFR | Issued for Review |  | 12-Oct-2026 11:48:33 | wisuda.c@jutal.com | 12-Oct-2026 17:31:40 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 |  | Pornlert Wanaphattharaphan | 27-Oct-2026 |  |  |  |  | 28-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000628 | MM-ZTK-1F-ZWP21-STR-CAL-2031 | ZWP21 TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT(EXTREME LEVEL EARTHQUAKE - ELE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 18:10:13 | wisuda.c@jutal.com | 29-May-2026 18:49:02 | Jumpol Sudjitjul | 10-Jun-2026 | 10-Jun-2026 07:48:39 | Sompop Singhatiraj | 12-Jun-2026 | 19-Jun-2026 19:32:49 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 19-Jun-2026 21:28:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 21-Jun-2026 21:30:19 | 22-Jun-2026 00:32:35 | 0 |  |  | Approver | Locate
AO-001103 | MM-ZTK-1F-ZWP21-STR-CAL-2031 | ZWP21 TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT(EXTREME LEVEL EARTHQUAKE - ELE) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 14-Jul-2026 12:47:18 | wisuda.c@jutal.com | 14-Jul-2026 13:51:39 | Jumpol Sudjitjul | 21-Jul-2026 |  | Sompop Singhatiraj | 23-Jul-2026 | 12-Aug-2026 18:50:09 | Pornlert Wanaphattharaphan | 24-Jul-2026 | 12-Aug-2026 19:29:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Jul-2026 | 13-Aug-2026 11:43:53 | 13-Aug-2026 05:32:25 | 0 |  |  | Approver | Locate
AO-001687 | MM-ZTK-1F-ZWP21-STR-CAL-2031 | ZWP21 TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT(EXTREME LEVEL EARTHQUAKE - ELE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 09:50:06 | wisuda.c@jutal.com | 25-Aug-2026 09:49:47 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 02-Sep-2026 16:02:59 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:50:40 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:02:15 | 07-Sep-2026 12:17:04 | 0 |  |  | Approver | Locate
AO-000630 | MM-ZTK-1F-ZWP21-STR-CAL-2032 | ZWP21 TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (ABNORMAL LEVEL EARTHQUAKE-ALE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 18:53:27 | wisuda.c@jutal.com | 29-May-2026 19:01:37 | Jumpol Sudjitjul | 10-Jun-2026 | 12-Jun-2026 10:54:51 | Sompop Singhatiraj | 12-Jun-2026 | 21-Jun-2026 14:20:17 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 22-Jun-2026 11:45:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 22-Jun-2026 13:03:12 | 22-Jun-2026 07:07:09 | 0 |  |  | Approver | Locate
AO-001103 | MM-ZTK-1F-ZWP21-STR-CAL-2032 | ZWP21 TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (ABNORMAL LEVEL EARTHQUAKE-ALE) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 14-Jul-2026 12:48:04 | wisuda.c@jutal.com | 14-Jul-2026 13:52:01 | Jumpol Sudjitjul | 21-Jul-2026 |  | Sompop Singhatiraj | 23-Jul-2026 | 13-Aug-2026 18:38:20 | Pornlert Wanaphattharaphan | 24-Jul-2026 | 13-Aug-2026 23:44:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Jul-2026 | 14-Aug-2026 08:30:54 | 14-Aug-2026 02:34:14 | 0 |  |  | Approver | Locate
AO-001769 | MM-ZTK-1F-ZWP21-STR-CAL-2032 | ZWP21 TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (ABNORMAL LEVEL EARTHQUAKE-ALE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 29-Aug-2026 14:04:42 | wisuda.c@jutal.com | 29-Aug-2026 14:16:57 | Jumpol Sudjitjul | 04-Sep-2026 |  | Sompop Singhatiraj | 08-Sep-2026 | 02-Sep-2026 18:21:59 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 04-Sep-2026 23:53:12 | APPR | Approved | Jumpol Sudjitjul | 10-Sep-2026 | 05-Sep-2026 18:05:18 | 05-Sep-2026 11:45:29 | 0 |  |  | Approver | Locate
AO-000697 | MM-ZTK-1F-ZWP21-STR-CAL-2041 | ZWP21 JACKET PUSHOVER ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 07-Jun-2026 17:49:36 | wisuda.c@jutal.com | 07-Jun-2026 18:20:51 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 19-Jun-2026 15:57:06 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 21:18:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 22-Jun-2026 13:04:00 | 22-Jun-2026 07:11:36 | 0 |  |  | Approver | Locate
AO-001187 | MM-ZTK-1F-ZWP21-STR-CAL-2041 | ZWP21 JACKET PUSHOVER ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 08:45:58 | wisuda.c@jutal.com | 20-Jul-2026 14:30:00 | Jumpol Sudjitjul | 27-Jul-2026 |  | Sompop Singhatiraj | 31-Jul-2026 | 13-Aug-2026 19:23:28 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 13-Aug-2026 23:55:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 14-Aug-2026 08:33:46 | 14-Aug-2026 02:25:05 | 0 |  |  | Approver | Locate
AO-002299 | MM-ZTK-1F-ZWP21-STR-CAL-2041 | ZWP21 JACKET PUSHOVER ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 08:36:28 | wisuda.c@jutal.com | 28-Sep-2026 09:53:40 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 07-Oct-2026 16:00:19 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 10-Oct-2026 01:28:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 10-Oct-2026 17:34:23 | 10-Oct-2026 10:56:38 | 0 |  |  | Approver | Locate
AO-000328 | MM-ZTK-1F-ZWP21-STR-CAL-2050 | ZWP21 JACKET CONSTRUCTION MODEL REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 06-May-2026 16:34:18 | wisuda.c@jutal.com | 06-May-2026 17:22:01 | Jumpol Sudjitjul | 14-May-2026 | 25-May-2026 10:34:42 | Sompop Singhatiraj | 18-May-2026 | 25-May-2026 16:54:25 | Pornlert Wanaphattharaphan | 19-May-2026 | 25-May-2026 20:26:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-May-2026 | 25-May-2026 21:16:34 | 25-May-2026 14:47:23 | 0 |  |  | Approver | Locate
AO-001103 | MM-ZTK-1F-ZWP21-STR-CAL-2050 | ZWP21 JACKET CONSTRUCTION MODEL REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 14-Jul-2026 12:48:36 | wisuda.c@jutal.com | 14-Jul-2026 13:52:21 | Jumpol Sudjitjul | 21-Jul-2026 | 15-Jul-2026 22:54:38 | Sompop Singhatiraj | 23-Jul-2026 | 13-Aug-2026 08:07:52 | Pornlert Wanaphattharaphan | 24-Jul-2026 | 13-Aug-2026 23:20:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Jul-2026 | 14-Aug-2026 08:29:23 | 14-Aug-2026 02:32:42 | 0 |  |  | Approver | Locate
AO-002271 | MM-ZTK-1F-ZWP21-STR-CAL-2050 | ZWP21 JACKET CONSTRUCTION MODEL REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 18:39:18 | wisuda.c@jutal.com | 26-Sep-2026 16:29:50 | Jumpol Sudjitjul | 02-Oct-2026 |  | Sompop Singhatiraj | 06-Oct-2026 | 06-Oct-2026 14:23:13 | Pornlert Wanaphattharaphan | 07-Oct-2026 | 10-Oct-2026 00:47:57 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 10-Oct-2026 17:35:27 | 10-Oct-2026 11:14:17 | 0 |  |  | Approver | Locate
AO-002259 | MM-ZTK-1F-ZWP21-STR-CAL-2801 | ZWP21 RISER CLAMP DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | In Review | IFR | Issued for Review |  | 25-Sep-2026 14:11:23 | wisuda.c@jutal.com | 25-Sep-2026 15:00:42 | Jumpol Sudjitjul | 02-Oct-2026 |  | Sompop Singhatiraj | 06-Oct-2026 |  | Pornlert Wanaphattharaphan | 07-Oct-2026 |  |  |  |  | 08-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000197 | MM-ZTK-1F-ZWP21-STR-DWG-2100 | ZWP21 JACKET - VERTICAL FRAMING ROW 'A' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:35:49 | wisuda.c@jutal.com | 22-Apr-2026 10:47:35 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 09:29:56 | Pornlert Wanaphattharaphan | 06-May-2026 | 24-Apr-2026 00:39:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 08:51:14 | 24-Apr-2026 02:34:01 | 0 |  |  | Approver | Locate
AO-000895 | MM-ZTK-1F-ZWP21-STR-DWG-2100 | ZWP21 JACKET - VERTICAL FRAMING ROW 'A' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 23:09:35 | wisuda.c@jutal.com | 26-Jun-2026 08:29:01 | Jumpol Sudjitjul | 03-Jul-2026 |  | Sompop Singhatiraj | 07-Jul-2026 | 26-Jun-2026 17:46:53 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 29-Jun-2026 01:25:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 30-Jun-2026 09:32:26 | 30-Jun-2026 03:45:56 | 0 |  |  | Approver | Locate
AO-001403 | MM-ZTK-1F-ZWP21-STR-DWG-2100 | ZWP21 JACKET - VERTICAL FRAMING ROW 'A' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 16:45:41 | wisuda.c@jutal.com | 04-Aug-2026 08:08:15 | Jumpol Sudjitjul | 11-Aug-2026 |  | Sompop Singhatiraj | 14-Aug-2026 | 06-Aug-2026 16:06:46 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 10-Aug-2026 00:52:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 17:46:19 | 10-Aug-2026 11:12:21 | 0 |  |  | Approver | Locate
AO-000193 | MM-ZTK-1F-ZWP21-STR-DWG-2101 | ZWP21 JACKET - VERTICAL FRAMING ROW 'B' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 14:02:45 | wisuda.c@jutal.com | 21-Apr-2026 14:18:56 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 11:18:51 | Pornlert Wanaphattharaphan | 05-May-2026 | 24-Apr-2026 00:03:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 08:53:15 | 24-Apr-2026 02:55:40 | 0 |  |  | Approver | Locate
AO-000895 | MM-ZTK-1F-ZWP21-STR-DWG-2101 | ZWP21 JACKET - VERTICAL FRAMING ROW 'B' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 23:10:00 | wisuda.c@jutal.com | 26-Jun-2026 08:29:01 | Jumpol Sudjitjul | 03-Jul-2026 |  | Sompop Singhatiraj | 07-Jul-2026 | 26-Jun-2026 17:48:09 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 29-Jun-2026 01:26:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 30-Jun-2026 09:29:44 | 30-Jun-2026 03:49:35 | 0 |  |  | Approver | Locate
AO-001403 | MM-ZTK-1F-ZWP21-STR-DWG-2101 | ZWP21 JACKET - VERTICAL FRAMING ROW 'B' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 16:46:07 | wisuda.c@jutal.com | 04-Aug-2026 08:08:20 | Jumpol Sudjitjul | 11-Aug-2026 |  | Sompop Singhatiraj | 14-Aug-2026 | 06-Aug-2026 16:06:39 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 10-Aug-2026 00:52:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 17:45:54 | 10-Aug-2026 11:11:05 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP21-STR-DWG-2102 | ZWP21 JACKET - VERTICAL FRAMING ROW '1' & '1.1' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:32:21 | wisuda.c@jutal.com | 21-Apr-2026 14:19:23 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 24-Apr-2026 09:08:38 | Pornlert Wanaphattharaphan | 05-May-2026 | 24-Apr-2026 11:59:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 14:21:53 | 24-Apr-2026 07:32:39 | 0 |  |  | Approver | Locate
AO-000895 | MM-ZTK-1F-ZWP21-STR-DWG-2102 | ZWP21 JACKET - VERTICAL FRAMING ROW '1' & '1.1' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 23:10:27 | wisuda.c@jutal.com | 26-Jun-2026 08:29:01 | Jumpol Sudjitjul | 03-Jul-2026 |  | Sompop Singhatiraj | 07-Jul-2026 | 26-Jun-2026 17:48:44 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 29-Jun-2026 01:26:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 30-Jun-2026 09:27:52 | 30-Jun-2026 03:44:38 | 0 |  |  | Approver | Locate
AO-001403 | MM-ZTK-1F-ZWP21-STR-DWG-2102 | ZWP21 JACKET - VERTICAL FRAMING ROW '1' & '1.1' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 16:46:35 | wisuda.c@jutal.com | 04-Aug-2026 08:08:20 | Jumpol Sudjitjul | 11-Aug-2026 |  | Sompop Singhatiraj | 14-Aug-2026 | 06-Aug-2026 16:06:52 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 10-Aug-2026 00:53:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 17:45:28 | 10-Aug-2026 11:08:30 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP21-STR-DWG-2103 | ZWP21 JACKET - VERTICAL FRAMING ROW '2' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:32:46 | wisuda.c@jutal.com | 21-Apr-2026 14:19:49 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 12:23:52 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 23:54:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 08:55:44 | 24-Apr-2026 02:36:26 | 0 |  |  | Approver | Locate
AO-000895 | MM-ZTK-1F-ZWP21-STR-DWG-2103 | ZWP21 JACKET - VERTICAL FRAMING ROW '2' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 23:10:52 | wisuda.c@jutal.com | 26-Jun-2026 08:29:01 | Jumpol Sudjitjul | 03-Jul-2026 |  | Sompop Singhatiraj | 07-Jul-2026 | 26-Jun-2026 17:50:56 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 29-Jun-2026 01:26:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 30-Jun-2026 09:17:25 | 30-Jun-2026 03:43:18 | 0 |  |  | Approver | Locate
AO-001403 | MM-ZTK-1F-ZWP21-STR-DWG-2103 | ZWP21 JACKET - VERTICAL FRAMING ROW '2' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 16:46:59 | wisuda.c@jutal.com | 04-Aug-2026 08:08:17 | Jumpol Sudjitjul | 11-Aug-2026 |  | Sompop Singhatiraj | 14-Aug-2026 | 06-Aug-2026 16:08:40 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 10-Aug-2026 00:53:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 17:45:01 | 10-Aug-2026 11:07:12 | 0 |  |  | Approver | Locate
AO-000190 | MM-ZTK-1F-ZWP21-STR-DWG-2104 | ZWP21 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'AA' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 14:03:12 | wisuda.c@jutal.com | 21-Apr-2026 14:20:11 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 12:24:59 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 23:52:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 08:58:04 | 24-Apr-2026 02:56:53 | 0 |  |  | Approver | Locate
AO-000895 | MM-ZTK-1F-ZWP21-STR-DWG-2104 | ZWP21 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'AA' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 23:11:18 | wisuda.c@jutal.com | 26-Jun-2026 08:29:01 | Jumpol Sudjitjul | 03-Jul-2026 |  | Sompop Singhatiraj | 07-Jul-2026 | 26-Jun-2026 17:51:10 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 29-Jun-2026 01:27:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 30-Jun-2026 09:15:50 | 30-Jun-2026 03:39:08 | 0 |  |  | Approver | Locate
AO-001403 | MM-ZTK-1F-ZWP21-STR-DWG-2104 | ZWP21 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'AA' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 16:47:27 | wisuda.c@jutal.com | 04-Aug-2026 08:08:17 | Jumpol Sudjitjul | 11-Aug-2026 |  | Sompop Singhatiraj | 14-Aug-2026 | 06-Aug-2026 16:08:52 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 10-Aug-2026 00:54:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 17:44:29 | 10-Aug-2026 11:05:51 | 0 |  |  | Approver | Locate
AO-000191 | MM-ZTK-1F-ZWP21-STR-DWG-2105 | ZWP21 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'BB' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 14:03:40 | wisuda.c@jutal.com | 21-Apr-2026 14:24:09 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 12:27:16 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 23:50:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 08:59:27 | 24-Apr-2026 02:58:07 | 0 |  |  | Approver | Locate
AO-000895 | MM-ZTK-1F-ZWP21-STR-DWG-2105 | ZWP21 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'BB' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 23:11:43 | wisuda.c@jutal.com | 26-Jun-2026 08:29:02 | Jumpol Sudjitjul | 03-Jul-2026 |  | Sompop Singhatiraj | 07-Jul-2026 | 26-Jun-2026 17:52:09 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 29-Jun-2026 01:27:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 30-Jun-2026 09:14:42 | 30-Jun-2026 03:35:09 | 0 |  |  | Approver | Locate
AO-001403 | MM-ZTK-1F-ZWP21-STR-DWG-2105 | ZWP21 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'BB' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 16:47:55 | wisuda.c@jutal.com | 04-Aug-2026 08:08:14 | Jumpol Sudjitjul | 11-Aug-2026 |  | Sompop Singhatiraj | 14-Aug-2026 | 06-Aug-2026 16:08:02 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 10-Aug-2026 00:57:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 17:44:01 | 10-Aug-2026 11:23:06 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP21-STR-DWG-2110 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(+) 8000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:33:16 | wisuda.c@jutal.com | 21-Apr-2026 14:24:32 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 13:51:07 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 22:52:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 09:00:35 | 24-Apr-2026 02:38:50 | 0 |  |  | Approver | Locate
AO-000895 | MM-ZTK-1F-ZWP21-STR-DWG-2110 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(+) 8000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 23:12:08 | wisuda.c@jutal.com | 26-Jun-2026 08:29:01 | Jumpol Sudjitjul | 03-Jul-2026 |  | Sompop Singhatiraj | 07-Jul-2026 | 26-Jun-2026 18:22:51 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 29-Jun-2026 01:28:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 30-Jun-2026 09:14:05 | 30-Jun-2026 03:33:45 | 0 |  |  | Approver | Locate
AO-001403 | MM-ZTK-1F-ZWP21-STR-DWG-2110 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(+) 8000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 16:48:20 | wisuda.c@jutal.com | 04-Aug-2026 08:18:24 | Jumpol Sudjitjul | 11-Aug-2026 |  | Sompop Singhatiraj | 14-Aug-2026 | 07-Aug-2026 10:16:58 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 10-Aug-2026 00:58:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 14:08:20 | 10-Aug-2026 08:28:35 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP21-STR-DWG-2111 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 3000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:33:49 | wisuda.c@jutal.com | 21-Apr-2026 14:24:45 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 13:53:45 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 23:05:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 09:01:43 | 24-Apr-2026 02:40:02 | 0 |  |  | Approver | Locate
AO-000895 | MM-ZTK-1F-ZWP21-STR-DWG-2111 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 3000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 23:12:32 | wisuda.c@jutal.com | 26-Jun-2026 08:29:02 | Jumpol Sudjitjul | 03-Jul-2026 |  | Sompop Singhatiraj | 07-Jul-2026 | 26-Jun-2026 18:23:00 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 29-Jun-2026 01:28:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 30-Jun-2026 09:12:43 | 30-Jun-2026 03:36:31 | 0 |  |  | Approver | Locate
AO-001403 | MM-ZTK-1F-ZWP21-STR-DWG-2111 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 3000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 16:48:46 | wisuda.c@jutal.com | 04-Aug-2026 08:18:29 | Jumpol Sudjitjul | 11-Aug-2026 |  | Sompop Singhatiraj | 14-Aug-2026 | 07-Aug-2026 10:17:46 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 10-Aug-2026 00:58:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 17:43:32 | 10-Aug-2026 11:21:49 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP21-STR-DWG-2112 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 14000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:34:14 | wisuda.c@jutal.com | 21-Apr-2026 14:24:58 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 14:43:55 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 22:32:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 09:03:26 | 24-Apr-2026 02:41:14 | 0 |  |  | Approver | Locate
AO-000895 | MM-ZTK-1F-ZWP21-STR-DWG-2112 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 14000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 23:13:00 | wisuda.c@jutal.com | 26-Jun-2026 08:32:41 | Jumpol Sudjitjul | 03-Jul-2026 |  | Sompop Singhatiraj | 07-Jul-2026 | 26-Jun-2026 18:26:35 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 29-Jun-2026 01:29:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 30-Jun-2026 09:11:51 | 30-Jun-2026 03:32:19 | 0 |  |  | Approver | Locate
AO-001403 | MM-ZTK-1F-ZWP21-STR-DWG-2112 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 14000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 16:49:13 | wisuda.c@jutal.com | 04-Aug-2026 08:18:25 | Jumpol Sudjitjul | 11-Aug-2026 |  | Sompop Singhatiraj | 14-Aug-2026 | 07-Aug-2026 10:17:56 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 10-Aug-2026 01:14:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 14:09:14 | 10-Aug-2026 08:29:55 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP21-STR-DWG-2113 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 26000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:34:39 | wisuda.c@jutal.com | 21-Apr-2026 14:29:23 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 14:42:51 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 22:34:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 08:55:40 | 24-Apr-2026 02:35:12 | 0 |  |  | Approver | Locate
AO-000895 | MM-ZTK-1F-ZWP21-STR-DWG-2113 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 26000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 23:13:23 | wisuda.c@jutal.com | 26-Jun-2026 08:32:39 | Jumpol Sudjitjul | 03-Jul-2026 |  | Sompop Singhatiraj | 07-Jul-2026 | 26-Jun-2026 18:27:04 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 29-Jun-2026 01:29:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 30-Jun-2026 09:11:19 | 30-Jun-2026 03:02:14 | 0 |  |  | Approver | Locate
AO-001403 | MM-ZTK-1F-ZWP21-STR-DWG-2113 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 26000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 16:49:46 | wisuda.c@jutal.com | 04-Aug-2026 08:18:28 | Jumpol Sudjitjul | 11-Aug-2026 |  | Sompop Singhatiraj | 14-Aug-2026 | 07-Aug-2026 10:18:05 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 10-Aug-2026 01:15:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 14:09:49 | 10-Aug-2026 08:31:17 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP21-STR-DWG-2114 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 38000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:35:05 | wisuda.c@jutal.com | 21-Apr-2026 14:29:50 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 14:44:18 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 22:30:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 09:04:31 | 24-Apr-2026 02:42:25 | 0 |  |  | Approver | Locate
AO-000895 | MM-ZTK-1F-ZWP21-STR-DWG-2114 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 38000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 23:13:48 | wisuda.c@jutal.com | 26-Jun-2026 08:32:40 | Jumpol Sudjitjul | 03-Jul-2026 |  | Sompop Singhatiraj | 07-Jul-2026 | 26-Jun-2026 18:25:52 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 29-Jun-2026 01:29:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 30-Jun-2026 09:10:31 | 30-Jun-2026 03:00:52 | 0 |  |  | Approver | Locate
AO-001403 | MM-ZTK-1F-ZWP21-STR-DWG-2114 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 38000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 16:50:16 | wisuda.c@jutal.com | 04-Aug-2026 08:18:24 | Jumpol Sudjitjul | 11-Aug-2026 |  | Sompop Singhatiraj | 14-Aug-2026 | 07-Aug-2026 10:19:55 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 10-Aug-2026 01:16:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 17:43:06 | 10-Aug-2026 11:20:31 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP21-STR-DWG-2115 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 52000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:35:37 | wisuda.c@jutal.com | 21-Apr-2026 14:30:03 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 15:36:08 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 19:53:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 09:05:46 | 24-Apr-2026 02:43:39 | 0 |  |  | Approver | Locate
AO-000895 | MM-ZTK-1F-ZWP21-STR-DWG-2115 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 52000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 23:14:12 | wisuda.c@jutal.com | 26-Jun-2026 08:32:42 | Jumpol Sudjitjul | 03-Jul-2026 |  | Sompop Singhatiraj | 07-Jul-2026 | 26-Jun-2026 18:25:07 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 29-Jun-2026 01:28:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 30-Jun-2026 09:09:33 | 30-Jun-2026 02:58:35 | 0 |  |  | Approver | Locate
AO-001403 | MM-ZTK-1F-ZWP21-STR-DWG-2115 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 52000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 16:50:48 | wisuda.c@jutal.com | 04-Aug-2026 08:18:26 | Jumpol Sudjitjul | 11-Aug-2026 |  | Sompop Singhatiraj | 14-Aug-2026 | 07-Aug-2026 10:20:05 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 10-Aug-2026 01:19:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 14:05:36 | 10-Aug-2026 08:27:11 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP21-STR-DWG-2116 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 66000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:36:07 | wisuda.c@jutal.com | 21-Apr-2026 14:30:22 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 15:36:53 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 19:51:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 08:58:44 | 24-Apr-2026 02:37:40 | 0 |  |  | Approver | Locate
AO-000895 | MM-ZTK-1F-ZWP21-STR-DWG-2116 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 66000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 23:14:36 | wisuda.c@jutal.com | 26-Jun-2026 08:32:40 | Jumpol Sudjitjul | 03-Jul-2026 |  | Sompop Singhatiraj | 07-Jul-2026 | 26-Jun-2026 18:28:17 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 29-Jun-2026 01:30:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 30-Jun-2026 09:05:43 | 30-Jun-2026 02:37:42 | 0 |  |  | Approver | Locate
AO-001403 | MM-ZTK-1F-ZWP21-STR-DWG-2116 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 66000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 16:51:21 | wisuda.c@jutal.com | 04-Aug-2026 08:18:26 | Jumpol Sudjitjul | 11-Aug-2026 |  | Sompop Singhatiraj | 14-Aug-2026 | 07-Aug-2026 10:20:08 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 10-Aug-2026 01:19:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 17:42:46 | 10-Aug-2026 11:19:10 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP21-STR-DWG-2117 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 79500 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:36:36 | wisuda.c@jutal.com | 21-Apr-2026 14:32:10 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 15:38:12 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 19:48:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 09:07:07 | 24-Apr-2026 02:44:53 | 0 |  |  | Approver | Locate
AO-000895 | MM-ZTK-1F-ZWP21-STR-DWG-2117 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 79500 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 23:15:00 | wisuda.c@jutal.com | 26-Jun-2026 08:32:46 | Jumpol Sudjitjul | 03-Jul-2026 |  | Sompop Singhatiraj | 07-Jul-2026 | 26-Jun-2026 18:28:25 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 29-Jun-2026 01:30:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 30-Jun-2026 09:08:06 | 30-Jun-2026 02:57:12 | 0 |  |  | Approver | Locate
AO-001403 | MM-ZTK-1F-ZWP21-STR-DWG-2117 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 79500 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 16:51:55 | wisuda.c@jutal.com | 04-Aug-2026 08:18:28 | Jumpol Sudjitjul | 11-Aug-2026 |  | Sompop Singhatiraj | 14-Aug-2026 | 07-Aug-2026 10:20:18 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 10-Aug-2026 01:20:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 17:42:01 | 10-Aug-2026 11:17:51 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP21-STR-DWG-2118 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 93000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:37:01 | wisuda.c@jutal.com | 21-Apr-2026 14:32:23 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 15:39:20 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 19:42:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 09:08:03 | 24-Apr-2026 02:46:04 | 0 |  |  | Approver | Locate
AO-000895 | MM-ZTK-1F-ZWP21-STR-DWG-2118 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 93000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 23:15:25 | wisuda.c@jutal.com | 26-Jun-2026 08:32:40 | Jumpol Sudjitjul | 03-Jul-2026 |  | Sompop Singhatiraj | 07-Jul-2026 | 26-Jun-2026 18:28:36 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 29-Jun-2026 01:31:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 30-Jun-2026 09:07:18 | 30-Jun-2026 02:55:00 | 0 |  |  | Approver | Locate
AO-001403 | MM-ZTK-1F-ZWP21-STR-DWG-2118 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 93000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 16:52:33 | wisuda.c@jutal.com | 04-Aug-2026 08:18:34 | Jumpol Sudjitjul | 11-Aug-2026 |  | Sompop Singhatiraj | 14-Aug-2026 | 07-Aug-2026 10:22:16 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 10-Aug-2026 01:21:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 14:15:36 | 10-Aug-2026 08:38:11 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP21-STR-DWG-2119 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 107000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:37:30 | wisuda.c@jutal.com | 21-Apr-2026 14:32:41 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 15:39:04 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 19:44:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 09:06:39 | 24-Apr-2026 03:01:48 | 0 |  |  | Approver | Locate
AO-000895 | MM-ZTK-1F-ZWP21-STR-DWG-2119 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 107000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 23:15:49 | wisuda.c@jutal.com | 26-Jun-2026 08:32:38 | Jumpol Sudjitjul | 03-Jul-2026 |  | Sompop Singhatiraj | 07-Jul-2026 | 26-Jun-2026 18:30:04 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 29-Jun-2026 01:31:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 30-Jun-2026 09:06:35 | 30-Jun-2026 02:40:27 | 0 |  |  | Approver | Locate
AO-001403 | MM-ZTK-1F-ZWP21-STR-DWG-2119 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 107000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 16:53:08 | wisuda.c@jutal.com | 04-Aug-2026 08:18:25 | Jumpol Sudjitjul | 11-Aug-2026 |  | Sompop Singhatiraj | 14-Aug-2026 | 07-Aug-2026 10:22:22 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 10-Aug-2026 01:22:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 14:14:30 | 10-Aug-2026 08:36:52 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP21-STR-DWG-2120 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 121000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:37:56 | wisuda.c@jutal.com | 21-Apr-2026 14:32:56 | Jumpol Sudjitjul | 28-Apr-2026 | 24-Apr-2026 11:29:05 | Sompop Singhatiraj | 30-Apr-2026 | 24-Apr-2026 11:49:58 | Pornlert Wanaphattharaphan | 05-May-2026 | 29-Apr-2026 22:52:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 30-Apr-2026 08:17:53 | 30-Apr-2026 01:52:37 | 0 |  |  | Approver | Locate
AO-000895 | MM-ZTK-1F-ZWP21-STR-DWG-2120 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 121000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 23:16:14 | wisuda.c@jutal.com | 26-Jun-2026 08:32:43 | Jumpol Sudjitjul | 03-Jul-2026 |  | Sompop Singhatiraj | 07-Jul-2026 | 26-Jun-2026 18:30:14 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 29-Jun-2026 01:31:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 30-Jun-2026 09:00:00 | 30-Jun-2026 02:30:11 | 0 |  |  | Approver | Locate
AO-001403 | MM-ZTK-1F-ZWP21-STR-DWG-2120 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 121000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 16:53:40 | wisuda.c@jutal.com | 04-Aug-2026 08:18:32 | Jumpol Sudjitjul | 11-Aug-2026 |  | Sompop Singhatiraj | 14-Aug-2026 | 07-Aug-2026 10:22:29 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 10-Aug-2026 01:22:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 14:13:52 | 10-Aug-2026 08:35:29 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP21-STR-DWG-2121 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 135000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:38:20 | wisuda.c@jutal.com | 21-Apr-2026 14:34:46 | Jumpol Sudjitjul | 28-Apr-2026 | 24-Apr-2026 11:29:56 | Sompop Singhatiraj | 30-Apr-2026 | 24-Apr-2026 17:37:19 | Pornlert Wanaphattharaphan | 05-May-2026 | 29-Apr-2026 22:56:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 30-Apr-2026 08:41:16 | 30-Apr-2026 01:53:50 | 0 |  |  | Approver | Locate
AO-000895 | MM-ZTK-1F-ZWP21-STR-DWG-2121 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 135000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 23:16:40 | wisuda.c@jutal.com | 26-Jun-2026 08:32:35 | Jumpol Sudjitjul | 03-Jul-2026 |  | Sompop Singhatiraj | 07-Jul-2026 | 26-Jun-2026 18:30:24 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 29-Jun-2026 01:32:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 30-Jun-2026 08:58:00 | 30-Jun-2026 02:27:12 | 0 |  |  | Approver | Locate
AO-001403 | MM-ZTK-1F-ZWP21-STR-DWG-2121 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 135000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 16:54:10 | wisuda.c@jutal.com | 04-Aug-2026 08:18:36 | Jumpol Sudjitjul | 11-Aug-2026 |  | Sompop Singhatiraj | 14-Aug-2026 | 07-Aug-2026 10:25:51 | Pornlert Wanaphattharaphan | 17-Aug-2026 | 10-Aug-2026 01:23:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Aug-2026 | 10-Aug-2026 14:12:54 | 10-Aug-2026 08:34:06 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP21-STR-DWG-2122 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 149000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:38:44 | wisuda.c@jutal.com | 21-Apr-2026 14:35:04 | Jumpol Sudjitjul | 28-Apr-2026 | 24-Apr-2026 11:30:46 | Sompop Singhatiraj | 30-Apr-2026 | 24-Apr-2026 17:37:29 | Pornlert Wanaphattharaphan | 05-May-2026 | 29-Apr-2026 23:00:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 30-Apr-2026 09:17:12 | 30-Apr-2026 02:52:16 | 0 |  |  | Approver | Locate
AO-000895 | MM-ZTK-1F-ZWP21-STR-DWG-2122 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 149000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 25-Jun-2026 23:17:05 | wisuda.c@jutal.com | 26-Jun-2026 08:32:35 | Jumpol Sudjitjul | 03-Jul-2026 |  | Sompop Singhatiraj | 07-Jul-2026 | 26-Jun-2026 18:31:16 | Pornlert Wanaphattharaphan | 08-Jul-2026 | 29-Jun-2026 01:32:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jul-2026 | 30-Jun-2026 08:56:50 | 30-Jun-2026 02:33:51 | 0 |  |  | Approver | Locate
AO-001390 | MM-ZTK-1F-ZWP21-STR-DWG-2122 | ZWP21 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 149000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 03-Aug-2026 10:08:33 | wisuda.c@jutal.com | 03-Aug-2026 13:05:37 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 07-Aug-2026 10:26:34 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 10-Aug-2026 01:23:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 14:12:10 | 10-Aug-2026 08:32:36 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP21-STR-DWG-2123 | ZWP21 JACKET - FRAMING SECTIONS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:39:08 | wisuda.c@jutal.com | 21-Apr-2026 14:35:18 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 16:14:09 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 18:31:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 09:02:59 | 24-Apr-2026 03:00:36 | 0 |  |  | Approver | Locate
AO-001216 | MM-ZTK-1F-ZWP21-STR-DWG-2123 | ZWP21 JACKET - FRAMING SECTIONS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jul-2026 07:51:42 | wisuda.c@jutal.com | 21-Jul-2026 08:13:45 | Jumpol Sudjitjul | 30-Jul-2026 |  | Sompop Singhatiraj | 03-Aug-2026 | 24-Jul-2026 09:36:22 | Pornlert Wanaphattharaphan | 04-Aug-2026 | 24-Jul-2026 22:54:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Aug-2026 | 27-Jul-2026 15:03:54 | 27-Jul-2026 10:08:29 | 0 |  |  | Approver | Locate
AO-001517 | MM-ZTK-1F-ZWP21-STR-DWG-2123 | ZWP21 JACKET - FRAMING SECTIONS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 13-Aug-2026 16:54:58 | wisuda.c@jutal.com | 13-Aug-2026 17:00:16 | Jumpol Sudjitjul | 20-Aug-2026 |  | Sompop Singhatiraj | 24-Aug-2026 | 21-Aug-2026 11:07:15 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 21-Aug-2026 20:26:44 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 24-Aug-2026 18:15:15 | 24-Aug-2026 12:10:17 | 0 |  |  | Approver | Locate
AO-000308 | MM-ZTK-1F-ZWP21-STR-DWG-2130 | ZWP21 JACKET - LAUNCH CRADLE GENERAL ARRANGEMENT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 05-May-2026 19:05:16 | wisuda.c@jutal.com | 06-May-2026 10:00:56 | Jumpol Sudjitjul | 13-May-2026 |  | Sompop Singhatiraj | 15-May-2026 | 16-May-2026 13:46:27 | Pornlert Wanaphattharaphan | 18-May-2026 | 19-May-2026 00:28:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 19-May-2026 10:29:33 | 19-May-2026 04:44:57 | 0 |  |  | Approver | Locate
AO-000948 | MM-ZTK-1F-ZWP21-STR-DWG-2130 | ZWP21 JACKET - LAUNCH CRADLE GENERAL ARRANGEMENT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 30-Jun-2026 09:24:20 | wisuda.c@jutal.com | 30-Jun-2026 11:32:49 | Jumpol Sudjitjul | 07-Jul-2026 |  | Sompop Singhatiraj | 09-Jul-2026 | 01-Jul-2026 17:46:41 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 02-Jul-2026 00:26:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 02-Jul-2026 10:03:26 | 02-Jul-2026 04:15:57 | 0 |  |  | Approver | Locate
AO-001517 | MM-ZTK-1F-ZWP21-STR-DWG-2130 | ZWP21 JACKET - LAUNCH CRADLE GENERAL ARRANGEMENT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 13-Aug-2026 16:55:29 | wisuda.c@jutal.com | 13-Aug-2026 17:00:21 | Jumpol Sudjitjul | 20-Aug-2026 |  | Sompop Singhatiraj | 24-Aug-2026 | 21-Aug-2026 11:14:34 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 21-Aug-2026 20:28:15 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 24-Aug-2026 18:21:22 | 24-Aug-2026 12:11:23 | 0 |  |  | Approver | Locate
AO-000308 | MM-ZTK-1F-ZWP21-STR-DWG-2131 | ZWP21 JACKET - LAUNCH CRADLE DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 05-May-2026 19:05:40 | wisuda.c@jutal.com | 06-May-2026 10:01:19 | Jumpol Sudjitjul | 13-May-2026 |  | Sompop Singhatiraj | 15-May-2026 | 16-May-2026 13:47:49 | Pornlert Wanaphattharaphan | 18-May-2026 | 19-May-2026 00:27:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 19-May-2026 10:33:37 | 19-May-2026 04:47:24 | 0 |  |  | Approver | Locate
AO-000948 | MM-ZTK-1F-ZWP21-STR-DWG-2131 | ZWP21 JACKET - LAUNCH CRADLE DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 30-Jun-2026 09:25:22 | wisuda.c@jutal.com | 30-Jun-2026 11:33:12 | Jumpol Sudjitjul | 07-Jul-2026 |  | Sompop Singhatiraj | 09-Jul-2026 | 01-Jul-2026 17:49:46 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 02-Jul-2026 00:28:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 02-Jul-2026 10:02:49 | 02-Jul-2026 04:14:31 | 0 |  |  | Approver | Locate
AO-001517 | MM-ZTK-1F-ZWP21-STR-DWG-2131 | ZWP21 JACKET - LAUNCH CRADLE DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 13-Aug-2026 16:55:55 | wisuda.c@jutal.com | 13-Aug-2026 17:00:20 | Jumpol Sudjitjul | 20-Aug-2026 |  | Sompop Singhatiraj | 24-Aug-2026 | 21-Aug-2026 11:18:09 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 21-Aug-2026 20:28:49 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 24-Aug-2026 18:21:52 | 24-Aug-2026 12:12:30 | 0 |  |  | Approver | Locate
AO-000308 | MM-ZTK-1F-ZWP21-STR-DWG-2132 | ZWP21 JACKET - LAUNCH CRADLE DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 05-May-2026 19:06:04 | wisuda.c@jutal.com | 06-May-2026 10:01:34 | Jumpol Sudjitjul | 13-May-2026 |  | Sompop Singhatiraj | 15-May-2026 | 16-May-2026 13:52:27 | Pornlert Wanaphattharaphan | 18-May-2026 | 19-May-2026 00:30:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 19-May-2026 10:34:46 | 19-May-2026 04:51:15 | 0 |  |  | Approver | Locate
AO-000948 | MM-ZTK-1F-ZWP21-STR-DWG-2132 | ZWP21 JACKET - LAUNCH CRADLE DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 30-Jun-2026 09:26:35 | wisuda.c@jutal.com | 30-Jun-2026 11:33:31 | Jumpol Sudjitjul | 07-Jul-2026 |  | Sompop Singhatiraj | 09-Jul-2026 | 01-Jul-2026 17:51:42 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 02-Jul-2026 00:32:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 02-Jul-2026 10:00:24 | 02-Jul-2026 04:12:52 | 0 |  |  | Approver | Locate
AO-001517 | MM-ZTK-1F-ZWP21-STR-DWG-2132 | ZWP21 JACKET - LAUNCH CRADLE DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 13-Aug-2026 16:56:21 | wisuda.c@jutal.com | 13-Aug-2026 17:00:15 | Jumpol Sudjitjul | 20-Aug-2026 |  | Sompop Singhatiraj | 24-Aug-2026 | 20-Aug-2026 13:53:01 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 21-Aug-2026 20:09:49 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 24-Aug-2026 18:41:06 | 24-Aug-2026 12:43:07 | 0 |  |  | Approver | Locate
AO-000308 | MM-ZTK-1F-ZWP21-STR-DWG-2133 | ZWP21 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 05-May-2026 19:06:29 | wisuda.c@jutal.com | 06-May-2026 10:01:48 | Jumpol Sudjitjul | 13-May-2026 | 17-May-2026 06:56:55 | Sompop Singhatiraj | 15-May-2026 | 16-May-2026 13:48:54 | Pornlert Wanaphattharaphan | 18-May-2026 | 21-May-2026 23:15:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 22-May-2026 08:41:06 | 22-May-2026 09:26:04 | 0 |  |  | Approver | Locate
AO-000802 | MM-ZTK-1F-ZWP21-STR-DWG-2133 | ZWP21 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 15-Jun-2026 15:36:19 | wisuda.c@jutal.com | 15-Jun-2026 16:33:06 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:44:32 | Sompop Singhatiraj | 24-Jun-2026 | 23-Jun-2026 11:37:23 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 23-Jun-2026 23:17:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Jun-2026 | 24-Jun-2026 13:36:25 | 24-Jun-2026 06:45:32 | 0 |  |  | Approver | Locate
AO-001517 | MM-ZTK-1F-ZWP21-STR-DWG-2133 | ZWP21 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 13-Aug-2026 16:56:53 | wisuda.c@jutal.com | 13-Aug-2026 17:00:16 | Jumpol Sudjitjul | 20-Aug-2026 |  | Sompop Singhatiraj | 24-Aug-2026 | 24-Aug-2026 09:21:25 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 27-Aug-2026 14:49:24 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 28-Aug-2026 10:57:04 | 28-Aug-2026 04:52:34 | 0 |  |  | Approver | Locate
AO-000308 | MM-ZTK-1F-ZWP21-STR-DWG-2134 | ZWP21 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 05-May-2026 19:06:54 | wisuda.c@jutal.com | 06-May-2026 10:05:29 | Jumpol Sudjitjul | 13-May-2026 |  | Sompop Singhatiraj | 15-May-2026 | 16-May-2026 13:52:41 | Pornlert Wanaphattharaphan | 18-May-2026 | 19-May-2026 00:25:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 19-May-2026 10:16:10 | 19-May-2026 11:33:21 | 0 |  |  | Approver | Locate
AO-000802 | MM-ZTK-1F-ZWP21-STR-DWG-2134 | ZWP21 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 15-Jun-2026 15:36:51 | wisuda.c@jutal.com | 15-Jun-2026 16:33:25 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:50:12 | Sompop Singhatiraj | 24-Jun-2026 | 24-Jun-2026 10:13:16 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 24-Jun-2026 23:16:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Jun-2026 | 25-Jun-2026 13:53:12 | 25-Jun-2026 08:04:25 | 0 |  |  | Approver | Locate
AO-001517 | MM-ZTK-1F-ZWP21-STR-DWG-2134 | ZWP21 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 13-Aug-2026 16:57:26 | wisuda.c@jutal.com | 13-Aug-2026 17:00:25 | Jumpol Sudjitjul | 20-Aug-2026 |  | Sompop Singhatiraj | 24-Aug-2026 | 24-Aug-2026 09:24:40 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 27-Aug-2026 14:50:58 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 28-Aug-2026 11:00:48 | 28-Aug-2026 04:53:42 | 0 |  |  | Approver | Locate
AO-000308 | MM-ZTK-1F-ZWP21-STR-DWG-2135 | ZWP21 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 05-May-2026 19:07:16 | wisuda.c@jutal.com | 06-May-2026 10:05:44 | Jumpol Sudjitjul | 13-May-2026 |  | Sompop Singhatiraj | 15-May-2026 | 16-May-2026 13:50:03 | Pornlert Wanaphattharaphan | 18-May-2026 | 21-May-2026 23:13:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 22-May-2026 08:43:23 | 22-May-2026 09:27:17 | 0 |  |  | Approver | Locate
AO-000802 | MM-ZTK-1F-ZWP21-STR-DWG-2135 | ZWP21 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 15-Jun-2026 15:37:22 | wisuda.c@jutal.com | 15-Jun-2026 16:33:39 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:50:39 | Sompop Singhatiraj | 24-Jun-2026 | 24-Jun-2026 10:15:31 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 24-Jun-2026 23:17:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Jun-2026 | 25-Jun-2026 13:54:01 | 25-Jun-2026 08:05:54 | 0 |  |  | Approver | Locate
AO-001517 | MM-ZTK-1F-ZWP21-STR-DWG-2135 | ZWP21 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 3 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 13-Aug-2026 16:57:57 | wisuda.c@jutal.com | 13-Aug-2026 17:00:22 | Jumpol Sudjitjul | 20-Aug-2026 |  | Sompop Singhatiraj | 24-Aug-2026 | 24-Aug-2026 09:24:43 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 27-Aug-2026 14:52:56 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 28-Aug-2026 11:01:36 | 28-Aug-2026 04:54:50 | 0 |  |  | Approver | Locate
AO-000308 | MM-ZTK-1F-ZWP21-STR-DWG-2136 | ZWP21 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 05-May-2026 19:07:39 | wisuda.c@jutal.com | 06-May-2026 10:05:56 | Jumpol Sudjitjul | 13-May-2026 |  | Sompop Singhatiraj | 15-May-2026 | 16-May-2026 13:51:07 | Pornlert Wanaphattharaphan | 18-May-2026 | 19-May-2026 00:29:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 19-May-2026 10:47:37 | 19-May-2026 11:53:44 | 0 |  |  | Approver | Locate
AO-000802 | MM-ZTK-1F-ZWP21-STR-DWG-2136 | ZWP21 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 4 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 15-Jun-2026 15:37:59 | wisuda.c@jutal.com | 15-Jun-2026 16:33:52 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:51:04 | Sompop Singhatiraj | 24-Jun-2026 | 24-Jun-2026 14:20:22 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 24-Jun-2026 23:19:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Jun-2026 | 25-Jun-2026 13:54:53 | 25-Jun-2026 08:07:22 | 0 |  |  | Approver | Locate
AO-001517 | MM-ZTK-1F-ZWP21-STR-DWG-2136 | ZWP21 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 4 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 13-Aug-2026 16:58:26 | wisuda.c@jutal.com | 13-Aug-2026 17:00:24 | Jumpol Sudjitjul | 20-Aug-2026 |  | Sompop Singhatiraj | 24-Aug-2026 | 24-Aug-2026 09:25:47 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 27-Aug-2026 14:54:32 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 28-Aug-2026 11:02:00 | 28-Aug-2026 04:55:56 | 0 |  |  | Approver | Locate
AO-000400 | MM-ZTK-1F-ZWP21-STR-DWG-2141 | ZWP21 JACKET - PILE CLUSTER ARRANGEMENT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 09:31:05 | wisuda.c@jutal.com | 15-May-2026 11:55:44 | Jumpol Sudjitjul | 22-May-2026 |  | Sompop Singhatiraj | 26-May-2026 | 20-May-2026 12:06:11 | Pornlert Wanaphattharaphan | 27-May-2026 | 22-May-2026 00:29:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 22-May-2026 08:23:48 | 22-May-2026 02:00:06 | 0 |  |  | Approver | Locate
AO-001545 | MM-ZTK-1F-ZWP21-STR-DWG-2141 | ZWP21 JACKET - PILE CLUSTER ARRANGEMENT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:24:39 | wisuda.c@jutal.com | 17-Aug-2026 15:22:02 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 21-Aug-2026 10:51:01 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:29:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 18:24:39 | 24-Aug-2026 12:47:47 | 0 |  |  | Approver | Locate
AO-002310 | MM-ZTK-1F-ZWP21-STR-DWG-2141 | ZWP21 JACKET - PILE CLUSTER ARRANGEMENT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 30-Sep-2026 09:25:30 | wisuda.c@jutal.com | 30-Sep-2026 16:04:37 | Jumpol Sudjitjul | 07-Oct-2026 |  | Sompop Singhatiraj | 09-Oct-2026 | 01-Oct-2026 15:53:54 | Pornlert Wanaphattharaphan | 12-Oct-2026 | 01-Oct-2026 22:53:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Oct-2026 | 02-Oct-2026 13:31:02 | 02-Oct-2026 07:27:37 | 0 |  |  | Approver | Locate
AO-000400 | MM-ZTK-1F-ZWP21-STR-DWG-2142 | ZWP21 JACKET - PILE SLEEVE DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 09:31:30 | wisuda.c@jutal.com | 15-May-2026 11:55:47 | Jumpol Sudjitjul | 22-May-2026 |  | Sompop Singhatiraj | 26-May-2026 | 20-May-2026 11:59:49 | Pornlert Wanaphattharaphan | 27-May-2026 | 22-May-2026 00:24:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 22-May-2026 08:22:35 | 22-May-2026 01:57:30 | 0 |  |  | Approver | Locate
AO-001545 | MM-ZTK-1F-ZWP21-STR-DWG-2142 | ZWP21 JACKET - PILE SLEEVE DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:25:21 | wisuda.c@jutal.com | 17-Aug-2026 15:21:57 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 21-Aug-2026 10:35:54 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:27:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 18:23:06 | 24-Aug-2026 12:46:33 | 0 |  |  | Approver | Locate
AO-002310 | MM-ZTK-1F-ZWP21-STR-DWG-2142 | ZWP21 JACKET - PILE SLEEVE DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 30-Sep-2026 09:26:20 | wisuda.c@jutal.com | 30-Sep-2026 16:04:37 | Jumpol Sudjitjul | 07-Oct-2026 |  | Sompop Singhatiraj | 09-Oct-2026 | 01-Oct-2026 17:38:13 | Pornlert Wanaphattharaphan | 12-Oct-2026 | 01-Oct-2026 22:52:37 | APPR | Approved | Jumpol Sudjitjul | 14-Oct-2026 | 02-Oct-2026 13:34:25 | 02-Oct-2026 07:28:48 | 0 |  |  | Approver | Locate
AO-000400 | MM-ZTK-1F-ZWP21-STR-DWG-2143 | ZWP21 JACKET - SKIRT SLEEVE MARKING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 09:31:54 | wisuda.c@jutal.com | 15-May-2026 11:55:46 | Jumpol Sudjitjul | 22-May-2026 |  | Sompop Singhatiraj | 26-May-2026 | 20-May-2026 12:00:59 | Pornlert Wanaphattharaphan | 27-May-2026 | 22-May-2026 00:28:53 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 28-May-2026 | 22-May-2026 08:52:23 | 22-May-2026 02:38:44 | 0 |  |  | Approver | Locate
AO-001550 | MM-ZTK-1F-ZWP21-STR-DWG-2143 | ZWP21 JACKET - SKIRT SLEEVE MARKING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 14:25:56 | wisuda.c@jutal.com | 17-Aug-2026 15:21:57 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 21-Aug-2026 10:24:48 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:26:50 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 18:22:15 | 24-Aug-2026 12:45:14 | 0 |  |  | Approver | Locate
AO-000329 | MM-ZTK-1F-ZWP21-STR-DWG-2144 | ZWP21 JACKET - PILE MAKE-UP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 06-May-2026 16:34:46 | wisuda.c@jutal.com | 06-May-2026 17:16:15 | Jumpol Sudjitjul | 14-May-2026 |  | Sompop Singhatiraj | 18-May-2026 | 16-May-2026 10:37:46 | Pornlert Wanaphattharaphan | 19-May-2026 | 19-May-2026 00:31:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-May-2026 | 19-May-2026 10:18:52 | 19-May-2026 04:21:01 | 0 |  |  | Approver | Locate
AO-001529 | MM-ZTK-1F-ZWP21-STR-DWG-2144 | ZWP21 JACKET - PILE MAKE-UP |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 16:16:55 | wisuda.c@jutal.com | 14-Aug-2026 16:27:19 | Jumpol Sudjitjul | 21-Aug-2026 |  | Sompop Singhatiraj | 25-Aug-2026 | 21-Aug-2026 10:59:32 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 22-Aug-2026 12:59:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 18:21:40 | 24-Aug-2026 11:42:40 | 0 |  |  | Approver | Locate
AO-002308 | MM-ZTK-1F-ZWP21-STR-DWG-2144 | ZWP21 JACKET - PILE MAKE-UP |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 30-Sep-2026 09:27:02 | wisuda.c@jutal.com | 30-Sep-2026 16:04:37 | Jumpol Sudjitjul | 07-Oct-2026 |  | Sompop Singhatiraj | 09-Oct-2026 | 01-Oct-2026 15:41:55 | Pornlert Wanaphattharaphan | 12-Oct-2026 | 01-Oct-2026 22:51:21 | APPR | Approved | Jumpol Sudjitjul | 14-Oct-2026 | 02-Oct-2026 13:35:00 | 02-Oct-2026 07:29:56 | 0 |  |  | Approver | Locate
AO-001530 | MM-ZTK-1F-ZWP21-STR-DWG-2145 | ZWP21 JACKET - PILE MARKING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 17:31:19 | wisuda.c@jutal.com | 14-Aug-2026 17:41:31 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 21-Aug-2026 10:20:24 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:26:10 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 18:21:08 | 24-Aug-2026 11:41:24 | 0 |  |  | Approver | Locate
AO-000508 | MM-ZTK-1F-ZWP21-STR-DWG-2200 | ZWP21 JACKET - HYDROSTATIC RING DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 13:31:47 | wisuda.c@jutal.com | 19-May-2026 13:38:41 | Jumpol Sudjitjul | 26-May-2026 |  | Sompop Singhatiraj | 28-May-2026 | 25-May-2026 16:00:21 | Pornlert Wanaphattharaphan | 29-May-2026 | 25-May-2026 20:48:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 25-May-2026 21:15:48 | 25-May-2026 21:31:35 | 0 |  |  | Approver | Locate
AO-000802 | MM-ZTK-1F-ZWP21-STR-DWG-2200 | ZWP21 JACKET - HYDROSTATIC RING DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 15-Jun-2026 15:38:29 | wisuda.c@jutal.com | 15-Jun-2026 16:41:47 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:52:02 | Sompop Singhatiraj | 24-Jun-2026 | 24-Jun-2026 08:22:38 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 24-Jun-2026 23:15:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Jun-2026 | 25-Jun-2026 13:56:04 | 25-Jun-2026 08:09:00 | 0 |  |  | Approver | Locate
AO-001531 | MM-ZTK-1F-ZWP21-STR-DWG-2200 | ZWP21 JACKET - HYDROSTATIC RING DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Aug-2026 17:31:49 | wisuda.c@jutal.com | 14-Aug-2026 17:39:55 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 24-Aug-2026 10:37:09 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 27-Aug-2026 22:30:37 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 28-Aug-2026 11:03:17 | 28-Aug-2026 04:57:02 | 0 |  |  | Approver | Locate
AO-000509 | MM-ZTK-1F-ZWP21-STR-DWG-2201 | ZWP21 JACKET - HYDROSTATIC RING DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 13:32:33 | wisuda.c@jutal.com | 19-May-2026 13:39:07 | Jumpol Sudjitjul | 26-May-2026 |  | Sompop Singhatiraj | 28-May-2026 | 25-May-2026 16:01:40 | Pornlert Wanaphattharaphan | 29-May-2026 | 25-May-2026 20:49:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 25-May-2026 21:15:37 | 25-May-2026 21:30:16 | 0 |  |  | Approver | Locate
AO-000802 | MM-ZTK-1F-ZWP21-STR-DWG-2201 | ZWP21 JACKET - HYDROSTATIC RING DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 15-Jun-2026 15:38:58 | wisuda.c@jutal.com | 15-Jun-2026 16:42:02 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:53:10 | Sompop Singhatiraj | 24-Jun-2026 | 24-Jun-2026 08:25:52 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 24-Jun-2026 23:15:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Jun-2026 | 25-Jun-2026 13:57:00 | 25-Jun-2026 08:10:37 | 0 |  |  | Approver | Locate
AO-001532 | MM-ZTK-1F-ZWP21-STR-DWG-2201 | ZWP21 JACKET - HYDROSTATIC RING DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Aug-2026 17:32:14 | wisuda.c@jutal.com | 14-Aug-2026 17:40:10 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 24-Aug-2026 10:35:26 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 27-Aug-2026 22:30:03 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 28-Aug-2026 11:06:06 | 28-Aug-2026 04:58:06 | 0 |  |  | Approver | Locate
AO-000740 | MM-ZTK-1F-ZWP21-STR-DWG-2241 | ZWP21 JACKET - RISER PROTECTOR |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 18:12:40 | wisuda.c@jutal.com | 12-Jun-2026 09:48:54 | Jumpol Sudjitjul | 19-Jun-2026 |  | Sompop Singhatiraj | 23-Jun-2026 | 15-Jun-2026 15:58:01 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 18-Jun-2026 19:57:56 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 25-Jun-2026 | 19-Jun-2026 08:57:28 | 19-Jun-2026 02:44:19 | 0 |  |  | Approver | Locate
AO-001638 | MM-ZTK-1F-ZWP21-STR-DWG-2241 | ZWP21 JACKET - RISER PROTECTOR |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 10:23:05 | wisuda.c@jutal.com | 21-Aug-2026 10:59:11 | Jumpol Sudjitjul | 28-Aug-2026 |  | Sompop Singhatiraj | 01-Sep-2026 | 24-Aug-2026 15:46:26 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 29-Aug-2026 23:56:58 | APPR | Approved | Jumpol Sudjitjul | 03-Sep-2026 | 30-Aug-2026 16:50:32 | 30-Aug-2026 10:20:27 | 0 |  |  | Approver | Locate
AO-000740 | MM-ZTK-1F-ZWP21-STR-DWG-2300 | ZWP21 JACKET - CASING GUIDE ARRANGEMENT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 18:13:04 | wisuda.c@jutal.com | 12-Jun-2026 10:29:19 | Jumpol Sudjitjul | 19-Jun-2026 |  | Sompop Singhatiraj | 23-Jun-2026 | 15-Jun-2026 15:15:49 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 18-Jun-2026 19:55:59 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 25-Jun-2026 | 19-Jun-2026 08:57:04 | 19-Jun-2026 02:41:44 | 0 |  |  | Approver | Locate
AO-001638 | MM-ZTK-1F-ZWP21-STR-DWG-2300 | ZWP21 JACKET - CASING GUIDE ARRANGEMENT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 10:24:18 | wisuda.c@jutal.com | 21-Aug-2026 10:59:11 | Jumpol Sudjitjul | 28-Aug-2026 |  | Sompop Singhatiraj | 01-Sep-2026 | 24-Aug-2026 15:55:08 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 29-Aug-2026 23:59:50 | APPR | Approved | Jumpol Sudjitjul | 03-Sep-2026 | 30-Aug-2026 16:52:28 | 30-Aug-2026 10:21:34 | 0 |  |  | Approver | Locate
AO-000740 | MM-ZTK-1F-ZWP21-STR-DWG-2301 | ZWP21 JACKET - CASING GUIDE DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 18:13:28 | wisuda.c@jutal.com | 12-Jun-2026 10:29:36 | Jumpol Sudjitjul | 19-Jun-2026 |  | Sompop Singhatiraj | 23-Jun-2026 | 15-Jun-2026 15:17:37 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 18-Jun-2026 19:57:01 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 25-Jun-2026 | 19-Jun-2026 08:56:40 | 19-Jun-2026 02:39:10 | 0 |  |  | Approver | Locate
AO-001638 | MM-ZTK-1F-ZWP21-STR-DWG-2301 | ZWP21 JACKET - CASING GUIDE DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 10:25:03 | wisuda.c@jutal.com | 21-Aug-2026 10:59:11 | Jumpol Sudjitjul | 28-Aug-2026 |  | Sompop Singhatiraj | 01-Sep-2026 | 24-Aug-2026 15:57:44 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 30-Aug-2026 00:00:34 | APPR | Approved | Jumpol Sudjitjul | 03-Sep-2026 | 30-Aug-2026 16:55:38 | 30-Aug-2026 10:24:52 | 0 |  |  | Approver | Locate
AO-000257 | MM-ZTK-1F-ZWP21-STR-DWG-2311 | ZWP21 JACKET - ANODE STRUCTURE AND INSTALLATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-Apr-2026 12:35:52 | wisuda.c@jutal.com | 29-Apr-2026 13:23:41 | Jumpol Sudjitjul | 08-May-2026 | 30-Apr-2026 10:11:21 | Sompop Singhatiraj | 12-May-2026 | 11-May-2026 14:13:00 | Pornlert Wanaphattharaphan | 13-May-2026 | 15-May-2026 00:51:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-May-2026 | 15-May-2026 10:31:39 | 15-May-2026 03:56:29 | 0 |  |  | Approver | Locate
AO-001448 | MM-ZTK-1F-ZWP21-STR-DWG-2311 | ZWP21 JACKET - ANODE STRUCTURE AND INSTALLATION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:39:07 | wisuda.c@jutal.com | 07-Aug-2026 16:02:54 | Jumpol Sudjitjul | 17-Aug-2026 |  | Sompop Singhatiraj | 19-Aug-2026 | 19-Aug-2026 15:22:44 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:49:13 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 18:20:42 | 24-Aug-2026 12:40:54 | 0 |  |  | Approver | Locate
AO-002144 | MM-ZTK-1F-ZWP21-STR-DWG-2311 | ZWP21 JACKET - ANODE STRUCTURE AND INSTALLATION |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:00:23 | wisuda.c@jutal.com | 18-Sep-2026 17:02:13 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 23-Sep-2026 19:18:17 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 23-Sep-2026 21:57:13 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 24-Sep-2026 09:23:03 | 24-Sep-2026 02:37:17 | 0 |  |  | Approver | Locate
AO-000288 | MM-ZTK-1F-ZWP21-STR-DWG-2312 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'A' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 11:03:16 | wisuda.c@jutal.com | 04-May-2026 11:21:45 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 14:07:30 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 14:44:40 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:36:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:13:21 | 19-May-2026 04:19:38 | 0 |  |  | Approver | Locate
AO-001448 | MM-ZTK-1F-ZWP21-STR-DWG-2312 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'A' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:39:34 | wisuda.c@jutal.com | 07-Aug-2026 16:02:55 | Jumpol Sudjitjul | 17-Aug-2026 |  | Sompop Singhatiraj | 19-Aug-2026 | 19-Aug-2026 15:27:03 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:52:00 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 18:19:20 | 24-Aug-2026 12:39:39 | 0 |  |  | Approver | Locate
AO-002144 | MM-ZTK-1F-ZWP21-STR-DWG-2312 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'A' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:00:51 | wisuda.c@jutal.com | 18-Sep-2026 17:02:11 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 23-Sep-2026 19:16:58 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 23-Sep-2026 21:56:20 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 24-Sep-2026 09:24:05 | 24-Sep-2026 02:38:25 | 0 |  |  | Approver | Locate
AO-000288 | MM-ZTK-1F-ZWP21-STR-DWG-2313 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'B' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 11:03:39 | wisuda.c@jutal.com | 04-May-2026 11:41:17 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 14:10:25 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 14:46:57 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:37:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:47:34 | 19-May-2026 04:52:26 | 0 |  |  | Approver | Locate
AO-001448 | MM-ZTK-1F-ZWP21-STR-DWG-2313 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'B' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:40:00 | wisuda.c@jutal.com | 07-Aug-2026 16:02:55 | Jumpol Sudjitjul | 17-Aug-2026 |  | Sompop Singhatiraj | 19-Aug-2026 | 19-Aug-2026 15:22:51 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:49:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 18:18:04 | 24-Aug-2026 12:37:03 | 0 |  |  | Approver | Locate
AO-002144 | MM-ZTK-1F-ZWP21-STR-DWG-2313 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'B' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:01:28 | wisuda.c@jutal.com | 18-Sep-2026 17:02:18 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 23-Sep-2026 19:16:41 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 23-Sep-2026 21:54:58 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 24-Sep-2026 09:25:26 | 24-Sep-2026 02:39:30 | 0 |  |  | Approver | Locate
AO-000288 | MM-ZTK-1F-ZWP21-STR-DWG-2314 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '1' & '1.1' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 11:04:02 | wisuda.c@jutal.com | 04-May-2026 11:41:29 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 14:12:40 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 14:47:08 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:38:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:33:57 | 19-May-2026 04:48:41 | 0 |  |  | Approver | Locate
AO-001448 | MM-ZTK-1F-ZWP21-STR-DWG-2314 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '1' & '1.1' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:40:28 | wisuda.c@jutal.com | 07-Aug-2026 16:03:01 | Jumpol Sudjitjul | 17-Aug-2026 |  | Sompop Singhatiraj | 19-Aug-2026 | 19-Aug-2026 15:25:59 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:51:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 18:18:23 | 24-Aug-2026 12:38:23 | 0 |  |  | Approver | Locate
AO-002144 | MM-ZTK-1F-ZWP21-STR-DWG-2314 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '1' & '1.1' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:02:03 | wisuda.c@jutal.com | 18-Sep-2026 17:02:17 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 23-Sep-2026 19:16:29 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 23-Sep-2026 21:47:07 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 24-Sep-2026 08:57:59 | 24-Sep-2026 02:32:56 | 0 |  |  | Approver | Locate
AO-000288 | MM-ZTK-1F-ZWP21-STR-DWG-2315 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '2' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 11:04:25 | wisuda.c@jutal.com | 04-May-2026 11:41:42 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 14:15:00 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 15:53:14 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:45:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:34:34 | 19-May-2026 04:50:01 | 0 |  |  | Approver | Locate
AO-001448 | MM-ZTK-1F-ZWP21-STR-DWG-2315 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '2' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:40:55 | wisuda.c@jutal.com | 07-Aug-2026 16:02:58 | Jumpol Sudjitjul | 17-Aug-2026 |  | Sompop Singhatiraj | 19-Aug-2026 | 19-Aug-2026 15:28:26 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:53:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 18:15:45 | 24-Aug-2026 12:35:45 | 0 |  |  | Approver | Locate
AO-002144 | MM-ZTK-1F-ZWP21-STR-DWG-2315 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '2' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:02:29 | wisuda.c@jutal.com | 18-Sep-2026 17:02:17 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 23-Sep-2026 19:15:09 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 23-Sep-2026 21:46:32 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 24-Sep-2026 09:26:00 | 24-Sep-2026 03:04:51 | 0 |  |  | Approver | Locate
AO-000288 | MM-ZTK-1F-ZWP21-STR-DWG-2316 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'AA' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 11:04:52 | wisuda.c@jutal.com | 04-May-2026 11:41:56 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 14:17:02 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 14:48:37 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:39:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:11:07 | 19-May-2026 04:18:14 | 0 |  |  | Approver | Locate
AO-001448 | MM-ZTK-1F-ZWP21-STR-DWG-2316 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'AA' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:41:22 | wisuda.c@jutal.com | 07-Aug-2026 16:02:57 | Jumpol Sudjitjul | 17-Aug-2026 |  | Sompop Singhatiraj | 19-Aug-2026 | 10-Aug-2026 13:25:37 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 12-Aug-2026 01:16:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 13-Aug-2026 11:45:43 | 13-Aug-2026 05:12:24 | 0 |  |  | Approver | Locate
AO-002144 | MM-ZTK-1F-ZWP21-STR-DWG-2316 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'AA' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:02:57 | wisuda.c@jutal.com | 18-Sep-2026 17:02:19 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 23-Sep-2026 19:20:18 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 23-Sep-2026 22:03:43 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 24-Sep-2026 09:26:33 | 24-Sep-2026 03:06:00 | 0 |  |  | Approver | Locate
AO-000288 | MM-ZTK-1F-ZWP21-STR-DWG-2317 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'BB' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 11:05:17 | wisuda.c@jutal.com | 04-May-2026 12:51:36 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 14:19:38 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 14:48:24 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:39:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:04:24 | 19-May-2026 04:07:32 | 0 |  |  | Approver | Locate
AO-001448 | MM-ZTK-1F-ZWP21-STR-DWG-2317 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'BB' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:41:49 | wisuda.c@jutal.com | 07-Aug-2026 16:02:56 | Jumpol Sudjitjul | 17-Aug-2026 |  | Sompop Singhatiraj | 19-Aug-2026 | 10-Aug-2026 13:25:51 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 12-Aug-2026 01:17:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 13-Aug-2026 11:52:33 | 13-Aug-2026 05:13:39 | 0 |  |  | Approver | Locate
AO-002144 | MM-ZTK-1F-ZWP21-STR-DWG-2317 | ZWP21 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'BB' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:03:27 | wisuda.c@jutal.com | 18-Sep-2026 17:02:12 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 23-Sep-2026 19:19:46 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 23-Sep-2026 21:57:48 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 24-Sep-2026 09:26:58 | 24-Sep-2026 03:07:07 | 0 |  |  | Approver | Locate
AO-000288 | MM-ZTK-1F-ZWP21-STR-DWG-2321 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 14000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 11:05:42 | wisuda.c@jutal.com | 04-May-2026 12:52:38 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 14:22:58 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:40:16 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:01:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:32:34 | 19-May-2026 04:46:12 | 0 |  |  | Approver | Locate
AO-001448 | MM-ZTK-1F-ZWP21-STR-DWG-2321 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 14000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:42:16 | wisuda.c@jutal.com | 07-Aug-2026 16:03:00 | Jumpol Sudjitjul | 17-Aug-2026 |  | Sompop Singhatiraj | 19-Aug-2026 | 10-Aug-2026 13:36:04 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 12-Aug-2026 01:19:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 13-Aug-2026 11:54:18 | 13-Aug-2026 05:33:46 | 0 |  |  | Approver | Locate
AO-002144 | MM-ZTK-1F-ZWP21-STR-DWG-2321 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 14000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:03:58 | wisuda.c@jutal.com | 18-Sep-2026 17:02:11 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 23-Sep-2026 19:19:53 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 23-Sep-2026 22:00:51 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 24-Sep-2026 08:58:57 | 24-Sep-2026 02:42:30 | 0 |  |  | Approver | Locate
AO-000288 | MM-ZTK-1F-ZWP21-STR-DWG-2322 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 26000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 11:06:04 | wisuda.c@jutal.com | 04-May-2026 11:46:17 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 14:25:19 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:40:24 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:01:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:28:50 | 19-May-2026 04:43:45 | 0 |  |  | Approver | Locate
AO-001448 | MM-ZTK-1F-ZWP21-STR-DWG-2322 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 26000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:42:45 | wisuda.c@jutal.com | 07-Aug-2026 16:02:59 | Jumpol Sudjitjul | 17-Aug-2026 |  | Sompop Singhatiraj | 19-Aug-2026 | 10-Aug-2026 13:35:56 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 12-Aug-2026 01:17:38 | APPR | Approved | Jumpol Sudjitjul | 21-Aug-2026 | 13-Aug-2026 12:55:52 | 13-Aug-2026 06:14:23 | 0 |  |  | Approver | Locate
AO-002144 | MM-ZTK-1F-ZWP21-STR-DWG-2322 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 26000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:04:27 | wisuda.c@jutal.com | 18-Sep-2026 17:02:20 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 23-Sep-2026 19:20:03 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 23-Sep-2026 22:02:06 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 24-Sep-2026 08:58:27 | 24-Sep-2026 02:41:27 | 0 |  |  | Approver | Locate
AO-000288 | MM-ZTK-1F-ZWP21-STR-DWG-2323 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 38000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 11:06:27 | wisuda.c@jutal.com | 04-May-2026 11:46:29 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 14:27:16 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:40:34 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:02:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:26:41 | 19-May-2026 04:41:25 | 0 |  |  | Approver | Locate
AO-001448 | MM-ZTK-1F-ZWP21-STR-DWG-2323 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 38000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:43:14 | wisuda.c@jutal.com | 07-Aug-2026 16:03:01 | Jumpol Sudjitjul | 17-Aug-2026 |  | Sompop Singhatiraj | 19-Aug-2026 | 19-Aug-2026 15:26:10 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:51:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 18:10:07 | 24-Aug-2026 12:29:20 | 0 |  |  | Approver | Locate
AO-002144 | MM-ZTK-1F-ZWP21-STR-DWG-2323 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 38000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:04:58 | wisuda.c@jutal.com | 18-Sep-2026 17:02:17 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 23-Sep-2026 19:20:10 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 23-Sep-2026 22:03:09 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 24-Sep-2026 09:28:02 | 24-Sep-2026 03:08:13 | 0 |  |  | Approver | Locate
AO-000288 | MM-ZTK-1F-ZWP21-STR-DWG-2324 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 52000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 11:06:52 | wisuda.c@jutal.com | 04-May-2026 11:46:41 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 14:30:12 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:41:40 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:02:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:09:08 | 19-May-2026 04:13:34 | 0 |  |  | Approver | Locate
AO-001448 | MM-ZTK-1F-ZWP21-STR-DWG-2324 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 52000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:43:42 | wisuda.c@jutal.com | 07-Aug-2026 16:04:16 | Jumpol Sudjitjul | 17-Aug-2026 |  | Sompop Singhatiraj | 19-Aug-2026 | 10-Aug-2026 13:39:40 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 12-Aug-2026 01:18:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 13-Aug-2026 12:56:49 | 13-Aug-2026 06:15:39 | 0 |  |  | Approver | Locate
AO-002144 | MM-ZTK-1F-ZWP21-STR-DWG-2324 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 52000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:05:29 | wisuda.c@jutal.com | 18-Sep-2026 17:02:23 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 23-Sep-2026 19:29:44 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 23-Sep-2026 22:04:53 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 24-Sep-2026 09:29:58 | 24-Sep-2026 03:11:47 | 0 |  |  | Approver | Locate
AO-000288 | MM-ZTK-1F-ZWP21-STR-DWG-2325 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 66000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 11:07:14 | wisuda.c@jutal.com | 04-May-2026 11:46:53 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 14:32:22 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:41:49 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:03:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:23:59 | 19-May-2026 04:25:57 | 0 |  |  | Approver | Locate
AO-001448 | MM-ZTK-1F-ZWP21-STR-DWG-2325 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 66000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:44:11 | wisuda.c@jutal.com | 07-Aug-2026 16:04:23 | Jumpol Sudjitjul | 17-Aug-2026 |  | Sompop Singhatiraj | 19-Aug-2026 | 10-Aug-2026 13:39:51 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 12-Aug-2026 01:18:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 13-Aug-2026 12:57:36 | 13-Aug-2026 06:17:00 | 0 |  |  | Approver | Locate
AO-002144 | MM-ZTK-1F-ZWP21-STR-DWG-2325 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 66000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:06:01 | wisuda.c@jutal.com | 18-Sep-2026 17:02:23 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 23-Sep-2026 19:36:49 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 23-Sep-2026 22:12:47 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 24-Sep-2026 09:30:56 | 24-Sep-2026 03:14:09 | 0 |  |  | Approver | Locate
AO-000288 | MM-ZTK-1F-ZWP21-STR-DWG-2326 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 79500 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 11:07:37 | wisuda.c@jutal.com | 04-May-2026 12:48:51 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 14:35:02 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:41:59 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:04:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:21:17 | 19-May-2026 04:24:44 | 0 |  |  | Approver | Locate
AO-001448 | MM-ZTK-1F-ZWP21-STR-DWG-2326 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 79500 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:44:37 | wisuda.c@jutal.com | 07-Aug-2026 16:04:26 | Jumpol Sudjitjul | 17-Aug-2026 |  | Sompop Singhatiraj | 19-Aug-2026 | 10-Aug-2026 13:41:44 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 12-Aug-2026 01:19:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 13-Aug-2026 12:47:35 | 13-Aug-2026 06:13:15 | 0 |  |  | Approver | Locate
AO-002144 | MM-ZTK-1F-ZWP21-STR-DWG-2326 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 79500 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:06:28 | wisuda.c@jutal.com | 18-Sep-2026 17:02:16 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 23-Sep-2026 19:28:44 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 23-Sep-2026 22:04:28 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 24-Sep-2026 09:31:30 | 24-Sep-2026 03:15:23 | 0 |  |  | Approver | Locate
AO-000288 | MM-ZTK-1F-ZWP21-STR-DWG-2327 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 93000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 11:08:00 | wisuda.c@jutal.com | 04-May-2026 12:49:03 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 14:42:16 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:43:07 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:05:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:20:19 | 19-May-2026 04:22:18 | 0 |  |  | Approver | Locate
AO-001448 | MM-ZTK-1F-ZWP21-STR-DWG-2327 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 93000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:45:04 | wisuda.c@jutal.com | 07-Aug-2026 16:04:20 | Jumpol Sudjitjul | 17-Aug-2026 |  | Sompop Singhatiraj | 19-Aug-2026 | 19-Aug-2026 15:25:51 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:50:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 18:15:00 | 24-Aug-2026 12:34:29 | 0 |  |  | Approver | Locate
AO-002144 | MM-ZTK-1F-ZWP21-STR-DWG-2327 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 93000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:06:54 | wisuda.c@jutal.com | 18-Sep-2026 17:02:21 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 23-Sep-2026 19:37:32 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 23-Sep-2026 22:13:44 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 24-Sep-2026 09:31:54 | 24-Sep-2026 03:16:36 | 0 |  |  | Approver | Locate
AO-000288 | MM-ZTK-1F-ZWP21-STR-DWG-2328 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 107000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 11:08:26 | wisuda.c@jutal.com | 04-May-2026 12:05:02 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 14:45:45 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:43:18 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:05:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:19:09 | 19-May-2026 04:37:18 | 0 |  |  | Approver | Locate
AO-001448 | MM-ZTK-1F-ZWP21-STR-DWG-2328 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 107000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:45:32 | wisuda.c@jutal.com | 07-Aug-2026 16:04:26 | Jumpol Sudjitjul | 17-Aug-2026 |  | Sompop Singhatiraj | 19-Aug-2026 | 19-Aug-2026 15:28:19 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:52:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 18:13:55 | 24-Aug-2026 12:33:11 | 0 |  |  | Approver | Locate
AO-002144 | MM-ZTK-1F-ZWP21-STR-DWG-2328 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 107000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:07:23 | wisuda.c@jutal.com | 18-Sep-2026 17:02:20 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 23-Sep-2026 19:30:11 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 23-Sep-2026 22:05:53 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 24-Sep-2026 09:35:53 | 24-Sep-2026 03:17:45 | 0 |  |  | Approver | Locate
AO-000288 | MM-ZTK-1F-ZWP21-STR-DWG-2329 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 121000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 11:08:50 | wisuda.c@jutal.com | 04-May-2026 12:05:14 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 14:49:04 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:43:25 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:06:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:17:41 | 19-May-2026 04:36:04 | 0 |  |  | Approver | Locate
AO-001448 | MM-ZTK-1F-ZWP21-STR-DWG-2329 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 121000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:45:58 | wisuda.c@jutal.com | 07-Aug-2026 16:04:24 | Jumpol Sudjitjul | 17-Aug-2026 |  | Sompop Singhatiraj | 19-Aug-2026 | 19-Aug-2026 15:29:22 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:54:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 18:13:27 | 24-Aug-2026 12:31:54 | 0 |  |  | Approver | Locate
AO-002144 | MM-ZTK-1F-ZWP21-STR-DWG-2329 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 121000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:07:57 | wisuda.c@jutal.com | 18-Sep-2026 17:02:18 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 23-Sep-2026 19:36:12 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 23-Sep-2026 22:11:27 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 24-Sep-2026 09:36:45 | 24-Sep-2026 03:18:54 | 0 |  |  | Approver | Locate
AO-000288 | MM-ZTK-1F-ZWP21-STR-DWG-2330 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 135000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 11:09:12 | wisuda.c@jutal.com | 04-May-2026 12:05:26 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 14:55:44 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:35:01 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:59:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:16:15 | 19-May-2026 04:34:41 | 0 |  |  | Approver | Locate
AO-001448 | MM-ZTK-1F-ZWP21-STR-DWG-2330 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 135000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:46:24 | wisuda.c@jutal.com | 07-Aug-2026 16:04:21 | Jumpol Sudjitjul | 17-Aug-2026 |  | Sompop Singhatiraj | 19-Aug-2026 | 19-Aug-2026 15:29:31 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:55:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 18:09:37 | 24-Aug-2026 12:28:03 | 0 |  |  | Approver | Locate
AO-002144 | MM-ZTK-1F-ZWP21-STR-DWG-2330 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 135000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:08:30 | wisuda.c@jutal.com | 18-Sep-2026 17:02:20 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 23-Sep-2026 19:35:40 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 23-Sep-2026 22:10:41 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 24-Sep-2026 09:30:47 | 24-Sep-2026 03:12:59 | 0 |  |  | Approver | Locate
AO-000288 | MM-ZTK-1F-ZWP21-STR-DWG-2331 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 149000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 11:09:34 | wisuda.c@jutal.com | 04-May-2026 12:05:38 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 15:11:59 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:45:24 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:06:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:12:55 | 19-May-2026 04:31:58 | 0 |  |  | Approver | Locate
AO-001448 | MM-ZTK-1F-ZWP21-STR-DWG-2331 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 149000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:46:52 | wisuda.c@jutal.com | 07-Aug-2026 16:04:29 | Jumpol Sudjitjul | 17-Aug-2026 |  | Sompop Singhatiraj | 19-Aug-2026 | 19-Aug-2026 15:30:28 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 21-Aug-2026 18:56:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 24-Aug-2026 18:13:01 | 24-Aug-2026 12:30:36 | 0 |  |  | Approver | Locate
AO-002144 | MM-ZTK-1F-ZWP21-STR-DWG-2331 | ZWP21 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 149000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:09:05 | wisuda.c@jutal.com | 18-Sep-2026 17:02:28 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 23-Sep-2026 19:33:10 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 23-Sep-2026 22:08:11 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 24-Sep-2026 09:29:53 | 24-Sep-2026 03:10:33 | 0 |  |  | Approver | Locate
AO-000288 | MM-ZTK-1F-ZWP21-STR-DWG-2332 | ZWP21 JACKET - ANODE DISTRIBUTION OF PILE CLUSTER |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 11:09:59 | wisuda.c@jutal.com | 04-May-2026 11:59:39 | Jumpol Sudjitjul | 11-May-2026 | 06-May-2026 15:14:50 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:27:35 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:58:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:10:12 | 19-May-2026 04:30:41 | 0 |  |  | Approver | Locate
AO-001448 | MM-ZTK-1F-ZWP21-STR-DWG-2332 | ZWP21 JACKET - ANODE DISTRIBUTION OF PILE CLUSTER |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 15:47:22 | wisuda.c@jutal.com | 07-Aug-2026 16:04:28 | Jumpol Sudjitjul | 17-Aug-2026 |  | Sompop Singhatiraj | 19-Aug-2026 | 10-Aug-2026 10:19:31 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 12-Aug-2026 01:16:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 13-Aug-2026 13:00:08 | 13-Aug-2026 06:11:58 | 0 |  |  | Approver | Locate
AO-002144 | MM-ZTK-1F-ZWP21-STR-DWG-2332 | ZWP21 JACKET - ANODE DISTRIBUTION OF PILE CLUSTER |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:09:34 | wisuda.c@jutal.com | 18-Sep-2026 17:02:20 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 23-Sep-2026 19:32:49 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 23-Sep-2026 22:06:47 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 24-Sep-2026 09:28:11 | 24-Sep-2026 03:09:21 | 0 |  |  | Approver | Locate
AO-000822 | MM-ZTK-1F-ZWP21-STR-DWG-2801 | ZWP21 JACKET RISER AND RISER SUPPORT LOCATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 10:02:52 | wisuda.c@jutal.com | 18-Jun-2026 10:06:02 | Jumpol Sudjitjul | 25-Jun-2026 | 18-Jun-2026 15:57:07 | Sompop Singhatiraj | 29-Jun-2026 | 19-Jun-2026 17:04:26 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 20-Jun-2026 17:24:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 21-Jun-2026 21:30:40 | 22-Jun-2026 00:53:47 | 0 |  |  | Approver | Locate
AO-001660 | MM-ZTK-1F-ZWP21-STR-DWG-2801 | ZWP21 JACKET RISER AND RISER SUPPORT LOCATION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 10:48:23 | wisuda.c@jutal.com | 24-Aug-2026 20:32:57 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 03-Sep-2026 08:19:44 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:57:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:03:09 | 07-Sep-2026 12:10:00 | 0 |  |  | Approver | Locate
AO-002361 | MM-ZTK-1F-ZWP21-STR-DWG-2801 | ZWP21 JACKET RISER AND RISER SUPPORT LOCATION |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 05-Oct-2026 10:08:12 | wisuda.c@jutal.com | 05-Oct-2026 10:25:13 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 |  | Pornlert Wanaphattharaphan | 16-Oct-2026 |  |  |  |  | 19-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001657 | MM-ZTK-1F-ZWP21-STR-DWG-2802 | ZWP21 JACKET - 18" RISER CLAMP DETAILS - HANGER CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 10:48:55 | wisuda.c@jutal.com | 24-Aug-2026 20:39:59 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 25-Aug-2026 15:06:53 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 17:26:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 21:17:22 | 30-Aug-2026 14:27:57 | 0 |  |  | Approver | Locate
AO-002359 | MM-ZTK-1F-ZWP21-STR-DWG-2802 | ZWP21 JACKET - 18" RISER CLAMP DETAILS - HANGER CLAMP |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 05-Oct-2026 09:17:26 | wisuda.c@jutal.com | 05-Oct-2026 09:55:40 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 |  | Pornlert Wanaphattharaphan | 16-Oct-2026 |  |  |  |  | 19-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001657 | MM-ZTK-1F-ZWP21-STR-DWG-2803 | ZWP21 JACKET - 18" RISER CLAMP DETAILS - SLIDING CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 09:50:55 | wisuda.c@jutal.com | 24-Aug-2026 20:39:59 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 25-Aug-2026 15:08:46 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 17:28:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 21:17:57 | 30-Aug-2026 14:25:19 | 0 |  |  | Approver | Locate
AO-002359 | MM-ZTK-1F-ZWP21-STR-DWG-2803 | ZWP21 JACKET - 18" RISER CLAMP DETAILS - SLIDING CLAMP |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 05-Oct-2026 09:18:02 | wisuda.c@jutal.com | 05-Oct-2026 09:55:42 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 |  | Pornlert Wanaphattharaphan | 16-Oct-2026 |  |  |  |  | 19-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001657 | MM-ZTK-1F-ZWP21-STR-DWG-2804 | ZWP21 JACKET - 18" RISER CLAMP DETAILS - SLIDING CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 10:49:25 | wisuda.c@jutal.com | 24-Aug-2026 20:39:59 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 25-Aug-2026 15:10:47 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 17:43:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 21:18:20 | 30-Aug-2026 14:29:09 | 0 |  |  | Approver | Locate
AO-002359 | MM-ZTK-1F-ZWP21-STR-DWG-2804 | ZWP21 JACKET - 18" RISER CLAMP DETAILS - SLIDING CLAMP |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 05-Oct-2026 09:18:36 | wisuda.c@jutal.com | 05-Oct-2026 09:55:40 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 |  | Pornlert Wanaphattharaphan | 16-Oct-2026 |  |  |  |  | 19-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001657 | MM-ZTK-1F-ZWP21-STR-DWG-2805 | ZWP21 JACKET - 18" RISER CLAMP DETAILS - TEMPORARY CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 10:49:52 | wisuda.c@jutal.com | 24-Aug-2026 20:40:05 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 25-Aug-2026 15:11:14 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 17:58:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 21:20:08 | 30-Aug-2026 14:30:18 | 0 |  |  | Approver | Locate
AO-002359 | MM-ZTK-1F-ZWP21-STR-DWG-2805 | ZWP21 JACKET - 18" RISER CLAMP DETAILS - TEMPORARY CLAMP |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 05-Oct-2026 09:19:10 | wisuda.c@jutal.com | 05-Oct-2026 09:55:42 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 |  | Pornlert Wanaphattharaphan | 16-Oct-2026 |  |  |  |  | 19-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001657 | MM-ZTK-1F-ZWP21-STR-DWG-2806 | ZWP21 JACKET - 10" RISER CLAMP DETAILS - HANGER CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 10:50:20 | wisuda.c@jutal.com | 24-Aug-2026 20:39:59 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 25-Aug-2026 15:12:05 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 18:06:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 21:21:06 | 30-Aug-2026 14:55:35 | 0 |  |  | Approver | Locate
AO-002359 | MM-ZTK-1F-ZWP21-STR-DWG-2806 | ZWP21 JACKET - 10" RISER CLAMP DETAILS - HANGER CLAMP |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 05-Oct-2026 09:19:52 | wisuda.c@jutal.com | 05-Oct-2026 09:55:41 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 |  | Pornlert Wanaphattharaphan | 16-Oct-2026 |  |  |  |  | 19-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001657 | MM-ZTK-1F-ZWP21-STR-DWG-2807 | ZWP21 JACKET - 10" RISER CLAMP DETAILS - SLIDING CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 09:51:30 | wisuda.c@jutal.com | 24-Aug-2026 20:40:01 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 25-Aug-2026 15:14:10 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 18:07:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 21:21:49 | 30-Aug-2026 14:50:48 | 0 |  |  | Approver | Locate
AO-002359 | MM-ZTK-1F-ZWP21-STR-DWG-2807 | ZWP21 JACKET - 10" RISER CLAMP DETAILS - SLIDING CLAMP |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 05-Oct-2026 09:20:39 | wisuda.c@jutal.com | 05-Oct-2026 09:55:43 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 |  | Pornlert Wanaphattharaphan | 16-Oct-2026 |  |  |  |  | 19-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001657 | MM-ZTK-1F-ZWP21-STR-DWG-2808 | ZWP21 JACKET - 10" RISER CLAMP DETAILS - SLIDING CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 10:50:47 | wisuda.c@jutal.com | 24-Aug-2026 20:40:00 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 25-Aug-2026 15:13:47 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 18:07:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 21:23:50 | 30-Aug-2026 14:56:45 | 0 |  |  | Approver | Locate
AO-002359 | MM-ZTK-1F-ZWP21-STR-DWG-2808 | ZWP21 JACKET - 10" RISER CLAMP DETAILS - SLIDING CLAMP |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 05-Oct-2026 09:21:09 | wisuda.c@jutal.com | 05-Oct-2026 09:55:42 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 |  | Pornlert Wanaphattharaphan | 16-Oct-2026 |  |  |  |  | 19-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001710 | MM-ZTK-1F-ZWP21-STR-DWG-2809 | ZWP21 JACKET - 10" RISER CLAMP DETAILS - TEMPORARY CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 25-Aug-2026 18:33:57 | wisuda.c@jutal.com | 26-Aug-2026 10:02:38 | Jumpol Sudjitjul | 02-Sep-2026 |  | Sompop Singhatiraj | 04-Sep-2026 | 27-Aug-2026 13:06:37 | Pornlert Wanaphattharaphan | 07-Sep-2026 | 31-Aug-2026 00:20:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Sep-2026 | 31-Aug-2026 16:09:51 | 31-Aug-2026 10:07:45 | 0 |  |  | Approver | Locate
AO-002359 | MM-ZTK-1F-ZWP21-STR-DWG-2809 | ZWP21 JACKET - 10" RISER CLAMP DETAILS - TEMPORARY CLAMP |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 05-Oct-2026 09:21:39 | wisuda.c@jutal.com | 05-Oct-2026 09:55:44 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 |  | Pornlert Wanaphattharaphan | 16-Oct-2026 |  |  |  |  | 19-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000740 | MM-ZTK-1F-ZWP21-STR-DWG-2900 | ZWP21 JACKET - CLOSURE PLATE DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 18:13:52 | wisuda.c@jutal.com | 12-Jun-2026 10:14:21 | Jumpol Sudjitjul | 19-Jun-2026 |  | Sompop Singhatiraj | 23-Jun-2026 | 15-Jun-2026 16:57:40 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 18-Jun-2026 19:58:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 19-Jun-2026 08:56:12 | 19-Jun-2026 02:37:53 | 0 |  |  | Approver | Locate
AO-001895 | MM-ZTK-1F-ZWP21-STR-DWG-2900 | ZWP21 JACKET - CLOSURE PLATE DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:22:22 | wisuda.c@jutal.com | 08-Sep-2026 08:56:51 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 15:53:04 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 13:16:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:22:14 | 20-Sep-2026 13:11:40 | 0 |  |  | Approver | Locate
AO-002413 | MM-ZTK-1F-ZWP21-STR-DWG-2900 | ZWP21 JACKET - CLOSURE PLATE DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 08-Oct-2026 09:17:47 | wisuda.c@jutal.com | 08-Oct-2026 10:32:11 | Jumpol Sudjitjul | 16-Oct-2026 |  | Sompop Singhatiraj | 20-Oct-2026 | 08-Oct-2026 15:01:20 | Pornlert Wanaphattharaphan | 21-Oct-2026 | 11-Oct-2026 00:21:53 | APPR | Approved | Jumpol Sudjitjul | 22-Oct-2026 | 11-Oct-2026 10:07:39 | 11-Oct-2026 03:48:26 | 0 |  |  | Approver | Locate
AO-000740 | MM-ZTK-1F-ZWP21-STR-DWG-2901 | ZWP21 JACKET - CLOSURE PLATE DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 18:14:16 | wisuda.c@jutal.com | 12-Jun-2026 10:14:21 | Jumpol Sudjitjul | 19-Jun-2026 |  | Sompop Singhatiraj | 23-Jun-2026 | 15-Jun-2026 16:57:53 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 18-Jun-2026 20:04:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 19-Jun-2026 08:55:47 | 19-Jun-2026 02:35:22 | 0 |  |  | Approver | Locate
AO-001895 | MM-ZTK-1F-ZWP21-STR-DWG-2901 | ZWP21 JACKET - CLOSURE PLATE DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:22:52 | wisuda.c@jutal.com | 08-Sep-2026 08:57:10 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 15:54:48 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 13:17:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:22:57 | 20-Sep-2026 13:12:50 | 0 |  |  | Approver | Locate
AO-002415 | MM-ZTK-1F-ZWP21-STR-DWG-2901 | ZWP21 JACKET - CLOSURE PLATE DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 08-Oct-2026 09:18:29 | wisuda.c@jutal.com | 08-Oct-2026 10:32:11 | Jumpol Sudjitjul | 16-Oct-2026 |  | Sompop Singhatiraj | 20-Oct-2026 | 08-Oct-2026 15:18:19 | Pornlert Wanaphattharaphan | 21-Oct-2026 | 11-Oct-2026 00:23:28 | APPR | Approved | Jumpol Sudjitjul | 22-Oct-2026 | 11-Oct-2026 10:08:09 | 11-Oct-2026 03:49:34 | 0 |  |  | Approver | Locate
AO-000512 | MM-ZTK-1F-ZWP21-STR-DWG-2902 | ZWP21 JACKET - LEG PARTITION DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 13:33:14 | wisuda.c@jutal.com | 19-May-2026 13:43:01 | Jumpol Sudjitjul | 26-May-2026 |  | Sompop Singhatiraj | 28-May-2026 | 25-May-2026 16:03:08 | Pornlert Wanaphattharaphan | 29-May-2026 | 25-May-2026 20:50:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 25-May-2026 21:14:50 | 25-May-2026 14:28:57 | 0 |  |  | Approver | Locate
AO-001774 | MM-ZTK-1F-ZWP21-STR-DWG-2902 | ZWP21 JACKET - LEG PARTITION DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:28:21 | wisuda.c@jutal.com | 31-Aug-2026 11:08:01 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 03-Sep-2026 09:23:21 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 04-Sep-2026 23:48:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 05-Sep-2026 18:06:04 | 05-Sep-2026 11:59:27 | 0 |  |  | Approver | Locate
AO-002416 | MM-ZTK-1F-ZWP21-STR-DWG-2902 | ZWP21 JACKET - LEG PARTITION DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 08-Oct-2026 09:19:06 | wisuda.c@jutal.com | 08-Oct-2026 10:32:14 | Jumpol Sudjitjul | 16-Oct-2026 |  | Sompop Singhatiraj | 20-Oct-2026 | 08-Oct-2026 15:24:28 | Pornlert Wanaphattharaphan | 21-Oct-2026 | 11-Oct-2026 00:24:34 | APPR | Approved | Jumpol Sudjitjul | 22-Oct-2026 | 11-Oct-2026 10:50:26 | 11-Oct-2026 03:56:26 | 0 |  |  | Approver | Locate
AO-000744 | MM-ZTK-1F-ZWP21-STR-DWG-2911 | ZWP21 JACKET - UPENDING ARRANGEMENT AND DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 12-Jun-2026 08:39:28 | wisuda.c@jutal.com | 12-Jun-2026 10:37:42 | Jumpol Sudjitjul | 19-Jun-2026 |  | Sompop Singhatiraj | 23-Jun-2026 | 15-Jun-2026 17:41:54 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 18-Jun-2026 20:18:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 19-Jun-2026 08:55:16 | 19-Jun-2026 02:30:05 | 0 |  |  | Approver | Locate
AO-002302 | MM-ZTK-1F-ZWP21-STR-DWG-2911 | ZWP21 JACKET - UPENDING ARRANGEMENT AND DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 28-Sep-2026 17:59:47 | wisuda.c@jutal.com | 29-Sep-2026 14:26:44 | Jumpol Sudjitjul | 06-Oct-2026 |  | Sompop Singhatiraj | 08-Oct-2026 | 06-Oct-2026 09:33:08 | Pornlert Wanaphattharaphan | 09-Oct-2026 | 10-Oct-2026 01:37:43 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 12-Oct-2026 | 10-Oct-2026 17:34:57 | 10-Oct-2026 10:55:14 | 0 |  |  | Approver | Locate
AO-000330 | MM-ZTK-1F-ZWP21-STR-DWG-2931 | ZWP21 JACKET - BALLAST / DEBALLAST SCHEMATIC |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 06-May-2026 16:35:33 | wisuda.c@jutal.com | 06-May-2026 17:16:30 | Jumpol Sudjitjul | 14-May-2026 |  | Sompop Singhatiraj | 18-May-2026 | 16-May-2026 11:50:47 | Pornlert Wanaphattharaphan | 19-May-2026 | 19-May-2026 00:32:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-May-2026 | 19-May-2026 10:07:18 | 19-May-2026 04:09:58 | 0 |  |  | Approver | Locate
AO-001660 | MM-ZTK-1F-ZWP21-STR-DWG-2931 | ZWP21 JACKET - BALLAST / DEBALLAST SCHEMATIC |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 10:51:20 | wisuda.c@jutal.com | 24-Aug-2026 20:32:49 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 03-Sep-2026 12:42:55 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 01:00:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:02:44 | 07-Sep-2026 12:08:35 | 0 |  |  | Approver | Locate
AO-000331 | MM-ZTK-1F-ZWP21-STR-DWG-2932 | ZWP21 JACKET - GROUTING SCHEMATIC |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 06-May-2026 16:36:00 | wisuda.c@jutal.com | 06-May-2026 17:16:46 | Jumpol Sudjitjul | 14-May-2026 |  | Sompop Singhatiraj | 18-May-2026 | 16-May-2026 11:50:57 | Pornlert Wanaphattharaphan | 19-May-2026 | 19-May-2026 00:26:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 20-May-2026 | 19-May-2026 10:03:53 | 19-May-2026 04:06:13 | 0 |  |  | Approver | Locate
AO-001660 | MM-ZTK-1F-ZWP21-STR-DWG-2932 | ZWP21 JACKET - GROUTING SCHEMATIC |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 10:51:48 | wisuda.c@jutal.com | 24-Aug-2026 20:32:58 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 03-Sep-2026 11:32:45 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 04-Sep-2026 23:28:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 05-Sep-2026 18:07:59 | 05-Sep-2026 11:46:51 | 0 |  |  | Approver | Locate
AO-000835 | MM-ZTK-1F-ZWP21-STR-DWG-2933 | ZWP21 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT ROW A ELEVATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 09:25:15 | wisuda.c@jutal.com | 19-Jun-2026 10:18:05 | Jumpol Sudjitjul | 26-Jun-2026 |  | Sompop Singhatiraj | 30-Jun-2026 | 22-Jun-2026 16:30:41 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 22-Jun-2026 16:55:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 22-Jun-2026 16:57:29 | 22-Jun-2026 10:15:58 | 0 |  |  | Approver | Locate
AO-001774 | MM-ZTK-1F-ZWP21-STR-DWG-2933 | ZWP21 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT ROW A ELEVATION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:28:53 | wisuda.c@jutal.com | 31-Aug-2026 11:08:01 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 03-Sep-2026 13:55:18 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 04-Sep-2026 23:30:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 05-Sep-2026 18:08:25 | 05-Sep-2026 12:00:52 | 0 |  |  | Approver | Locate
AO-000835 | MM-ZTK-1F-ZWP21-STR-DWG-2934 | ZWP21 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT ROW B ELEVATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 09:25:40 | wisuda.c@jutal.com | 19-Jun-2026 10:18:35 | Jumpol Sudjitjul | 26-Jun-2026 |  | Sompop Singhatiraj | 30-Jun-2026 | 23-Jun-2026 06:53:09 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 23-Jun-2026 23:06:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 24-Jun-2026 13:47:13 | 24-Jun-2026 07:24:33 | 0 |  |  | Approver | Locate
AO-001774 | MM-ZTK-1F-ZWP21-STR-DWG-2934 | ZWP21 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT ROW B ELEVATION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:29:26 | wisuda.c@jutal.com | 31-Aug-2026 11:08:00 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 03-Sep-2026 13:55:29 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 04-Sep-2026 23:30:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 05-Sep-2026 18:08:50 | 05-Sep-2026 12:02:15 | 0 |  |  | Approver | Locate
AO-000835 | MM-ZTK-1F-ZWP21-STR-DWG-2935 | ZWP21 JACKET - BALLAST AND GROUTING SYSTEM SUPPORT DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 09:26:08 | wisuda.c@jutal.com | 19-Jun-2026 10:18:50 | Jumpol Sudjitjul | 26-Jun-2026 |  | Sompop Singhatiraj | 30-Jun-2026 | 22-Jun-2026 16:36:15 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 22-Jun-2026 22:23:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 23-Jun-2026 09:42:41 | 23-Jun-2026 03:47:57 | 0 |  |  | Approver | Locate
AO-000835 | MM-ZTK-1F-ZWP21-STR-DWG-2936 | ZWP21 JACKET - BALLAST AND GROUTING SYSTEM SUPPORT DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 09:26:33 | wisuda.c@jutal.com | 19-Jun-2026 10:19:04 | Jumpol Sudjitjul | 26-Jun-2026 |  | Sompop Singhatiraj | 30-Jun-2026 | 22-Jun-2026 16:37:17 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 22-Jun-2026 22:21:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 23-Jun-2026 09:42:09 | 23-Jun-2026 03:49:20 | 0 |  |  | Approver | Locate
AO-000835 | MM-ZTK-1F-ZWP21-STR-DWG-2937 | ZWP21 JACKET - BALLAST SYSTEM VALVE DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 09:26:58 | wisuda.c@jutal.com | 19-Jun-2026 10:19:19 | Jumpol Sudjitjul | 26-Jun-2026 |  | Sompop Singhatiraj | 30-Jun-2026 | 22-Jun-2026 16:38:22 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 22-Jun-2026 17:06:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 23-Jun-2026 09:41:34 | 23-Jun-2026 03:50:37 | 0 |  |  | Approver | Locate
AO-000835 | MM-ZTK-1F-ZWP21-STR-DWG-2938 | ZWP21 JACKET -GROUT, SKIRT SLEEVE VENT AND FLOODING DETAILS AT SKIRT PILE SLEEVE SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 09:27:24 | wisuda.c@jutal.com | 19-Jun-2026 10:21:08 | Jumpol Sudjitjul | 26-Jun-2026 |  | Sompop Singhatiraj | 30-Jun-2026 | 22-Jun-2026 16:38:57 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 22-Jun-2026 17:01:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 23-Jun-2026 09:41:12 | 23-Jun-2026 03:51:51 | 0 |  |  | Approver | Locate
AO-000835 | MM-ZTK-1F-ZWP21-STR-DWG-2939 | ZWP21 JACKET -GROUT, SKIRT SLEEVE VENT AND FLOODING DETAILS AT SKIRT PILE SLEEVE SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 09:28:00 | wisuda.c@jutal.com | 19-Jun-2026 10:21:22 | Jumpol Sudjitjul | 26-Jun-2026 |  | Sompop Singhatiraj | 30-Jun-2026 | 22-Jun-2026 16:39:36 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 22-Jun-2026 17:00:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 23-Jun-2026 09:40:53 | 23-Jun-2026 03:53:05 | 0 |  |  | Approver | Locate
AO-000835 | MM-ZTK-1F-ZWP21-STR-DWG-2940 | ZWP21 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT EL(+) 8000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 09:28:31 | wisuda.c@jutal.com | 19-Jun-2026 10:25:46 | Jumpol Sudjitjul | 26-Jun-2026 |  | Sompop Singhatiraj | 30-Jun-2026 | 22-Jun-2026 15:08:11 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 22-Jun-2026 16:47:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 22-Jun-2026 16:50:23 | 22-Jun-2026 10:14:30 | 0 |  |  | Approver | Locate
AO-000835 | MM-ZTK-1F-ZWP21-STR-DWG-2941 | ZWP21 JACKET - GROUT SYSTEM DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-Jun-2026 09:29:06 | wisuda.c@jutal.com | 19-Jun-2026 10:25:30 | Jumpol Sudjitjul | 26-Jun-2026 |  | Sompop Singhatiraj | 30-Jun-2026 | 22-Jun-2026 15:09:49 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 22-Jun-2026 16:53:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 22-Jun-2026 16:56:23 | 22-Jun-2026 10:07:34 | 0 |  |  | Approver | Locate
AO-000822 | MM-ZTK-1F-ZWP21-STR-DWG-2971 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 10:03:37 | wisuda.c@jutal.com | 18-Jun-2026 10:34:58 | Jumpol Sudjitjul | 25-Jun-2026 |  | Sompop Singhatiraj | 29-Jun-2026 | 22-Jun-2026 17:17:32 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 22-Jun-2026 22:26:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 23-Jun-2026 09:40:28 | 23-Jun-2026 03:00:50 | 0 |  |  | Approver | Locate
AO-001517 | MM-ZTK-1F-ZWP21-STR-DWG-2971 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 16:59:00 | wisuda.c@jutal.com | 13-Aug-2026 17:00:16 | Jumpol Sudjitjul | 20-Aug-2026 |  | Sompop Singhatiraj | 24-Aug-2026 | 20-Aug-2026 13:03:15 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 21-Aug-2026 20:09:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Aug-2026 | 24-Aug-2026 18:12:11 | 24-Aug-2026 12:09:10 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP21-STR-DWG-2971 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 09:25:42 | wisuda.c@jutal.com | 14-Oct-2026 09:45:05 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 13:27:39 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:21:55 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 14:50:36 | 16-Oct-2026 08:08:29 | 0 |  |  | Approver | Locate
AO-000822 | MM-ZTK-1F-ZWP21-STR-DWG-2972 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 10:04:08 | wisuda.c@jutal.com | 18-Jun-2026 10:35:17 | Jumpol Sudjitjul | 25-Jun-2026 |  | Sompop Singhatiraj | 29-Jun-2026 | 22-Jun-2026 17:18:21 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 22-Jun-2026 22:31:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 23-Jun-2026 09:31:02 | 23-Jun-2026 02:58:10 | 0 |  |  | Approver | Locate
AO-001517 | MM-ZTK-1F-ZWP21-STR-DWG-2972 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 16:59:26 | wisuda.c@jutal.com | 13-Aug-2026 17:11:51 | Jumpol Sudjitjul | 21-Aug-2026 | 14-Aug-2026 16:26:42 | Sompop Singhatiraj | 25-Aug-2026 | 20-Aug-2026 13:00:28 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 23-Aug-2026 17:19:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 18:11:42 | 24-Aug-2026 12:07:56 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP21-STR-DWG-2972 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 09:26:17 | wisuda.c@jutal.com | 14-Oct-2026 09:45:10 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 13:28:28 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:22:49 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 14:52:00 | 16-Oct-2026 08:10:55 | 0 |  |  | Approver | Locate
AO-000822 | MM-ZTK-1F-ZWP21-STR-DWG-2973 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 10:04:38 | wisuda.c@jutal.com | 18-Jun-2026 10:35:32 | Jumpol Sudjitjul | 25-Jun-2026 |  | Sompop Singhatiraj | 29-Jun-2026 | 22-Jun-2026 17:19:28 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 22-Jun-2026 22:32:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 23-Jun-2026 09:29:41 | 23-Jun-2026 02:56:51 | 0 |  |  | Approver | Locate
AO-001517 | MM-ZTK-1F-ZWP21-STR-DWG-2973 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 16:59:54 | wisuda.c@jutal.com | 13-Aug-2026 17:11:48 | Jumpol Sudjitjul | 21-Aug-2026 | 14-Aug-2026 16:25:00 | Sompop Singhatiraj | 25-Aug-2026 | 20-Aug-2026 13:03:25 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 23-Aug-2026 17:21:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 18:11:15 | 24-Aug-2026 12:06:37 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP21-STR-DWG-2973 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 3 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 09:26:53 | wisuda.c@jutal.com | 14-Oct-2026 09:45:06 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 13:28:32 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:23:18 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 14:53:07 | 16-Oct-2026 08:12:06 | 0 |  |  | Approver | Locate
AO-000822 | MM-ZTK-1F-ZWP21-STR-DWG-2974 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 10:05:12 | wisuda.c@jutal.com | 18-Jun-2026 10:35:45 | Jumpol Sudjitjul | 25-Jun-2026 |  | Sompop Singhatiraj | 29-Jun-2026 | 22-Jun-2026 17:23:50 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 22-Jun-2026 22:34:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 23-Jun-2026 09:26:04 | 23-Jun-2026 02:54:18 | 0 |  |  | Approver | Locate
AO-001517 | MM-ZTK-1F-ZWP21-STR-DWG-2974 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 4 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 17:00:41 | wisuda.c@jutal.com | 13-Aug-2026 17:11:48 | Jumpol Sudjitjul | 21-Aug-2026 | 14-Aug-2026 16:26:23 | Sompop Singhatiraj | 25-Aug-2026 | 20-Aug-2026 13:03:35 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 23-Aug-2026 17:29:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 18:04:24 | 24-Aug-2026 11:56:29 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP21-STR-DWG-2974 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 4 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 08:44:12 | wisuda.c@jutal.com | 14-Oct-2026 09:45:05 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 13:28:46 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:23:45 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 14:55:05 | 16-Oct-2026 08:17:08 | 0 |  |  | Approver | Locate
AO-000822 | MM-ZTK-1F-ZWP21-STR-DWG-2975 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 5 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 09:15:15 | wisuda.c@jutal.com | 18-Jun-2026 10:00:24 | Jumpol Sudjitjul | 25-Jun-2026 |  | Sompop Singhatiraj | 29-Jun-2026 | 22-Jun-2026 17:24:16 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 22-Jun-2026 22:35:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 23-Jun-2026 09:26:35 | 23-Jun-2026 02:55:37 | 0 |  |  | Approver | Locate
AO-001517 | MM-ZTK-1F-ZWP21-STR-DWG-2975 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 5 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 17:01:19 | wisuda.c@jutal.com | 13-Aug-2026 17:11:55 | Jumpol Sudjitjul | 21-Aug-2026 | 14-Aug-2026 16:29:48 | Sompop Singhatiraj | 25-Aug-2026 | 20-Aug-2026 13:00:38 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 23-Aug-2026 17:19:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 18:10:45 | 24-Aug-2026 12:05:21 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP21-STR-DWG-2975 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 5 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 08:44:45 | wisuda.c@jutal.com | 14-Oct-2026 09:45:09 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 13:28:38 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:24:10 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 14:55:55 | 16-Oct-2026 08:18:17 | 0 |  |  | Approver | Locate
AO-000822 | MM-ZTK-1F-ZWP21-STR-DWG-2976 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 6 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 09:15:41 | wisuda.c@jutal.com | 18-Jun-2026 10:00:47 | Jumpol Sudjitjul | 25-Jun-2026 |  | Sompop Singhatiraj | 29-Jun-2026 | 22-Jun-2026 17:25:19 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 22-Jun-2026 22:36:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 23-Jun-2026 09:25:31 | 23-Jun-2026 02:53:00 | 0 |  |  | Approver | Locate
AO-001517 | MM-ZTK-1F-ZWP21-STR-DWG-2976 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 6 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 13-Aug-2026 17:01:50 | wisuda.c@jutal.com | 13-Aug-2026 17:11:50 | Jumpol Sudjitjul | 21-Aug-2026 | 14-Aug-2026 16:27:06 | Sompop Singhatiraj | 25-Aug-2026 | 20-Aug-2026 13:04:50 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 23-Aug-2026 17:29:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 18:03:52 | 24-Aug-2026 11:55:13 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP21-STR-DWG-2976 | ZWP21 JACKET - WELD PROFILE CONTROL SHEET 6 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 08:45:17 | wisuda.c@jutal.com | 14-Oct-2026 09:45:08 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 13:28:44 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:24:36 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 14:59:07 | 16-Oct-2026 08:19:25 | 0 |  |  | Approver | Locate
AO-001165 | MM-ZTK-1F-ZWP21-STR-DWG-2981 | ZWP21 JACKET - LEG PAINT MARKING DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 10:36:16 | wisuda.c@jutal.com | 20-Jul-2026 15:36:01 | Jumpol Sudjitjul | 27-Jul-2026 |  | Sompop Singhatiraj | 31-Jul-2026 | 24-Jul-2026 10:20:17 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 22:38:28 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 15:07:48 | 27-Jul-2026 09:38:33 | 0 |  |  | Approver | Locate
AO-001638 | MM-ZTK-1F-ZWP21-STR-DWG-2981 | ZWP21 JACKET - LEG PAINT MARKING DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 10:25:39 | wisuda.c@jutal.com | 21-Aug-2026 10:59:12 | Jumpol Sudjitjul | 28-Aug-2026 |  | Sompop Singhatiraj | 01-Sep-2026 | 24-Aug-2026 15:51:59 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 29-Aug-2026 23:59:23 | APPR | Approved | Jumpol Sudjitjul | 03-Sep-2026 | 30-Aug-2026 16:54:35 | 30-Aug-2026 10:23:48 | 0 |  |  | Approver | Locate
AO-001165 | MM-ZTK-1F-ZWP21-STR-DWG-2982 | ZWP21 JACKET - LEG PAINT MARKING DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 10:36:44 | wisuda.c@jutal.com | 20-Jul-2026 15:36:32 | Jumpol Sudjitjul | 27-Jul-2026 |  | Sompop Singhatiraj | 31-Jul-2026 | 24-Jul-2026 10:23:35 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 22:39:03 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 15:08:22 | 27-Jul-2026 09:39:50 | 0 |  |  | Approver | Locate
AO-001638 | MM-ZTK-1F-ZWP21-STR-DWG-2982 | ZWP21 JACKET - LEG PAINT MARKING DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 10:26:13 | wisuda.c@jutal.com | 21-Aug-2026 10:59:14 | Jumpol Sudjitjul | 28-Aug-2026 |  | Sompop Singhatiraj | 01-Sep-2026 | 24-Aug-2026 15:50:27 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 29-Aug-2026 23:58:50 | APPR | Approved | Jumpol Sudjitjul | 03-Sep-2026 | 30-Aug-2026 16:53:35 | 30-Aug-2026 10:22:41 | 0 |  |  | Approver | Locate
AO-001165 | MM-ZTK-1F-ZWP21-STR-DWG-2991 | ZWP21 JACKET - JACKET TRANSPORTATION ARRANGEMENT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 10:37:14 | wisuda.c@jutal.com | 20-Jul-2026 15:38:12 | Jumpol Sudjitjul | 27-Jul-2026 |  | Sompop Singhatiraj | 31-Jul-2026 | 24-Jul-2026 10:23:57 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 22:42:53 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 15:09:29 | 27-Jul-2026 09:42:21 | 0 |  |  | Approver | Locate
AO-001638 | MM-ZTK-1F-ZWP21-STR-DWG-2991 | ZWP21 JACKET - JACKET TRANSPORTATION ARRANGEMENT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Aug-2026 10:26:46 | wisuda.c@jutal.com | 21-Aug-2026 10:59:12 | Jumpol Sudjitjul | 28-Aug-2026 |  | Sompop Singhatiraj | 01-Sep-2026 | 24-Aug-2026 15:49:02 | Pornlert Wanaphattharaphan | 02-Sep-2026 | 29-Aug-2026 23:58:07 | APPR | Approved | Jumpol Sudjitjul | 03-Sep-2026 | 30-Aug-2026 16:51:53 | 30-Aug-2026 11:04:40 | 0 |  |  | Approver | Locate
AO-001533 | MM-ZTK-1F-ZWP21-STR-DWG-2994 | ZWP21 JACKET - VORTEX SHEDDING PREVENTION - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 17:32:41 | wisuda.c@jutal.com | 14-Aug-2026 17:42:33 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 21-Aug-2026 15:47:11 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:30:55 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 18:10:13 | 24-Aug-2026 11:40:12 | 0 |  |  | Approver | Locate
AO-001534 | MM-ZTK-1F-ZWP21-STR-DWG-2995 | ZWP21 JACKET - VORTEX SHEDDING PREVENTION - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP21 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 17:33:07 | wisuda.c@jutal.com | 14-Aug-2026 17:42:47 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 21-Aug-2026 15:44:17 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:30:07 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 18:09:44 | 24-Aug-2026 11:38:56 | 0 |  |  | Approver | Locate
AO-000294 | MM-ZTK-1F-ZWP21-STR-MR-2001 | MATERIAL REǪUISITION FOR ZWP21 JACKET PRIMARY TUBULAR STEEL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 02:02:08 | wisuda.c@jutal.com | 04-May-2026 13:11:25 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 08:22:30 | Sompop Singhatiraj | 13-May-2026 | 15-May-2026 16:01:03 | Pornlert Wanaphattharaphan | 14-May-2026 | 15-May-2026 23:19:31 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 15-May-2026 | 17-May-2026 10:28:55 | 17-May-2026 11:02:21 | 0 |  |  | Approver | Locate
AO-000317 | MM-ZTK-1F-ZWP21-STR-MR-2002 | MATERIAL REǪUISITION FOR ZWP21 JACKET PRIMARY STEEL (PLATE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 06-May-2026 09:05:39 | wisuda.c@jutal.com | 06-May-2026 10:32:08 | Jumpol Sudjitjul | 13-May-2026 | 15-May-2026 07:39:18 | Sompop Singhatiraj | 15-May-2026 | 15-May-2026 16:49:04 | Pornlert Wanaphattharaphan | 18-May-2026 | 15-May-2026 23:33:14 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 19-May-2026 | 17-May-2026 10:27:49 | 17-May-2026 11:02:42 | 0 |  |  | Approver | Locate
AO-001065 | MM-ZTK-1F-ZWP21-STR-MR-2003 | MATERIAL REQUISITION FOR ZWP21 JACKET SECONDARY AND TERTIARY STEEL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | AFC | Approved for Construction |  | 10-Jul-2026 17:32:50 | wisuda.c@jutal.com | 10-Jul-2026 18:12:15 | Jumpol Sudjitjul | 20-Jul-2026 |  | Sompop Singhatiraj | 22-Jul-2026 | 13-Jul-2026 09:04:22 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 13-Jul-2026 22:33:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 14-Jul-2026 08:48:52 | 14-Jul-2026 02:21:09 | 0 |  |  | Approver | Locate
AO-001017 | MM-ZTK-1F-ZWP21-STR-MTO-2001 | ZWP21 JACKET PRIMARY STEEL AND PILE MTO REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 23:37:20 | wisuda.c@jutal.com | 04-Jul-2026 14:34:14 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 07-Jul-2026 09:51:53 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 08-Jul-2026 01:16:11 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 16-Jul-2026 | 08-Jul-2026 09:44:56 | 08-Jul-2026 03:22:31 | 0 |  |  | Approver | Locate
AO-001018 | MM-ZTK-1F-ZWP21-STR-MTO-2002 | ZWP21 JACKET SECONDARY AND TERTIARY STEEL MTO REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 23:37:51 | wisuda.c@jutal.com | 04-Jul-2026 14:34:32 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 07-Jul-2026 09:52:28 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 08-Jul-2026 01:16:54 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 16-Jul-2026 | 08-Jul-2026 09:44:15 | 08-Jul-2026 03:02:19 | 0 |  |  | Approver | Locate
AO-000761 | MM-ZTK-1F-ZWP21-STR-TBE-1001 | TECHNICAL BID EVALUATION FOR ZWP21 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 12-Jun-2026 19:52:01 | wisuda.c@jutal.com | 13-Jun-2026 07:29:00 | Jumpol Sudjitjul | 19-Jun-2026 |  | Sompop Singhatiraj | 23-Jun-2026 | 17-Jun-2026 14:52:35 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 18-Jun-2026 14:44:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 18-Jun-2026 14:49:04 | 18-Jun-2026 08:16:38 | 0 |  |  | Approver | Locate
AO-000952 | MM-ZTK-1F-ZWP21-STR-TBE-2001 | TECHNICAL BID EVALUATION FOR LAUNCH TIMBER |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 30-Jun-2026 10:30:51 | wisuda.c@jutal.com | 30-Jun-2026 14:23:27 | Jumpol Sudjitjul | 07-Jul-2026 |  | Sompop Singhatiraj | 09-Jul-2026 | 02-Jul-2026 08:11:13 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 04-Jul-2026 20:33:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 05-Jul-2026 10:48:55 | 05-Jul-2026 04:44:08 | 0 |  |  | Approver | Locate
AO-000128 | MM-ZTK-1F-ZWP21-STR-WCR-2001 | ZWP21 JACKET WEIGHT CONTROL REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | WCR | Weight Control Report | 0 | Submitted | IFR | Issued for Review |  | 14-Apr-2026 10:50:14 | zm169dc@jutal.com | 16-Apr-2026 12:47:37 | Jumpol Sudjitjul | 23-Apr-2026 |  | Sompop Singhatiraj | 27-Apr-2026 | 20-Apr-2026 16:29:27 | Pornlert Wanaphattharaphan | 28-Apr-2026 | 24-Apr-2026 00:13:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-Apr-2026 | 24-Apr-2026 09:00:55 | 24-Apr-2026 02:59:23 | 0 |  |  | Approver | Locate
AO-000950 | MM-ZTK-1F-ZWP21-STR-WCR-2001 | ZWP21 JACKET WEIGHT CONTROL REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | WCR | Weight Control Report | 0 | Submitted | IFA | Issued for Approval |  | 30-Jun-2026 08:32:55 | wisuda.c@jutal.com | 30-Jun-2026 11:11:10 | Jumpol Sudjitjul | 07-Jul-2026 |  | Sompop Singhatiraj | 09-Jul-2026 | 06-Jul-2026 17:32:11 | Pornlert Wanaphattharaphan | 10-Jul-2026 | 08-Jul-2026 01:14:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Jul-2026 | 08-Jul-2026 09:43:13 | 08-Jul-2026 03:35:30 | 0 |  |  | Approver | Locate
AO-001543 | MM-ZTK-1F-ZWP21-STR-WCR-2001 | ZWP21 JACKET WEIGHT CONTROL REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP21 |  |  | STR | Structural | WCR | Weight Control Report | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 14:26:36 | wisuda.c@jutal.com | 17-Aug-2026 16:25:21 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 27-Aug-2026 14:51:05 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 23:04:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 16:59:23 | 30-Aug-2026 10:39:35 | 0 |  |  | Approver | Locate
AO-001975 | MM-ZTK-1F-ZWP21-TNI-DWG-8001 | ZWP21 JACKET TRANSPORTATION STOWAGE PLAN |  | A1 | Project Document | Engineering Document | Part F - Transportation & Installation | ZWP21 |  |  | TNI | Transportation and Installation | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Sep-2026 16:25:00 | kjb@coes.cn | 10-Sep-2026 17:23:01 | Jumpol Sudjitjul | 18-Sep-2026 | 11-Sep-2026 07:16:49 | Sukit Nualchanchai | 22-Sep-2026 | 28-Sep-2026 15:56:53 | Prin Jitatisil | 23-Sep-2026 | 29-Sep-2026 09:13:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Sep-2026 | 29-Sep-2026 10:22:57 | 29-Sep-2026 03:34:28 | 0 |  |  | Approver | Locate
AO-002511 | MM-ZTK-1F-ZWP21-TNI-DWG-8001 | ZWP21 JACKET TRANSPORTATION STOWAGE PLAN |  | B1 | Project Document | Engineering Document | Part F - Transportation & Installation | ZWP21 |  |  | TNI | Transportation and Installation | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 14-Oct-2026 12:29:30 | kjb@coes.cn | 14-Oct-2026 13:26:21 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sukit Nualchanchai | 26-Oct-2026 | 15-Oct-2026 16:34:20 | Prin Jitatisil | 27-Oct-2026 | 15-Oct-2026 16:56:04 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 15-Oct-2026 16:59:01 | 15-Oct-2026 10:49:22 | 0 |  |  | Approver | Locate
AO-000647 | MM-ZTK-1F-ZWP22-COR-CAL-0001 | ZWP22 CATHODIC PROTECTION CALCULATION |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | COR | Corrosion | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 02-Jun-2026 10:51:05 | wisuda.c@jutal.com | 02-Jun-2026 15:10:42 | Jumpol Sudjitjul | 10-Jun-2026 |  | Sompop Singhatiraj | 12-Jun-2026 | 07-Jun-2026 11:38:32 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 10-Jun-2026 21:38:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 11-Jun-2026 13:49:02 | 11-Jun-2026 07:27:39 | 0 |  |  | Approver | Locate
AO-001767 | MM-ZTK-1F-ZWP22-COR-CAL-0001 | ZWP22 CATHODIC PROTECTION CALCULATION |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | COR | Corrosion | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 29-Aug-2026 14:03:57 | wisuda.c@jutal.com | 29-Aug-2026 14:18:02 | Jumpol Sudjitjul | 04-Sep-2026 |  | Sompop Singhatiraj | 08-Sep-2026 | 02-Sep-2026 10:49:15 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 07-Sep-2026 01:14:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 07-Sep-2026 18:04:25 | 07-Sep-2026 12:11:20 | 0 |  |  | Approver | Locate
AO-001681 | MM-ZTK-1F-ZWP22-NVA-CAL-2011 | ZWP22 JACKET BARGE MOTION ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 10:01:14 | wisuda.c@jutal.com | 25-Aug-2026 10:21:25 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 31-Aug-2026 10:41:33 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:47:16 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:05:13 | 10-Sep-2026 02:46:56 | 0 |  |  | Approver | Locate
AO-000662 | MM-ZTK-1F-ZWP22-NVA-CAL-2012 | ZWP22 JACKET LAUNCH ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 04-Jun-2026 09:38:25 | wisuda.c@jutal.com | 04-Jun-2026 13:42:36 | Jumpol Sudjitjul | 11-Jun-2026 |  | Sompop Singhatiraj | 15-Jun-2026 | 05-Jun-2026 19:36:04 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 10-Jun-2026 21:42:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 11-Jun-2026 13:48:34 | 11-Jun-2026 07:21:17 | 0 |  |  | Approver | Locate
AO-001688 | MM-ZTK-1F-ZWP22-NVA-CAL-2012 | ZWP22 JACKET LAUNCH ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 10:01:49 | wisuda.c@jutal.com | 25-Aug-2026 10:20:16 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 28-Aug-2026 15:58:37 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 31-Aug-2026 00:21:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 16:14:17 | 31-Aug-2026 10:14:31 | 0 |  |  | Approver | Locate
AO-002369 | MM-ZTK-1F-ZWP22-NVA-CAL-2012 | ZWP22 JACKET LAUNCH ANALYSIS REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 10:15:45 | wisuda.c@jutal.com | 06-Oct-2026 08:45:30 | Jumpol Sudjitjul | 14-Oct-2026 |  | Sompop Singhatiraj | 16-Oct-2026 | 12-Oct-2026 15:16:33 | Pornlert Wanaphattharaphan | 19-Oct-2026 | 13-Oct-2026 14:38:33 | APPR | Approved | Jumpol Sudjitjul | 20-Oct-2026 | 14-Oct-2026 16:47:37 | 14-Oct-2026 10:19:54 | 0 |  |  | Approver | Locate
AO-001525 | MM-ZTK-1F-ZWP22-NVA-CAL-2013 | ZWP22 JACKET FREE FLOATATION AND UPENDING ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 16:19:01 | wisuda.c@jutal.com | 14-Aug-2026 16:32:03 | Jumpol Sudjitjul | 21-Aug-2026 |  | Sompop Singhatiraj | 25-Aug-2026 | 16-Aug-2026 16:34:57 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 16-Aug-2026 17:37:55 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 27-Aug-2026 | 17-Aug-2026 14:22:14 | 17-Aug-2026 08:47:43 | 0 |  |  | Approver | Locate
AO-002294 | MM-ZTK-1F-ZWP22-NVA-CAL-2013 | ZWP22 JACKET FREE FLOATATION AND UPENDING ANALYSIS REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 09:52:00 | wisuda.c@jutal.com | 28-Sep-2026 10:41:27 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 12-Oct-2026 14:31:23 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 13-Oct-2026 14:38:59 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 14-Oct-2026 16:47:14 | 14-Oct-2026 10:37:36 | 0 |  |  | Approver | Locate
AO-000477 | MM-ZTK-1F-ZWP22-PIP-LAY-0005 | EQUIPMENT LAYOUT SUMP DECK PLAN T.O.S. EL.(+) 14.700 M. & BOAT LANDING PLAN T.O.S EL.(+) 5.000 M. |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 14:08:42 | wisuda.c@jutal.com | 18-May-2026 08:19:37 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 21:48:09 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 22:07:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:36:58 | 07-Jun-2026 11:03:23 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWP22-PIP-LAY-0005 | EQUIPMENT LAYOUT SUMP DECK PLAN T.O.S. EL.(+) 14.700 M. & BOAT LANDING PLAN T.O.S EL.(+) 5.000 M. |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:37:17 | wisuda.c@jutal.com | 15-Sep-2026 10:02:01 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:26:41 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 21:55:43 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 23:12:18 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 10:10:38 | 08-Oct-2026 04:24:04 | 0 |  |  | Approver | Locate
AO-000478 | MM-ZTK-1F-ZWP22-PIP-LAY-0006 | EQUIPMENT LAYOUT ELEVATION LOOKING NORTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 14:09:07 | wisuda.c@jutal.com | 18-May-2026 08:20:06 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 21:50:10 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 22:27:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:37:25 | 07-Jun-2026 11:04:39 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWP22-PIP-LAY-0006 | EQUIPMENT LAYOUT ELEVATION LOOKING NORTH |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:38:01 | wisuda.c@jutal.com | 15-Sep-2026 10:03:06 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:14:37 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 21:57:45 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 23:14:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 10:11:35 | 08-Oct-2026 04:25:25 | 0 |  |  | Approver | Locate
AO-000479 | MM-ZTK-1F-ZWP22-PIP-LAY-0007 | EQUIPMENT LAYOUT ELEVATION LOOKING EAST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 14:09:31 | wisuda.c@jutal.com | 18-May-2026 08:20:38 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 21:51:54 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 22:29:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:38:45 | 07-Jun-2026 11:07:10 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWP22-PIP-LAY-0007 | EQUIPMENT LAYOUT ELEVATION LOOKING EAST |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:38:34 | wisuda.c@jutal.com | 15-Sep-2026 10:03:44 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:13:33 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 22:00:24 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 23:14:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 10:13:48 | 08-Oct-2026 04:26:46 | 0 |  |  | Approver | Locate
AO-000480 | MM-ZTK-1F-ZWP22-PIP-LAY-0008 | EQUIPMENT LAYOUT ELEVATION LOOKING SOUTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 14:09:58 | wisuda.c@jutal.com | 18-May-2026 08:21:02 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 21:53:43 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 22:30:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:39:19 | 07-Jun-2026 11:08:29 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWP22-PIP-LAY-0008 | EQUIPMENT LAYOUT ELEVATION LOOKING SOUTH |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:39:09 | wisuda.c@jutal.com | 15-Sep-2026 10:04:28 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:20:09 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 22:02:26 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 23:15:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 10:14:30 | 08-Oct-2026 04:28:07 | 0 |  |  | Approver | Locate
AO-000481 | MM-ZTK-1F-ZWP22-PIP-LAY-0009 | EQUIPMENT LAYOUT ELEVATION LOOKING WEST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 14:10:21 | wisuda.c@jutal.com | 18-May-2026 08:21:24 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 21:55:27 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 22:31:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:38:18 | 07-Jun-2026 11:05:54 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWP22-PIP-LAY-0009 | EQUIPMENT LAYOUT ELEVATION LOOKING WEST |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:39:42 | wisuda.c@jutal.com | 15-Sep-2026 10:05:13 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:16:06 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 22:05:24 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 23:16:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 10:15:20 | 08-Oct-2026 04:29:26 | 0 |  |  | Approver | Locate
AO-001376 | MM-ZTK-1F-ZWP22-PRC-UPO-5001 | PRIMARY STEEL PLATES FOR ZWP22 (CUT-OFF DATE 31-JUL-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | ZWP22 |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 03-Aug-2026 10:54:26 | zm169dc@jutal.com | 03-Aug-2026 14:05:19 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 12-Aug-2026 19:34:40 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 13-Aug-2026 12:47:57 | 13-Aug-2026 06:07:59 | 0 |  |  | For Info | Locate
AO-002524 | MM-ZTK-1F-ZWP22-PRC-UPO-5002 | UNPRICED PO FOR STEEL PLATES FOR ZWP22(CUT-OFF DATE 12-OCT-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | ZWP22 |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 14-Oct-2026 17:38:43 | zhaoli@jutal.com | 15-Oct-2026 11:17:53 | Jumpol Sudjitjul |  |  | Jirayu Pantito | [11 empty] | 0 |  |  | For Info | Locate
AO-002158 | MM-ZTK-1F-ZWP22-PRC-UPO-5100 | UNPRICED PO FOR ANODE FOR ZWP22 (CUT-OFF DATE 17-SEP-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | ZWP22 |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 18-Sep-2026 17:26:57 | zm169dc@jutal.com | 20-Sep-2026 12:58:33 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  |  | Prin Jitatisil | [8 empty] | 0 |  |  | For Info | Locate
AO-000515 | MM-ZTK-1F-ZWP22-STR-CAL-2001 | ZWP22 JACKET COMPUTER MODELING AND LOAD FORMULATION |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 16:15:42 | wisuda.c@jutal.com | 19-May-2026 16:36:48 | Jumpol Sudjitjul | 26-May-2026 |  | Sompop Singhatiraj | 28-May-2026 | 25-May-2026 14:38:07 | Pornlert Wanaphattharaphan | 29-May-2026 | 25-May-2026 20:29:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 25-May-2026 21:13:24 | 25-May-2026 14:27:31 | 0 |  |  | Approver | Locate
AO-001776 | MM-ZTK-1F-ZWP22-STR-CAL-2001 | ZWP22 JACKET COMPUTER MODELING AND LOAD FORMULATION |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:30:22 | wisuda.c@jutal.com | 31-Aug-2026 11:31:17 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 11-Sep-2026 07:43:44 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 12-Sep-2026 15:23:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 13-Sep-2026 08:41:15 | 13-Sep-2026 01:52:14 | 0 |  |  | Approver | Locate
AO-000933 | MM-ZTK-1F-ZWP22-STR-CAL-2011 | ZWP22 JACKET IN-PLACE ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 19:01:45 | wisuda.c@jutal.com | 27-Jun-2026 19:09:25 | Jumpol Sudjitjul | 06-Jul-2026 |  | Sompop Singhatiraj | 08-Jul-2026 | 03-Jul-2026 15:45:53 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 08-Jul-2026 00:56:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 08-Jul-2026 09:41:47 | 08-Jul-2026 03:32:26 | 0 |  |  | Approver | Locate
AO-001537 | MM-ZTK-1F-ZWP22-STR-CAL-2011 | ZWP22 JACKET IN-PLACE ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 17:33:41 | wisuda.c@jutal.com | 14-Aug-2026 17:44:35 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 16-Aug-2026 17:59:35 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 17-Aug-2026 21:17:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 18-Aug-2026 08:23:02 | 18-Aug-2026 01:41:54 | 0 |  |  | Approver | Locate
AO-000661 | MM-ZTK-1F-ZWP22-STR-CAL-2012 | ZWP22 JACKET DYNAMIC ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 04-Jun-2026 09:37:46 | wisuda.c@jutal.com | 04-Jun-2026 13:34:03 | Jumpol Sudjitjul | 11-Jun-2026 |  | Sompop Singhatiraj | 15-Jun-2026 | 08-Jun-2026 08:42:02 | Pornlert Wanaphattharaphan | 16-Jun-2026 | 10-Jun-2026 21:42:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Jun-2026 | 11-Jun-2026 13:47:34 | 11-Jun-2026 07:19:38 | 0 |  |  | Approver | Locate
AO-001487 | MM-ZTK-1F-ZWP22-STR-CAL-2012 | ZWP22 JACKET DYNAMIC ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:45:22 | wisuda.c@jutal.com | 10-Aug-2026 14:37:16 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 14-Aug-2026 09:44:31 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 17-Aug-2026 00:06:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 17-Aug-2026 14:18:31 | 17-Aug-2026 09:04:35 | 0 |  |  | Approver | Locate
AO-001779 | MM-ZTK-1F-ZWP22-STR-CAL-2013 | ZWP22 IN-SERVICE COMBINED TOPSIDES AND JACKET FATIGUE ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 31-Aug-2026 09:30:59 | wisuda.c@jutal.com | 31-Aug-2026 12:59:30 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 14-Sep-2026 14:29:50 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 15-Sep-2026 22:30:42 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-Sep-2026 | 17-Sep-2026 12:02:09 | 17-Sep-2026 05:54:21 | 0 |  |  | Approver | Locate
AO-002508 | MM-ZTK-1F-ZWP22-STR-CAL-2013 | ZWP22 IN-SERVICE COMBINED TOPSIDES AND JACKET FATIGUE ANALYSIS REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | In Review | AFC | Approved for Construction |  | 14-Oct-2026 11:21:17 | wisuda.c@jutal.com | 14-Oct-2026 13:31:48 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 |  | Pornlert Wanaphattharaphan | 27-Oct-2026 |  |  |  |  | 28-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000515 | MM-ZTK-1F-ZWP22-STR-CAL-2014 | ZWP22 JACKET LOADOUT ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 16:16:14 | wisuda.c@jutal.com | 19-May-2026 16:36:20 | Jumpol Sudjitjul | 26-May-2026 | 04-Jun-2026 11:19:19 | Sompop Singhatiraj | 28-May-2026 | 04-Jun-2026 13:36:20 | Pornlert Wanaphattharaphan | 29-May-2026 | 06-Jun-2026 00:00:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 07-Jun-2026 17:46:37 | 07-Jun-2026 11:47:20 | 0 |  |  | Approver | Locate
AO-001488 | MM-ZTK-1F-ZWP22-STR-CAL-2014 | ZWP22 JACKET LOADOUT ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:46:01 | wisuda.c@jutal.com | 10-Aug-2026 14:37:35 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 31-Aug-2026 13:23:52 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 01-Sep-2026 23:26:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 02-Sep-2026 15:30:54 | 02-Sep-2026 09:05:40 | 0 |  |  | Approver | Locate
AO-002367 | MM-ZTK-1F-ZWP22-STR-CAL-2014 | ZWP22 JACKET LOADOUT ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 10:10:52 | wisuda.c@jutal.com | 05-Oct-2026 10:37:29 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 12-Oct-2026 12:41:46 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 13-Oct-2026 14:39:32 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 14-Oct-2026 16:46:36 | 14-Oct-2026 10:14:06 | 0 |  |  | Approver | Locate
AO-000515 | MM-ZTK-1F-ZWP22-STR-CAL-2015 | ZWP22 JACKET TRANSPORTATION ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 15:29:38 | wisuda.c@jutal.com | 19-May-2026 15:48:25 | Jumpol Sudjitjul | 26-May-2026 | 04-Jun-2026 11:24:35 | Sompop Singhatiraj | 28-May-2026 | 04-Jun-2026 16:30:59 | Pornlert Wanaphattharaphan | 29-May-2026 | 06-Jun-2026 00:00:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 07-Jun-2026 17:46:42 | 07-Jun-2026 12:05:30 | 0 |  |  | Approver | Locate
AO-001608 | MM-ZTK-1F-ZWP22-STR-CAL-2015 | ZWP22 JACKET TRANSPORTATION ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 19-Aug-2026 09:58:23 | wisuda.c@jutal.com | 19-Aug-2026 11:12:15 | Jumpol Sudjitjul | 26-Aug-2026 |  | Sompop Singhatiraj | 28-Aug-2026 | 31-Aug-2026 12:34:22 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 02-Sep-2026 23:17:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Sep-2026 | 03-Sep-2026 10:04:30 | 03-Sep-2026 04:16:09 | 0 |  |  | Approver | Locate
AO-001399 | MM-ZTK-1F-ZWP22-STR-CAL-2016 | ZWP22 JACKET TRANSPORTATION FATIGUE ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 15:20:56 | wisuda.c@jutal.com | 03-Aug-2026 15:43:08 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 17-Aug-2026 15:59:52 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 17-Aug-2026 21:05:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 18-Aug-2026 08:24:21 | 18-Aug-2026 02:10:02 | 0 |  |  | Approver | Locate
AO-001689 | MM-ZTK-1F-ZWP22-STR-CAL-2016 | ZWP22 JACKET TRANSPORTATION FATIGUE ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:52:08 | wisuda.c@jutal.com | 25-Aug-2026 09:50:37 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 27-Aug-2026 16:20:33 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 31-Aug-2026 00:22:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 16:28:18 | 31-Aug-2026 10:56:44 | 0 |  |  | Approver | Locate
AO-002488 | MM-ZTK-1F-ZWP22-STR-CAL-2016 | ZWP22 JACKET TRANSPORTATION FATIGUE ANALYSIS REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 11:49:11 | wisuda.c@jutal.com | 12-Oct-2026 11:56:45 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001283 | MM-ZTK-1F-ZWP22-STR-CAL-2017 | ZWP22 JACKET BOAT IMPACT ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 27-Jul-2026 09:22:10 | wisuda.c@jutal.com | 27-Jul-2026 15:54:35 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 12-Aug-2026 09:54:26 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 12:58:55 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 13:04:15 | 13-Aug-2026 07:09:27 | 0 |  |  | Approver | Locate
AO-001393 | MM-ZTK-1F-ZWP22-STR-CAL-2018 | ZWP22 JACKET ON-BOTTOM STABILITY ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 10:09:16 | wisuda.c@jutal.com | 03-Aug-2026 13:23:53 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 13-Aug-2026 16:03:34 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 14-Aug-2026 00:09:38 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 17-Aug-2026 | 14-Aug-2026 08:34:05 | 14-Aug-2026 02:23:39 | 0 |  |  | Approver | Locate
AO-001262 | MM-ZTK-1F-ZWP22-STR-CAL-2019 | ZWP22 JACKET MISCELLANEOUS DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 12:06:07 | wisuda.c@jutal.com | 26-Jul-2026 23:42:33 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 16-Sep-2026 18:33:44 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 17-Sep-2026 14:27:01 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-Aug-2026 | 17-Sep-2026 16:16:50 | 17-Sep-2026 10:05:34 | 0 |  |  | Approver | Locate
AO-002258 | MM-ZTK-1F-ZWP22-STR-CAL-2020 | ZWP22 JACKET LEVELLING ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 13:28:28 | wisuda.c@jutal.com | 25-Sep-2026 14:04:07 | Jumpol Sudjitjul | 02-Oct-2026 |  | Sompop Singhatiraj | 06-Oct-2026 | 06-Oct-2026 18:24:28 | Pornlert Wanaphattharaphan | 07-Oct-2026 | 10-Oct-2026 00:51:05 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 08-Oct-2026 | 10-Oct-2026 17:35:51 | 10-Oct-2026 11:39:07 | 0 |  |  | Approver | Locate
AO-001684 | MM-ZTK-1F-ZWP22-STR-CAL-2021 | ZWP22 JACKET PILE HANDLING AND STICK-UP ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 09:52:45 | wisuda.c@jutal.com | 25-Aug-2026 10:12:50 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 28-Aug-2026 11:49:24 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 31-Aug-2026 00:23:35 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 16:14:14 | 31-Aug-2026 10:50:43 | 0 |  |  | Approver | Locate
AO-001524 | MM-ZTK-1F-ZWP22-STR-CAL-2022 | ZWP22 PILE DRIVEABILITY AND PILE FATIGUE ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 16:17:39 | wisuda.c@jutal.com | 14-Aug-2026 16:34:28 | Jumpol Sudjitjul | 21-Aug-2026 |  | Sompop Singhatiraj | 25-Aug-2026 | 31-Aug-2026 07:53:29 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 02-Sep-2026 23:12:11 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 27-Aug-2026 | 03-Sep-2026 10:06:39 | 03-Sep-2026 04:30:08 | 0 |  |  | Approver | Locate
AO-002489 | MM-ZTK-1F-ZWP22-STR-CAL-2022 | ZWP22 PILE DRIVEABILITY AND PILE FATIGUE ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 11:49:59 | wisuda.c@jutal.com | 12-Oct-2026 11:56:46 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001768 | MM-ZTK-1F-ZWP22-STR-CAL-2023 | ZWP22 JACKET PILE CLUSTER FEA REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 29-Aug-2026 14:05:13 | wisuda.c@jutal.com | 29-Aug-2026 14:17:16 | Jumpol Sudjitjul | 04-Sep-2026 |  | Sompop Singhatiraj | 08-Sep-2026 | 10-Sep-2026 18:23:13 | Pornlert Wanaphattharaphan | 09-Sep-2026 | 11-Sep-2026 22:34:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Sep-2026 | 13-Sep-2026 08:46:17 | 13-Sep-2026 01:50:51 | 0 |  |  | Approver | Locate
AO-001258 | MM-ZTK-1F-ZWP22-STR-CAL-2024 | ZWP22 PILE GROUP EFFECT ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 24-Jul-2026 08:41:59 | wisuda.c@jutal.com | 24-Jul-2026 10:59:38 | Jumpol Sudjitjul | 04-Aug-2026 |  | Sompop Singhatiraj | 06-Aug-2026 | 12-Aug-2026 10:15:38 | Pornlert Wanaphattharaphan | 07-Aug-2026 | 12-Aug-2026 12:54:19 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 10-Aug-2026 | 13-Aug-2026 12:56:24 | 13-Aug-2026 06:19:21 | 0 |  |  | Approver | Locate
AO-002018 | MM-ZTK-1F-ZWP22-STR-CAL-2025 | ZWP22 MUDMAT FEA ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 11-Sep-2026 20:50:22 | wisuda.c@jutal.com | 11-Sep-2026 20:55:44 | Jumpol Sudjitjul | 21-Sep-2026 |  | Sompop Singhatiraj | 23-Sep-2026 | 22-Sep-2026 11:03:52 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 22-Sep-2026 19:50:44 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 25-Sep-2026 | 23-Sep-2026 13:34:39 | 23-Sep-2026 07:31:24 | 0 |  |  | Approver | Locate
AO-002504 | MM-ZTK-1F-ZWP22-STR-CAL-2026 | ZWP22 & ZWP20 PILE TRANSPORTATION FATIGUE ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | In Review | IFR | Issued for Review |  | 14-Oct-2026 09:27:29 | wisuda.c@jutal.com | 14-Oct-2026 09:57:30 | Jumpol Sudjitjul | 21-Oct-2026 | 14-Oct-2026 10:11:04 | Sompop Singhatiraj | 26-Oct-2026 |  | Pornlert Wanaphattharaphan | 27-Oct-2026 |  |  |  |  | 28-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000763 | MM-ZTK-1F-ZWP22-STR-CAL-2031 | ZWP22 TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (EXTREME LEVEL EARTHQUAKE - ELE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 13-Jun-2026 08:18:12 | wisuda.c@jutal.com | 13-Jun-2026 08:30:43 | Jumpol Sudjitjul | 19-Jun-2026 |  | Sompop Singhatiraj | 23-Jun-2026 | 19-Jun-2026 19:34:25 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 21-Jun-2026 16:06:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 22-Jun-2026 13:03:32 | 22-Jun-2026 07:09:51 | 0 |  |  | Approver | Locate
AO-001541 | MM-ZTK-1F-ZWP22-STR-CAL-2031 | ZWP22 TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (EXTREME LEVEL EARTHQUAKE - ELE) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 14-Aug-2026 18:12:16 | wisuda.c@jutal.com | 15-Aug-2026 14:59:46 | Jumpol Sudjitjul | 21-Aug-2026 |  | Sompop Singhatiraj | 25-Aug-2026 | 02-Sep-2026 16:00:53 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 02-Sep-2026 23:14:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 03-Sep-2026 10:07:54 | 03-Sep-2026 03:59:43 | 0 |  |  | Approver | Locate
AO-002294 | MM-ZTK-1F-ZWP22-STR-CAL-2031 | ZWP22 TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (EXTREME LEVEL EARTHQUAKE - ELE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 09:47:48 | wisuda.c@jutal.com | 28-Sep-2026 09:53:43 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 12-Oct-2026 10:11:25 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 13-Oct-2026 14:39:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 14-Oct-2026 16:45:48 | 14-Oct-2026 10:35:01 | 0 |  |  | Approver | Locate
AO-000806 | MM-ZTK-1F-ZWP22-STR-CAL-2032 | ZWP22 TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT(ABNORMAL LEVEL EARTHQUAKE-ALE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 15-Jun-2026 22:49:19 | wisuda.c@jutal.com | 16-Jun-2026 10:43:23 | Jumpol Sudjitjul | 23-Jun-2026 |  | Sompop Singhatiraj | 25-Jun-2026 | 21-Jun-2026 14:24:11 | Pornlert Wanaphattharaphan | 26-Jun-2026 | 22-Jun-2026 14:15:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-Jun-2026 | 22-Jun-2026 14:25:09 | 22-Jun-2026 07:49:15 | 0 |  |  | Approver | Locate
AO-001566 | MM-ZTK-1F-ZWP22-STR-CAL-2032 | ZWP22 TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT(ABNORMAL LEVEL EARTHQUAKE-ALE) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:27:26 | wisuda.c@jutal.com | 17-Aug-2026 15:50:15 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 02-Sep-2026 18:23:41 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 02-Sep-2026 23:17:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 03-Sep-2026 10:18:52 | 03-Sep-2026 04:01:17 | 0 |  |  | Approver | Locate
AO-002371 | MM-ZTK-1F-ZWP22-STR-CAL-2032 | ZWP22 TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT(ABNORMAL LEVEL EARTHQUAKE-ALE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 10:11:41 | wisuda.c@jutal.com | 05-Oct-2026 10:37:24 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 12-Oct-2026 15:16:44 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 13-Oct-2026 14:40:24 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 14-Oct-2026 16:44:59 | 14-Oct-2026 10:11:17 | 0 |  |  | Approver | Locate
AO-001902 | MM-ZTK-1F-ZWP22-STR-CAL-2041 | ZWP22 JACKET PUSHOVER ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 07-Sep-2026 10:23:28 | wisuda.c@jutal.com | 08-Sep-2026 12:01:24 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 21-Sep-2026 14:46:03 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 22-Sep-2026 19:50:16 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Sep-2026 | 23-Sep-2026 13:36:08 | 23-Sep-2026 07:11:11 | 0 |  |  | Approver | Locate
AO-000515 | MM-ZTK-1F-ZWP22-STR-CAL-2050 | ZWP22 JACKET CONSTRUCTION MODEL REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 15:30:26 | wisuda.c@jutal.com | 19-May-2026 15:52:47 | Jumpol Sudjitjul | 26-May-2026 |  | Sompop Singhatiraj | 28-May-2026 | 25-May-2026 16:55:54 | Pornlert Wanaphattharaphan | 29-May-2026 | 25-May-2026 20:41:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 25-May-2026 21:04:46 | 25-May-2026 14:42:54 | 0 |  |  | Approver | Locate
AO-001776 | MM-ZTK-1F-ZWP22-STR-CAL-2050 | ZWP22 JACKET CONSTRUCTION MODEL REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:31:31 | wisuda.c@jutal.com | 31-Aug-2026 11:31:39 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 11-Sep-2026 07:45:21 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 12-Sep-2026 15:25:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 13-Sep-2026 08:52:26 | 13-Sep-2026 02:31:24 | 0 |  |  | Approver | Locate
AO-002261 | MM-ZTK-1F-ZWP22-STR-CAL-2801 | ZWP22 RISER CLAMP DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | In Review | IFR | Issued for Review |  | 25-Sep-2026 14:11:52 | wisuda.c@jutal.com | 25-Sep-2026 15:01:10 | Jumpol Sudjitjul | 02-Oct-2026 |  | Sompop Singhatiraj | 06-Oct-2026 |  | Pornlert Wanaphattharaphan | 07-Oct-2026 |  |  |  |  | 08-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP22-STR-DWG-2100 | ZWP22 JACKET - VERTICAL FRAMING ROW 'A' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:52:04 | wisuda.c@jutal.com | 22-Apr-2026 10:47:48 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 09:33:49 | Pornlert Wanaphattharaphan | 06-May-2026 | 24-Apr-2026 00:37:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 09:08:46 | 24-Apr-2026 03:02:58 | 0 |  |  | Approver | Locate
AO-001225 | MM-ZTK-1F-ZWP22-STR-DWG-2100 | ZWP22 JACKET - VERTICAL FRAMING ROW 'A' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 09:26:31 | wisuda.c@jutal.com | 23-Jul-2026 09:29:37 | Jumpol Sudjitjul | 03-Aug-2026 |  | Sompop Singhatiraj | 05-Aug-2026 | 24-Jul-2026 14:14:51 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 24-Jul-2026 22:56:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 27-Jul-2026 15:08:50 | 27-Jul-2026 09:41:08 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2100 | ZWP22 JACKET - VERTICAL FRAMING ROW 'A' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:14:43 | wisuda.c@jutal.com | 21-Sep-2026 18:02:13 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 25-Sep-2026 16:15:01 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 26-Sep-2026 05:24:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Oct-2026 | 26-Sep-2026 16:01:45 | 26-Sep-2026 09:15:15 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP22-STR-DWG-2101 | ZWP22 JACKET - VERTICAL FRAMING ROW 'B' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:52:27 | wisuda.c@jutal.com | 22-Apr-2026 10:48:02 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 11:23:22 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 23:56:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 09:09:27 | 24-Apr-2026 03:05:21 | 0 |  |  | Approver | Locate
AO-001225 | MM-ZTK-1F-ZWP22-STR-DWG-2101 | ZWP22 JACKET - VERTICAL FRAMING ROW 'B' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 09:26:59 | wisuda.c@jutal.com | 23-Jul-2026 09:29:35 | Jumpol Sudjitjul | 03-Aug-2026 |  | Sompop Singhatiraj | 05-Aug-2026 | 24-Jul-2026 14:15:04 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 24-Jul-2026 23:04:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 27-Jul-2026 15:10:10 | 27-Jul-2026 09:43:39 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2101 | ZWP22 JACKET - VERTICAL FRAMING ROW 'B' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:15:11 | wisuda.c@jutal.com | 21-Sep-2026 18:02:19 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 25-Sep-2026 16:10:18 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 26-Sep-2026 05:25:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Oct-2026 | 26-Sep-2026 16:05:29 | 26-Sep-2026 09:19:00 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP22-STR-DWG-2102 | ZWP22 JACKET - VERTICAL FRAMING ROW '1' & '1.1' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:52:49 | wisuda.c@jutal.com | 22-Apr-2026 10:48:19 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 11:02:33 | Pornlert Wanaphattharaphan | 06-May-2026 | 24-Apr-2026 00:32:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 09:10:10 | 24-Apr-2026 03:06:32 | 0 |  |  | Approver | Locate
AO-001225 | MM-ZTK-1F-ZWP22-STR-DWG-2102 | ZWP22 JACKET - VERTICAL FRAMING ROW '1' & '1.1' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 09:27:26 | wisuda.c@jutal.com | 23-Jul-2026 09:29:35 | Jumpol Sudjitjul | 03-Aug-2026 |  | Sompop Singhatiraj | 05-Aug-2026 | 24-Jul-2026 14:15:14 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 24-Jul-2026 23:05:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 27-Jul-2026 15:10:39 | 27-Jul-2026 09:44:55 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2102 | ZWP22 JACKET - VERTICAL FRAMING ROW '1' & '1.1' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:15:40 | wisuda.c@jutal.com | 21-Sep-2026 18:02:14 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 25-Sep-2026 16:21:23 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 26-Sep-2026 05:23:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Oct-2026 | 26-Sep-2026 16:06:02 | 26-Sep-2026 09:20:20 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP22-STR-DWG-2103 | ZWP22 JACKET - VERTICAL FRAMING ROW '2' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:53:11 | wisuda.c@jutal.com | 22-Apr-2026 10:56:40 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 12:36:01 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 23:14:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 09:10:47 | 24-Apr-2026 03:07:49 | 0 |  |  | Approver | Locate
AO-001225 | MM-ZTK-1F-ZWP22-STR-DWG-2103 | ZWP22 JACKET - VERTICAL FRAMING ROW '2' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 09:27:55 | wisuda.c@jutal.com | 23-Jul-2026 09:29:38 | Jumpol Sudjitjul | 03-Aug-2026 |  | Sompop Singhatiraj | 05-Aug-2026 | 24-Jul-2026 14:16:55 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 24-Jul-2026 22:53:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 27-Jul-2026 15:11:15 | 27-Jul-2026 09:46:13 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2103 | ZWP22 JACKET - VERTICAL FRAMING ROW '2' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:16:11 | wisuda.c@jutal.com | 21-Sep-2026 18:02:17 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 25-Sep-2026 16:13:39 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 26-Sep-2026 05:25:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Oct-2026 | 26-Sep-2026 16:04:43 | 26-Sep-2026 09:17:46 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP22-STR-DWG-2104 | ZWP22 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'AA' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 20:53:41 | wisuda.c@jutal.com | 22-Apr-2026 10:57:03 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 12:37:04 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 23:11:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 09:12:02 | 24-Apr-2026 02:21:39 | 0 |  |  | Approver | Locate
AO-001225 | MM-ZTK-1F-ZWP22-STR-DWG-2104 | ZWP22 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'AA' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 09:28:23 | wisuda.c@jutal.com | 23-Jul-2026 10:10:04 | Jumpol Sudjitjul | 03-Aug-2026 |  | Sompop Singhatiraj | 05-Aug-2026 | 24-Jul-2026 14:17:08 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 24-Jul-2026 22:55:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 27-Jul-2026 15:11:42 | 27-Jul-2026 09:47:28 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2104 | ZWP22 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'AA' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:16:47 | wisuda.c@jutal.com | 21-Sep-2026 18:02:16 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 25-Sep-2026 16:18:18 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 26-Sep-2026 05:24:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Oct-2026 | 26-Sep-2026 14:15:00 | 26-Sep-2026 07:54:29 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP22-STR-DWG-2105 | ZWP22 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'BB' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 20:54:04 | wisuda.c@jutal.com | 22-Apr-2026 10:57:19 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 12:38:27 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 23:08:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 09:14:00 | 24-Apr-2026 02:22:53 | 0 |  |  | Approver | Locate
AO-001225 | MM-ZTK-1F-ZWP22-STR-DWG-2105 | ZWP22 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'BB' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 09:28:55 | wisuda.c@jutal.com | 23-Jul-2026 10:10:08 | Jumpol Sudjitjul | 03-Aug-2026 |  | Sompop Singhatiraj | 05-Aug-2026 | 24-Jul-2026 14:17:18 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 24-Jul-2026 22:52:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 27-Jul-2026 15:12:11 | 27-Jul-2026 09:48:49 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2105 | ZWP22 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'BB' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:17:19 | wisuda.c@jutal.com | 21-Sep-2026 18:02:16 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 25-Sep-2026 16:21:09 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 26-Sep-2026 05:23:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Oct-2026 | 26-Sep-2026 16:06:25 | 26-Sep-2026 09:21:36 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP22-STR-DWG-2110 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(+) 8000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 20:54:25 | wisuda.c@jutal.com | 22-Apr-2026 10:57:38 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 13:56:41 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 22:49:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 09:15:31 | 24-Apr-2026 02:24:06 | 0 |  |  | Approver | Locate
AO-001225 | MM-ZTK-1F-ZWP22-STR-DWG-2110 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(+) 8000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 09:29:21 | wisuda.c@jutal.com | 23-Jul-2026 10:10:07 | Jumpol Sudjitjul | 03-Aug-2026 |  | Sompop Singhatiraj | 05-Aug-2026 | 24-Jul-2026 14:18:59 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 24-Jul-2026 22:51:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 27-Jul-2026 15:12:43 | 27-Jul-2026 09:50:07 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2110 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(+) 8000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:17:46 | wisuda.c@jutal.com | 21-Sep-2026 18:03:11 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 25-Sep-2026 13:54:30 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 26-Sep-2026 05:27:46 | APPR | Approved | Jumpol Sudjitjul | 05-Oct-2026 | 26-Sep-2026 16:07:33 | 26-Sep-2026 09:23:53 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP22-STR-DWG-2111 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 3000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:53:33 | wisuda.c@jutal.com | 22-Apr-2026 11:24:34 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 14:02:13 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 22:36:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 09:16:49 | 24-Apr-2026 03:10:15 | 0 |  |  | Approver | Locate
AO-001225 | MM-ZTK-1F-ZWP22-STR-DWG-2111 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 3000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 09:30:00 | wisuda.c@jutal.com | 23-Jul-2026 10:10:07 | Jumpol Sudjitjul | 03-Aug-2026 |  | Sompop Singhatiraj | 05-Aug-2026 | 24-Jul-2026 14:19:00 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 24-Jul-2026 22:50:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 27-Jul-2026 15:13:11 | 27-Jul-2026 09:51:25 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2111 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 3000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:18:16 | wisuda.c@jutal.com | 21-Sep-2026 18:03:10 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 25-Sep-2026 13:44:15 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 26-Sep-2026 05:29:34 | APPR | Approved | Jumpol Sudjitjul | 05-Oct-2026 | 26-Sep-2026 16:06:50 | 26-Sep-2026 09:22:46 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP22-STR-DWG-2112 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 14000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:53:56 | wisuda.c@jutal.com | 22-Apr-2026 11:24:49 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 14:49:25 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 22:20:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 09:18:19 | 24-Apr-2026 03:11:29 | 0 |  |  | Approver | Locate
AO-001225 | MM-ZTK-1F-ZWP22-STR-DWG-2112 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 14000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 09:30:33 | wisuda.c@jutal.com | 23-Jul-2026 10:10:04 | Jumpol Sudjitjul | 03-Aug-2026 |  | Sompop Singhatiraj | 05-Aug-2026 | 24-Jul-2026 14:19:13 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 24-Jul-2026 22:49:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 27-Jul-2026 15:13:36 | 27-Jul-2026 09:52:41 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2112 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 14000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:18:46 | wisuda.c@jutal.com | 21-Sep-2026 18:03:12 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 25-Sep-2026 16:07:00 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 26-Sep-2026 05:26:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Oct-2026 | 26-Sep-2026 16:03:09 | 26-Sep-2026 09:16:30 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP22-STR-DWG-2113 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 26000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:54:18 | wisuda.c@jutal.com | 22-Apr-2026 11:07:11 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 14:49:33 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 22:19:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 09:08:51 | 24-Apr-2026 03:04:09 | 0 |  |  | Approver | Locate
AO-001225 | MM-ZTK-1F-ZWP22-STR-DWG-2113 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 26000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 09:31:03 | wisuda.c@jutal.com | 23-Jul-2026 10:10:05 | Jumpol Sudjitjul | 03-Aug-2026 |  | Sompop Singhatiraj | 05-Aug-2026 | 24-Jul-2026 14:20:52 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 24-Jul-2026 22:48:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 27-Jul-2026 15:15:15 | 27-Jul-2026 09:53:56 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2113 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 26000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:19:25 | wisuda.c@jutal.com | 21-Sep-2026 18:03:13 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 25-Sep-2026 13:44:30 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 26-Sep-2026 05:29:11 | APPR | Approved | Jumpol Sudjitjul | 05-Oct-2026 | 26-Sep-2026 16:07:59 | 26-Sep-2026 09:24:58 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP22-STR-DWG-2114 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 38000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:54:41 | wisuda.c@jutal.com | 22-Apr-2026 11:07:31 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 14:52:46 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 22:14:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 09:27:04 | 24-Apr-2026 03:17:48 | 0 |  |  | Approver | Locate
AO-001225 | MM-ZTK-1F-ZWP22-STR-DWG-2114 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 38000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 09:31:35 | wisuda.c@jutal.com | 23-Jul-2026 10:10:08 | Jumpol Sudjitjul | 03-Aug-2026 |  | Sompop Singhatiraj | 05-Aug-2026 | 24-Jul-2026 14:21:02 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 24-Jul-2026 22:48:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 27-Jul-2026 15:16:14 | 27-Jul-2026 09:56:33 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2114 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 38000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:20:00 | wisuda.c@jutal.com | 21-Sep-2026 18:03:11 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 25-Sep-2026 15:36:41 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 26-Sep-2026 05:26:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Oct-2026 | 26-Sep-2026 14:22:05 | 26-Sep-2026 08:05:51 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP22-STR-DWG-2115 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 52000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:55:03 | wisuda.c@jutal.com | 22-Apr-2026 11:07:46 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 15:51:13 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 19:16:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 09:23:08 | 24-Apr-2026 03:16:35 | 0 |  |  | Approver | Locate
AO-001225 | MM-ZTK-1F-ZWP22-STR-DWG-2115 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 52000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 09:32:01 | wisuda.c@jutal.com | 23-Jul-2026 10:10:04 | Jumpol Sudjitjul | 03-Aug-2026 |  | Sompop Singhatiraj | 05-Aug-2026 | 24-Jul-2026 14:21:15 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 24-Jul-2026 22:47:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 27-Jul-2026 15:15:41 | 27-Jul-2026 09:55:16 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2115 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 52000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:20:33 | wisuda.c@jutal.com | 21-Sep-2026 18:03:16 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 25-Sep-2026 13:44:36 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 26-Sep-2026 05:28:49 | APPR | Approved | Jumpol Sudjitjul | 05-Oct-2026 | 26-Sep-2026 14:22:51 | 26-Sep-2026 08:08:07 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP22-STR-DWG-2116 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 66000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:55:26 | wisuda.c@jutal.com | 22-Apr-2026 11:08:01 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 15:53:21 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 18:53:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 09:09:40 | 24-Apr-2026 02:47:15 | 0 |  |  | Approver | Locate
AO-001225 | MM-ZTK-1F-ZWP22-STR-DWG-2116 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 66000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 09:32:34 | wisuda.c@jutal.com | 23-Jul-2026 10:10:07 | Jumpol Sudjitjul | 03-Aug-2026 |  | Sompop Singhatiraj | 05-Aug-2026 | 24-Jul-2026 14:23:01 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 24-Jul-2026 22:46:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 27-Jul-2026 15:16:40 | 27-Jul-2026 09:57:50 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2116 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 66000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:21:03 | wisuda.c@jutal.com | 21-Sep-2026 18:03:15 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 25-Sep-2026 15:35:23 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 26-Sep-2026 05:27:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Oct-2026 | 26-Sep-2026 14:21:27 | 26-Sep-2026 08:04:36 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP22-STR-DWG-2117 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 79500 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:55:48 | wisuda.c@jutal.com | 22-Apr-2026 11:25:21 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 15:48:59 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 19:24:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 09:19:43 | 24-Apr-2026 02:52:05 | 0 |  |  | Approver | Locate
AO-001225 | MM-ZTK-1F-ZWP22-STR-DWG-2117 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 79500 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 08:36:59 | wisuda.c@jutal.com | 23-Jul-2026 09:29:44 | Jumpol Sudjitjul | 03-Aug-2026 |  | Sompop Singhatiraj | 05-Aug-2026 | 24-Jul-2026 14:23:18 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 24-Jul-2026 22:44:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 27-Jul-2026 15:17:17 | 27-Jul-2026 10:35:56 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2117 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 79500 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:21:33 | wisuda.c@jutal.com | 21-Sep-2026 18:03:14 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 25-Sep-2026 13:51:12 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 26-Sep-2026 05:28:08 | APPR | Approved | Jumpol Sudjitjul | 05-Oct-2026 | 26-Sep-2026 16:09:19 | 26-Sep-2026 09:26:05 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP22-STR-DWG-2118 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 93000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:56:11 | wisuda.c@jutal.com | 22-Apr-2026 11:25:33 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 15:49:08 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 19:21:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 09:17:03 | 24-Apr-2026 02:50:51 | 0 |  |  | Approver | Locate
AO-001225 | MM-ZTK-1F-ZWP22-STR-DWG-2118 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 93000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 08:37:27 | wisuda.c@jutal.com | 23-Jul-2026 09:29:43 | Jumpol Sudjitjul | 03-Aug-2026 |  | Sompop Singhatiraj | 05-Aug-2026 | 24-Jul-2026 14:23:22 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 24-Jul-2026 22:43:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 27-Jul-2026 15:17:43 | 27-Jul-2026 10:37:12 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2118 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 93000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:22:05 | wisuda.c@jutal.com | 21-Sep-2026 18:03:18 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 25-Sep-2026 15:32:45 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 26-Sep-2026 05:27:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Oct-2026 | 26-Sep-2026 16:10:30 | 26-Sep-2026 09:27:20 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP22-STR-DWG-2119 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 103000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:56:34 | wisuda.c@jutal.com | 22-Apr-2026 11:25:09 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 15:55:48 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 18:38:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 09:15:35 | 24-Apr-2026 02:49:40 | 0 |  |  | Approver | Locate
AO-001225 | MM-ZTK-1F-ZWP22-STR-DWG-2119 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 103000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 08:37:53 | wisuda.c@jutal.com | 23-Jul-2026 09:29:47 | Jumpol Sudjitjul | 03-Aug-2026 |  | Sompop Singhatiraj | 05-Aug-2026 | 24-Jul-2026 14:24:51 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 24-Jul-2026 22:41:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 27-Jul-2026 15:11:55 | 27-Jul-2026 10:33:24 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2119 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 103000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:22:31 | wisuda.c@jutal.com | 21-Sep-2026 18:03:19 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 25-Sep-2026 13:49:50 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 26-Sep-2026 05:28:27 | APPR | Approved | Jumpol Sudjitjul | 05-Oct-2026 | 26-Sep-2026 16:11:00 | 26-Sep-2026 09:28:24 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP22-STR-DWG-2120 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 113000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:56:56 | wisuda.c@jutal.com | 22-Apr-2026 10:51:41 | Jumpol Sudjitjul | 29-Apr-2026 | 24-Apr-2026 11:59:38 | Sompop Singhatiraj | 05-May-2026 | 24-Apr-2026 17:42:02 | Pornlert Wanaphattharaphan | 06-May-2026 | 29-Apr-2026 23:05:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 30-Apr-2026 08:43:06 | 30-Apr-2026 01:50:10 | 0 |  |  | Approver | Locate
AO-001225 | MM-ZTK-1F-ZWP22-STR-DWG-2120 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 113000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 08:38:21 | wisuda.c@jutal.com | 23-Jul-2026 09:29:47 | Jumpol Sudjitjul | 03-Aug-2026 |  | Sompop Singhatiraj | 05-Aug-2026 | 24-Jul-2026 14:24:57 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 24-Jul-2026 22:40:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 27-Jul-2026 15:18:19 | 27-Jul-2026 10:38:29 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2120 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 113000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:22:59 | wisuda.c@jutal.com | 21-Sep-2026 18:03:19 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 25-Sep-2026 15:35:52 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 26-Sep-2026 05:26:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Oct-2026 | 26-Sep-2026 16:12:02 | 26-Sep-2026 09:54:27 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP22-STR-DWG-2121 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 126500 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:57:19 | wisuda.c@jutal.com | 22-Apr-2026 10:51:29 | Jumpol Sudjitjul | 29-Apr-2026 | 24-Apr-2026 12:00:36 | Sompop Singhatiraj | 05-May-2026 | 24-Apr-2026 17:41:52 | Pornlert Wanaphattharaphan | 06-May-2026 | 29-Apr-2026 23:07:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 30-Apr-2026 09:16:16 | 30-Apr-2026 02:51:04 | 0 |  |  | Approver | Locate
AO-001225 | MM-ZTK-1F-ZWP22-STR-DWG-2121 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 126500 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 08:38:55 | wisuda.c@jutal.com | 23-Jul-2026 09:29:43 | Jumpol Sudjitjul | 03-Aug-2026 |  | Sompop Singhatiraj | 05-Aug-2026 | 24-Jul-2026 14:25:04 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 24-Jul-2026 22:39:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 27-Jul-2026 15:18:58 | 27-Jul-2026 10:39:45 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2121 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 126500 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:23:28 | wisuda.c@jutal.com | 21-Sep-2026 18:03:22 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 25-Sep-2026 12:10:20 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 26-Sep-2026 05:30:03 | APPR | Approved | Jumpol Sudjitjul | 05-Oct-2026 | 26-Sep-2026 16:12:26 | 26-Sep-2026 09:33:14 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP22-STR-DWG-2122 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 140000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:57:44 | wisuda.c@jutal.com | 22-Apr-2026 10:51:16 | Jumpol Sudjitjul | 29-Apr-2026 | 24-Apr-2026 12:01:19 | Sompop Singhatiraj | 05-May-2026 | 24-Apr-2026 17:40:41 | Pornlert Wanaphattharaphan | 06-May-2026 | 29-Apr-2026 23:15:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 30-Apr-2026 09:12:42 | 30-Apr-2026 02:49:48 | 0 |  |  | Approver | Locate
AO-001225 | MM-ZTK-1F-ZWP22-STR-DWG-2122 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 140000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 08:39:43 | wisuda.c@jutal.com | 23-Jul-2026 09:29:40 | Jumpol Sudjitjul | 03-Aug-2026 |  | Sompop Singhatiraj | 05-Aug-2026 | 24-Jul-2026 14:26:13 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 24-Jul-2026 22:39:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 27-Jul-2026 15:12:36 | 27-Jul-2026 10:34:39 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2122 | ZWP22 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 140000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:23:54 | wisuda.c@jutal.com | 21-Sep-2026 18:03:21 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 25-Sep-2026 16:18:47 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 26-Sep-2026 05:24:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Oct-2026 | 26-Sep-2026 16:13:18 | 26-Sep-2026 09:34:27 | 0 |  |  | Approver | Locate
AO-000203 | MM-ZTK-1F-ZWP22-STR-DWG-2123 | ZWP22 JACKET - FRAMING SECTIONS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 18:58:06 | wisuda.c@jutal.com | 22-Apr-2026 10:51:01 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 23-Apr-2026 16:15:50 | Pornlert Wanaphattharaphan | 06-May-2026 | 23-Apr-2026 18:25:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 24-Apr-2026 09:10:26 | 24-Apr-2026 02:48:27 | 0 |  |  | Approver | Locate
AO-001225 | MM-ZTK-1F-ZWP22-STR-DWG-2123 | ZWP22 JACKET - FRAMING SECTIONS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 08:41:06 | wisuda.c@jutal.com | 23-Jul-2026 09:29:44 | Jumpol Sudjitjul | 03-Aug-2026 |  | Sompop Singhatiraj | 05-Aug-2026 | 24-Jul-2026 09:39:56 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 24-Jul-2026 22:55:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 27-Jul-2026 15:10:41 | 27-Jul-2026 10:32:10 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2123 | ZWP22 JACKET - FRAMING SECTIONS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:24:23 | wisuda.c@jutal.com | 21-Sep-2026 18:03:49 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 25-Sep-2026 12:07:13 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 26-Sep-2026 05:30:35 | APPR | Approved | Jumpol Sudjitjul | 05-Oct-2026 | 26-Sep-2026 16:16:19 | 26-Sep-2026 09:50:32 | 0 |  |  | Approver | Locate
AO-000371 | MM-ZTK-1F-ZWP22-STR-DWG-2130 | ZWP22 JACKET - LAUNCH CRADLE GENERAL ARRANGEMENT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 18:45:43 | wisuda.c@jutal.com | 12-May-2026 11:12:07 | Jumpol Sudjitjul | 19-May-2026 |  | Sompop Singhatiraj | 21-May-2026 | 18-May-2026 10:46:28 | Pornlert Wanaphattharaphan | 22-May-2026 | 22-May-2026 00:26:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-May-2026 | 22-May-2026 08:25:02 | 22-May-2026 02:02:44 | 0 |  |  | Approver | Locate
AO-000985 | MM-ZTK-1F-ZWP22-STR-DWG-2130 | ZWP22 JACKET - LAUNCH CRADLE GENERAL ARRANGEMENT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 10:50:50 | wisuda.c@jutal.com | 03-Jul-2026 14:06:37 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 03-Jul-2026 17:31:39 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 04-Jul-2026 20:10:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 05-Jul-2026 10:51:11 | 05-Jul-2026 04:45:27 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2130 | ZWP22 JACKET - LAUNCH CRADLE GENERAL ARRANGEMENT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:24:49 | wisuda.c@jutal.com | 21-Sep-2026 18:03:45 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 22-Sep-2026 14:09:03 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 22-Sep-2026 19:49:47 | APPR | Approved | Jumpol Sudjitjul | 05-Oct-2026 | 23-Sep-2026 13:38:50 | 23-Sep-2026 06:54:56 | 0 |  |  | Approver | Locate
AO-000371 | MM-ZTK-1F-ZWP22-STR-DWG-2131 | ZWP22 JACKET - LAUNCH CRADLE DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 18:46:07 | wisuda.c@jutal.com | 12-May-2026 11:12:20 | Jumpol Sudjitjul | 19-May-2026 |  | Sompop Singhatiraj | 21-May-2026 | 18-May-2026 10:46:37 | Pornlert Wanaphattharaphan | 22-May-2026 | 22-May-2026 00:27:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-May-2026 | 22-May-2026 08:26:11 | 22-May-2026 02:04:00 | 0 |  |  | Approver | Locate
AO-000985 | MM-ZTK-1F-ZWP22-STR-DWG-2131 | ZWP22 JACKET - LAUNCH CRADLE DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 09:47:53 | wisuda.c@jutal.com | 03-Jul-2026 14:06:36 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 03-Jul-2026 17:29:48 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 04-Jul-2026 20:09:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 05-Jul-2026 10:38:44 | 05-Jul-2026 04:02:42 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2131 | ZWP22 JACKET - LAUNCH CRADLE DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 16:25:16 | wisuda.c@jutal.com | 21-Sep-2026 18:03:49 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 22-Sep-2026 14:11:29 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 22-Sep-2026 19:48:43 | APPR | Approved | Jumpol Sudjitjul | 05-Oct-2026 | 23-Sep-2026 13:39:24 | 23-Sep-2026 06:56:04 | 0 |  |  | Approver | Locate
AO-000371 | MM-ZTK-1F-ZWP22-STR-DWG-2132 | ZWP22 JACKET - LAUNCH CRADLE DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 18:07:59 | wisuda.c@jutal.com | 11-May-2026 18:16:30 | Jumpol Sudjitjul | 19-May-2026 |  | Sompop Singhatiraj | 21-May-2026 | 18-May-2026 10:48:02 | Pornlert Wanaphattharaphan | 22-May-2026 | 22-May-2026 00:40:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-May-2026 | 22-May-2026 08:27:27 | 22-May-2026 02:29:41 | 0 |  |  | Approver | Locate
AO-000985 | MM-ZTK-1F-ZWP22-STR-DWG-2132 | ZWP22 JACKET - LAUNCH CRADLE DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 10:51:42 | wisuda.c@jutal.com | 03-Jul-2026 14:06:36 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 03-Jul-2026 17:31:46 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 04-Jul-2026 20:14:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 05-Jul-2026 10:37:35 | 05-Jul-2026 04:13:07 | 0 |  |  | Approver | Locate
AO-001553 | MM-ZTK-1F-ZWP22-STR-DWG-2132 | ZWP22 JACKET - LAUNCH CRADLE DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 14:28:11 | wisuda.c@jutal.com | 17-Aug-2026 15:22:01 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 20-Aug-2026 13:51:30 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:21:09 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 18:09:13 | 24-Aug-2026 12:25:27 | 0 |  |  | Approver | Locate
AO-000518 | MM-ZTK-1F-ZWP22-STR-DWG-2133 | ZWP22 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 18:16:12 | wisuda.c@jutal.com | 19-May-2026 18:28:16 | Jumpol Sudjitjul | 27-May-2026 |  | Sompop Singhatiraj | 29-May-2026 | 20-May-2026 10:16:34 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 22-May-2026 01:05:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Jun-2026 | 22-May-2026 08:29:57 | 22-May-2026 02:46:25 | 0 |  |  | Approver | Locate
AO-001821 | MM-ZTK-1F-ZWP22-STR-DWG-2133 | ZWP22 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:44:41 | wisuda.c@jutal.com | 03-Sep-2026 11:06:07 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 08-Sep-2026 10:45:47 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 16:41:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 08:53:38 | 13-Sep-2026 02:32:39 | 0 |  |  | Approver | Locate
AO-000518 | MM-ZTK-1F-ZWP22-STR-DWG-2134 | ZWP22 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 18:16:37 | wisuda.c@jutal.com | 19-May-2026 18:28:18 | Jumpol Sudjitjul | 27-May-2026 |  | Sompop Singhatiraj | 29-May-2026 | 20-May-2026 10:19:08 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 22-May-2026 01:06:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Jun-2026 | 22-May-2026 09:11:33 | 22-May-2026 06:09:01 | 0 |  |  | Approver | Locate
AO-001821 | MM-ZTK-1F-ZWP22-STR-DWG-2134 | ZWP22 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:07:38 | wisuda.c@jutal.com | 03-Sep-2026 11:06:12 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 08-Sep-2026 10:45:59 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 16:42:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 08:43:09 | 13-Sep-2026 02:10:06 | 0 |  |  | Approver | Locate
AO-000518 | MM-ZTK-1F-ZWP22-STR-DWG-2135 | ZWP22 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 18:17:05 | wisuda.c@jutal.com | 19-May-2026 18:28:17 | Jumpol Sudjitjul | 27-May-2026 |  | Sompop Singhatiraj | 29-May-2026 | 20-May-2026 10:18:55 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 22-May-2026 01:06:16 | AWC |  | Jumpol Sudjitjul | 04-Jun-2026 | 22-May-2026 09:15:18 | 10-Jun-2026 08:43:09 | 0 |  |  | Approver | Locate
AO-001821 | MM-ZTK-1F-ZWP22-STR-DWG-2135 | ZWP22 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:08:18 | wisuda.c@jutal.com | 03-Sep-2026 11:06:07 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 08-Sep-2026 10:46:05 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 16:42:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 08:45:36 | 13-Sep-2026 02:12:29 | 0 |  |  | Approver | Locate
AO-000518 | MM-ZTK-1F-ZWP22-STR-DWG-2136 | ZWP22 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 18:17:34 | wisuda.c@jutal.com | 19-May-2026 18:28:19 | Jumpol Sudjitjul | 27-May-2026 |  | Sompop Singhatiraj | 29-May-2026 | 20-May-2026 10:28:25 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 22-May-2026 01:10:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Jun-2026 | 22-May-2026 09:17:29 | 22-May-2026 06:10:24 | 0 |  |  | Approver | Locate
AO-000985 | MM-ZTK-1F-ZWP22-STR-DWG-2136 | ZWP22 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 4 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 10:52:17 | wisuda.c@jutal.com | 03-Jul-2026 14:06:48 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 03-Jul-2026 17:54:05 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 04-Jul-2026 20:55:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 05-Jul-2026 10:50:55 | 05-Jul-2026 04:50:43 | 0 |  |  | Approver | Locate
AO-000400 | MM-ZTK-1F-ZWP22-STR-DWG-2141 | ZWP22 JACKET - PILE CLUSTER ARRANGEMENT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 10:47:57 | wisuda.c@jutal.com | 15-May-2026 13:25:57 | Jumpol Sudjitjul | 22-May-2026 |  | Sompop Singhatiraj | 26-May-2026 | 20-May-2026 12:06:23 | Pornlert Wanaphattharaphan | 27-May-2026 | 22-May-2026 00:30:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 22-May-2026 09:19:07 | 22-May-2026 05:41:11 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2141 | ZWP22 JACKET - PILE CLUSTER ARRANGEMENT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Sep-2026 16:25:45 | wisuda.c@jutal.com | 21-Sep-2026 18:03:53 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 22-Sep-2026 17:19:39 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 22-Sep-2026 19:48:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Oct-2026 | 23-Sep-2026 13:45:34 | 23-Sep-2026 06:58:25 | 0 |  |  | Approver | Locate
AO-002310 | MM-ZTK-1F-ZWP22-STR-DWG-2141 | ZWP22 JACKET - PILE CLUSTER ARRANGEMENT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 30-Sep-2026 09:28:13 | wisuda.c@jutal.com | 30-Sep-2026 16:08:42 | Jumpol Sudjitjul | 07-Oct-2026 |  | Sompop Singhatiraj | 09-Oct-2026 | 01-Oct-2026 15:54:00 | Pornlert Wanaphattharaphan | 12-Oct-2026 | 01-Oct-2026 22:47:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Oct-2026 | 02-Oct-2026 13:36:26 | 02-Oct-2026 07:32:28 | 0 |  |  | Approver | Locate
AO-000400 | MM-ZTK-1F-ZWP22-STR-DWG-2142 | ZWP22 JACKET - PILE SLEEVE DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 10:48:24 | wisuda.c@jutal.com | 15-May-2026 13:25:53 | Jumpol Sudjitjul | 22-May-2026 |  | Sompop Singhatiraj | 26-May-2026 | 20-May-2026 12:07:58 | Pornlert Wanaphattharaphan | 27-May-2026 | 22-May-2026 00:32:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 22-May-2026 09:21:04 | 22-May-2026 05:43:55 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP22-STR-DWG-2142 | ZWP22 JACKET - PILE SLEEVE DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Sep-2026 16:26:15 | wisuda.c@jutal.com | 21-Sep-2026 18:03:48 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 22-Sep-2026 17:20:19 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 22-Sep-2026 19:47:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Oct-2026 | 23-Sep-2026 13:46:23 | 23-Sep-2026 06:59:41 | 0 |  |  | Approver | Locate
AO-002310 | MM-ZTK-1F-ZWP22-STR-DWG-2142 | ZWP22 JACKET - PILE SLEEVE DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 30-Sep-2026 09:29:25 | wisuda.c@jutal.com | 30-Sep-2026 16:08:43 | Jumpol Sudjitjul | 07-Oct-2026 |  | Sompop Singhatiraj | 09-Oct-2026 | 01-Oct-2026 17:42:35 | Pornlert Wanaphattharaphan | 12-Oct-2026 | 01-Oct-2026 22:46:47 | APPR | Approved | Jumpol Sudjitjul | 14-Oct-2026 | 02-Oct-2026 13:35:03 | 02-Oct-2026 07:31:06 | 0 |  |  | Approver | Locate
AO-000400 | MM-ZTK-1F-ZWP22-STR-DWG-2143 | ZWP22 JACKET - SKIRT SLEEVE MARKING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 10:48:54 | wisuda.c@jutal.com | 15-May-2026 13:25:54 | Jumpol Sudjitjul | 22-May-2026 |  | Sompop Singhatiraj | 26-May-2026 | 20-May-2026 12:08:05 | Pornlert Wanaphattharaphan | 27-May-2026 | 22-May-2026 00:32:33 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 28-May-2026 | 22-May-2026 09:29:50 | 22-May-2026 05:39:58 | 0 |  |  | Approver | Locate
AO-000699 | MM-ZTK-1F-ZWP22-STR-DWG-2144 | ZWP22 JACKET - PILE MAKE-UP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 09:22:21 | wisuda.c@jutal.com | 08-Jun-2026 15:54:44 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 12-Jun-2026 13:40:52 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 13-Jun-2026 00:50:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 13-Jun-2026 07:02:23 | 13-Jun-2026 00:30:10 | 0 |  |  | Approver | Locate
AO-001821 | MM-ZTK-1F-ZWP22-STR-DWG-2144 | ZWP22 JACKET - PILE MAKE-UP |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:08:56 | wisuda.c@jutal.com | 03-Sep-2026 11:06:15 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 07-Sep-2026 13:46:29 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 15:51:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 08:50:14 | 13-Sep-2026 02:30:03 | 0 |  |  | Approver | Locate
AO-002308 | MM-ZTK-1F-ZWP22-STR-DWG-2144 | ZWP22 JACKET - PILE MAKE-UP |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 30-Sep-2026 09:30:49 | wisuda.c@jutal.com | 30-Sep-2026 16:08:41 | Jumpol Sudjitjul | 07-Oct-2026 |  | Sompop Singhatiraj | 09-Oct-2026 | 01-Oct-2026 15:42:02 | Pornlert Wanaphattharaphan | 12-Oct-2026 | 01-Oct-2026 22:47:21 | APPR | Approved | Jumpol Sudjitjul | 14-Oct-2026 | 02-Oct-2026 13:18:00 | 02-Oct-2026 07:14:40 | 0 |  |  | Approver | Locate
AO-000984 | MM-ZTK-1F-ZWP22-STR-DWG-2200 | ZWP22 JACKET - HYDROSTATIC RING DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 10:52:52 | wisuda.c@jutal.com | 03-Jul-2026 14:09:54 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 03-Jul-2026 17:54:13 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 04-Jul-2026 20:56:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 05-Jul-2026 10:48:04 | 05-Jul-2026 04:49:23 | 0 |  |  | Approver | Locate
AO-002164 | MM-ZTK-1F-ZWP22-STR-DWG-2200 | ZWP22 JACKET - HYDROSTATIC RING DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 18-Sep-2026 19:00:07 | wisuda.c@jutal.com | 20-Sep-2026 12:44:49 | Jumpol Sudjitjul | 25-Sep-2026 |  | Sompop Singhatiraj | 29-Sep-2026 | 29-Sep-2026 07:07:18 | Pornlert Wanaphattharaphan | 30-Sep-2026 | 30-Sep-2026 00:49:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Oct-2026 | 30-Sep-2026 15:48:16 | 30-Sep-2026 10:32:50 | 0 |  |  | Approver | Locate
AO-000984 | MM-ZTK-1F-ZWP22-STR-DWG-2201 | ZWP22 JACKET - HYDROSTATIC RING DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Jul-2026 10:53:27 | wisuda.c@jutal.com | 03-Jul-2026 14:10:26 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 03-Jul-2026 17:55:27 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 04-Jul-2026 20:57:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 05-Jul-2026 10:47:17 | 05-Jul-2026 04:48:07 | 0 |  |  | Approver | Locate
AO-002164 | MM-ZTK-1F-ZWP22-STR-DWG-2201 | ZWP22 JACKET - HYDROSTATIC RING DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 18-Sep-2026 19:00:38 | wisuda.c@jutal.com | 20-Sep-2026 12:46:35 | Jumpol Sudjitjul | 25-Sep-2026 |  | Sompop Singhatiraj | 29-Sep-2026 | 28-Sep-2026 10:21:49 | Pornlert Wanaphattharaphan | 30-Sep-2026 | 28-Sep-2026 22:09:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Oct-2026 | 29-Sep-2026 10:49:33 | 29-Sep-2026 04:44:45 | 0 |  |  | Approver | Locate
AO-000740 | MM-ZTK-1F-ZWP22-STR-DWG-2241 | ZWP22 JACKET - RISER PROTECTOR |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 18:14:43 | wisuda.c@jutal.com | 12-Jun-2026 09:49:10 | Jumpol Sudjitjul | 19-Jun-2026 |  | Sompop Singhatiraj | 23-Jun-2026 | 15-Jun-2026 16:01:01 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 18-Jun-2026 20:21:19 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 25-Jun-2026 | 19-Jun-2026 08:51:17 | 19-Jun-2026 02:25:08 | 0 |  |  | Approver | Locate
AO-001845 | MM-ZTK-1F-ZWP22-STR-DWG-2300 | ZWP22 JACKET - CASING GUIDE ARRANGEMENT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Sep-2026 16:46:07 | wisuda.c@jutal.com | 03-Sep-2026 17:37:46 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 07-Sep-2026 13:57:09 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 16:46:39 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 08:49:40 | 13-Sep-2026 02:27:39 | 0 |  |  | Approver | Locate
AO-002217 | MM-ZTK-1F-ZWP22-STR-DWG-2300 | ZWP22 JACKET - CASING GUIDE ARRANGEMENT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 23-Sep-2026 09:28:28 | wisuda.c@jutal.com | 23-Sep-2026 13:57:07 | Jumpol Sudjitjul | 30-Sep-2026 |  | Sompop Singhatiraj | 02-Oct-2026 | 25-Sep-2026 11:23:36 | Pornlert Wanaphattharaphan | 05-Oct-2026 |  |  |  |  | 06-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001845 | MM-ZTK-1F-ZWP22-STR-DWG-2301 | ZWP22 JACKET - CASING GUIDE DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Sep-2026 16:46:39 | wisuda.c@jutal.com | 03-Sep-2026 17:37:47 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 07-Sep-2026 14:09:43 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 16:52:19 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 10:30:08 | 13-Sep-2026 03:53:06 | 0 |  |  | Approver | Locate
AO-002217 | MM-ZTK-1F-ZWP22-STR-DWG-2301 | ZWP22 JACKET - CASING GUIDE DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 23-Sep-2026 09:29:03 | wisuda.c@jutal.com | 23-Sep-2026 13:57:05 | Jumpol Sudjitjul | 30-Sep-2026 |  | Sompop Singhatiraj | 02-Oct-2026 | 25-Sep-2026 11:16:01 | Pornlert Wanaphattharaphan | 05-Oct-2026 | 26-Sep-2026 05:22:56 | APPR | Approved | Jumpol Sudjitjul | 06-Oct-2026 | 26-Sep-2026 16:17:44 | 26-Sep-2026 09:56:14 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP22-STR-DWG-2311 | ZWP22 JACKET - ANODE STRUCTURE AND INSTALLATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:05:31 | wisuda.c@jutal.com | 04-May-2026 11:59:53 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 10:48:44 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 15:10:44 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:40:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:02:01 | 19-May-2026 03:47:47 | 0 |  |  | Approver | Locate
AO-001848 | MM-ZTK-1F-ZWP22-STR-DWG-2311 | ZWP22 JACKET - ANODE STRUCTURE AND INSTALLATION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Sep-2026 18:13:47 | wisuda.c@jutal.com | 04-Sep-2026 08:04:00 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 07-Sep-2026 14:53:26 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 16:53:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 10:33:55 | 13-Sep-2026 03:57:50 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP22-STR-DWG-2311 | ZWP22 JACKET - ANODE STRUCTURE AND INSTALLATION |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 09:28:09 | wisuda.c@jutal.com | 14-Oct-2026 09:46:15 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 15:18:26 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:35:02 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:03:39 | 16-Oct-2026 09:11:23 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP22-STR-DWG-2312 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'A' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:05:54 | wisuda.c@jutal.com | 04-May-2026 12:00:07 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 10:51:20 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 15:57:25 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:48:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 09:59:33 | 19-May-2026 03:46:30 | 0 |  |  | Approver | Locate
AO-001848 | MM-ZTK-1F-ZWP22-STR-DWG-2312 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'A' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Sep-2026 18:14:12 | wisuda.c@jutal.com | 04-Sep-2026 08:04:00 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 07-Sep-2026 15:36:08 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 16:55:48 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 10:35:47 | 13-Sep-2026 04:01:39 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP22-STR-DWG-2312 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'A' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 09:28:40 | wisuda.c@jutal.com | 14-Oct-2026 09:46:15 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 15:18:29 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:35:44 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:04:10 | 16-Oct-2026 09:12:35 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP22-STR-DWG-2313 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'B' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:06:17 | wisuda.c@jutal.com | 04-May-2026 12:00:18 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 10:53:29 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 08:45:45 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:52:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 09:58:16 | 19-May-2026 03:44:28 | 0 |  |  | Approver | Locate
AO-001848 | MM-ZTK-1F-ZWP22-STR-DWG-2313 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'B' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Sep-2026 18:14:37 | wisuda.c@jutal.com | 04-Sep-2026 08:04:01 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 07-Sep-2026 15:36:14 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 16:57:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 08:53:04 | 13-Sep-2026 02:26:33 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP22-STR-DWG-2313 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'B' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 09:29:20 | wisuda.c@jutal.com | 14-Oct-2026 09:46:21 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 15:22:06 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:36:53 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:07:46 | 16-Oct-2026 09:13:47 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP22-STR-DWG-2314 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '1' & '1.1' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:06:41 | wisuda.c@jutal.com | 04-May-2026 12:49:15 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 10:55:14 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 15:59:00 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:48:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 10:02:42 | 19-May-2026 03:48:57 | 0 |  |  | Approver | Locate
AO-001848 | MM-ZTK-1F-ZWP22-STR-DWG-2314 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '1' & '1.1' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Sep-2026 18:15:02 | wisuda.c@jutal.com | 04-Sep-2026 08:04:00 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 07-Sep-2026 15:36:21 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 16:57:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 08:51:37 | 13-Sep-2026 02:24:04 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP22-STR-DWG-2314 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '1' & '1.1' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 09:29:56 | wisuda.c@jutal.com | 14-Oct-2026 09:46:15 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 15:18:39 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:36:29 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:09:16 | 16-Oct-2026 09:14:58 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP22-STR-DWG-2315 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '2' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:07:07 | wisuda.c@jutal.com | 04-May-2026 12:49:27 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 10:56:46 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 16:00:11 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:48:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 09:22:26 | 19-May-2026 03:31:40 | 0 |  |  | Approver | Locate
AO-001848 | MM-ZTK-1F-ZWP22-STR-DWG-2315 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '2' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Sep-2026 18:15:27 | wisuda.c@jutal.com | 04-Sep-2026 08:04:01 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 07-Sep-2026 15:36:29 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 16:58:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 10:37:33 | 13-Sep-2026 04:02:53 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP22-STR-DWG-2315 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '2' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 09:30:33 | wisuda.c@jutal.com | 14-Oct-2026 09:46:14 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 15:22:16 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:37:21 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:10:58 | 16-Oct-2026 09:17:21 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP22-STR-DWG-2316 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'AA' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:07:30 | wisuda.c@jutal.com | 04-May-2026 12:53:28 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 10:59:21 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 15:55:01 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:46:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 14:39:10 | 19-May-2026 08:48:15 | 0 |  |  | Approver | Locate
AO-001848 | MM-ZTK-1F-ZWP22-STR-DWG-2316 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'AA' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Sep-2026 18:15:53 | wisuda.c@jutal.com | 04-Sep-2026 08:04:12 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 07-Sep-2026 15:38:15 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 17:01:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 10:40:11 | 13-Sep-2026 04:04:10 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP22-STR-DWG-2316 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'AA' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 09:31:02 | wisuda.c@jutal.com | 14-Oct-2026 09:46:17 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 15:24:13 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:37:47 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:14:34 | 16-Oct-2026 09:18:36 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP22-STR-DWG-2317 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'BB' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:07:53 | wisuda.c@jutal.com | 04-May-2026 12:46:08 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:02:03 | Sompop Singhatiraj | 13-May-2026 | 12-May-2026 10:33:07 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:51:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 14:38:29 | 19-May-2026 08:49:47 | 0 |  |  | Approver | Locate
AO-001848 | MM-ZTK-1F-ZWP22-STR-DWG-2317 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'BB' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Sep-2026 18:16:18 | wisuda.c@jutal.com | 04-Sep-2026 08:04:07 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 07-Sep-2026 15:38:05 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 17:00:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 08:52:32 | 13-Sep-2026 02:25:20 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP22-STR-DWG-2317 | ZWP22 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'BB' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 09:31:32 | wisuda.c@jutal.com | 14-Oct-2026 09:46:19 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 15:24:17 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:38:14 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:15:19 | 16-Oct-2026 09:19:47 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP22-STR-DWG-2321 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 14000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:08:17 | wisuda.c@jutal.com | 04-May-2026 12:45:56 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:03:45 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:50:35 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:07:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 09:47:55 | 19-May-2026 03:42:15 | 0 |  |  | Approver | Locate
AO-001869 | MM-ZTK-1F-ZWP22-STR-DWG-2321 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 14000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 08:40:14 | wisuda.c@jutal.com | 04-Sep-2026 11:13:54 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 07-Sep-2026 16:08:24 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 17:02:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 10:45:26 | 13-Sep-2026 03:52:03 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP22-STR-DWG-2321 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 14000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 09:32:00 | wisuda.c@jutal.com | 14-Oct-2026 09:47:36 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 15:24:22 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:39:14 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:15:44 | 16-Oct-2026 09:20:58 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP22-STR-DWG-2322 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 26000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:08:40 | wisuda.c@jutal.com | 04-May-2026 11:51:02 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:05:32 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:50:49 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:08:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 09:35:17 | 19-May-2026 03:41:03 | 0 |  |  | Approver | Locate
AO-001857 | MM-ZTK-1F-ZWP22-STR-DWG-2322 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 26000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Sep-2026 18:16:42 | wisuda.c@jutal.com | 04-Sep-2026 08:04:04 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 08-Sep-2026 06:58:00 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 17:16:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 10:34:55 | 13-Sep-2026 03:59:04 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP22-STR-DWG-2322 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 26000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 09:32:27 | wisuda.c@jutal.com | 14-Oct-2026 09:47:42 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 15:24:26 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:39:54 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:16:44 | 16-Oct-2026 09:22:07 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP22-STR-DWG-2323 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 38000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:09:04 | wisuda.c@jutal.com | 04-May-2026 11:51:15 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:07:18 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:50:24 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:07:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 09:30:41 | 19-May-2026 03:34:51 | 0 |  |  | Approver | Locate
AO-001861 | MM-ZTK-1F-ZWP22-STR-DWG-2323 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 38000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 08:40:40 | wisuda.c@jutal.com | 04-Sep-2026 11:13:54 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 07-Sep-2026 16:14:23 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 17:05:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 10:54:58 | 13-Sep-2026 04:27:36 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP22-STR-DWG-2323 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 38000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 09:33:05 | wisuda.c@jutal.com | 14-Oct-2026 09:47:44 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 15:24:29 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:41:38 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:19:27 | 16-Oct-2026 09:24:29 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP22-STR-DWG-2324 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 52000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:09:28 | wisuda.c@jutal.com | 04-May-2026 11:51:28 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:08:59 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:52:14 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:08:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 09:31:50 | 19-May-2026 03:36:54 | 0 |  |  | Approver | Locate
AO-001863 | MM-ZTK-1F-ZWP22-STR-DWG-2324 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 52000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 08:41:05 | wisuda.c@jutal.com | 04-Sep-2026 11:13:58 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 07-Sep-2026 16:13:17 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 17:03:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 11:03:29 | 13-Sep-2026 04:30:14 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP22-STR-DWG-2324 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 52000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 09:33:42 | wisuda.c@jutal.com | 14-Oct-2026 09:47:49 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 15:27:07 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:42:14 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:21:37 | 16-Oct-2026 09:25:39 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP22-STR-DWG-2325 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 66000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:09:50 | wisuda.c@jutal.com | 04-May-2026 11:51:40 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:11:18 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:52:21 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:09:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 09:22:30 | 19-May-2026 03:32:48 | 0 |  |  | Approver | Locate
AO-001865 | MM-ZTK-1F-ZWP22-STR-DWG-2325 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 66000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 08:41:30 | wisuda.c@jutal.com | 04-Sep-2026 11:13:56 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 07-Sep-2026 16:14:30 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 17:11:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 10:26:05 | 13-Sep-2026 03:49:26 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP22-STR-DWG-2325 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 66000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 09:34:12 | wisuda.c@jutal.com | 14-Oct-2026 09:47:53 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 15:27:10 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:42:55 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:22:01 | 16-Oct-2026 09:26:50 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP22-STR-DWG-2326 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 79500 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:10:14 | wisuda.c@jutal.com | 04-May-2026 11:54:31 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:13:38 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:52:29 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:10:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 09:20:27 | 19-May-2026 03:30:31 | 0 |  |  | Approver | Locate
AO-001867 | MM-ZTK-1F-ZWP22-STR-DWG-2326 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 79500 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 08:41:57 | wisuda.c@jutal.com | 04-Sep-2026 11:13:59 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 07-Sep-2026 16:17:27 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 17:15:51 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 10:31:30 | 13-Sep-2026 03:50:45 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP22-STR-DWG-2326 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 79500 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 09:34:42 | wisuda.c@jutal.com | 14-Oct-2026 09:47:42 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 15:27:15 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:43:21 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:22:48 | 16-Oct-2026 09:28:00 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP22-STR-DWG-2327 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 93000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:10:38 | wisuda.c@jutal.com | 04-May-2026 11:48:36 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:23:15 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:53:38 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:11:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 09:18:15 | 19-May-2026 03:29:16 | 0 |  |  | Approver | Locate
AO-001868 | MM-ZTK-1F-ZWP22-STR-DWG-2327 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 93000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 08:42:20 | wisuda.c@jutal.com | 04-Sep-2026 11:13:56 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 07-Sep-2026 16:17:12 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 17:13:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 11:08:19 | 13-Sep-2026 04:36:46 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP22-STR-DWG-2327 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 93000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 09:35:11 | wisuda.c@jutal.com | 14-Oct-2026 09:47:51 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 15:27:20 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:44:14 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:23:18 | 16-Oct-2026 09:29:14 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP22-STR-DWG-2328 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 103000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:11:04 | wisuda.c@jutal.com | 04-May-2026 11:48:50 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:25:31 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:53:48 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:10:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 09:15:35 | 19-May-2026 03:28:06 | 0 |  |  | Approver | Locate
AO-001866 | MM-ZTK-1F-ZWP22-STR-DWG-2328 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 103000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 08:42:49 | wisuda.c@jutal.com | 04-Sep-2026 11:14:00 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 07-Sep-2026 16:17:19 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 17:14:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 11:09:52 | 13-Sep-2026 04:39:18 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP22-STR-DWG-2328 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 103000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 09:35:44 | wisuda.c@jutal.com | 14-Oct-2026 09:47:49 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 15:27:24 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:45:03 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:25:27 | 16-Oct-2026 09:31:33 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP22-STR-DWG-2329 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 113000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 17:11:28 | wisuda.c@jutal.com | 04-May-2026 11:49:03 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:28:39 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:53:52 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:11:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 09:10:47 | 19-May-2026 03:26:50 | 0 |  |  | Approver | Locate
AO-001864 | MM-ZTK-1F-ZWP22-STR-DWG-2329 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 113000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 08:43:14 | wisuda.c@jutal.com | 04-Sep-2026 11:14:02 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 08-Sep-2026 06:58:47 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 17:17:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 10:53:32 | 13-Sep-2026 04:26:17 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP22-STR-DWG-2329 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 113000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 09:36:12 | wisuda.c@jutal.com | 14-Oct-2026 09:47:56 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 15:29:52 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:46:43 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:24:33 | 16-Oct-2026 09:30:22 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP22-STR-DWG-2330 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 126500 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 16:32:42 | wisuda.c@jutal.com | 04-May-2026 11:49:15 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:31:45 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:36:45 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:00:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 09:08:38 | 19-May-2026 03:52:16 | 0 |  |  | Approver | Locate
AO-001862 | MM-ZTK-1F-ZWP22-STR-DWG-2330 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 126500 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 08:43:40 | wisuda.c@jutal.com | 04-Sep-2026 11:14:07 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 08-Sep-2026 07:03:30 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 17:27:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 10:59:19 | 13-Sep-2026 04:28:58 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP22-STR-DWG-2330 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 126500 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 09:36:45 | wisuda.c@jutal.com | 14-Oct-2026 09:47:56 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 15:29:57 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:49:38 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:26:23 | 16-Oct-2026 09:32:43 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP22-STR-DWG-2331 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 140000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 16:33:07 | wisuda.c@jutal.com | 04-May-2026 11:54:43 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:35:43 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:54:23 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:12:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 09:02:29 | 19-May-2026 02:18:45 | 0 |  |  | Approver | Locate
AO-001859 | MM-ZTK-1F-ZWP22-STR-DWG-2331 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 140000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Sep-2026 18:17:06 | wisuda.c@jutal.com | 04-Sep-2026 08:04:04 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 08-Sep-2026 06:59:48 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 17:19:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 11:10:58 | 13-Sep-2026 04:22:34 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP22-STR-DWG-2331 | ZWP22 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 140000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 09:37:14 | wisuda.c@jutal.com | 14-Oct-2026 09:47:50 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 15:30:01 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:47:36 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:10:28 | 16-Oct-2026 09:16:09 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP22-STR-DWG-2332 | ZWP22 JACKET - ANODE DISTRIBUTION OF PILE CLUSTER |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 16:33:32 | wisuda.c@jutal.com | 04-May-2026 11:54:55 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:35:07 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:27:43 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:58:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 09:00:26 | 19-May-2026 02:17:22 | 0 |  |  | Approver | Locate
AO-001856 | MM-ZTK-1F-ZWP22-STR-DWG-2332 | ZWP22 JACKET - ANODE DISTRIBUTION OF PILE CLUSTER |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Sep-2026 18:17:31 | wisuda.c@jutal.com | 04-Sep-2026 08:04:10 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 08-Sep-2026 07:00:51 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 17:26:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 10:35:41 | 13-Sep-2026 04:00:21 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP22-STR-DWG-2332 | ZWP22 JACKET - ANODE DISTRIBUTION OF PILE CLUSTER |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 09:37:41 | wisuda.c@jutal.com | 14-Oct-2026 09:50:43 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 15:30:04 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:45:49 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:19:14 | 16-Oct-2026 09:23:15 | 0 |  |  | Approver | Locate
AO-000822 | MM-ZTK-1F-ZWP22-STR-DWG-2801 | ZWP22 JACKET RISER AND RISER SUPPORT LOCATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 09:16:14 | wisuda.c@jutal.com | 18-Jun-2026 10:03:18 | Jumpol Sudjitjul | 25-Jun-2026 | 18-Jun-2026 15:54:32 | Sompop Singhatiraj | 29-Jun-2026 | 19-Jun-2026 16:58:35 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 20-Jun-2026 17:30:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 21-Jun-2026 21:31:17 | 22-Jun-2026 00:23:10 | 0 |  |  | Approver | Locate
AO-002032 | MM-ZTK-1F-ZWP22-STR-DWG-2801 | ZWP22 JACKET RISER AND RISER SUPPORT LOCATION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 14-Sep-2026 09:48:55 | wisuda.c@jutal.com | 15-Sep-2026 15:03:45 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 17-Sep-2026 17:55:45 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 19-Sep-2026 15:54:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 20-Sep-2026 18:23:38 | 20-Sep-2026 13:16:09 | 0 |  |  | Approver | Locate
AO-002063 | MM-ZTK-1F-ZWP22-STR-DWG-2802 | ZWP22 JACKET 18" RISER CLAMP DETAILS - HANGER CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Sep-2026 19:25:34 | wisuda.c@jutal.com | 15-Sep-2026 14:52:30 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 17-Sep-2026 18:06:24 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 19-Sep-2026 15:55:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 20-Sep-2026 18:24:07 | 20-Sep-2026 13:17:15 | 0 |  |  | Approver | Locate
AO-002064 | MM-ZTK-1F-ZWP22-STR-DWG-2803 | ZWP22 JACKET 18" RISER CLAMP DETAILS - SLIDING CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Sep-2026 20:04:06 | wisuda.c@jutal.com | 15-Sep-2026 14:52:27 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 17-Sep-2026 18:06:35 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 19-Sep-2026 15:56:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 20-Sep-2026 18:24:53 | 20-Sep-2026 12:39:51 | 0 |  |  | Approver | Locate
AO-002033 | MM-ZTK-1F-ZWP22-STR-DWG-2804 | ZWP22 JACKET 18" RISER CLAMP DETAILS - SLIDING CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Sep-2026 10:29:14 | wisuda.c@jutal.com | 15-Sep-2026 14:52:34 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 17-Sep-2026 18:06:41 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 19-Sep-2026 15:57:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 20-Sep-2026 18:25:25 | 20-Sep-2026 12:10:39 | 0 |  |  | Approver | Locate
AO-002033 | MM-ZTK-1F-ZWP22-STR-DWG-2805 | ZWP22 JACKET 18" RISER CLAMP DETAILS - TEMPORARY CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Sep-2026 10:30:06 | wisuda.c@jutal.com | 15-Sep-2026 14:52:27 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 17-Sep-2026 18:07:40 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 19-Sep-2026 15:57:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 20-Sep-2026 18:25:51 | 20-Sep-2026 12:11:49 | 0 |  |  | Approver | Locate
AO-002033 | MM-ZTK-1F-ZWP22-STR-DWG-2806 | ZWP22 JACKET - 10" RISER CLAMP DETAILS - HANGER CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Sep-2026 09:49:38 | wisuda.c@jutal.com | 15-Sep-2026 14:52:32 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 17-Sep-2026 18:09:02 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 19-Sep-2026 15:59:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 20-Sep-2026 18:26:55 | 20-Sep-2026 13:18:22 | 0 |  |  | Approver | Locate
AO-002033 | MM-ZTK-1F-ZWP22-STR-DWG-2807 | ZWP22 JACKET - 10" RISER CLAMP DETAILS - SLIDING CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Sep-2026 10:31:02 | wisuda.c@jutal.com | 15-Sep-2026 14:52:34 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 17-Sep-2026 18:09:17 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 19-Sep-2026 15:59:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 20-Sep-2026 18:28:32 | 20-Sep-2026 12:12:58 | 0 |  |  | Approver | Locate
AO-002033 | MM-ZTK-1F-ZWP22-STR-DWG-2808 | ZWP22 JACKET - 10" RISER CLAMP DETAILS - SLIDING CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Sep-2026 09:50:10 | wisuda.c@jutal.com | 15-Sep-2026 14:52:32 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 17-Sep-2026 18:09:23 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 19-Sep-2026 16:00:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 20-Sep-2026 18:28:00 | 20-Sep-2026 13:19:30 | 0 |  |  | Approver | Locate
AO-002033 | MM-ZTK-1F-ZWP22-STR-DWG-2809 | ZWP22 JACKET - 10" RISER CLAMP DETAILS - TEMPORARY CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Sep-2026 09:50:40 | wisuda.c@jutal.com | 15-Sep-2026 14:52:32 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 17-Sep-2026 18:10:02 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 19-Sep-2026 16:01:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 20-Sep-2026 18:29:24 | 20-Sep-2026 13:20:40 | 0 |  |  | Approver | Locate
AO-000740 | MM-ZTK-1F-ZWP22-STR-DWG-2900 | ZWP22 JACKET - CLOSURE PLATE DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 18:15:09 | wisuda.c@jutal.com | 12-Jun-2026 10:14:21 | Jumpol Sudjitjul | 19-Jun-2026 |  | Sompop Singhatiraj | 23-Jun-2026 | 15-Jun-2026 17:05:08 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 18-Jun-2026 20:29:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 19-Jun-2026 08:47:58 | 19-Jun-2026 02:23:51 | 0 |  |  | Approver | Locate
AO-001895 | MM-ZTK-1F-ZWP22-STR-DWG-2900 | ZWP22 JACKET - CLOSURE PLATE DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:23:56 | wisuda.c@jutal.com | 08-Sep-2026 08:57:27 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 15:56:04 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 13:19:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:31:12 | 20-Sep-2026 13:14:00 | 0 |  |  | Approver | Locate
AO-002417 | MM-ZTK-1F-ZWP22-STR-DWG-2900 | ZWP22 JACKET - CLOSURE PLATE DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 08-Oct-2026 09:19:47 | wisuda.c@jutal.com | 08-Oct-2026 10:32:11 | Jumpol Sudjitjul | 16-Oct-2026 |  | Sompop Singhatiraj | 20-Oct-2026 | 08-Oct-2026 15:00:38 | Pornlert Wanaphattharaphan | 21-Oct-2026 | 11-Oct-2026 00:20:19 | APPR | Approved | Jumpol Sudjitjul | 22-Oct-2026 | 11-Oct-2026 10:51:07 | 11-Oct-2026 03:57:35 | 0 |  |  | Approver | Locate
AO-000740 | MM-ZTK-1F-ZWP22-STR-DWG-2901 | ZWP22 JACKET - CLOSURE PLATE DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 18:15:36 | wisuda.c@jutal.com | 12-Jun-2026 10:14:21 | Jumpol Sudjitjul | 19-Jun-2026 |  | Sompop Singhatiraj | 23-Jun-2026 | 15-Jun-2026 17:06:42 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 18-Jun-2026 20:34:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 19-Jun-2026 08:46:09 | 19-Jun-2026 02:22:37 | 0 |  |  | Approver | Locate
AO-001895 | MM-ZTK-1F-ZWP22-STR-DWG-2901 | ZWP22 JACKET - CLOSURE PLATE DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:24:28 | wisuda.c@jutal.com | 08-Sep-2026 08:57:45 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 15:56:09 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 13:23:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:33:02 | 20-Sep-2026 13:15:08 | 0 |  |  | Approver | Locate
AO-002418 | MM-ZTK-1F-ZWP22-STR-DWG-2901 | ZWP22 JACKET - CLOSURE PLATE DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 08-Oct-2026 09:20:22 | wisuda.c@jutal.com | 08-Oct-2026 10:32:14 | Jumpol Sudjitjul | 16-Oct-2026 |  | Sompop Singhatiraj | 20-Oct-2026 | 08-Oct-2026 15:19:10 | Pornlert Wanaphattharaphan | 21-Oct-2026 | 11-Oct-2026 00:24:04 | APPR | Approved | Jumpol Sudjitjul | 22-Oct-2026 | 11-Oct-2026 10:52:11 | 11-Oct-2026 04:27:48 | 0 |  |  | Approver | Locate
AO-000742 | MM-ZTK-1F-ZWP22-STR-DWG-2902 | ZWP22 JACKET - LEG PARTITION DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 12-Jun-2026 08:39:54 | wisuda.c@jutal.com | 12-Jun-2026 10:14:22 | Jumpol Sudjitjul | 19-Jun-2026 |  | Sompop Singhatiraj | 23-Jun-2026 | 15-Jun-2026 17:07:27 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 18-Jun-2026 20:35:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 19-Jun-2026 08:45:36 | 19-Jun-2026 02:28:42 | 0 |  |  | Approver | Locate
AO-001774 | MM-ZTK-1F-ZWP22-STR-DWG-2902 | ZWP22 JACKET - LEG PARTITION DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:32:05 | wisuda.c@jutal.com | 31-Aug-2026 11:08:00 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 03-Sep-2026 09:23:01 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 04-Sep-2026 23:49:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 05-Sep-2026 18:09:17 | 05-Sep-2026 12:03:36 | 0 |  |  | Approver | Locate
AO-002419 | MM-ZTK-1F-ZWP22-STR-DWG-2902 | ZWP22 JACKET - LEG PARTITION DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 08-Oct-2026 09:21:03 | wisuda.c@jutal.com | 08-Oct-2026 10:32:11 | Jumpol Sudjitjul | 16-Oct-2026 |  | Sompop Singhatiraj | 20-Oct-2026 | 08-Oct-2026 15:25:32 | Pornlert Wanaphattharaphan | 21-Oct-2026 | 11-Oct-2026 00:25:07 | APPR | Approved | Jumpol Sudjitjul | 22-Oct-2026 | 11-Oct-2026 10:52:43 | 11-Oct-2026 04:28:58 | 0 |  |  | Approver | Locate
AO-002301 | MM-ZTK-1F-ZWP22-STR-DWG-2911 | ZWP22 JACKET - UPENDING ARRANGEMENT AND DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-Sep-2026 18:00:20 | wisuda.c@jutal.com | 29-Sep-2026 14:27:10 | Jumpol Sudjitjul | 06-Oct-2026 |  | Sompop Singhatiraj | 08-Oct-2026 | 06-Oct-2026 09:31:33 | Pornlert Wanaphattharaphan | 09-Oct-2026 | 10-Oct-2026 01:36:32 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 12-Oct-2026 | 10-Oct-2026 17:38:44 | 10-Oct-2026 10:57:52 | 0 |  |  | Approver | Locate
AO-000308 | MM-ZTK-1F-ZWP22-STR-DWG-2931 | ZWP22 JACKET - BALLAST / DEBASSAST SCHEMATIC |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 05-May-2026 19:08:02 | wisuda.c@jutal.com | 06-May-2026 10:09:10 | Jumpol Sudjitjul | 13-May-2026 |  | Sompop Singhatiraj | 15-May-2026 | 16-May-2026 11:46:35 | Pornlert Wanaphattharaphan | 18-May-2026 | 18-May-2026 23:26:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 19-May-2026 08:42:03 | 19-May-2026 02:23:11 | 0 |  |  | Approver | Locate
AO-001660 | MM-ZTK-1F-ZWP22-STR-DWG-2931 | ZWP22 JACKET - BALLAST / DEBASSAST SCHEMATIC |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:53:18 | wisuda.c@jutal.com | 24-Aug-2026 20:32:51 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 03-Sep-2026 12:43:49 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 01:01:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:05:57 | 08-Sep-2026 04:52:17 | 0 |  |  | Approver | Locate
AO-000308 | MM-ZTK-1F-ZWP22-STR-DWG-2932 | ZWP22 JACKET - GROUTING SCHEMATIC |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 05-May-2026 19:08:24 | wisuda.c@jutal.com | 06-May-2026 10:09:23 | Jumpol Sudjitjul | 13-May-2026 |  | Sompop Singhatiraj | 15-May-2026 | 16-May-2026 11:48:32 | Pornlert Wanaphattharaphan | 18-May-2026 | 18-May-2026 23:28:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 19-May-2026 08:58:38 | 19-May-2026 02:24:29 | 0 |  |  | Approver | Locate
AO-001660 | MM-ZTK-1F-ZWP22-STR-DWG-2932 | ZWP22 JACKET - GROUTING SCHEMATIC |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 10:52:17 | wisuda.c@jutal.com | 24-Aug-2026 20:32:52 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 03-Sep-2026 11:32:53 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:58:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:06:17 | 08-Sep-2026 04:35:48 | 0 |  |  | Approver | Locate
AO-001775 | MM-ZTK-1F-ZWP22-STR-DWG-2933 | ZWP22 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT ROW A ELEVATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 31-Aug-2026 09:32:35 | wisuda.c@jutal.com | 31-Aug-2026 11:27:07 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 03-Sep-2026 13:59:46 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 04-Sep-2026 23:29:27 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-Sep-2026 | 05-Sep-2026 18:09:43 | 05-Sep-2026 12:04:53 | 0 |  |  | Approver | Locate
AO-001775 | MM-ZTK-1F-ZWP22-STR-DWG-2934 | ZWP22 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT ROW B ELEVATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 31-Aug-2026 09:33:07 | wisuda.c@jutal.com | 31-Aug-2026 11:27:31 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 03-Sep-2026 13:59:54 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 04-Sep-2026 23:29:08 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-Sep-2026 | 05-Sep-2026 18:10:17 | 05-Sep-2026 12:06:11 | 0 |  |  | Approver | Locate
AO-002019 | MM-ZTK-1F-ZWP22-STR-DWG-2935 | ZWP22 JACKET - BALLAST AND GROUTING SYSTEM SUPPORT DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Sep-2026 20:50:50 | wisuda.c@jutal.com | 11-Sep-2026 21:02:14 | Jumpol Sudjitjul | 21-Sep-2026 |  | Sompop Singhatiraj | 23-Sep-2026 | 22-Sep-2026 12:17:15 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 22-Sep-2026 19:46:58 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 25-Sep-2026 | 23-Sep-2026 13:47:00 | 23-Sep-2026 07:32:41 | 0 |  |  | Approver | Locate
AO-002019 | MM-ZTK-1F-ZWP22-STR-DWG-2936 | ZWP22 JACKET - BALLAST AND GROUTING SYSTEM SUPPORT DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Sep-2026 20:51:16 | wisuda.c@jutal.com | 11-Sep-2026 21:02:14 | Jumpol Sudjitjul | 21-Sep-2026 |  | Sompop Singhatiraj | 23-Sep-2026 | 22-Sep-2026 12:17:25 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 22-Sep-2026 19:46:39 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 25-Sep-2026 | 23-Sep-2026 13:21:48 | 23-Sep-2026 07:20:49 | 0 |  |  | Approver | Locate
AO-002019 | MM-ZTK-1F-ZWP22-STR-DWG-2937 | ZWP22 JACKET - BALLAST SYSTEM VALVE DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Sep-2026 20:51:43 | wisuda.c@jutal.com | 11-Sep-2026 21:02:14 | Jumpol Sudjitjul | 21-Sep-2026 |  | Sompop Singhatiraj | 23-Sep-2026 | 22-Sep-2026 12:19:46 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 22-Sep-2026 19:46:14 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 25-Sep-2026 | 23-Sep-2026 13:47:42 | 23-Sep-2026 07:15:55 | 0 |  |  | Approver | Locate
AO-002019 | MM-ZTK-1F-ZWP22-STR-DWG-2938 | ZWP22 JACKET -GROUT, SKIRT SLEEVE VENT AND FLOODING DETAILS AT SKIRT PILE SLEEVE SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Sep-2026 20:52:20 | wisuda.c@jutal.com | 11-Sep-2026 21:02:15 | Jumpol Sudjitjul | 21-Sep-2026 |  | Sompop Singhatiraj | 23-Sep-2026 | 22-Sep-2026 12:19:49 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 22-Sep-2026 19:45:43 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 25-Sep-2026 | 23-Sep-2026 13:48:33 | 23-Sep-2026 07:18:14 | 0 |  |  | Approver | Locate
AO-002019 | MM-ZTK-1F-ZWP22-STR-DWG-2939 | ZWP22 JACKET -GROUT, SKIRT SLEEVE VENT AND FLOODING DETAILS AT SKIRT PILE SLEEVE SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Sep-2026 20:52:47 | wisuda.c@jutal.com | 11-Sep-2026 21:02:14 | Jumpol Sudjitjul | 21-Sep-2026 |  | Sompop Singhatiraj | 23-Sep-2026 | 22-Sep-2026 12:19:55 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 22-Sep-2026 19:45:06 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 25-Sep-2026 | 23-Sep-2026 13:48:30 | 23-Sep-2026 07:17:04 | 0 |  |  | Approver | Locate
AO-002019 | MM-ZTK-1F-ZWP22-STR-DWG-2940 | ZWP22 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT EL(+) 8000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Sep-2026 20:53:13 | wisuda.c@jutal.com | 11-Sep-2026 21:02:23 | Jumpol Sudjitjul | 21-Sep-2026 |  | Sompop Singhatiraj | 23-Sep-2026 | 22-Sep-2026 12:21:50 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 22-Sep-2026 19:44:41 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 25-Sep-2026 | 23-Sep-2026 13:47:22 | 23-Sep-2026 07:14:45 | 0 |  |  | Approver | Locate
AO-002019 | MM-ZTK-1F-ZWP22-STR-DWG-2941 | ZWP22 JACKET - GROUT SYSTEM DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Sep-2026 20:53:47 | wisuda.c@jutal.com | 11-Sep-2026 21:02:17 | Jumpol Sudjitjul | 21-Sep-2026 |  | Sompop Singhatiraj | 23-Sep-2026 | 22-Sep-2026 12:21:56 | Pornlert Wanaphattharaphan | 24-Sep-2026 | 22-Sep-2026 19:44:14 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 25-Sep-2026 | 23-Sep-2026 13:46:43 | 23-Sep-2026 07:13:31 | 0 |  |  | Approver | Locate
AO-001919 | MM-ZTK-1F-ZWP22-STR-DWG-2971 | ZWP22 JACKET - WELD PROFILE CONTROL SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Sep-2026 17:56:42 | wisuda.c@jutal.com | 08-Sep-2026 09:01:42 | Jumpol Sudjitjul | 15-Sep-2026 | 09-Sep-2026 11:07:52 | Sompop Singhatiraj | 17-Sep-2026 | 10-Sep-2026 11:34:33 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 12-Sep-2026 23:19:48 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 10:46:34 | 13-Sep-2026 03:56:38 | 0 |  |  | Approver | Locate
AO-001919 | MM-ZTK-1F-ZWP22-STR-DWG-2972 | ZWP22 JACKET - WELD PROFILE CONTROL SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Sep-2026 17:57:09 | wisuda.c@jutal.com | 08-Sep-2026 09:01:33 | Jumpol Sudjitjul | 15-Sep-2026 | 09-Sep-2026 10:51:06 | Sompop Singhatiraj | 17-Sep-2026 | 10-Sep-2026 11:36:57 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 12-Sep-2026 23:28:13 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 11:21:42 | 13-Sep-2026 05:10:49 | 0 |  |  | Approver | Locate
AO-001919 | MM-ZTK-1F-ZWP22-STR-DWG-2973 | ZWP22 JACKET - WELD PROFILE CONTROL SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Sep-2026 17:57:35 | wisuda.c@jutal.com | 08-Sep-2026 09:01:40 | Jumpol Sudjitjul | 15-Sep-2026 | 09-Sep-2026 10:54:00 | Sompop Singhatiraj | 17-Sep-2026 | 10-Sep-2026 14:02:23 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 12-Sep-2026 23:41:24 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 10:37:30 | 13-Sep-2026 03:54:16 | 0 |  |  | Approver | Locate
AO-001919 | MM-ZTK-1F-ZWP22-STR-DWG-2974 | ZWP22 JACKET - WELD PROFILE CONTROL SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Sep-2026 17:58:04 | wisuda.c@jutal.com | 08-Sep-2026 09:01:34 | Jumpol Sudjitjul | 15-Sep-2026 | 09-Sep-2026 10:46:40 | Sompop Singhatiraj | 17-Sep-2026 | 10-Sep-2026 14:02:35 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 12-Sep-2026 23:41:02 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 10:44:04 | 13-Sep-2026 03:55:30 | 0 |  |  | Approver | Locate
AO-001919 | MM-ZTK-1F-ZWP22-STR-DWG-2975 | ZWP22 JACKET - WELD PROFILE CONTROL SHEET 5 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Sep-2026 17:58:37 | wisuda.c@jutal.com | 08-Sep-2026 09:01:40 | Jumpol Sudjitjul | 15-Sep-2026 | 09-Sep-2026 10:56:05 | Sompop Singhatiraj | 17-Sep-2026 | 10-Sep-2026 14:02:45 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 12-Sep-2026 23:50:08 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 11:24:14 | 13-Sep-2026 05:13:30 | 0 |  |  | Approver | Locate
AO-001919 | MM-ZTK-1F-ZWP22-STR-DWG-2976 | ZWP22 JACKET - WELD PROFILE CONTROL SHEET 6 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Sep-2026 17:59:08 | wisuda.c@jutal.com | 08-Sep-2026 09:01:40 | Jumpol Sudjitjul | 15-Sep-2026 | 09-Sep-2026 11:01:54 | Sompop Singhatiraj | 17-Sep-2026 | 10-Sep-2026 14:02:53 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 12-Sep-2026 23:46:46 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 21-Sep-2026 | 13-Sep-2026 11:14:03 | 13-Sep-2026 04:25:00 | 0 |  |  | Approver | Locate
AO-002309 | MM-ZTK-1F-ZWP22-STR-DWG-2984 | ZWP22 JACKET - PULLING LUG DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 30-Sep-2026 09:32:02 | wisuda.c@jutal.com | 30-Sep-2026 16:08:44 | Jumpol Sudjitjul | 07-Oct-2026 |  | Sompop Singhatiraj | 09-Oct-2026 | 06-Oct-2026 10:48:50 | Pornlert Wanaphattharaphan | 12-Oct-2026 | 10-Oct-2026 01:42:27 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 14-Oct-2026 | 10-Oct-2026 17:35:18 | 10-Oct-2026 11:12:57 | 0 |  |  | Approver | Locate
AO-001981 | MM-ZTK-1F-ZWP22-STR-DWG-2991 | ZWP22 JACKET - JACKET TRANSPORTATION ARRANGEMENT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Sep-2026 18:06:32 | wisuda.c@jutal.com | 10-Sep-2026 19:47:33 | Jumpol Sudjitjul | 18-Sep-2026 |  | Sompop Singhatiraj | 22-Sep-2026 | 18-Sep-2026 08:34:30 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 19-Sep-2026 15:51:56 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 24-Sep-2026 | 20-Sep-2026 18:32:05 | 20-Sep-2026 12:14:09 | 0 |  |  | Approver | Locate
AO-002545 | MM-ZTK-1F-ZWP22-STR-DWG-2991 | ZWP22 JACKET - JACKET TRANSPORTATION ARRANGEMENT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP22 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 16-Oct-2026 10:12:47 | wisuda.c@jutal.com | 16-Oct-2026 16:06:38 | Jumpol Sudjitjul | 26-Oct-2026 |  | Sompop Singhatiraj | 28-Oct-2026 |  | Pornlert Wanaphattharaphan | 29-Oct-2026 |  |  |  |  | 30-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000295 | MM-ZTK-1F-ZWP22-STR-MR-2001 | MATERIAL REǪUISITION FOR ZWP22 JACKET PRIMARY TUBULAR STEEL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 02:02:36 | wisuda.c@jutal.com | 04-May-2026 13:11:39 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 08:24:46 | Sompop Singhatiraj | 13-May-2026 | 15-May-2026 16:01:50 | Pornlert Wanaphattharaphan | 14-May-2026 | 15-May-2026 23:31:52 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 15-May-2026 | 17-May-2026 10:12:52 | 17-May-2026 11:02:24 | 0 |  |  | Approver | Locate
AO-000317 | MM-ZTK-1F-ZWP22-STR-MR-2002 | MATERIAL REǪUISITION FOR ZWP22 JACKET PRIMARY STEEL (PLATE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 06-May-2026 09:06:07 | wisuda.c@jutal.com | 06-May-2026 10:32:27 | Jumpol Sudjitjul | 13-May-2026 | 15-May-2026 07:41:14 | Sompop Singhatiraj | 15-May-2026 | 15-May-2026 16:47:09 | Pornlert Wanaphattharaphan | 18-May-2026 | 15-May-2026 23:22:53 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 19-May-2026 | 17-May-2026 10:10:15 | 17-May-2026 11:02:46 | 0 |  |  | Approver | Locate
AO-001316 | MM-ZTK-1F-ZWP22-STR-MTO-2001 | ZWP22 JACKET PRIMARY STEEL MTO REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 27-Jul-2026 08:45:35 | wisuda.c@jutal.com | 27-Jul-2026 16:13:42 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 11-Aug-2026 10:06:23 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 01:04:52 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 13:04:48 | 13-Aug-2026 07:12:15 | 0 |  |  | Approver | Locate
AO-001314 | MM-ZTK-1F-ZWP22-STR-MTO-2002 | ZWP22 JACKET SECONDARY STEEL MTO REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 27-Jul-2026 08:46:02 | wisuda.c@jutal.com | 27-Jul-2026 16:13:58 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 11-Aug-2026 10:06:14 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 01:04:33 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 13:05:10 | 13-Aug-2026 07:15:03 | 0 |  |  | Approver | Locate
AO-001310 | MM-ZTK-1F-ZWP22-STR-TBE-1001 | TECHNICAL BID EVALUATION FOR ZWP22 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 27-Jul-2026 08:46:30 | wisuda.c@jutal.com | 27-Jul-2026 16:11:01 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 03-Aug-2026 08:49:53 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 03-Aug-2026 23:32:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 04-Aug-2026 09:08:03 | 04-Aug-2026 02:26:53 | 0 |  |  | Approver | Locate
AO-000202 | MM-ZTK-1F-ZWP22-STR-WCR-2001 | ZWP22 JACKET WEIGHT CONTROL REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | WCR | Weight Control Report | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:36:22 | wisuda.c@jutal.com | 22-Apr-2026 10:41:16 | Jumpol Sudjitjul | 29-Apr-2026 |  | Sompop Singhatiraj | 05-May-2026 | 24-Apr-2026 10:25:16 | Pornlert Wanaphattharaphan | 06-May-2026 | 29-Apr-2026 23:11:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 30-Apr-2026 08:57:56 | 30-Apr-2026 02:46:46 | 0 |  |  | Approver | Locate
AO-001312 | MM-ZTK-1F-ZWP22-STR-WCR-2001 | ZWP22 JACKET WEIGHT CONTROL REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | WCR | Weight Control Report | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 08:46:58 | wisuda.c@jutal.com | 27-Jul-2026 16:06:36 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 10-Aug-2026 20:09:23 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 01:04:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 13:05:48 | 13-Aug-2026 07:16:26 | 0 |  |  | Approver | Locate
AO-002182 | MM-ZTK-1F-ZWP22-STR-WCR-2001 | ZWP22 JACKET WEIGHT CONTROL REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP22 |  |  | STR | Structural | WCR | Weight Control Report | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 09:35:14 | wisuda.c@jutal.com | 21-Sep-2026 10:11:41 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 01-Oct-2026 11:21:47 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 01-Oct-2026 20:43:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Oct-2026 | 02-Oct-2026 13:19:10 | 02-Oct-2026 07:08:16 | 0 |  |  | Approver | Locate
AO-000648 | MM-ZTK-1F-ZWP23-COR-CAL-0001 | ZWP23 CATHODIC PROTECTION CALCULATION |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | COR | Corrosion | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 02-Jun-2026 10:51:31 | wisuda.c@jutal.com | 02-Jun-2026 15:10:57 | Jumpol Sudjitjul | 10-Jun-2026 |  | Sompop Singhatiraj | 12-Jun-2026 | 07-Jun-2026 11:38:41 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 10-Jun-2026 21:38:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 11-Jun-2026 13:46:49 | 11-Jun-2026 07:26:04 | 0 |  |  | Approver | Locate
AO-001690 | MM-ZTK-1F-ZWP23-COR-CAL-0001 | ZWP23 CATHODIC PROTECTION CALCULATION |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | COR | Corrosion | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:37:51 | wisuda.c@jutal.com | 25-Aug-2026 08:30:00 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 02-Sep-2026 10:48:54 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:49:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:06:39 | 07-Sep-2026 12:03:24 | 0 |  |  | Approver | Locate
AO-000858 | MM-ZTK-1F-ZWP23-NVA-CAL-2011 | ZWP23 JACKET BARGE MOTION ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 22:40:49 | wisuda.c@jutal.com | 22-Jun-2026 14:02:07 | Jumpol Sudjitjul | 29-Jun-2026 |  | Sompop Singhatiraj | 01-Jul-2026 | 25-Jun-2026 13:47:55 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 29-Jun-2026 00:48:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 29-Jun-2026 21:22:07 | 29-Jun-2026 14:52:28 | 0 |  |  | Approver | Locate
AO-001281 | MM-ZTK-1F-ZWP23-NVA-CAL-2011 | ZWP23 JACKET BARGE MOTION ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 25-Jul-2026 09:16:00 | wisuda.c@jutal.com | 26-Jul-2026 23:52:44 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 13-Aug-2026 13:22:39 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 15-Aug-2026 13:38:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 15-Aug-2026 14:46:56 | 15-Aug-2026 08:15:17 | 0 |  |  | Approver | Locate
AO-002183 | MM-ZTK-1F-ZWP23-NVA-CAL-2011 | ZWP23 JACKET BARGE MOTION ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 11:10:12 | wisuda.c@jutal.com | 21-Sep-2026 14:20:57 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 28-Sep-2026 15:33:47 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 28-Sep-2026 22:46:55 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 29-Sep-2026 10:44:47 | 29-Sep-2026 05:02:53 | 0 |  |  | Approver | Locate
AO-000391 | MM-ZTK-1F-ZWP23-NVA-CAL-2012 | ZWP23 JACKET LAUNCH ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 13-May-2026 15:31:56 | wisuda.c@jutal.com | 13-May-2026 15:51:52 | Jumpol Sudjitjul | 20-May-2026 | 25-May-2026 15:26:44 | Sompop Singhatiraj | 22-May-2026 | 05-Jun-2026 19:33:44 | Pornlert Wanaphattharaphan | 25-May-2026 | 05-Jun-2026 23:59:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-May-2026 | 07-Jun-2026 17:47:50 | 07-Jun-2026 19:26:57 | 0 |  |  | Approver | Locate
AO-001507 | MM-ZTK-1F-ZWP23-NVA-CAL-2012 | ZWP23 JACKET LAUNCH ANALYSIS REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 11-Aug-2026 11:59:06 | wisuda.c@jutal.com | 11-Aug-2026 13:03:31 | Jumpol Sudjitjul | 19-Aug-2026 |  | Sompop Singhatiraj | 21-Aug-2026 | 28-Aug-2026 15:58:49 | Pornlert Wanaphattharaphan | 24-Aug-2026 | 29-Aug-2026 17:00:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Aug-2026 | 30-Aug-2026 17:09:11 | 30-Aug-2026 11:16:09 | 0 |  |  | Approver | Locate
AO-002188 | MM-ZTK-1F-ZWP23-NVA-CAL-2012 | ZWP23 JACKET LAUNCH ANALYSIS REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 11:11:01 | wisuda.c@jutal.com | 21-Sep-2026 14:21:12 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 28-Sep-2026 13:44:50 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 28-Sep-2026 22:30:45 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 29-Sep-2026 10:41:18 | 29-Sep-2026 05:01:31 | 0 |  |  | Approver | Locate
AO-001395 | MM-ZTK-1F-ZWP23-NVA-CAL-2013 | ZWP23 JACKET FREE FLOATATION AND UPENDING ANALYSIS REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 10:18:40 | wisuda.c@jutal.com | 03-Aug-2026 13:26:20 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 16-Aug-2026 16:37:42 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 17:23:33 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 14:17:54 | 17-Aug-2026 09:02:57 | 0 |  |  | Approver | Locate
AO-002189 | MM-ZTK-1F-ZWP23-NVA-CAL-2013 | ZWP23 JACKET FREE FLOATATION AND UPENDING ANALYSIS REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | NVA | Naval | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 09:37:55 | wisuda.c@jutal.com | 21-Sep-2026 10:04:00 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 28-Sep-2026 14:42:40 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 28-Sep-2026 22:31:20 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 29-Sep-2026 10:38:51 | 29-Sep-2026 04:42:07 | 0 |  |  | Approver | Locate
AO-000482 | MM-ZTK-1F-ZWP23-PIP-LAY-0005 | EQUIPMENT LAYOUT SUMP DECK PLAN T.O.S. EL.(+) 14.700 M. & BOAT LANDING PLAN T.O.S EL.(+) 5.000 M. |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 14:10:46 | wisuda.c@jutal.com | 18-May-2026 08:54:28 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 21:56:48 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 22:32:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:39:45 | 07-Jun-2026 11:09:42 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWP23-PIP-LAY-0005 | EQUIPMENT LAYOUT SUMP DECK PLAN T.O.S. EL.(+) 14.700 M. & BOAT LANDING PLAN T.O.S EL.(+) 5.000 M. |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:40:12 | wisuda.c@jutal.com | 15-Sep-2026 11:07:04 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:26:48 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 22:06:49 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 23:16:52 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 10:16:10 | 08-Oct-2026 04:30:37 | 0 |  |  | Approver | Locate
AO-000483 | MM-ZTK-1F-ZWP23-PIP-LAY-0006 | EQUIPMENT LAYOUT ELEVATION LOOKING NORTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 14:11:11 | wisuda.c@jutal.com | 18-May-2026 08:55:01 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 21:58:15 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 22:33:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:40:13 | 07-Jun-2026 11:10:58 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWP23-PIP-LAY-0006 | EQUIPMENT LAYOUT ELEVATION LOOKING NORTH |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:40:51 | wisuda.c@jutal.com | 15-Sep-2026 11:08:01 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:14:40 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 22:09:18 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 23:19:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 10:19:32 | 08-Oct-2026 04:32:04 | 0 |  |  | Approver | Locate
AO-000484 | MM-ZTK-1F-ZWP23-PIP-LAY-0007 | EQUIPMENT LAYOUT ELEVATION LOOKING EAST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 14:11:35 | wisuda.c@jutal.com | 18-May-2026 08:55:26 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 21:59:44 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 22:34:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:40:41 | 07-Jun-2026 11:12:15 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWP23-PIP-LAY-0007 | EQUIPMENT LAYOUT ELEVATION LOOKING EAST |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:41:32 | wisuda.c@jutal.com | 15-Sep-2026 11:08:27 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:13:41 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 22:12:05 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 23:20:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 10:21:00 | 08-Oct-2026 04:33:19 | 0 |  |  | Approver | Locate
AO-000485 | MM-ZTK-1F-ZWP23-PIP-LAY-0008 | EQUIPMENT LAYOUT ELEVATION LOOKING SOUTH |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 17-May-2026 00:13:59 | wisuda.c@jutal.com | 18-May-2026 08:55:56 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 22:02:04 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 22:35:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:41:04 | 07-Jun-2026 11:43:03 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWP23-PIP-LAY-0008 | EQUIPMENT LAYOUT ELEVATION LOOKING SOUTH |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:42:09 | wisuda.c@jutal.com | 15-Sep-2026 11:08:49 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:23:40 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 22:14:16 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 23:20:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 10:24:51 | 08-Oct-2026 04:34:33 | 0 |  |  | Approver | Locate
AO-000486 | MM-ZTK-1F-ZWP23-PIP-LAY-0009 | EQUIPMENT LAYOUT ELEVATION LOOKING WEST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 17-May-2026 00:14:27 | wisuda.c@jutal.com | 18-May-2026 08:56:28 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 22:04:22 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 22:53:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:41:28 | 07-Jun-2026 11:56:33 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWP23-PIP-LAY-0009 | EQUIPMENT LAYOUT ELEVATION LOOKING WEST |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:42:43 | wisuda.c@jutal.com | 15-Sep-2026 11:09:13 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:16:12 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 22:16:51 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 23:21:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 10:26:25 | 08-Oct-2026 04:35:55 | 0 |  |  | Approver | Locate
AO-001043 | MM-ZTK-1F-ZWP23-PRC-UPO-5001 | UNPRICED PO FOR PRIMARY STEEL PLATES FOR ZWP23 (CUT-OFF DATE 3-JUL-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | ZWP23 |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 09-Jul-2026 15:35:25 | zm169dc@jutal.com | 09-Jul-2026 17:16:30 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 12-Aug-2026 09:25:33 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 13-Aug-2026 13:06:12 | 13-Aug-2026 07:17:43 | 0 |  |  | For Info | Locate
AO-001516 | MM-ZTK-1F-ZWP23-PRC-UPO-5001 | UNPRICED PO FOR PRIMARY STEEL PLATES FOR ZWP23 (CUT-OFF DATE 3-JUL-26) |  | A2 | Project Document | Engineering Document | Part A - Project Management Doc | ZWP23 |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 13-Aug-2026 16:54:29 | zm169dc@jutal.com | 13-Aug-2026 16:58:31 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 16-Aug-2026 09:11:42 |  |  |  | REC | Received | Jumpol Sudjitjul |  | 16-Aug-2026 09:48:51 | 16-Aug-2026 03:01:37 | 0 |  |  | For Info | Locate
AO-001271 | MM-ZTK-1F-ZWP23-PRC-UPO-5002 | UNPRICED PO FOR PRIMARY STEEL PLATES FOR ZWP23(CUT-OFF DATE 24-JUL-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | ZWP23 |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 25-Jul-2026 09:13:11 | zm169dc@jutal.com | 26-Jul-2026 23:54:19 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 11-Aug-2026 09:28:41 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 11-Aug-2026 13:11:48 | 11-Aug-2026 06:36:33 | 0 |  |  | For Info | Locate
AO-001344 | MM-ZTK-1F-ZWP23-PRC-UPO-5003 | UNPRICED PO FOR PRIMARY STEEL PLATES FOR ZWP23(CUT-OFF DATE 27-JUL-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | ZWP23 |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | Submitted | IFI | Issued for Information |  | 30-Jul-2026 17:24:00 | zm169dc@jutal.com | 30-Jul-2026 19:18:29 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  | 11-Aug-2026 09:30:04 |  |  |  | AWC | Approved with Comment | Jumpol Sudjitjul |  | 11-Aug-2026 13:10:40 | 11-Aug-2026 06:35:07 | 0 |  |  | For Info | Locate
AO-002121 | MM-ZTK-1F-ZWP23-PRC-UPO-5004 | UNPRICED PO FOR STEEL PLATES FOR ZWP23(CUT-OFF DATE 15-SEP-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | ZWP23 |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 17-Sep-2026 12:42:15 | zm169dc@jutal.com | 18-Sep-2026 16:24:22 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  |  | Prin Jitatisil | [8 empty] | 0 |  |  | For Info | Locate
AO-002524 | MM-ZTK-1F-ZWP23-PRC-UPO-5005 | UNPRICED PO FOR STEEL PLATES FOR ZWP23(CUT-OFF DATE 12-OCT-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | ZWP23 |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 14-Oct-2026 17:39:11 | zhaoli@jutal.com | 15-Oct-2026 11:18:10 | Jumpol Sudjitjul |  |  | Jirayu Pantito | [11 empty] | 0 |  |  | For Info | Locate
AO-002158 | MM-ZTK-1F-ZWP23-PRC-UPO-5100 | UNPRICED PO FOR ANODE FOR ZWP23 (CUT-OFF DATE 17-SEP-26) |  | A1 | Project Document | Engineering Document | Part A - Project Management Doc | ZWP23 |  |  | PRC | Procurement | UPO | Unpriced Purchase Order | 0 | In Review | IFI | Issued for Information |  | 18-Sep-2026 17:27:23 | zm169dc@jutal.com | 20-Sep-2026 12:58:47 | Jumpol Sudjitjul |  |  | Jirayu Pantito |  |  | Prin Jitatisil | [8 empty] | 0 |  |  | For Info | Locate
AO-000546 | MM-ZTK-1F-ZWP23-PRO-PID-0012 | PIPING AND INSTRUMENTATION DIAGRAM PIG LAUNCHER AND EXPORT LINE |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 17:51:35 | wisuda.c@jutal.com | 21-May-2026 18:03:17 | Jumpol Sudjitjul | 29-May-2026 |  | Chananun Rojanarungruengporn | 04-Jun-2026 | 29-May-2026 12:58:48 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:04:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 13:46:11 | 11-Jun-2026 14:18:00 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWP23-PRO-PID-0012 | PIPING AND INSTRUMENTATION DIAGRAM PIG LAUNCHER AND EXPORT LINE |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 16:53:22 | wisuda.c@jutal.com | 18-Jun-2026 17:34:46 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 01-Jul-2026 23:12:47 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 02-Jul-2026 22:09:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 11:29:21 | 03-Jul-2026 05:01:48 | 0 |  |  | Approver | Locate
AO-001668 | MM-ZTK-1F-ZWP23-PRO-PID-0012 | PIPING AND INSTRUMENTATION DIAGRAM PIG LAUNCHER AND EXPORT LINE |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 11:08:11 | wisuda.c@jutal.com | 25-Aug-2026 09:45:58 | Jumpol Sudjitjul | 01-Sep-2026 | 02-Sep-2026 23:46:44 | Chananun Rojanarungruengporn | 03-Sep-2026 | 03-Sep-2026 08:07:47 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:56:35 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:07:24 | 08-Sep-2026 04:47:57 | 0 |  |  | Approver | Locate
AO-002218 | MM-ZTK-1F-ZWP23-PRO-PID-0012 | PIPING AND INSTRUMENTATION DIAGRAM PIG LAUNCHER AND EXPORT LINE |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 23-Sep-2026 09:31:21 | wisuda.c@jutal.com | 23-Sep-2026 14:03:16 | Jumpol Sudjitjul | 30-Sep-2026 |  | Chananun Rojanarungruengporn | 02-Oct-2026 | 05-Oct-2026 07:49:53 | Pornlert Wanaphattharaphan | 05-Oct-2026 | 10-Oct-2026 00:15:13 | APPR | Approved | Jumpol Sudjitjul | 06-Oct-2026 | 10-Oct-2026 17:48:11 | 10-Oct-2026 11:49:31 | 0 |  |  | Approver | Locate
AO-000198 | MM-ZTK-1F-ZWP23-PRO-PID-0014 | P&ID PIG RECEIVER |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:36:51 | wisuda.c@jutal.com | 22-Apr-2026 12:42:52 | Jumpol Sudjitjul | 29-Apr-2026 |  | Chananun Rojanarungruengporn | 05-May-2026 | 05-May-2026 17:21:16 | Pornlert Wanaphattharaphan | 06-May-2026 | 07-May-2026 22:26:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 08:19:22 | 08-May-2026 08:38:11 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWP23-PRO-PID-0014 | P&ID PIG RECEIVER |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 16:53:52 | wisuda.c@jutal.com | 18-Jun-2026 17:35:13 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 30-Jun-2026 23:58:04 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 03-Jul-2026 00:16:23 | APPR | Approved | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 11:10:07 | 03-Jul-2026 04:25:14 | 0 |  |  | Approver | Locate
AO-001668 | MM-ZTK-1F-ZWP23-PRO-PID-0014 | P&ID PIG RECEIVER |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 10:04:44 | wisuda.c@jutal.com | 25-Aug-2026 09:45:58 | Jumpol Sudjitjul | 01-Sep-2026 | 02-Sep-2026 23:44:34 | Chananun Rojanarungruengporn | 03-Sep-2026 | 03-Sep-2026 08:07:11 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:56:01 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:08:24 | 08-Sep-2026 04:36:56 | 0 |  |  | Approver | Locate
AO-000547 | MM-ZTK-1F-ZWP23-PRO-PID-0017 | PIPING AND INSTRUMENTATION DIAGRAM INSTRUMENT GAS SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 17:51:58 | wisuda.c@jutal.com | 21-May-2026 18:03:35 | Jumpol Sudjitjul | 29-May-2026 |  | Chananun Rojanarungruengporn | 04-Jun-2026 | 29-May-2026 13:17:40 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:04:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 13:44:44 | 11-Jun-2026 14:16:35 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWP23-PRO-PID-0017 | PIPING AND INSTRUMENTATION DIAGRAM INSTRUMENT GAS SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 16:54:24 | wisuda.c@jutal.com | 18-Jun-2026 17:35:33 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 01-Jul-2026 00:02:17 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 03-Jul-2026 00:26:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 11:33:45 | 03-Jul-2026 05:04:47 | 0 |  |  | Approver | Locate
AO-001725 | MM-ZTK-1F-ZWP23-PRO-PID-0017 | PIPING AND INSTRUMENTATION DIAGRAM INSTRUMENT GAS SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 26-Aug-2026 18:38:49 | wisuda.c@jutal.com | 27-Aug-2026 08:53:15 | Jumpol Sudjitjul | 03-Sep-2026 | 03-Sep-2026 23:41:13 | Chananun Rojanarungruengporn | 07-Sep-2026 | 04-Sep-2026 14:02:21 | Pornlert Wanaphattharaphan | 08-Sep-2026 | 07-Sep-2026 01:10:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Sep-2026 | 07-Sep-2026 18:08:45 | 08-Sep-2026 04:49:01 | 0 |  |  | Approver | Locate
AO-000548 | MM-ZTK-1F-ZWP23-PRO-PID-0021 | PIPING AND INSTRUMENTATION DIAGRAM HAZARDOUS OPEN DRAINS AND CLOSE DRAINS SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 17:52:22 | wisuda.c@jutal.com | 21-May-2026 18:03:52 | Jumpol Sudjitjul | 29-May-2026 |  | Chananun Rojanarungruengporn | 04-Jun-2026 | 29-May-2026 13:19:49 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:05:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 13:38:34 | 11-Jun-2026 13:47:21 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWP23-PRO-PID-0021 | PIPING AND INSTRUMENTATION DIAGRAM HAZARDOUS OPEN DRAINS AND CLOSE DRAINS SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 16:54:53 | wisuda.c@jutal.com | 18-Jun-2026 17:35:48 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 01-Jul-2026 00:06:00 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 03-Jul-2026 00:27:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 11:00:57 | 03-Jul-2026 04:23:48 | 0 |  |  | Approver | Locate
AO-001668 | MM-ZTK-1F-ZWP23-PRO-PID-0021 | PIPING AND INSTRUMENTATION DIAGRAM HAZARDOUS OPEN DRAINS AND CLOSE DRAINS SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 10:05:48 | wisuda.c@jutal.com | 25-Aug-2026 09:45:58 | Jumpol Sudjitjul | 01-Sep-2026 | 02-Sep-2026 23:45:33 | Chananun Rojanarungruengporn | 03-Sep-2026 | 03-Sep-2026 08:06:36 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:55:38 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:09:05 | 08-Sep-2026 04:38:03 | 0 |  |  | Approver | Locate
AO-000549 | MM-ZTK-1F-ZWP23-PRO-PID-0023 | PIPING AND INSTRUMENTATION DIAGRAM VENT SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 17:52:46 | wisuda.c@jutal.com | 21-May-2026 18:04:07 | Jumpol Sudjitjul | 29-May-2026 |  | Chananun Rojanarungruengporn | 04-Jun-2026 | 29-May-2026 13:49:40 | Pornlert Wanaphattharaphan | 05-Jun-2026 | 10-Jun-2026 21:06:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 08-Jun-2026 | 11-Jun-2026 13:37:22 | 11-Jun-2026 13:45:58 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWP23-PRO-PID-0023 | PIPING AND INSTRUMENTATION DIAGRAM VENT SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 16:55:20 | wisuda.c@jutal.com | 18-Jun-2026 17:36:05 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 01-Jul-2026 00:06:58 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 03-Jul-2026 00:28:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 11:01:35 | 03-Jul-2026 04:16:17 | 0 |  |  | Approver | Locate
AO-001668 | MM-ZTK-1F-ZWP23-PRO-PID-0023 | PIPING AND INSTRUMENTATION DIAGRAM VENT SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 10:06:21 | wisuda.c@jutal.com | 25-Aug-2026 09:46:00 | Jumpol Sudjitjul | 01-Sep-2026 | 02-Sep-2026 23:46:29 | Chananun Rojanarungruengporn | 03-Sep-2026 | 03-Sep-2026 08:06:07 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:55:14 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:09:35 | 08-Sep-2026 04:39:10 | 0 |  |  | Approver | Locate
AO-000367 | MM-ZTK-1F-ZWP23-STR-CAL-2001 | ZWP23 JACKET COMPUTER MODELING AND LOAD FORMULATION |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:13:44 | wisuda.c@jutal.com | 11-May-2026 13:09:16 | Jumpol Sudjitjul | 18-May-2026 | 25-May-2026 13:23:14 | Sompop Singhatiraj | 20-May-2026 | 25-May-2026 14:35:06 | Pornlert Wanaphattharaphan | 21-May-2026 | 25-May-2026 20:31:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 25-May-2026 21:08:49 | 25-May-2026 14:40:28 | 0 |  |  | Approver | Locate
AO-001190 | MM-ZTK-1F-ZWP23-STR-CAL-2001 | ZWP23 JACKET COMPUTER MODELING AND LOAD FORMULATION |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 08:46:31 | wisuda.c@jutal.com | 20-Jul-2026 14:30:30 | Jumpol Sudjitjul | 27-Jul-2026 | 13-Aug-2026 12:31:51 | Sompop Singhatiraj | 31-Jul-2026 | 14-Aug-2026 09:01:32 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 15-Aug-2026 06:42:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 15-Aug-2026 14:47:23 | 15-Aug-2026 08:23:57 | 0 |  |  | Approver | Locate
AO-002271 | MM-ZTK-1F-ZWP23-STR-CAL-2001 | ZWP23 JACKET COMPUTER MODELING AND LOAD FORMULATION |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 18:39:49 | wisuda.c@jutal.com | 26-Sep-2026 16:29:50 | Jumpol Sudjitjul | 02-Oct-2026 |  | Sompop Singhatiraj | 06-Oct-2026 | 06-Oct-2026 14:22:51 | Pornlert Wanaphattharaphan | 07-Oct-2026 | 10-Oct-2026 00:47:12 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 10-Oct-2026 17:48:34 | 10-Oct-2026 11:50:53 | 0 |  |  | Approver | Locate
AO-000708 | MM-ZTK-1F-ZWP23-STR-CAL-2011 | ZWP23 JACKET IN-PLACE ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 09:22:50 | wisuda.c@jutal.com | 08-Jun-2026 14:33:01 | Jumpol Sudjitjul | 15-Jun-2026 | 17-Jun-2026 22:57:28 | Sompop Singhatiraj | 17-Jun-2026 | 22-Jun-2026 12:37:12 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 22-Jun-2026 14:07:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 22-Jun-2026 14:36:22 | 22-Jun-2026 08:10:12 | 0 |  |  | Approver | Locate
AO-001315 | MM-ZTK-1F-ZWP23-STR-CAL-2011 | ZWP23 JACKET IN-PLACE ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 08:47:33 | wisuda.c@jutal.com | 27-Jul-2026 15:53:20 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 16-Aug-2026 18:00:27 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 16-Aug-2026 22:33:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 17-Aug-2026 14:17:22 | 17-Aug-2026 09:01:28 | 0 |  |  | Approver | Locate
AO-002473 | MM-ZTK-1F-ZWP23-STR-CAL-2011 | ZWP23 JACKET IN-PLACE ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 11:50:33 | wisuda.c@jutal.com | 12-Oct-2026 11:56:46 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000515 | MM-ZTK-1F-ZWP23-STR-CAL-2012 | ZWP23 JACKET DYNAMIC ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 15:31:30 | wisuda.c@jutal.com | 19-May-2026 15:53:02 | Jumpol Sudjitjul | 26-May-2026 | 04-Jun-2026 14:31:02 | Sompop Singhatiraj | 28-May-2026 | 08-Jun-2026 08:37:55 | Pornlert Wanaphattharaphan | 29-May-2026 | 10-Jun-2026 21:01:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 11-Jun-2026 13:34:12 | 11-Jun-2026 06:44:31 | 0 |  |  | Approver | Locate
AO-001218 | MM-ZTK-1F-ZWP23-STR-CAL-2012 | ZWP23 JACKET DYNAMIC ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 21-Jul-2026 12:37:05 | wisuda.c@jutal.com | 21-Jul-2026 13:25:20 | Jumpol Sudjitjul | 30-Jul-2026 |  | Sompop Singhatiraj | 03-Aug-2026 | 14-Aug-2026 08:31:44 | Pornlert Wanaphattharaphan | 04-Aug-2026 | 15-Aug-2026 06:43:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Aug-2026 | 15-Aug-2026 14:47:42 | 15-Aug-2026 08:42:39 | 0 |  |  | Approver | Locate
AO-002184 | MM-ZTK-1F-ZWP23-STR-CAL-2012 | ZWP23 JACKET DYNAMIC ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 09:36:08 | wisuda.c@jutal.com | 21-Sep-2026 10:10:10 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 01-Oct-2026 11:51:57 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 01-Oct-2026 20:42:15 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 02-Oct-2026 13:20:45 | 02-Oct-2026 07:09:33 | 0 |  |  | Approver | Locate
AO-000962 | MM-ZTK-1F-ZWP23-STR-CAL-2013 | ZWP23 JACKET IN-PLACE SPECTRAL FATIGUE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 30-Jun-2026 18:39:14 | wisuda.c@jutal.com | 01-Jul-2026 09:54:29 | Jumpol Sudjitjul | 08-Jul-2026 |  | Sompop Singhatiraj | 10-Jul-2026 | 08-Jul-2026 10:10:30 | Pornlert Wanaphattharaphan | 13-Jul-2026 | 10-Jul-2026 00:56:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Jul-2026 | 10-Jul-2026 08:01:03 | 10-Jul-2026 01:50:13 | 0 |  |  | Approver | Locate
AO-001490 | MM-ZTK-1F-ZWP23-STR-CAL-2013 | ZWP23 JACKET IN-PLACE SPECTRAL FATIGUE |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:46:46 | wisuda.c@jutal.com | 10-Aug-2026 14:37:59 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 31-Aug-2026 17:11:18 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 01-Sep-2026 23:35:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 02-Sep-2026 14:45:20 | 02-Sep-2026 08:34:04 | 0 |  |  | Approver | Locate
AO-002294 | MM-ZTK-1F-ZWP23-STR-CAL-2013 | ZWP23 JACKET IN-PLACE SPECTRAL FATIGUE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 09:48:42 | wisuda.c@jutal.com | 28-Sep-2026 09:53:42 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 28-Sep-2026 14:50:46 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 28-Sep-2026 23:02:25 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 29-Sep-2026 10:37:05 | 29-Sep-2026 04:32:11 | 0 |  |  | Approver | Locate
AO-000368 | MM-ZTK-1F-ZWP23-STR-CAL-2014 | ZWP23 JACKET LOADOUT ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:14:10 | wisuda.c@jutal.com | 11-May-2026 13:09:42 | Jumpol Sudjitjul | 18-May-2026 | 25-May-2026 13:29:38 | Sompop Singhatiraj | 20-May-2026 | 04-Jun-2026 13:32:50 | Pornlert Wanaphattharaphan | 21-May-2026 | 05-Jun-2026 23:45:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 07-Jun-2026 17:47:16 | 07-Jun-2026 11:48:41 | 0 |  |  | Approver | Locate
AO-001329 | MM-ZTK-1F-ZWP23-STR-CAL-2014 | ZWP23 JACKET LOADOUT ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 28-Jul-2026 09:13:01 | wisuda.c@jutal.com | 28-Jul-2026 20:25:50 | Jumpol Sudjitjul | 06-Aug-2026 |  | Sompop Singhatiraj | 10-Aug-2026 | 17-Aug-2026 12:46:02 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 17-Aug-2026 21:04:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Aug-2026 | 18-Aug-2026 08:26:23 | 18-Aug-2026 02:18:44 | 0 |  |  | Approver | Locate
AO-002186 | MM-ZTK-1F-ZWP23-STR-CAL-2014 | ZWP23 JACKET LOADOUT ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 11:08:53 | wisuda.c@jutal.com | 21-Sep-2026 14:18:39 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 28-Sep-2026 15:12:52 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 28-Sep-2026 22:46:27 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 29-Sep-2026 10:35:17 | 29-Sep-2026 04:57:30 | 0 |  |  | Approver | Locate
AO-000392 | MM-ZTK-1F-ZWP23-STR-CAL-2015 | ZWP23 JACKET TRANSPORTATION ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 13-May-2026 15:30:59 | wisuda.c@jutal.com | 13-May-2026 15:49:06 | Jumpol Sudjitjul | 20-May-2026 | 25-May-2026 14:46:15 | Sompop Singhatiraj | 22-May-2026 | 04-Jun-2026 16:26:34 | Pornlert Wanaphattharaphan | 25-May-2026 | 05-Jun-2026 23:45:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-May-2026 | 07-Jun-2026 17:47:14 | 07-Jun-2026 12:25:28 | 0 |  |  | Approver | Locate
AO-001328 | MM-ZTK-1F-ZWP23-STR-CAL-2015 | ZWP23 JACKET TRANSPORTATION ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 28-Jul-2026 09:13:32 | wisuda.c@jutal.com | 28-Jul-2026 20:26:15 | Jumpol Sudjitjul | 06-Aug-2026 |  | Sompop Singhatiraj | 10-Aug-2026 | 13-Aug-2026 13:51:15 | Pornlert Wanaphattharaphan | 11-Aug-2026 | 14-Aug-2026 00:00:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 13-Aug-2026 | 14-Aug-2026 08:34:18 | 14-Aug-2026 02:26:30 | 0 |  |  | Approver | Locate
AO-002185 | MM-ZTK-1F-ZWP23-STR-CAL-2015 | ZWP23 JACKET TRANSPORTATION ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 09:37:01 | wisuda.c@jutal.com | 21-Sep-2026 10:10:37 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 28-Sep-2026 12:00:00 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 28-Sep-2026 22:30:18 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 29-Sep-2026 10:33:08 | 29-Sep-2026 04:40:45 | 0 |  |  | Approver | Locate
AO-000769 | MM-ZTK-1F-ZWP23-STR-CAL-2016 | ZWP23 JACKET TRANSPORTATION FATIGUE |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 13-Jun-2026 09:17:22 | wisuda.c@jutal.com | 13-Jun-2026 09:41:07 | Jumpol Sudjitjul | 19-Jun-2026 | 22-Jun-2026 13:58:09 | Sompop Singhatiraj | 23-Jun-2026 | 25-Jun-2026 14:51:09 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 28-Jun-2026 10:13:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 29-Jun-2026 21:19:09 | 29-Jun-2026 14:50:44 | 0 |  |  | Approver | Locate
AO-001489 | MM-ZTK-1F-ZWP23-STR-CAL-2016 | ZWP23 JACKET TRANSPORTATION FATIGUE |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:47:20 | wisuda.c@jutal.com | 10-Aug-2026 14:38:19 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 17-Aug-2026 16:02:23 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:23:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 18:08:42 | 24-Aug-2026 12:26:47 | 0 |  |  | Approver | Locate
AO-002294 | MM-ZTK-1F-ZWP23-STR-CAL-2016 | ZWP23 JACKET TRANSPORTATION FATIGUE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 09:49:31 | wisuda.c@jutal.com | 28-Sep-2026 09:53:44 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 12-Oct-2026 13:24:21 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 13-Oct-2026 14:40:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 14-Oct-2026 16:43:46 | 14-Oct-2026 10:33:28 | 0 |  |  | Approver | Locate
AO-001217 | MM-ZTK-1F-ZWP23-STR-CAL-2017 | ZWP23 JACKET BOAT IMPACT ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 21-Jul-2026 07:52:12 | wisuda.c@jutal.com | 21-Jul-2026 08:12:23 | Jumpol Sudjitjul | 30-Jul-2026 |  | Sompop Singhatiraj | 03-Aug-2026 | 12-Aug-2026 09:54:34 | Pornlert Wanaphattharaphan | 04-Aug-2026 | 12-Aug-2026 12:45:46 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 05-Aug-2026 | 13-Aug-2026 13:06:53 | 13-Aug-2026 07:02:56 | 0 |  |  | Approver | Locate
AO-000713 | MM-ZTK-1F-ZWP23-STR-CAL-2018 | ZWP23 JACKET ON-BOTTOM STABILITY ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 18:36:45 | wisuda.c@jutal.com | 09-Jun-2026 08:51:08 | Jumpol Sudjitjul | 16-Jun-2026 | 18-Jun-2026 00:19:56 | Sompop Singhatiraj | 18-Jun-2026 | 22-Jun-2026 13:46:19 | Pornlert Wanaphattharaphan | 19-Jun-2026 | 22-Jun-2026 14:10:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jun-2026 | 22-Jun-2026 14:37:19 | 22-Jun-2026 08:13:55 | 0 |  |  | Approver | Locate
AO-001280 | MM-ZTK-1F-ZWP23-STR-CAL-2018 | ZWP23 JACKET ON-BOTTOM STABILITY ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 25-Jul-2026 09:15:31 | wisuda.c@jutal.com | 26-Jul-2026 23:41:32 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 13-Aug-2026 16:03:21 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 13-Aug-2026 23:56:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 14-Aug-2026 08:33:33 | 14-Aug-2026 02:22:19 | 0 |  |  | Approver | Locate
AO-002491 | MM-ZTK-1F-ZWP23-STR-CAL-2018 | ZWP23 JACKET ON-BOTTOM STABILITY ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 11:51:08 | wisuda.c@jutal.com | 12-Oct-2026 11:56:45 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001148 | MM-ZTK-1F-ZWP23-STR-CAL-2019 | ZWP23 JACKET MISCELLANEOUS DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 16-Jul-2026 21:14:33 | wisuda.c@jutal.com | 17-Jul-2026 10:40:35 | Jumpol Sudjitjul | 24-Jul-2026 | 13-Aug-2026 12:31:17 | Sompop Singhatiraj | 30-Jul-2026 | 16-Sep-2026 18:33:35 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 17-Sep-2026 13:21:38 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 03-Aug-2026 | 17-Sep-2026 13:31:51 | 17-Sep-2026 07:07:31 | 0 |  |  | Approver | Locate
AO-001141 | MM-ZTK-1F-ZWP23-STR-CAL-2020 | ZWP23 JACKET LEVELLING ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 16-Jul-2026 18:45:59 | wisuda.c@jutal.com | 16-Jul-2026 20:55:39 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sompop Singhatiraj | 30-Jul-2026 | 12-Aug-2026 10:56:27 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 12-Aug-2026 12:36:04 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 03-Aug-2026 | 13-Aug-2026 13:07:27 | 13-Aug-2026 07:04:31 | 0 |  |  | Approver | Locate
AO-002372 | MM-ZTK-1F-ZWP23-STR-CAL-2020 | ZWP23 JACKET LEVELLING ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 10:12:49 | wisuda.c@jutal.com | 05-Oct-2026 10:37:26 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 12-Oct-2026 13:53:16 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 13-Oct-2026 14:41:17 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 14-Oct-2026 16:42:54 | 14-Oct-2026 10:06:44 | 0 |  |  | Approver | Locate
AO-001142 | MM-ZTK-1F-ZWP23-STR-CAL-2021 | ZWP23 JACKET PILE HANDLING AND STICK-UP ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 16-Jul-2026 18:46:27 | wisuda.c@jutal.com | 16-Jul-2026 20:56:45 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sompop Singhatiraj | 30-Jul-2026 | 12-Aug-2026 13:34:36 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 12-Aug-2026 17:02:57 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 03-Aug-2026 | 13-Aug-2026 13:07:42 | 13-Aug-2026 07:06:00 | 0 |  |  | Approver | Locate
AO-002473 | MM-ZTK-1F-ZWP23-STR-CAL-2021 | ZWP23 JACKET PILE HANDLING AND STICK-UP ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 11:51:44 | wisuda.c@jutal.com | 12-Oct-2026 11:56:44 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000771 | MM-ZTK-1F-ZWP23-STR-CAL-2022 | ZWP23 PILE DRIVEABILITY AND PILE FATIGUE ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 13-Jun-2026 09:17:50 | wisuda.c@jutal.com | 13-Jun-2026 09:42:35 | Jumpol Sudjitjul | 19-Jun-2026 | 19-Jun-2026 01:46:01 | Sompop Singhatiraj | 23-Jun-2026 | 26-Jun-2026 12:35:36 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 28-Jun-2026 10:39:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 29-Jun-2026 21:05:48 | 29-Jun-2026 14:34:21 | 0 |  |  | Approver | Locate
AO-001227 | MM-ZTK-1F-ZWP23-STR-CAL-2022 | ZWP23 PILE DRIVEABILITY AND PILE FATIGUE ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 23-Jul-2026 11:03:23 | wisuda.c@jutal.com | 23-Jul-2026 16:07:52 | Jumpol Sudjitjul | 03-Aug-2026 |  | Sompop Singhatiraj | 05-Aug-2026 | 14-Aug-2026 12:51:33 | Pornlert Wanaphattharaphan | 06-Aug-2026 | 15-Aug-2026 06:43:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Aug-2026 | 15-Aug-2026 14:47:15 | 15-Aug-2026 08:09:01 | 0 |  |  | Approver | Locate
AO-002373 | MM-ZTK-1F-ZWP23-STR-CAL-2022 | ZWP23 PILE DRIVEABILITY AND PILE FATIGUE ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 10:44:35 | wisuda.c@jutal.com | 06-Oct-2026 08:48:30 | Jumpol Sudjitjul | 14-Oct-2026 |  | Sompop Singhatiraj | 16-Oct-2026 | 12-Oct-2026 14:09:00 | Pornlert Wanaphattharaphan | 19-Oct-2026 | 13-Oct-2026 14:41:49 | APPR | Approved | Jumpol Sudjitjul | 20-Oct-2026 | 14-Oct-2026 16:42:23 | 14-Oct-2026 10:30:54 | 0 |  |  | Approver | Locate
AO-001528 | MM-ZTK-1F-ZWP23-STR-CAL-2023 | ZWP23 JACKET PILE CLUSTER FEA REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 16:18:15 | wisuda.c@jutal.com | 14-Aug-2026 16:55:32 | Jumpol Sudjitjul | 21-Aug-2026 |  | Sompop Singhatiraj | 25-Aug-2026 | 26-Aug-2026 16:05:37 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 27-Aug-2026 22:24:59 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 27-Aug-2026 | 28-Aug-2026 11:07:39 | 28-Aug-2026 04:44:47 | 0 |  |  | Approver | Locate
AO-000936 | MM-ZTK-1F-ZWP23-STR-CAL-2024 | ZWP23 PILE GROUP EFFECT ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 19:02:22 | wisuda.c@jutal.com | 27-Jun-2026 19:10:43 | Jumpol Sudjitjul | 06-Jul-2026 | 29-Jun-2026 16:14:45 | Sompop Singhatiraj | 08-Jul-2026 | 02-Jul-2026 11:38:18 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 04-Jul-2026 22:21:08 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 10-Jul-2026 | 05-Jul-2026 10:46:27 | 05-Jul-2026 04:46:45 | 0 |  |  | Approver | Locate
AO-001549 | MM-ZTK-1F-ZWP23-STR-CAL-2025 | ZWP23 MUDMAT FEA ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 17-Aug-2026 14:28:49 | wisuda.c@jutal.com | 17-Aug-2026 15:49:42 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 26-Aug-2026 16:08:32 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 22:56:20 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 16:56:53 | 30-Aug-2026 10:55:11 | 0 |  |  | Approver | Locate
AO-000709 | MM-ZTK-1F-ZWP23-STR-CAL-2031 | ZWP23 TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (EXTREME LEVEL EARTHQUAKE - ELE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 09:23:24 | wisuda.c@jutal.com | 08-Jun-2026 14:35:17 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 19-Jun-2026 19:31:32 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 20-Jun-2026 21:18:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 22-Jun-2026 12:58:41 | 22-Jun-2026 06:59:09 | 0 |  |  | Approver | Locate
AO-001317 | MM-ZTK-1F-ZWP23-STR-CAL-2031 | ZWP23 TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (EXTREME LEVEL EARTHQUAKE - ELE) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 08:48:04 | wisuda.c@jutal.com | 27-Jul-2026 15:53:38 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 12-Aug-2026 18:50:01 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 19:30:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 13:07:16 | 13-Aug-2026 07:19:10 | 0 |  |  | Approver | Locate
AO-002187 | MM-ZTK-1F-ZWP23-STR-CAL-2031 | ZWP23 TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT (EXTREME LEVEL EARTHQUAKE - ELE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 11:09:30 | wisuda.c@jutal.com | 21-Sep-2026 14:19:09 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 01-Oct-2026 12:48:53 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 01-Oct-2026 20:41:36 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 02-Oct-2026 13:34:29 | 02-Oct-2026 07:10:51 | 0 |  |  | Approver | Locate
AO-000714 | MM-ZTK-1F-ZWP23-STR-CAL-2032 | ZWP23 TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT(ABNORMAL LEVEL EARTHQUAKE-ALE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 18:37:15 | wisuda.c@jutal.com | 09-Jun-2026 08:54:05 | Jumpol Sudjitjul | 16-Jun-2026 |  | Sompop Singhatiraj | 18-Jun-2026 | 21-Jun-2026 14:21:23 | Pornlert Wanaphattharaphan | 19-Jun-2026 | 22-Jun-2026 14:08:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Jun-2026 | 22-Jun-2026 14:26:03 | 22-Jun-2026 07:50:50 | 0 |  |  | Approver | Locate
AO-001319 | MM-ZTK-1F-ZWP23-STR-CAL-2032 | ZWP23 TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT(ABNORMAL LEVEL EARTHQUAKE-ALE) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 10:14:14 | wisuda.c@jutal.com | 27-Jul-2026 15:53:57 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 13-Aug-2026 18:36:36 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 14-Aug-2026 00:00:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 14-Aug-2026 08:30:48 | 14-Aug-2026 02:01:16 | 0 |  |  | Approver | Locate
AO-002143 | MM-ZTK-1F-ZWP23-STR-CAL-2032 | ZWP23 TOPSIDES AND JACKET SEISMIC ANALYSIS REPORT(ABNORMAL LEVEL EARTHQUAKE-ALE) |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | AFC | Approved for Construction |  | 18-Sep-2026 15:10:27 | wisuda.c@jutal.com | 18-Sep-2026 17:05:43 | Jumpol Sudjitjul | 28-Sep-2026 |  | Sompop Singhatiraj | 30-Sep-2026 | 01-Oct-2026 13:07:41 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 01-Oct-2026 20:41:08 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 02-Oct-2026 | 02-Oct-2026 13:32:39 | 02-Oct-2026 07:36:34 | 0 |  |  | Approver | Locate
AO-000859 | MM-ZTK-1F-ZWP23-STR-CAL-2041 | ZWP23 JACKET PUSHOVER ANALYSIS |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 22:39:48 | wisuda.c@jutal.com | 22-Jun-2026 13:57:36 | Jumpol Sudjitjul | 29-Jun-2026 |  | Sompop Singhatiraj | 01-Jul-2026 | 30-Jun-2026 12:54:38 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 02-Jul-2026 00:20:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 02-Jul-2026 09:59:23 | 02-Jul-2026 03:43:58 | 0 |  |  | Approver | Locate
AO-001394 | MM-ZTK-1F-ZWP23-STR-CAL-2041 | ZWP23 JACKET PUSHOVER ANALYSIS |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 03-Aug-2026 10:09:50 | wisuda.c@jutal.com | 03-Aug-2026 13:15:08 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 13-Aug-2026 19:24:04 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 14-Aug-2026 00:09:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 14-Aug-2026 08:30:14 | 14-Aug-2026 02:19:18 | 0 |  |  | Approver | Locate
AO-002473 | MM-ZTK-1F-ZWP23-STR-CAL-2041 | ZWP23 JACKET PUSHOVER ANALYSIS |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 11:52:21 | wisuda.c@jutal.com | 12-Oct-2026 11:56:44 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000369 | MM-ZTK-1F-ZWP23-STR-CAL-2050 | ZWP23 JACKET CONSTRUCTION MODEL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:14:36 | wisuda.c@jutal.com | 11-May-2026 13:09:57 | Jumpol Sudjitjul | 18-May-2026 | 25-May-2026 13:34:24 | Sompop Singhatiraj | 20-May-2026 | 25-May-2026 16:52:47 | Pornlert Wanaphattharaphan | 21-May-2026 | 25-May-2026 20:33:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 25-May-2026 21:06:45 | 25-May-2026 14:39:06 | 0 |  |  | Approver | Locate
AO-001191 | MM-ZTK-1F-ZWP23-STR-CAL-2050 | ZWP23 JACKET CONSTRUCTION MODEL |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 08:47:02 | wisuda.c@jutal.com | 20-Jul-2026 14:31:15 | Jumpol Sudjitjul | 27-Jul-2026 | 13-Aug-2026 12:33:09 | Sompop Singhatiraj | 31-Jul-2026 | 13-Aug-2026 14:01:07 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 13-Aug-2026 23:50:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 14-Aug-2026 08:29:48 | 14-Aug-2026 02:16:36 | 0 |  |  | Approver | Locate
AO-002271 | MM-ZTK-1F-ZWP23-STR-CAL-2050 | ZWP23 JACKET CONSTRUCTION MODEL |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 25-Sep-2026 18:18:12 | wisuda.c@jutal.com | 26-Sep-2026 16:29:52 | Jumpol Sudjitjul | 02-Oct-2026 |  | Sompop Singhatiraj | 06-Oct-2026 | 06-Oct-2026 14:22:55 | Pornlert Wanaphattharaphan | 07-Oct-2026 | 10-Oct-2026 00:49:01 | APPR | Approved | Jumpol Sudjitjul | 08-Oct-2026 | 10-Oct-2026 17:42:43 | 10-Oct-2026 11:17:30 | 0 |  |  | Approver | Locate
AO-002275 | MM-ZTK-1F-ZWP23-STR-CAL-2801 | ZWP23 RISER CLAMP DESIGN |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | CAL | Calculation Note, Calculation Report | 0 | In Review | IFR | Issued for Review |  | 28-Sep-2026 09:50:16 | wisuda.c@jutal.com | 28-Sep-2026 09:59:23 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 |  | Pornlert Wanaphattharaphan | 08-Oct-2026 |  |  |  |  | 09-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP23-STR-DWG-2100 | ZWP23 JACKET - VERTICAL FRAMING ROW 'A' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:39:33 | wisuda.c@jutal.com | 21-Apr-2026 14:41:55 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 09:28:46 | Pornlert Wanaphattharaphan | 05-May-2026 | 24-Apr-2026 00:40:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 09:37:22 | 24-Apr-2026 06:17:51 | 0 |  |  | Approver | Locate
AO-001135 | MM-ZTK-1F-ZWP23-STR-DWG-2100 | ZWP23 JACKET - VERTICAL FRAMING ROW 'A' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 17:52:56 | wisuda.c@jutal.com | 16-Jul-2026 20:31:33 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sompop Singhatiraj | 30-Jul-2026 | 20-Jul-2026 10:25:20 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 22:19:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 15:19:39 | 27-Jul-2026 10:43:46 | 0 |  |  | Approver | Locate
AO-001967 | MM-ZTK-1F-ZWP23-STR-DWG-2100 | ZWP23 JACKET - VERTICAL FRAMING ROW 'A' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 10:30:50 | wisuda.c@jutal.com | 10-Sep-2026 10:41:33 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 18-Sep-2026 14:51:34 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 15:14:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 18:34:28 | 20-Sep-2026 12:37:49 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP23-STR-DWG-2101 | ZWP23 JACKET - VERTICAL FRAMING ROW 'B' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:40:02 | wisuda.c@jutal.com | 21-Apr-2026 14:42:12 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 11:20:31 | Pornlert Wanaphattharaphan | 05-May-2026 | 24-Apr-2026 00:01:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 09:37:57 | 24-Apr-2026 06:19:15 | 0 |  |  | Approver | Locate
AO-001135 | MM-ZTK-1F-ZWP23-STR-DWG-2101 | ZWP23 JACKET - VERTICAL FRAMING ROW 'B' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 17:53:21 | wisuda.c@jutal.com | 16-Jul-2026 20:31:33 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sompop Singhatiraj | 30-Jul-2026 | 20-Jul-2026 10:28:14 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 22:23:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 15:20:04 | 27-Jul-2026 10:45:03 | 0 |  |  | Approver | Locate
AO-001967 | MM-ZTK-1F-ZWP23-STR-DWG-2101 | ZWP23 JACKET - VERTICAL FRAMING ROW 'B' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 10:31:33 | wisuda.c@jutal.com | 10-Sep-2026 10:41:34 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 18-Sep-2026 14:52:42 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 15:29:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 18:39:26 | 20-Sep-2026 12:22:56 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP23-STR-DWG-2102 | ZWP23 JACKET - VERTICAL FRAMING ROW '1' & '1.1' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:40:29 | wisuda.c@jutal.com | 21-Apr-2026 14:42:26 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 11:04:34 | Pornlert Wanaphattharaphan | 05-May-2026 | 24-Apr-2026 00:35:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 09:11:56 | 24-Apr-2026 03:09:02 | 0 |  |  | Approver | Locate
AO-001135 | MM-ZTK-1F-ZWP23-STR-DWG-2102 | ZWP23 JACKET - VERTICAL FRAMING ROW '1' & '1.1' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 17:53:46 | wisuda.c@jutal.com | 16-Jul-2026 20:31:33 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sompop Singhatiraj | 30-Jul-2026 | 20-Jul-2026 10:28:05 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 22:22:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 15:20:23 | 27-Jul-2026 10:46:18 | 0 |  |  | Approver | Locate
AO-001967 | MM-ZTK-1F-ZWP23-STR-DWG-2102 | ZWP23 JACKET - VERTICAL FRAMING ROW '1' & '1.1' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 10:32:27 | wisuda.c@jutal.com | 10-Sep-2026 10:41:40 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 18-Sep-2026 14:52:07 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 15:22:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 18:39:51 | 20-Sep-2026 12:24:09 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP23-STR-DWG-2103 | ZWP23 JACKET - VERTICAL FRAMING ROW '2' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:40:57 | wisuda.c@jutal.com | 21-Apr-2026 14:42:38 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 12:28:29 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 23:47:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 09:38:40 | 24-Apr-2026 06:20:41 | 0 |  |  | Approver | Locate
AO-001135 | MM-ZTK-1F-ZWP23-STR-DWG-2103 | ZWP23 JACKET - VERTICAL FRAMING ROW '2' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 17:54:10 | wisuda.c@jutal.com | 16-Jul-2026 20:31:33 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sompop Singhatiraj | 30-Jul-2026 | 20-Jul-2026 10:30:21 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 22:24:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 15:20:47 | 27-Jul-2026 10:47:35 | 0 |  |  | Approver | Locate
AO-001967 | MM-ZTK-1F-ZWP23-STR-DWG-2103 | ZWP23 JACKET - VERTICAL FRAMING ROW '2' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 10:33:05 | wisuda.c@jutal.com | 10-Sep-2026 10:41:33 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 18-Sep-2026 14:59:06 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 15:28:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 18:32:36 | 20-Sep-2026 12:15:25 | 0 |  |  | Approver | Locate
AO-000189 | MM-ZTK-1F-ZWP23-STR-DWG-2104 | ZWP23 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'AA' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 14:04:04 | wisuda.c@jutal.com | 21-Apr-2026 14:44:29 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 12:29:42 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 23:45:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 09:39:17 | 24-Apr-2026 06:24:48 | 0 |  |  | Approver | Locate
AO-001135 | MM-ZTK-1F-ZWP23-STR-DWG-2104 | ZWP23 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'AA' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 17:54:35 | wisuda.c@jutal.com | 16-Jul-2026 20:31:34 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sompop Singhatiraj | 30-Jul-2026 | 20-Jul-2026 10:32:43 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 22:25:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 15:21:10 | 27-Jul-2026 10:48:50 | 0 |  |  | Approver | Locate
AO-001967 | MM-ZTK-1F-ZWP23-STR-DWG-2104 | ZWP23 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'AA' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 10:33:43 | wisuda.c@jutal.com | 10-Sep-2026 10:41:36 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 18-Sep-2026 14:59:28 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 15:30:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 18:41:00 | 20-Sep-2026 12:25:23 | 0 |  |  | Approver | Locate
AO-000188 | MM-ZTK-1F-ZWP23-STR-DWG-2105 | ZWP23 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'BB' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 12:05:11 | wisuda.c@jutal.com | 21-Apr-2026 14:44:45 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 12:30:50 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 23:45:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 09:39:54 | 24-Apr-2026 06:27:40 | 0 |  |  | Approver | Locate
AO-001135 | MM-ZTK-1F-ZWP23-STR-DWG-2105 | ZWP23 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'BB' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 17:54:59 | wisuda.c@jutal.com | 16-Jul-2026 20:31:34 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sompop Singhatiraj | 30-Jul-2026 | 20-Jul-2026 10:30:29 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 22:25:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 15:21:39 | 27-Jul-2026 10:50:10 | 0 |  |  | Approver | Locate
AO-001967 | MM-ZTK-1F-ZWP23-STR-DWG-2105 | ZWP23 JACKET - VERTICAL FRAMING LAUNCH TRUSS ROW 'BB' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 10:34:42 | wisuda.c@jutal.com | 10-Sep-2026 10:41:42 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 18-Sep-2026 14:59:37 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 15:31:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 18:41:32 | 20-Sep-2026 12:26:37 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP23-STR-DWG-2110 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(+) 8000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:41:22 | wisuda.c@jutal.com | 21-Apr-2026 14:45:06 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 13:52:36 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 22:54:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 09:40:31 | 24-Apr-2026 06:22:07 | 0 |  |  | Approver | Locate
AO-001135 | MM-ZTK-1F-ZWP23-STR-DWG-2110 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(+) 8000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 17:55:23 | wisuda.c@jutal.com | 16-Jul-2026 20:33:09 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sompop Singhatiraj | 30-Jul-2026 | 20-Jul-2026 10:53:59 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 22:27:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 15:22:08 | 27-Jul-2026 10:51:29 | 0 |  |  | Approver | Locate
AO-001967 | MM-ZTK-1F-ZWP23-STR-DWG-2110 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(+) 8000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 10:35:29 | wisuda.c@jutal.com | 10-Sep-2026 10:41:39 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 18-Sep-2026 15:07:28 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 15:31:57 | APPR | Approved | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 18:39:14 | 20-Sep-2026 12:21:40 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP23-STR-DWG-2111 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 3000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:41:47 | wisuda.c@jutal.com | 21-Apr-2026 14:45:19 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 13:55:03 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 23:01:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 14:18:18 | 24-Apr-2026 07:41:01 | 0 |  |  | Approver | Locate
AO-001135 | MM-ZTK-1F-ZWP23-STR-DWG-2111 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 3000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 17:55:52 | wisuda.c@jutal.com | 16-Jul-2026 20:33:14 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sompop Singhatiraj | 30-Jul-2026 | 20-Jul-2026 10:54:40 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 22:29:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 15:22:35 | 27-Jul-2026 10:52:46 | 0 |  |  | Approver | Locate
AO-001967 | MM-ZTK-1F-ZWP23-STR-DWG-2111 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 3000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 10:36:02 | wisuda.c@jutal.com | 10-Sep-2026 10:41:37 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 18-Sep-2026 15:07:39 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 15:32:51 | APPR | Approved | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 18:42:02 | 20-Sep-2026 12:27:42 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP23-STR-DWG-2112 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 14000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:42:09 | wisuda.c@jutal.com | 21-Apr-2026 14:47:45 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 14:47:02 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 22:26:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 14:23:04 | 24-Apr-2026 07:43:16 | 0 |  |  | Approver | Locate
AO-001135 | MM-ZTK-1F-ZWP23-STR-DWG-2112 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 14000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 17:56:16 | wisuda.c@jutal.com | 16-Jul-2026 20:33:08 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sompop Singhatiraj | 30-Jul-2026 | 20-Jul-2026 10:55:46 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 22:26:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 15:23:01 | 27-Jul-2026 10:54:01 | 0 |  |  | Approver | Locate
AO-001967 | MM-ZTK-1F-ZWP23-STR-DWG-2112 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 14000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 10:36:37 | wisuda.c@jutal.com | 10-Sep-2026 10:41:36 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 18-Sep-2026 15:22:45 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 15:34:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 18:37:53 | 20-Sep-2026 12:20:35 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP23-STR-DWG-2113 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 26000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:42:35 | wisuda.c@jutal.com | 21-Apr-2026 14:47:57 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 14:46:53 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 22:27:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 14:24:13 | 24-Apr-2026 07:44:39 | 0 |  |  | Approver | Locate
AO-001135 | MM-ZTK-1F-ZWP23-STR-DWG-2113 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 26000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 17:56:41 | wisuda.c@jutal.com | 16-Jul-2026 20:33:09 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sompop Singhatiraj | 30-Jul-2026 | 20-Jul-2026 10:55:56 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 22:26:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 15:18:14 | 27-Jul-2026 10:42:28 | 0 |  |  | Approver | Locate
AO-001967 | MM-ZTK-1F-ZWP23-STR-DWG-2113 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 26000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 10:37:05 | wisuda.c@jutal.com | 10-Sep-2026 10:41:41 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 18-Sep-2026 15:22:31 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 15:33:48 | APPR | Approved | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 18:42:37 | 20-Sep-2026 12:42:12 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP23-STR-DWG-2114 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 38000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:43:01 | wisuda.c@jutal.com | 21-Apr-2026 14:48:10 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 14:47:58 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 22:22:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 14:25:20 | 24-Apr-2026 07:46:03 | 0 |  |  | Approver | Locate
AO-001135 | MM-ZTK-1F-ZWP23-STR-DWG-2114 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 38000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 17:57:04 | wisuda.c@jutal.com | 16-Jul-2026 20:33:16 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sompop Singhatiraj | 30-Jul-2026 | 20-Jul-2026 10:57:50 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 22:29:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 15:23:32 | 27-Jul-2026 10:55:17 | 0 |  |  | Approver | Locate
AO-001967 | MM-ZTK-1F-ZWP23-STR-DWG-2114 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 38000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 10:37:33 | wisuda.c@jutal.com | 10-Sep-2026 10:41:47 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 18-Sep-2026 15:27:54 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 15:35:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 18:43:16 | 20-Sep-2026 12:43:28 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP23-STR-DWG-2115 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 52000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:43:27 | wisuda.c@jutal.com | 21-Apr-2026 14:48:21 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 15:41:28 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 19:40:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 14:25:51 | 24-Apr-2026 07:47:26 | 0 |  |  | Approver | Locate
AO-001135 | MM-ZTK-1F-ZWP23-STR-DWG-2115 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 52000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 17:57:27 | wisuda.c@jutal.com | 16-Jul-2026 20:33:15 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sompop Singhatiraj | 30-Jul-2026 | 24-Jul-2026 08:25:55 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 22:32:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 15:23:57 | 27-Jul-2026 10:56:34 | 0 |  |  | Approver | Locate
AO-001967 | MM-ZTK-1F-ZWP23-STR-DWG-2115 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 52000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 10:38:06 | wisuda.c@jutal.com | 10-Sep-2026 11:58:01 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 18-Sep-2026 15:28:04 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 15:37:01 | APPR | Approved | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 18:43:50 | 20-Sep-2026 12:44:36 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP23-STR-DWG-2116 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 66000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:43:53 | wisuda.c@jutal.com | 21-Apr-2026 14:50:11 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 15:41:38 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 19:38:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 14:29:31 | 24-Apr-2026 08:37:52 | 0 |  |  | Approver | Locate
AO-001135 | MM-ZTK-1F-ZWP23-STR-DWG-2116 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 66000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 17:57:54 | wisuda.c@jutal.com | 16-Jul-2026 20:33:14 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sompop Singhatiraj | 30-Jul-2026 | 24-Jul-2026 08:24:24 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 22:30:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 15:24:30 | 27-Jul-2026 10:57:48 | 0 |  |  | Approver | Locate
AO-001967 | MM-ZTK-1F-ZWP23-STR-DWG-2116 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 66000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 10:38:37 | wisuda.c@jutal.com | 10-Sep-2026 11:58:26 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 18-Sep-2026 15:40:06 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 15:43:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 18:44:41 | 20-Sep-2026 12:45:48 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP23-STR-DWG-2117 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 79500 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:44:20 | wisuda.c@jutal.com | 21-Apr-2026 14:50:24 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 15:44:42 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 19:31:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 14:30:39 | 24-Apr-2026 08:39:14 | 0 |  |  | Approver | Locate
AO-001135 | MM-ZTK-1F-ZWP23-STR-DWG-2117 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 79500 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 17:58:18 | wisuda.c@jutal.com | 16-Jul-2026 20:33:16 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sompop Singhatiraj | 30-Jul-2026 | 24-Jul-2026 08:31:53 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 22:33:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 15:24:55 | 27-Jul-2026 10:59:03 | 0 |  |  | Approver | Locate
AO-001967 | MM-ZTK-1F-ZWP23-STR-DWG-2117 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 79500 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 10:39:07 | wisuda.c@jutal.com | 10-Sep-2026 11:58:40 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 18-Sep-2026 15:31:17 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 15:38:03 | APPR | Approved | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 18:45:12 | 20-Sep-2026 12:46:53 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP23-STR-DWG-2118 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 93000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:44:48 | wisuda.c@jutal.com | 21-Apr-2026 14:50:38 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 15:43:35 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 19:35:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 14:34:23 | 24-Apr-2026 08:40:42 | 0 |  |  | Approver | Locate
AO-001135 | MM-ZTK-1F-ZWP23-STR-DWG-2118 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 93000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 17:58:45 | wisuda.c@jutal.com | 16-Jul-2026 20:33:18 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sompop Singhatiraj | 30-Jul-2026 | 24-Jul-2026 08:32:53 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 22:33:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 15:25:20 | 27-Jul-2026 11:00:22 | 0 |  |  | Approver | Locate
AO-001967 | MM-ZTK-1F-ZWP23-STR-DWG-2118 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 93000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 10:39:36 | wisuda.c@jutal.com | 10-Sep-2026 11:58:53 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 18-Sep-2026 15:39:12 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 15:39:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 18:45:42 | 20-Sep-2026 12:48:06 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP23-STR-DWG-2119 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 107000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:45:18 | wisuda.c@jutal.com | 21-Apr-2026 14:50:50 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 15:44:54 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 19:27:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 14:39:53 | 24-Apr-2026 08:42:07 | 0 |  |  | Approver | Locate
AO-001135 | MM-ZTK-1F-ZWP23-STR-DWG-2119 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 107000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 17:59:12 | wisuda.c@jutal.com | 16-Jul-2026 20:33:23 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sompop Singhatiraj | 30-Jul-2026 | 24-Jul-2026 08:34:23 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 22:34:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 15:25:50 | 27-Jul-2026 11:01:44 | 0 |  |  | Approver | Locate
AO-001967 | MM-ZTK-1F-ZWP23-STR-DWG-2119 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 107000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 10:40:02 | wisuda.c@jutal.com | 10-Sep-2026 11:59:07 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 18-Sep-2026 15:36:01 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 15:38:51 | APPR | Approved | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 18:46:18 | 20-Sep-2026 12:49:11 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP23-STR-DWG-2120 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 121000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:45:49 | wisuda.c@jutal.com | 21-Apr-2026 14:52:23 | Jumpol Sudjitjul | 28-Apr-2026 | 24-Apr-2026 13:05:03 | Sompop Singhatiraj | 30-Apr-2026 | 24-Apr-2026 17:31:56 | Pornlert Wanaphattharaphan | 05-May-2026 | 29-Apr-2026 23:17:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 30-Apr-2026 08:44:42 | 30-Apr-2026 01:55:03 | 0 |  |  | Approver | Locate
AO-001135 | MM-ZTK-1F-ZWP23-STR-DWG-2120 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 121000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 17:59:37 | wisuda.c@jutal.com | 16-Jul-2026 20:33:20 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sompop Singhatiraj | 30-Jul-2026 | 24-Jul-2026 08:37:12 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 22:35:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 15:26:25 | 27-Jul-2026 11:03:00 | 0 |  |  | Approver | Locate
AO-001967 | MM-ZTK-1F-ZWP23-STR-DWG-2120 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 121000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 09:23:59 | wisuda.c@jutal.com | 10-Sep-2026 10:41:43 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 18-Sep-2026 15:39:17 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 15:40:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 18:46:43 | 20-Sep-2026 12:33:59 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP23-STR-DWG-2121 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 133000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:46:17 | wisuda.c@jutal.com | 21-Apr-2026 14:52:35 | Jumpol Sudjitjul | 28-Apr-2026 | 24-Apr-2026 13:06:04 | Sompop Singhatiraj | 30-Apr-2026 | 24-Apr-2026 17:35:58 | Pornlert Wanaphattharaphan | 05-May-2026 | 29-Apr-2026 23:18:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 30-Apr-2026 08:07:56 | 30-Apr-2026 01:51:23 | 0 |  |  | Approver | Locate
AO-001135 | MM-ZTK-1F-ZWP23-STR-DWG-2121 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 133000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 18:00:05 | wisuda.c@jutal.com | 16-Jul-2026 20:33:16 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sompop Singhatiraj | 30-Jul-2026 | 24-Jul-2026 08:37:10 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 22:36:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 15:26:48 | 27-Jul-2026 11:04:18 | 0 |  |  | Approver | Locate
AO-001967 | MM-ZTK-1F-ZWP23-STR-DWG-2121 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 133000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 09:24:38 | wisuda.c@jutal.com | 10-Sep-2026 10:41:45 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 18-Sep-2026 14:50:11 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 15:09:11 | APPR | Approved | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 18:47:13 | 20-Sep-2026 12:35:04 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP23-STR-DWG-2122 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 145000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:46:45 | wisuda.c@jutal.com | 21-Apr-2026 14:52:48 | Jumpol Sudjitjul | 28-Apr-2026 | 24-Apr-2026 13:06:55 | Sompop Singhatiraj | 30-Apr-2026 | 24-Apr-2026 17:36:07 | Pornlert Wanaphattharaphan | 05-May-2026 | 01-May-2026 19:44:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 03-May-2026 16:33:44 | 03-May-2026 10:25:42 | 0 |  |  | Approver | Locate
AO-001135 | MM-ZTK-1F-ZWP23-STR-DWG-2122 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 145000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 16-Jul-2026 18:00:48 | wisuda.c@jutal.com | 16-Jul-2026 20:33:15 | Jumpol Sudjitjul | 24-Jul-2026 |  | Sompop Singhatiraj | 30-Jul-2026 | 24-Jul-2026 08:38:44 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 24-Jul-2026 22:37:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 27-Jul-2026 15:27:18 | 27-Jul-2026 11:05:35 | 0 |  |  | Approver | Locate
AO-001967 | MM-ZTK-1F-ZWP23-STR-DWG-2122 | ZWP23 JACKET - HORIZONTAL FRAMING PLAN AT EL(-) 145000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 09:25:21 | wisuda.c@jutal.com | 10-Sep-2026 10:41:53 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 18-Sep-2026 15:39:53 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 15:42:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 18:47:46 | 20-Sep-2026 12:36:18 | 0 |  |  | Approver | Locate
AO-000180 | MM-ZTK-1F-ZWP23-STR-DWG-2123 | ZWP23 JACKET - FRAMING SECTIONS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 10:47:14 | wisuda.c@jutal.com | 21-Apr-2026 14:53:00 | Jumpol Sudjitjul | 28-Apr-2026 |  | Sompop Singhatiraj | 30-Apr-2026 | 23-Apr-2026 16:16:31 | Pornlert Wanaphattharaphan | 05-May-2026 | 23-Apr-2026 18:22:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-May-2026 | 24-Apr-2026 09:40:26 | 24-Apr-2026 06:23:32 | 0 |  |  | Approver | Locate
AO-001220 | MM-ZTK-1F-ZWP23-STR-DWG-2123 | ZWP23 JACKET - FRAMING SECTIONS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Jul-2026 15:57:56 | wisuda.c@jutal.com | 21-Jul-2026 16:21:54 | Jumpol Sudjitjul | 30-Jul-2026 |  | Sompop Singhatiraj | 03-Aug-2026 | 24-Jul-2026 09:38:31 | Pornlert Wanaphattharaphan | 04-Aug-2026 | 24-Jul-2026 22:52:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Aug-2026 | 27-Jul-2026 15:27:45 | 27-Jul-2026 10:41:14 | 0 |  |  | Approver | Locate
AO-001967 | MM-ZTK-1F-ZWP23-STR-DWG-2123 | ZWP23 JACKET - FRAMING SECTIONS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 09:25:57 | wisuda.c@jutal.com | 10-Sep-2026 10:41:49 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 18-Sep-2026 14:49:52 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 19-Sep-2026 15:07:28 | APPR | Approved | Jumpol Sudjitjul | 23-Sep-2026 | 20-Sep-2026 18:48:12 | 20-Sep-2026 12:37:26 | 0 |  |  | Approver | Locate
AO-000371 | MM-ZTK-1F-ZWP23-STR-DWG-2130 | ZWP23 JACKET - LAUNCH CRADLE GENERAL ARRANGEMENT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 18:08:26 | wisuda.c@jutal.com | 11-May-2026 18:16:45 | Jumpol Sudjitjul | 19-May-2026 |  | Sompop Singhatiraj | 21-May-2026 | 18-May-2026 10:48:30 | Pornlert Wanaphattharaphan | 22-May-2026 | 22-May-2026 00:41:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-May-2026 | 22-May-2026 08:44:34 | 22-May-2026 02:33:18 | 0 |  |  | Approver | Locate
AO-000985 | MM-ZTK-1F-ZWP23-STR-DWG-2130 | ZWP23 JACKET - LAUNCH CRADLE GENERAL ARRANGEMENT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 09:48:28 | wisuda.c@jutal.com | 03-Jul-2026 14:06:47 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 03-Jul-2026 17:33:31 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 04-Jul-2026 20:14:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 05-Jul-2026 10:45:21 | 05-Jul-2026 04:07:55 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP23-STR-DWG-2130 | ZWP23 JACKET - LAUNCH CRADLE GENERAL ARRANGEMENT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 15:48:52 | wisuda.c@jutal.com | 21-Sep-2026 18:03:50 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 22-Sep-2026 14:09:18 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 22-Sep-2026 19:43:38 | APPR | Approved | Jumpol Sudjitjul | 05-Oct-2026 | 23-Sep-2026 13:46:06 | 23-Sep-2026 07:12:18 | 0 |  |  | Approver | Locate
AO-000371 | MM-ZTK-1F-ZWP23-STR-DWG-2131 | ZWP23 JACKET - LAUNCH CRADLE DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 18:08:49 | wisuda.c@jutal.com | 11-May-2026 18:17:01 | Jumpol Sudjitjul | 19-May-2026 |  | Sompop Singhatiraj | 21-May-2026 | 18-May-2026 10:49:10 | Pornlert Wanaphattharaphan | 22-May-2026 | 22-May-2026 00:41:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-May-2026 | 22-May-2026 08:47:39 | 22-May-2026 02:34:26 | 0 |  |  | Approver | Locate
AO-000985 | MM-ZTK-1F-ZWP23-STR-DWG-2131 | ZWP23 JACKET - LAUNCH CRADLE DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 10:54:02 | wisuda.c@jutal.com | 03-Jul-2026 14:06:38 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 03-Jul-2026 17:33:40 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 04-Jul-2026 20:14:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 05-Jul-2026 10:41:44 | 05-Jul-2026 04:23:05 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP23-STR-DWG-2131 | ZWP23 JACKET - LAUNCH CRADLE DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 15:49:37 | wisuda.c@jutal.com | 21-Sep-2026 18:03:51 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 22-Sep-2026 14:09:27 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 22-Sep-2026 19:43:16 | APPR | Approved | Jumpol Sudjitjul | 05-Oct-2026 | 23-Sep-2026 13:33:13 | 23-Sep-2026 07:08:37 | 0 |  |  | Approver | Locate
AO-000371 | MM-ZTK-1F-ZWP23-STR-DWG-2132 | ZWP23 JACKET - LAUNCH CRADLE DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 18:09:16 | wisuda.c@jutal.com | 11-May-2026 18:17:14 | Jumpol Sudjitjul | 19-May-2026 |  | Sompop Singhatiraj | 21-May-2026 | 18-May-2026 10:50:20 | Pornlert Wanaphattharaphan | 22-May-2026 | 22-May-2026 00:42:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-May-2026 | 22-May-2026 08:48:45 | 22-May-2026 02:35:35 | 0 |  |  | Approver | Locate
AO-000985 | MM-ZTK-1F-ZWP23-STR-DWG-2132 | ZWP23 JACKET - LAUNCH CRADLE DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 10:54:33 | wisuda.c@jutal.com | 03-Jul-2026 14:06:33 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 03-Jul-2026 17:34:27 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 04-Jul-2026 20:15:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 05-Jul-2026 10:41:12 | 05-Jul-2026 04:21:49 | 0 |  |  | Approver | Locate
AO-001554 | MM-ZTK-1F-ZWP23-STR-DWG-2132 | ZWP23 JACKET - LAUNCH CRADLE DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 14:29:19 | wisuda.c@jutal.com | 17-Aug-2026 15:22:03 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 20-Aug-2026 13:51:21 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:18:23 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 18:07:48 | 24-Aug-2026 12:24:15 | 0 |  |  | Approver | Locate
AO-000518 | MM-ZTK-1F-ZWP23-STR-DWG-2133 | ZWP23 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 18:18:09 | wisuda.c@jutal.com | 19-May-2026 18:28:19 | Jumpol Sudjitjul | 27-May-2026 |  | Sompop Singhatiraj | 29-May-2026 | 20-May-2026 10:23:01 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 22-May-2026 01:07:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Jun-2026 | 22-May-2026 08:45:35 | 22-May-2026 09:28:29 | 0 |  |  | Approver | Locate
AO-000825 | MM-ZTK-1F-ZWP23-STR-DWG-2133 | ZWP23 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 10:05:55 | wisuda.c@jutal.com | 18-Jun-2026 10:37:00 | Jumpol Sudjitjul | 25-Jun-2026 | 18-Jun-2026 15:58:13 | Sompop Singhatiraj | 29-Jun-2026 | 25-Jun-2026 09:48:28 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 28-Jun-2026 21:45:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 29-Jun-2026 20:50:54 | 29-Jun-2026 14:17:54 | 0 |  |  | Approver | Locate
AO-002420 | MM-ZTK-1F-ZWP23-STR-DWG-2133 | ZWP23 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 08-Oct-2026 09:21:45 | wisuda.c@jutal.com | 08-Oct-2026 10:34:53 | Jumpol Sudjitjul | 16-Oct-2026 |  | Sompop Singhatiraj | 20-Oct-2026 | 09-Oct-2026 08:40:03 | Pornlert Wanaphattharaphan | 21-Oct-2026 | 11-Oct-2026 00:31:49 | APPR | Approved | Jumpol Sudjitjul | 22-Oct-2026 | 11-Oct-2026 10:53:15 | 11-Oct-2026 04:17:41 | 0 |  |  | Approver | Locate
AO-000518 | MM-ZTK-1F-ZWP23-STR-DWG-2134 | ZWP23 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 18:18:50 | wisuda.c@jutal.com | 19-May-2026 18:28:21 | Jumpol Sudjitjul | 27-May-2026 |  | Sompop Singhatiraj | 29-May-2026 | 20-May-2026 10:27:05 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 22-May-2026 01:09:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Jun-2026 | 22-May-2026 09:55:54 | 22-May-2026 12:05:02 | 0 |  |  | Approver | Locate
AO-000826 | MM-ZTK-1F-ZWP23-STR-DWG-2134 | ZWP23 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 10:06:27 | wisuda.c@jutal.com | 18-Jun-2026 10:37:14 | Jumpol Sudjitjul | 25-Jun-2026 | 18-Jun-2026 15:59:26 | Sompop Singhatiraj | 29-Jun-2026 | 25-Jun-2026 09:54:59 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 28-Jun-2026 21:47:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 29-Jun-2026 20:52:08 | 29-Jun-2026 14:19:29 | 0 |  |  | Approver | Locate
AO-002421 | MM-ZTK-1F-ZWP23-STR-DWG-2134 | ZWP23 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 08-Oct-2026 09:22:19 | wisuda.c@jutal.com | 08-Oct-2026 10:34:54 | Jumpol Sudjitjul | 16-Oct-2026 |  | Sompop Singhatiraj | 20-Oct-2026 | 09-Oct-2026 08:39:14 | Pornlert Wanaphattharaphan | 21-Oct-2026 | 11-Oct-2026 00:30:57 | APPR | Approved | Jumpol Sudjitjul | 22-Oct-2026 | 11-Oct-2026 10:53:50 | 11-Oct-2026 04:19:54 | 0 |  |  | Approver | Locate
AO-000518 | MM-ZTK-1F-ZWP23-STR-DWG-2135 | ZWP23 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 18:19:27 | wisuda.c@jutal.com | 19-May-2026 18:28:19 | Jumpol Sudjitjul | 27-May-2026 |  | Sompop Singhatiraj | 29-May-2026 | 20-May-2026 10:21:01 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 22-May-2026 01:07:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Jun-2026 | 22-May-2026 09:59:31 | 22-May-2026 12:22:52 | 0 |  |  | Approver | Locate
AO-000827 | MM-ZTK-1F-ZWP23-STR-DWG-2135 | ZWP23 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 10:39:52 | wisuda.c@jutal.com | 18-Jun-2026 11:58:46 | Jumpol Sudjitjul | 25-Jun-2026 | 18-Jun-2026 15:59:41 | Sompop Singhatiraj | 29-Jun-2026 | 25-Jun-2026 09:58:39 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 28-Jun-2026 21:48:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 30-Jun-2026 08:53:33 | 30-Jun-2026 02:21:47 | 0 |  |  | Approver | Locate
AO-002422 | MM-ZTK-1F-ZWP23-STR-DWG-2135 | ZWP23 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 3 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 08-Oct-2026 09:23:00 | wisuda.c@jutal.com | 08-Oct-2026 10:34:55 | Jumpol Sudjitjul | 16-Oct-2026 |  | Sompop Singhatiraj | 20-Oct-2026 | 09-Oct-2026 08:38:55 | Pornlert Wanaphattharaphan | 21-Oct-2026 | 11-Oct-2026 00:30:31 | APPR | Approved | Jumpol Sudjitjul | 22-Oct-2026 | 11-Oct-2026 10:54:37 | 11-Oct-2026 04:21:02 | 0 |  |  | Approver | Locate
AO-000518 | MM-ZTK-1F-ZWP23-STR-DWG-2136 | ZWP23 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 18:20:16 | wisuda.c@jutal.com | 19-May-2026 18:28:23 | Jumpol Sudjitjul | 27-May-2026 |  | Sompop Singhatiraj | 29-May-2026 | 20-May-2026 10:25:08 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 22-May-2026 01:08:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Jun-2026 | 22-May-2026 10:05:25 | 22-May-2026 12:10:37 | 0 |  |  | Approver | Locate
AO-000828 | MM-ZTK-1F-ZWP23-STR-DWG-2136 | ZWP23 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 4 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 11:17:06 | wisuda.c@jutal.com | 18-Jun-2026 11:59:04 | Jumpol Sudjitjul | 25-Jun-2026 | 18-Jun-2026 16:00:00 | Sompop Singhatiraj | 29-Jun-2026 | 25-Jun-2026 11:02:20 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 28-Jun-2026 21:49:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 30-Jun-2026 08:52:19 | 30-Jun-2026 02:18:43 | 0 |  |  | Approver | Locate
AO-002423 | MM-ZTK-1F-ZWP23-STR-DWG-2136 | ZWP23 JACKET - LAUNCH CRADLE AND VERTICAL FRAMING INTERNAL RING STIFFENER DETAILS - SHEET 4 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 08-Oct-2026 09:23:35 | wisuda.c@jutal.com | 08-Oct-2026 10:34:55 | Jumpol Sudjitjul | 16-Oct-2026 |  | Sompop Singhatiraj | 20-Oct-2026 | 09-Oct-2026 08:38:36 | Pornlert Wanaphattharaphan | 21-Oct-2026 | 11-Oct-2026 00:36:55 | APPR | Approved | Jumpol Sudjitjul | 22-Oct-2026 | 11-Oct-2026 10:55:13 | 11-Oct-2026 04:22:11 | 0 |  |  | Approver | Locate
AO-000400 | MM-ZTK-1F-ZWP23-STR-DWG-2141 | ZWP23 JACKET - PILE CLUSTER ARRANGEMENT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 10:49:19 | wisuda.c@jutal.com | 15-May-2026 13:25:58 | Jumpol Sudjitjul | 22-May-2026 |  | Sompop Singhatiraj | 26-May-2026 | 20-May-2026 12:09:23 | Pornlert Wanaphattharaphan | 27-May-2026 | 22-May-2026 00:33:21 | AWC |  | Jumpol Sudjitjul | 28-May-2026 | 22-May-2026 09:12:24 | 10-Jun-2026 08:54:07 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP23-STR-DWG-2141 | ZWP23 JACKET - PILE CLUSTER ARRANGEMENT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Sep-2026 15:50:21 | wisuda.c@jutal.com | 21-Sep-2026 18:03:51 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 22-Sep-2026 17:22:03 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 22-Sep-2026 19:42:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Oct-2026 | 23-Sep-2026 13:29:08 | 23-Sep-2026 07:02:23 | 0 |  |  | Approver | Locate
AO-002310 | MM-ZTK-1F-ZWP23-STR-DWG-2141 | ZWP23 JACKET - PILE CLUSTER ARRANGEMENT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 30-Sep-2026 09:32:59 | wisuda.c@jutal.com | 30-Sep-2026 16:08:44 | Jumpol Sudjitjul | 07-Oct-2026 |  | Sompop Singhatiraj | 09-Oct-2026 | 01-Oct-2026 15:56:21 | Pornlert Wanaphattharaphan | 12-Oct-2026 | 01-Oct-2026 22:46:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Oct-2026 | 02-Oct-2026 13:30:31 | 02-Oct-2026 07:26:16 | 0 |  |  | Approver | Locate
AO-000400 | MM-ZTK-1F-ZWP23-STR-DWG-2142 | ZWP23 JACKET - PILE SLEEVE DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 10:49:45 | wisuda.c@jutal.com | 15-May-2026 13:25:53 | Jumpol Sudjitjul | 22-May-2026 |  | Sompop Singhatiraj | 26-May-2026 | 20-May-2026 12:09:33 | Pornlert Wanaphattharaphan | 27-May-2026 | 22-May-2026 00:34:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-May-2026 | 22-May-2026 08:52:19 | 22-May-2026 02:39:55 | 0 |  |  | Approver | Locate
AO-002200 | MM-ZTK-1F-ZWP23-STR-DWG-2142 | ZWP23 JACKET - PILE SLEEVE DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 21-Sep-2026 15:51:33 | wisuda.c@jutal.com | 21-Sep-2026 18:03:53 | Jumpol Sudjitjul | 29-Sep-2026 |  | Sompop Singhatiraj | 01-Oct-2026 | 22-Sep-2026 17:22:08 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 22-Sep-2026 19:41:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 05-Oct-2026 | 23-Sep-2026 13:32:13 | 23-Sep-2026 07:06:17 | 0 |  |  | Approver | Locate
AO-002310 | MM-ZTK-1F-ZWP23-STR-DWG-2142 | ZWP23 JACKET - PILE SLEEVE DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 30-Sep-2026 09:34:07 | wisuda.c@jutal.com | 30-Sep-2026 16:08:44 | Jumpol Sudjitjul | 07-Oct-2026 |  | Sompop Singhatiraj | 09-Oct-2026 | 01-Oct-2026 17:37:56 | Pornlert Wanaphattharaphan | 12-Oct-2026 | 01-Oct-2026 22:45:39 | APPR | Approved | Jumpol Sudjitjul | 14-Oct-2026 | 02-Oct-2026 13:29:43 | 02-Oct-2026 07:24:57 | 0 |  |  | Approver | Locate
AO-000400 | MM-ZTK-1F-ZWP23-STR-DWG-2143 | ZWP23 JACKET - SKIRT SLEEVE MARKING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 10:50:13 | wisuda.c@jutal.com | 15-May-2026 13:25:53 | Jumpol Sudjitjul | 22-May-2026 |  | Sompop Singhatiraj | 26-May-2026 | 20-May-2026 12:10:47 | Pornlert Wanaphattharaphan | 27-May-2026 | 22-May-2026 00:33:47 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 28-May-2026 | 22-May-2026 08:50:21 | 22-May-2026 02:36:46 | 0 |  |  | Approver | Locate
AO-000700 | MM-ZTK-1F-ZWP23-STR-DWG-2144 | ZWP23 JACKET - PILE MAKE-UP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 09:23:51 | wisuda.c@jutal.com | 08-Jun-2026 15:54:58 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 12-Jun-2026 13:46:38 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 13-Jun-2026 00:50:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 13-Jun-2026 07:01:49 | 13-Jun-2026 00:28:52 | 0 |  |  | Approver | Locate
AO-001821 | MM-ZTK-1F-ZWP23-STR-DWG-2144 | ZWP23 JACKET - PILE MAKE-UP |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:09:30 | wisuda.c@jutal.com | 03-Sep-2026 11:06:12 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 07-Sep-2026 13:44:00 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 15:48:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 11:25:27 | 13-Sep-2026 05:18:29 | 0 |  |  | Approver | Locate
AO-002308 | MM-ZTK-1F-ZWP23-STR-DWG-2144 | ZWP23 JACKET - PILE MAKE-UP |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 30-Sep-2026 09:35:11 | wisuda.c@jutal.com | 30-Sep-2026 16:08:43 | Jumpol Sudjitjul | 07-Oct-2026 |  | Sompop Singhatiraj | 09-Oct-2026 | 01-Oct-2026 15:42:11 | Pornlert Wanaphattharaphan | 12-Oct-2026 | 01-Oct-2026 22:45:14 | APPR | Approved | Jumpol Sudjitjul | 14-Oct-2026 | 02-Oct-2026 13:26:22 | 02-Oct-2026 07:22:33 | 0 |  |  | Approver | Locate
AO-000829 | MM-ZTK-1F-ZWP23-STR-DWG-2200 | ZWP23 JACKET - HYDROSTATIC RING DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 15:57:47 | wisuda.c@jutal.com | 18-Jun-2026 17:31:29 | Jumpol Sudjitjul | 26-Jun-2026 | 19-Jun-2026 00:49:51 | Sompop Singhatiraj | 30-Jun-2026 | 25-Jun-2026 11:05:07 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 28-Jun-2026 23:11:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 30-Jun-2026 08:48:22 | 30-Jun-2026 02:17:12 | 0 |  |  | Approver | Locate
AO-002164 | MM-ZTK-1F-ZWP23-STR-DWG-2200 | ZWP23 JACKET - HYDROSTATIC RING DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 18-Sep-2026 19:01:09 | wisuda.c@jutal.com | 20-Sep-2026 12:45:01 | Jumpol Sudjitjul | 25-Sep-2026 |  | Sompop Singhatiraj | 29-Sep-2026 | 28-Sep-2026 09:55:07 | Pornlert Wanaphattharaphan | 30-Sep-2026 | 28-Sep-2026 22:07:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Oct-2026 | 29-Sep-2026 10:31:20 | 29-Sep-2026 04:39:24 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP23-STR-DWG-2200 | ZWP23 JACKET - HYDROSTATIC RING DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 14-Oct-2026 09:38:32 | wisuda.c@jutal.com | 14-Oct-2026 09:50:47 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 |  | Pornlert Wanaphattharaphan | 27-Oct-2026 |  |  |  |  | 28-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000830 | MM-ZTK-1F-ZWP23-STR-DWG-2201 | ZWP23 JACKET - HYDROSTATIC RING DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 15:58:16 | wisuda.c@jutal.com | 18-Jun-2026 17:31:52 | Jumpol Sudjitjul | 26-Jun-2026 | 19-Jun-2026 00:50:22 | Sompop Singhatiraj | 30-Jun-2026 | 25-Jun-2026 11:07:29 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 28-Jun-2026 23:14:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 29-Jun-2026 21:17:51 | 29-Jun-2026 14:53:54 | 0 |  |  | Approver | Locate
AO-002164 | MM-ZTK-1F-ZWP23-STR-DWG-2201 | ZWP23 JACKET - HYDROSTATIC RING DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 18-Sep-2026 19:01:37 | wisuda.c@jutal.com | 20-Sep-2026 12:45:53 | Jumpol Sudjitjul | 25-Sep-2026 |  | Sompop Singhatiraj | 29-Sep-2026 | 28-Sep-2026 10:20:35 | Pornlert Wanaphattharaphan | 30-Sep-2026 | 28-Sep-2026 22:08:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Oct-2026 | 29-Sep-2026 10:28:48 | 29-Sep-2026 03:53:28 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP23-STR-DWG-2201 | ZWP23 JACKET - HYDROSTATIC RING DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 09:39:12 | wisuda.c@jutal.com | 14-Oct-2026 09:50:45 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 15:56:20 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:50:29 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:27:43 | 16-Oct-2026 09:33:54 | 0 |  |  | Approver | Locate
AO-000740 | MM-ZTK-1F-ZWP23-STR-DWG-2241 | ZWP23 JACKET - RISER PROTECTOR |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 18:16:00 | wisuda.c@jutal.com | 12-Jun-2026 09:49:34 | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 00:45:01 | Sompop Singhatiraj | 23-Jun-2026 | 18-Jun-2026 07:43:05 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 18-Jun-2026 14:00:16 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 25-Jun-2026 | 18-Jun-2026 14:26:35 | 18-Jun-2026 08:05:06 | 0 |  |  | Approver | Locate
AO-001845 | MM-ZTK-1F-ZWP23-STR-DWG-2300 | ZWP23 JACKET - CASING GUIDE ARRANGEMENT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Sep-2026 16:47:08 | wisuda.c@jutal.com | 03-Sep-2026 17:37:46 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 07-Sep-2026 13:56:04 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 16:45:04 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 11:26:06 | 13-Sep-2026 05:08:33 | 0 |  |  | Approver | Locate
AO-002217 | MM-ZTK-1F-ZWP23-STR-DWG-2300 | ZWP23 JACKET - CASING GUIDE ARRANGEMENT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 23-Sep-2026 09:29:35 | wisuda.c@jutal.com | 23-Sep-2026 13:57:07 | Jumpol Sudjitjul | 30-Sep-2026 |  | Sompop Singhatiraj | 02-Oct-2026 | 25-Sep-2026 16:52:45 | Pornlert Wanaphattharaphan | 05-Oct-2026 | 26-Sep-2026 05:22:08 | APPR | Approved | Jumpol Sudjitjul | 06-Oct-2026 | 26-Sep-2026 16:18:26 | 26-Sep-2026 09:59:38 | 0 |  |  | Approver | Locate
AO-001845 | MM-ZTK-1F-ZWP23-STR-DWG-2301 | ZWP23 JACKET - CASING GUIDE DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Sep-2026 16:47:43 | wisuda.c@jutal.com | 03-Sep-2026 17:37:47 | Jumpol Sudjitjul | 11-Sep-2026 |  | Sompop Singhatiraj | 15-Sep-2026 | 07-Sep-2026 14:08:01 | Pornlert Wanaphattharaphan | 16-Sep-2026 | 12-Sep-2026 16:50:22 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 17-Sep-2026 | 13-Sep-2026 11:26:43 | 13-Sep-2026 05:09:36 | 0 |  |  | Approver | Locate
AO-002217 | MM-ZTK-1F-ZWP23-STR-DWG-2301 | ZWP23 JACKET - CASING GUIDE DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 23-Sep-2026 09:30:09 | wisuda.c@jutal.com | 23-Sep-2026 13:57:07 | Jumpol Sudjitjul | 30-Sep-2026 |  | Sompop Singhatiraj | 02-Oct-2026 | 25-Sep-2026 16:52:40 | Pornlert Wanaphattharaphan | 05-Oct-2026 | 26-Sep-2026 05:22:35 | APPR | Approved | Jumpol Sudjitjul | 06-Oct-2026 | 26-Sep-2026 16:18:53 | 26-Sep-2026 10:00:45 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP23-STR-DWG-2311 | ZWP23 JACKET - ANODE STRUCTURE AND INSTALLATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 16:33:56 | wisuda.c@jutal.com | 04-May-2026 11:55:08 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:39:54 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 15:56:17 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:47:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 08:46:17 | 19-May-2026 02:07:03 | 0 |  |  | Approver | Locate
AO-001820 | MM-ZTK-1F-ZWP23-STR-DWG-2311 | ZWP23 JACKET - ANODE STRUCTURE AND INSTALLATION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:10:07 | wisuda.c@jutal.com | 03-Sep-2026 11:10:30 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 07-Sep-2026 14:50:24 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 15:53:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 11:22:58 | 13-Sep-2026 05:16:01 | 0 |  |  | Approver | Locate
AO-002425 | MM-ZTK-1F-ZWP23-STR-DWG-2311 | ZWP23 JACKET - ANODE STRUCTURE AND INSTALLATION |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 08-Oct-2026 09:24:08 | wisuda.c@jutal.com | 08-Oct-2026 10:35:02 | Jumpol Sudjitjul | 16-Oct-2026 |  | Sompop Singhatiraj | 20-Oct-2026 | 09-Oct-2026 08:21:13 | Pornlert Wanaphattharaphan | 21-Oct-2026 | 11-Oct-2026 00:29:37 | APPR | Approved | Jumpol Sudjitjul | 22-Oct-2026 | 11-Oct-2026 10:55:45 | 11-Oct-2026 04:23:20 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP23-STR-DWG-2312 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'A' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 16:34:21 | wisuda.c@jutal.com | 04-May-2026 12:45:44 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:41:34 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 16:09:46 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:49:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 08:48:25 | 19-May-2026 02:11:04 | 0 |  |  | Approver | Locate
AO-001820 | MM-ZTK-1F-ZWP23-STR-DWG-2312 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'A' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:10:43 | wisuda.c@jutal.com | 03-Sep-2026 11:10:35 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 07-Sep-2026 15:30:21 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 15:56:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 11:22:18 | 13-Sep-2026 05:14:47 | 0 |  |  | Approver | Locate
AO-002426 | MM-ZTK-1F-ZWP23-STR-DWG-2312 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'A' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 08-Oct-2026 09:24:44 | wisuda.c@jutal.com | 08-Oct-2026 10:35:00 | Jumpol Sudjitjul | 16-Oct-2026 |  | Sompop Singhatiraj | 20-Oct-2026 | 09-Oct-2026 08:20:09 | Pornlert Wanaphattharaphan | 21-Oct-2026 | 11-Oct-2026 00:26:11 | APPR | Approved | Jumpol Sudjitjul | 22-Oct-2026 | 11-Oct-2026 10:58:57 | 11-Oct-2026 04:24:27 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP23-STR-DWG-2313 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'B' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 16:34:45 | wisuda.c@jutal.com | 04-May-2026 12:45:32 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:43:14 | Sompop Singhatiraj | 13-May-2026 | 12-May-2026 10:32:27 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:49:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 09:46:08 | 19-May-2026 03:59:40 | 0 |  |  | Approver | Locate
AO-001820 | MM-ZTK-1F-ZWP23-STR-DWG-2313 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'B' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:11:19 | wisuda.c@jutal.com | 03-Sep-2026 11:10:30 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 07-Sep-2026 15:30:24 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 15:56:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 11:23:36 | 13-Sep-2026 05:17:14 | 0 |  |  | Approver | Locate
AO-002427 | MM-ZTK-1F-ZWP23-STR-DWG-2313 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW 'B' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 08-Oct-2026 09:25:15 | wisuda.c@jutal.com | 08-Oct-2026 10:34:57 | Jumpol Sudjitjul | 16-Oct-2026 |  | Sompop Singhatiraj | 20-Oct-2026 | 09-Oct-2026 08:20:31 | Pornlert Wanaphattharaphan | 21-Oct-2026 | 11-Oct-2026 00:27:22 | APPR | Approved | Jumpol Sudjitjul | 22-Oct-2026 | 11-Oct-2026 10:52:29 | 11-Oct-2026 04:16:31 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP23-STR-DWG-2314 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '1' & '1.1' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 16:35:11 | wisuda.c@jutal.com | 04-May-2026 11:41:08 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:44:50 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 15:55:13 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:47:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 08:26:42 | 19-May-2026 01:38:42 | 0 |  |  | Approver | Locate
AO-001820 | MM-ZTK-1F-ZWP23-STR-DWG-2314 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '1' & '1.1' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:11:55 | wisuda.c@jutal.com | 03-Sep-2026 11:10:37 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 07-Sep-2026 15:32:46 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 15:58:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 11:27:08 | 13-Sep-2026 05:19:41 | 0 |  |  | Approver | Locate
AO-002428 | MM-ZTK-1F-ZWP23-STR-DWG-2314 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '1' & '1.1' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 08-Oct-2026 09:25:44 | wisuda.c@jutal.com | 08-Oct-2026 10:35:03 | Jumpol Sudjitjul | 16-Oct-2026 |  | Sompop Singhatiraj | 20-Oct-2026 | 09-Oct-2026 08:21:04 | Pornlert Wanaphattharaphan | 21-Oct-2026 | 11-Oct-2026 00:29:13 | APPR | Approved | Jumpol Sudjitjul | 22-Oct-2026 | 11-Oct-2026 10:59:36 | 11-Oct-2026 04:25:33 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP23-STR-DWG-2315 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '2' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 16:35:36 | wisuda.c@jutal.com | 04-May-2026 11:40:55 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:46:32 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 15:54:09 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:45:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 09:12:30 | 19-May-2026 03:53:32 | 0 |  |  | Approver | Locate
AO-001820 | MM-ZTK-1F-ZWP23-STR-DWG-2315 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '2' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:12:38 | wisuda.c@jutal.com | 03-Sep-2026 11:10:37 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 07-Sep-2026 15:32:54 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 16:29:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 11:27:53 | 13-Sep-2026 05:23:22 | 0 |  |  | Approver | Locate
AO-002429 | MM-ZTK-1F-ZWP23-STR-DWG-2315 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING ROW '2' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 08-Oct-2026 09:26:15 | wisuda.c@jutal.com | 08-Oct-2026 10:35:11 | Jumpol Sudjitjul | 16-Oct-2026 |  | Sompop Singhatiraj | 20-Oct-2026 | 09-Oct-2026 08:20:49 | Pornlert Wanaphattharaphan | 21-Oct-2026 | 11-Oct-2026 00:28:12 | APPR | Approved | Jumpol Sudjitjul | 22-Oct-2026 | 11-Oct-2026 11:00:08 | 11-Oct-2026 04:26:40 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP23-STR-DWG-2316 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'AA' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 16:35:59 | wisuda.c@jutal.com | 04-May-2026 11:40:43 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:48:16 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 15:54:18 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:46:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 08:18:29 | 19-May-2026 01:36:32 | 0 |  |  | Approver | Locate
AO-001820 | MM-ZTK-1F-ZWP23-STR-DWG-2316 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'AA' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:13:24 | wisuda.c@jutal.com | 03-Sep-2026 11:10:38 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 07-Sep-2026 15:30:29 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 15:57:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 11:28:31 | 13-Sep-2026 05:25:51 | 0 |  |  | Approver | Locate
AO-002431 | MM-ZTK-1F-ZWP23-STR-DWG-2316 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'AA' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 08-Oct-2026 09:26:53 | wisuda.c@jutal.com | 08-Oct-2026 10:35:12 | Jumpol Sudjitjul | 16-Oct-2026 |  | Sompop Singhatiraj | 20-Oct-2026 | 09-Oct-2026 08:18:34 | Pornlert Wanaphattharaphan | 21-Oct-2026 | 11-Oct-2026 00:25:44 | APPR | Approved | Jumpol Sudjitjul | 22-Oct-2026 | 11-Oct-2026 10:53:35 | 11-Oct-2026 04:18:48 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP23-STR-DWG-2317 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'BB' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 16:36:23 | wisuda.c@jutal.com | 04-May-2026 11:40:31 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:50:46 | Sompop Singhatiraj | 13-May-2026 | 11-May-2026 15:53:00 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:44:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 08:11:00 | 19-May-2026 01:32:51 | 0 |  |  | Approver | Locate
AO-001820 | MM-ZTK-1F-ZWP23-STR-DWG-2317 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'BB' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:14:05 | wisuda.c@jutal.com | 03-Sep-2026 11:10:35 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 07-Sep-2026 15:30:34 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 15:57:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 11:29:07 | 13-Sep-2026 05:28:17 | 0 |  |  | Approver | Locate
AO-002362 | MM-ZTK-1F-ZWP23-STR-DWG-2317 | ZWP23 JACKET - ANODE DISTRIBUTION OF VERTICAL FRAMING LAUNCH TRUSS ROW 'BB' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 09:27:55 | wisuda.c@jutal.com | 05-Oct-2026 10:01:49 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 06-Oct-2026 11:38:09 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 22:26:48 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 11-Oct-2026 10:53:00 | 11-Oct-2026 04:35:44 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP23-STR-DWG-2321 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 14000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 16:36:45 | wisuda.c@jutal.com | 04-May-2026 11:11:36 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:52:34 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:58:23 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:12:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 08:54:41 | 19-May-2026 02:16:03 | 0 |  |  | Approver | Locate
AO-001820 | MM-ZTK-1F-ZWP23-STR-DWG-2321 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 14000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:14:41 | wisuda.c@jutal.com | 03-Sep-2026 11:10:39 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 08-Sep-2026 07:52:52 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 16:32:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 11:29:28 | 13-Sep-2026 05:29:34 | 0 |  |  | Approver | Locate
AO-002362 | MM-ZTK-1F-ZWP23-STR-DWG-2321 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 14000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 09:28:43 | wisuda.c@jutal.com | 05-Oct-2026 10:01:49 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 06-Oct-2026 11:38:18 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 22:27:30 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 11-Oct-2026 11:12:53 | 11-Oct-2026 04:36:51 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP23-STR-DWG-2322 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 26000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 16:37:06 | wisuda.c@jutal.com | 04-May-2026 11:11:24 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:54:01 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:58:34 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:13:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 08:54:22 | 19-May-2026 02:14:48 | 0 |  |  | Approver | Locate
AO-001820 | MM-ZTK-1F-ZWP23-STR-DWG-2322 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 26000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:15:20 | wisuda.c@jutal.com | 03-Sep-2026 11:10:45 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 08-Sep-2026 07:51:16 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 16:31:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 11:30:37 | 13-Sep-2026 05:32:05 | 0 |  |  | Approver | Locate
AO-002362 | MM-ZTK-1F-ZWP23-STR-DWG-2322 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 26000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 09:29:16 | wisuda.c@jutal.com | 05-Oct-2026 10:01:49 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 06-Oct-2026 11:40:34 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 22:36:14 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 11-Oct-2026 11:13:24 | 11-Oct-2026 04:38:06 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP23-STR-DWG-2323 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 38000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 16:37:29 | wisuda.c@jutal.com | 04-May-2026 11:11:12 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:55:39 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:58:44 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:13:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 08:12:50 | 19-May-2026 01:34:06 | 0 |  |  | Approver | Locate
AO-001820 | MM-ZTK-1F-ZWP23-STR-DWG-2323 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 38000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:15:57 | wisuda.c@jutal.com | 03-Sep-2026 11:10:45 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 08-Sep-2026 07:47:20 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 16:30:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 11:31:37 | 13-Sep-2026 05:33:21 | 0 |  |  | Approver | Locate
AO-002362 | MM-ZTK-1F-ZWP23-STR-DWG-2323 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 38000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 09:29:51 | wisuda.c@jutal.com | 05-Oct-2026 10:01:48 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 06-Oct-2026 11:38:29 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 22:28:27 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 11-Oct-2026 11:13:52 | 11-Oct-2026 04:39:11 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP23-STR-DWG-2324 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 52000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 16:37:52 | wisuda.c@jutal.com | 04-May-2026 11:11:00 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:57:24 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 10:00:04 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:14:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 08:52:33 | 19-May-2026 02:13:33 | 0 |  |  | Approver | Locate
AO-001820 | MM-ZTK-1F-ZWP23-STR-DWG-2324 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 52000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:16:34 | wisuda.c@jutal.com | 03-Sep-2026 11:10:53 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 08-Sep-2026 07:47:09 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 16:30:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 11:32:17 | 13-Sep-2026 05:34:38 | 0 |  |  | Approver | Locate
AO-002362 | MM-ZTK-1F-ZWP23-STR-DWG-2324 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 52000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 09:30:46 | wisuda.c@jutal.com | 05-Oct-2026 10:01:59 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 06-Oct-2026 11:38:35 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 22:30:28 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 11-Oct-2026 11:14:26 | 11-Oct-2026 04:40:17 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP23-STR-DWG-2325 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 66000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 16:38:14 | wisuda.c@jutal.com | 04-May-2026 11:08:30 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 11:59:07 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 10:00:11 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:14:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 08:50:59 | 19-May-2026 02:12:19 | 0 |  |  | Approver | Locate
AO-001820 | MM-ZTK-1F-ZWP23-STR-DWG-2325 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 66000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:17:09 | wisuda.c@jutal.com | 03-Sep-2026 11:10:50 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 08-Sep-2026 07:53:03 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 16:33:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 11:27:24 | 13-Sep-2026 05:20:56 | 0 |  |  | Approver | Locate
AO-002362 | MM-ZTK-1F-ZWP23-STR-DWG-2325 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 66000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 09:31:18 | wisuda.c@jutal.com | 05-Oct-2026 10:01:55 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 06-Oct-2026 11:39:37 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 22:31:44 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 11-Oct-2026 11:14:52 | 11-Oct-2026 04:41:22 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP23-STR-DWG-2326 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 79500 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 16:38:36 | wisuda.c@jutal.com | 04-May-2026 11:08:16 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 12:44:40 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 10:00:20 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:15:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 08:48:21 | 19-May-2026 02:09:41 | 0 |  |  | Approver | Locate
AO-001820 | MM-ZTK-1F-ZWP23-STR-DWG-2326 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 79500 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:17:43 | wisuda.c@jutal.com | 03-Sep-2026 11:10:42 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 08-Sep-2026 07:53:10 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 16:33:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 11:28:45 | 13-Sep-2026 05:27:03 | 0 |  |  | Approver | Locate
AO-002362 | MM-ZTK-1F-ZWP23-STR-DWG-2326 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 79500 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 09:31:47 | wisuda.c@jutal.com | 05-Oct-2026 10:01:53 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 06-Oct-2026 11:39:51 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 22:32:39 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 11-Oct-2026 11:15:18 | 11-Oct-2026 04:57:40 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP23-STR-DWG-2327 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 93000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 16:38:58 | wisuda.c@jutal.com | 04-May-2026 11:08:03 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 12:46:02 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 10:01:27 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:15:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 08:46:25 | 19-May-2026 02:08:26 | 0 |  |  | Approver | Locate
AO-001820 | MM-ZTK-1F-ZWP23-STR-DWG-2327 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 93000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:18:25 | wisuda.c@jutal.com | 03-Sep-2026 11:10:45 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 08-Sep-2026 07:58:46 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 16:33:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 11:28:16 | 13-Sep-2026 05:24:35 | 0 |  |  | Approver | Locate
AO-002362 | MM-ZTK-1F-ZWP23-STR-DWG-2327 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 93000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 09:32:23 | wisuda.c@jutal.com | 05-Oct-2026 10:01:58 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 06-Oct-2026 11:40:07 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 22:33:36 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 11-Oct-2026 11:15:46 | 11-Oct-2026 04:51:04 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP23-STR-DWG-2328 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 107000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 16:39:21 | wisuda.c@jutal.com | 04-May-2026 11:07:50 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 12:49:50 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 10:01:35 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:16:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 08:44:10 | 19-May-2026 02:34:07 | 0 |  |  | Approver | Locate
AO-001820 | MM-ZTK-1F-ZWP23-STR-DWG-2328 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 107000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:19:10 | wisuda.c@jutal.com | 03-Sep-2026 11:10:52 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 08-Sep-2026 07:59:04 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 16:34:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 11:27:42 | 13-Sep-2026 05:22:10 | 0 |  |  | Approver | Locate
AO-002362 | MM-ZTK-1F-ZWP23-STR-DWG-2328 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 107000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 09:33:01 | wisuda.c@jutal.com | 05-Oct-2026 10:01:58 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 06-Oct-2026 11:40:20 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 22:34:57 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 11-Oct-2026 11:16:11 | 11-Oct-2026 04:53:17 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP23-STR-DWG-2329 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 121000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 16:39:44 | wisuda.c@jutal.com | 04-May-2026 11:05:23 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 12:51:23 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 10:01:45 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:16:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 08:41:36 | 19-May-2026 02:32:54 | 0 |  |  | Approver | Locate
AO-001820 | MM-ZTK-1F-ZWP23-STR-DWG-2329 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 121000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:19:50 | wisuda.c@jutal.com | 03-Sep-2026 11:10:50 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 08-Sep-2026 07:59:44 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 16:35:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 11:32:43 | 13-Sep-2026 05:35:57 | 0 |  |  | Approver | Locate
AO-002362 | MM-ZTK-1F-ZWP23-STR-DWG-2329 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 121000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 09:33:29 | wisuda.c@jutal.com | 05-Oct-2026 10:01:58 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 06-Oct-2026 11:42:46 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 22:37:51 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 11-Oct-2026 11:16:48 | 11-Oct-2026 04:55:29 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP23-STR-DWG-2330 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 133000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 16:40:06 | wisuda.c@jutal.com | 04-May-2026 11:05:08 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 12:52:50 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:37:18 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:00:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 08:37:43 | 19-May-2026 02:29:21 | 0 |  |  | Approver | Locate
AO-001820 | MM-ZTK-1F-ZWP23-STR-DWG-2330 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 133000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:20:25 | wisuda.c@jutal.com | 03-Sep-2026 11:10:58 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 08-Sep-2026 08:03:50 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 16:36:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 11:33:11 | 13-Sep-2026 05:37:14 | 0 |  |  | Approver | Locate
AO-002362 | MM-ZTK-1F-ZWP23-STR-DWG-2330 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 133000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 09:34:00 | wisuda.c@jutal.com | 05-Oct-2026 10:01:59 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 06-Oct-2026 11:43:17 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 22:38:32 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 11-Oct-2026 11:17:03 | 11-Oct-2026 04:56:35 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP23-STR-DWG-2331 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 145000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 16:40:28 | wisuda.c@jutal.com | 04-May-2026 11:04:56 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 12:54:14 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 10:02:24 | Pornlert Wanaphattharaphan | 14-May-2026 | 19-May-2026 00:17:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 08:25:34 | 19-May-2026 01:45:36 | 0 |  |  | Approver | Locate
AO-001820 | MM-ZTK-1F-ZWP23-STR-DWG-2331 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 145000 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:20:59 | wisuda.c@jutal.com | 03-Sep-2026 11:10:58 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 08-Sep-2026 08:06:50 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 16:37:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 11:30:00 | 13-Sep-2026 05:30:52 | 0 |  |  | Approver | Locate
AO-002362 | MM-ZTK-1F-ZWP23-STR-DWG-2331 | ZWP23 JACKET - ANODE DISTRIBUTION OF HORIZONTAL FRAMING PLAN AT EL(-) 145000 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 09:34:27 | wisuda.c@jutal.com | 05-Oct-2026 10:02:00 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 06-Oct-2026 11:43:37 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 22:43:38 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 11-Oct-2026 11:16:32 | 11-Oct-2026 04:54:22 | 0 |  |  | Approver | Locate
AO-000297 | MM-ZTK-1F-ZWP23-STR-DWG-2332 | ZWP23 JACKET - ANODE DISTRIBUTION OF PILE CLUSTER |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-May-2026 16:40:50 | wisuda.c@jutal.com | 04-May-2026 11:04:41 | Jumpol Sudjitjul | 11-May-2026 | 07-May-2026 12:56:04 | Sompop Singhatiraj | 13-May-2026 | 13-May-2026 09:28:24 | Pornlert Wanaphattharaphan | 14-May-2026 | 18-May-2026 23:59:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-May-2026 | 19-May-2026 08:24:17 | 19-May-2026 01:44:20 | 0 |  |  | Approver | Locate
AO-001820 | MM-ZTK-1F-ZWP23-STR-DWG-2332 | ZWP23 JACKET - ANODE DISTRIBUTION OF PILE CLUSTER |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 02-Sep-2026 18:21:38 | wisuda.c@jutal.com | 03-Sep-2026 11:10:53 | Jumpol Sudjitjul | 10-Sep-2026 |  | Sompop Singhatiraj | 14-Sep-2026 | 08-Sep-2026 08:08:02 | Pornlert Wanaphattharaphan | 15-Sep-2026 | 12-Sep-2026 16:38:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Sep-2026 | 13-Sep-2026 11:33:39 | 13-Sep-2026 05:38:29 | 0 |  |  | Approver | Locate
AO-002362 | MM-ZTK-1F-ZWP23-STR-DWG-2332 | ZWP23 JACKET - ANODE DISTRIBUTION OF PILE CLUSTER |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 09:34:56 | wisuda.c@jutal.com | 05-Oct-2026 10:01:59 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 06-Oct-2026 11:44:00 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 22:46:03 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 11-Oct-2026 11:15:51 | 11-Oct-2026 04:52:10 | 0 |  |  | Approver | Locate
AO-000822 | MM-ZTK-1F-ZWP23-STR-DWG-2801 | ZWP23 JACKET RISER AND RISER SUPPORT LOCATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 18-Jun-2026 09:16:43 | wisuda.c@jutal.com | 18-Jun-2026 10:02:56 | Jumpol Sudjitjul | 25-Jun-2026 | 18-Jun-2026 15:54:00 | Sompop Singhatiraj | 29-Jun-2026 | 19-Jun-2026 16:52:22 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 20-Jun-2026 17:33:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 21-Jun-2026 21:30:54 | 22-Jun-2026 00:21:53 | 0 |  |  | Approver | Locate
AO-001893 | MM-ZTK-1F-ZWP23-STR-DWG-2801 | ZWP23 JACKET RISER AND RISER SUPPORT LOCATION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:25:05 | wisuda.c@jutal.com | 08-Sep-2026 08:39:20 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 17:58:37 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 14:56:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:48:41 | 20-Sep-2026 13:16:19 | 0 |  |  | Approver | Locate
AO-002362 | MM-ZTK-1F-ZWP23-STR-DWG-2801 | ZWP23 JACKET RISER AND RISER SUPPORT LOCATION |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 05-Oct-2026 09:35:24 | wisuda.c@jutal.com | 05-Oct-2026 10:02:56 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 |  | Pornlert Wanaphattharaphan | 16-Oct-2026 |  |  |  |  | 19-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001915 | MM-ZTK-1F-ZWP23-STR-DWG-2802 | ZWP23 JACKET 18" RISER CLAMP DETAILS - HANGER CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Sep-2026 10:25:37 | wisuda.c@jutal.com | 08-Sep-2026 09:05:37 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 18:03:02 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 14:58:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:49:04 | 20-Sep-2026 12:54:07 | 0 |  |  | Approver | Locate
AO-002433 | MM-ZTK-1F-ZWP23-STR-DWG-2802 | ZWP23 JACKET 18" RISER CLAMP DETAILS - HANGER CLAMP |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 08-Oct-2026 09:27:27 | wisuda.c@jutal.com | 08-Oct-2026 10:35:07 | Jumpol Sudjitjul | 16-Oct-2026 |  | Sompop Singhatiraj | 20-Oct-2026 |  | Pornlert Wanaphattharaphan | 21-Oct-2026 |  |  |  |  | 22-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001915 | MM-ZTK-1F-ZWP23-STR-DWG-2803 | ZWP23 JACKET 18" RISER CLAMP DETAILS - SLIDING CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Review |  | 07-Sep-2026 10:26:08 | wisuda.c@jutal.com | 08-Sep-2026 09:06:06 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 18:02:14 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 14:57:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:42:05 | 20-Sep-2026 12:41:03 | 0 |  |  | Approver | Locate
AO-002434 | MM-ZTK-1F-ZWP23-STR-DWG-2803 | ZWP23 JACKET 18" RISER CLAMP DETAILS - SLIDING CLAMP |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 08-Oct-2026 09:28:13 | wisuda.c@jutal.com | 08-Oct-2026 10:35:11 | Jumpol Sudjitjul | 16-Oct-2026 |  | Sompop Singhatiraj | 20-Oct-2026 |  | Pornlert Wanaphattharaphan | 21-Oct-2026 |  |  |  |  | 22-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001915 | MM-ZTK-1F-ZWP23-STR-DWG-2804 | ZWP23 JACKET 18" RISER CLAMP DETAILS - SLIDING CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 07-Sep-2026 10:26:36 | wisuda.c@jutal.com | 08-Sep-2026 09:06:28 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 18:02:06 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 14:56:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:49:35 | 20-Sep-2026 12:56:25 | 0 |  |  | Approver | Locate
AO-002359 | MM-ZTK-1F-ZWP23-STR-DWG-2804 | ZWP23 JACKET 18" RISER CLAMP DETAILS - SLIDING CLAMP |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 05-Oct-2026 10:14:36 | wisuda.c@jutal.com | 05-Oct-2026 10:25:18 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 |  | Pornlert Wanaphattharaphan | 16-Oct-2026 |  |  |  |  | 19-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001915 | MM-ZTK-1F-ZWP23-STR-DWG-2805 | ZWP23 JACKET 18" RISER CLAMP DETAILS - TEMPORARY CLAMP |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Review |  | 07-Sep-2026 10:27:07 | wisuda.c@jutal.com | 08-Sep-2026 09:06:53 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 18:04:54 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 14:59:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:49:14 | 20-Sep-2026 12:55:15 | 0 |  |  | Approver | Locate
AO-002437 | MM-ZTK-1F-ZWP23-STR-DWG-2805 | ZWP23 JACKET 18" RISER CLAMP DETAILS - TEMPORARY CLAMP |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 08-Oct-2026 09:28:44 | wisuda.c@jutal.com | 08-Oct-2026 10:35:11 | Jumpol Sudjitjul | 16-Oct-2026 |  | Sompop Singhatiraj | 20-Oct-2026 |  | Pornlert Wanaphattharaphan | 21-Oct-2026 |  |  |  |  | 22-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000740 | MM-ZTK-1F-ZWP23-STR-DWG-2900 | ZWP23 JACKET - CLOSURE PLATE DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 18:16:26 | wisuda.c@jutal.com | 12-Jun-2026 10:14:22 | Jumpol Sudjitjul | 19-Jun-2026 |  | Sompop Singhatiraj | 23-Jun-2026 | 15-Jun-2026 17:02:33 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 18-Jun-2026 20:28:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 19-Jun-2026 08:45:04 | 19-Jun-2026 02:21:20 | 0 |  |  | Approver | Locate
AO-001895 | MM-ZTK-1F-ZWP23-STR-DWG-2900 | ZWP23 JACKET - CLOSURE PLATE DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:27:42 | wisuda.c@jutal.com | 08-Sep-2026 08:39:41 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 15:57:13 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 13:24:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:48:44 | 20-Sep-2026 12:52:58 | 0 |  |  | Approver | Locate
AO-002362 | MM-ZTK-1F-ZWP23-STR-DWG-2900 | ZWP23 JACKET - CLOSURE PLATE DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 09:35:51 | wisuda.c@jutal.com | 05-Oct-2026 10:03:00 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 08-Oct-2026 14:59:39 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 23:01:35 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 11-Oct-2026 11:15:26 | 11-Oct-2026 04:49:57 | 0 |  |  | Approver | Locate
AO-000740 | MM-ZTK-1F-ZWP23-STR-DWG-2901 | ZWP23 JACKET - CLOSURE PLATE DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-Jun-2026 18:16:51 | wisuda.c@jutal.com | 12-Jun-2026 10:14:21 | Jumpol Sudjitjul | 19-Jun-2026 |  | Sompop Singhatiraj | 23-Jun-2026 | 15-Jun-2026 17:02:24 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 18-Jun-2026 20:27:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 19-Jun-2026 08:44:35 | 19-Jun-2026 02:19:59 | 0 |  |  | Approver | Locate
AO-001895 | MM-ZTK-1F-ZWP23-STR-DWG-2901 | ZWP23 JACKET - CLOSURE PLATE DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 07-Sep-2026 10:28:19 | wisuda.c@jutal.com | 08-Sep-2026 08:39:56 | Jumpol Sudjitjul | 15-Sep-2026 |  | Sompop Singhatiraj | 17-Sep-2026 | 17-Sep-2026 15:57:52 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 13:25:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:48:17 | 20-Sep-2026 12:51:45 | 0 |  |  | Approver | Locate
AO-002362 | MM-ZTK-1F-ZWP23-STR-DWG-2901 | ZWP23 JACKET - CLOSURE PLATE DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 09:36:17 | wisuda.c@jutal.com | 05-Oct-2026 10:03:01 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 08-Oct-2026 15:19:35 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 23:53:45 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 11-Oct-2026 11:14:57 | 11-Oct-2026 04:34:37 | 0 |  |  | Approver | Locate
AO-000743 | MM-ZTK-1F-ZWP23-STR-DWG-2902 | ZWP23 JACKET - LEG PARTITION DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 12-Jun-2026 08:40:18 | wisuda.c@jutal.com | 12-Jun-2026 10:14:22 | Jumpol Sudjitjul | 19-Jun-2026 |  | Sompop Singhatiraj | 23-Jun-2026 | 15-Jun-2026 17:04:29 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 18-Jun-2026 20:29:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 19-Jun-2026 08:44:08 | 19-Jun-2026 02:27:23 | 0 |  |  | Approver | Locate
AO-001774 | MM-ZTK-1F-ZWP23-STR-DWG-2902 | ZWP23 JACKET - LEG PARTITION DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:33:33 | wisuda.c@jutal.com | 31-Aug-2026 11:08:05 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 03-Sep-2026 09:23:11 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 04-Sep-2026 23:49:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 05-Sep-2026 18:10:52 | 05-Sep-2026 12:09:06 | 0 |  |  | Approver | Locate
AO-002362 | MM-ZTK-1F-ZWP23-STR-DWG-2902 | ZWP23 JACKET - LEG PARTITION DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 09:36:45 | wisuda.c@jutal.com | 05-Oct-2026 10:02:58 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 08-Oct-2026 15:24:57 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 23:56:38 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 11-Oct-2026 11:14:29 | 11-Oct-2026 04:33:30 | 0 |  |  | Approver | Locate
AO-002301 | MM-ZTK-1F-ZWP23-STR-DWG-2911 | ZWP23 JACKET - UPENDING ARRANGEMENT AND DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-Sep-2026 18:00:51 | wisuda.c@jutal.com | 29-Sep-2026 14:27:25 | Jumpol Sudjitjul | 06-Oct-2026 |  | Sompop Singhatiraj | 08-Oct-2026 | 06-Oct-2026 09:31:25 | Pornlert Wanaphattharaphan | 09-Oct-2026 | 06-Oct-2026 23:40:31 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 12-Oct-2026 | 07-Oct-2026 08:35:02 | 07-Oct-2026 01:58:11 | 0 |  |  | Approver | Locate
AO-000308 | MM-ZTK-1F-ZWP23-STR-DWG-2931 | ZWP23 JACKET - BALLAST / DEBASSAST SCHEMATIC |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 05-May-2026 19:08:50 | wisuda.c@jutal.com | 06-May-2026 10:11:05 | Jumpol Sudjitjul | 13-May-2026 |  | Sompop Singhatiraj | 15-May-2026 | 16-May-2026 11:51:18 | Pornlert Wanaphattharaphan | 18-May-2026 | 18-May-2026 23:31:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 19-May-2026 08:11:07 | 19-May-2026 01:39:58 | 0 |  |  | Approver | Locate
AO-001660 | MM-ZTK-1F-ZWP23-STR-DWG-2931 | ZWP23 JACKET - BALLAST / DEBASSAST SCHEMATIC |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:53:55 | wisuda.c@jutal.com | 24-Aug-2026 20:32:53 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 03-Sep-2026 12:42:46 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:59:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:10:26 | 09-Sep-2026 06:58:27 | 0 |  |  | Approver | Locate
AO-000308 | MM-ZTK-1F-ZWP23-STR-DWG-2932 | ZWP23 JACKET - GROUTING SCHEMATIC |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 05-May-2026 19:09:14 | wisuda.c@jutal.com | 06-May-2026 10:10:48 | Jumpol Sudjitjul | 13-May-2026 |  | Sompop Singhatiraj | 15-May-2026 | 16-May-2026 11:48:48 | Pornlert Wanaphattharaphan | 18-May-2026 | 18-May-2026 23:34:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-May-2026 | 19-May-2026 08:19:47 | 19-May-2026 01:41:16 | 0 |  |  | Approver | Locate
AO-001660 | MM-ZTK-1F-ZWP23-STR-DWG-2932 | ZWP23 JACKET - GROUTING SCHEMATIC |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 10:52:46 | wisuda.c@jutal.com | 24-Aug-2026 20:32:54 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 03-Sep-2026 11:34:32 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:59:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:10:53 | 08-Sep-2026 04:31:19 | 0 |  |  | Approver | Locate
AO-001221 | MM-ZTK-1F-ZWP23-STR-DWG-2933 | ZWP23 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT ROW A ELEVATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Jul-2026 16:49:19 | wisuda.c@jutal.com | 22-Jul-2026 08:35:26 | Jumpol Sudjitjul | 31-Jul-2026 |  | Sompop Singhatiraj | 04-Aug-2026 | 24-Jul-2026 11:33:11 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 24-Jul-2026 22:57:13 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 06-Aug-2026 | 27-Jul-2026 15:28:13 | 27-Jul-2026 10:09:46 | 0 |  |  | Approver | Locate
AO-001774 | MM-ZTK-1F-ZWP23-STR-DWG-2933 | ZWP23 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT ROW A ELEVATION |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 31-Aug-2026 09:34:02 | wisuda.c@jutal.com | 31-Aug-2026 11:08:09 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 03-Sep-2026 13:57:44 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 04-Sep-2026 23:30:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 05-Sep-2026 18:11:18 | 05-Sep-2026 12:10:29 | 0 |  |  | Approver | Locate
AO-001221 | MM-ZTK-1F-ZWP23-STR-DWG-2934 | ZWP23 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT ROW B ELEVATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Jul-2026 16:49:50 | wisuda.c@jutal.com | 22-Jul-2026 08:35:28 | Jumpol Sudjitjul | 31-Jul-2026 |  | Sompop Singhatiraj | 04-Aug-2026 | 24-Jul-2026 11:34:29 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 24-Jul-2026 22:57:51 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 06-Aug-2026 | 27-Jul-2026 15:28:39 | 27-Jul-2026 10:12:17 | 0 |  |  | Approver | Locate
AO-001774 | MM-ZTK-1F-ZWP23-STR-DWG-2934 | ZWP23 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT ROW B ELEVATION |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 31-Aug-2026 09:34:28 | wisuda.c@jutal.com | 31-Aug-2026 11:08:06 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 03-Sep-2026 13:57:56 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 04-Sep-2026 23:29:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 05-Sep-2026 18:10:56 | 05-Sep-2026 12:07:39 | 0 |  |  | Approver | Locate
AO-001221 | MM-ZTK-1F-ZWP23-STR-DWG-2935 | ZWP23 JACKET - BALLAST AND GROUTING SYSTEM SUPPORT DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Jul-2026 16:50:17 | wisuda.c@jutal.com | 22-Jul-2026 08:35:26 | Jumpol Sudjitjul | 31-Jul-2026 |  | Sompop Singhatiraj | 04-Aug-2026 | 24-Jul-2026 11:35:25 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 24-Jul-2026 22:58:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 27-Jul-2026 15:29:08 | 27-Jul-2026 10:13:31 | 0 |  |  | Approver | Locate
AO-001221 | MM-ZTK-1F-ZWP23-STR-DWG-2936 | ZWP23 JACKET - BALLAST AND GROUTING SYSTEM SUPPORT DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Jul-2026 16:50:49 | wisuda.c@jutal.com | 22-Jul-2026 08:35:28 | Jumpol Sudjitjul | 31-Jul-2026 |  | Sompop Singhatiraj | 04-Aug-2026 | 24-Jul-2026 11:36:17 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 24-Jul-2026 22:59:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 27-Jul-2026 15:29:31 | 27-Jul-2026 10:16:07 | 0 |  |  | Approver | Locate
AO-001221 | MM-ZTK-1F-ZWP23-STR-DWG-2937 | ZWP23 JACKET - BALLAST SYSTEM VALVE DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Jul-2026 16:51:17 | wisuda.c@jutal.com | 22-Jul-2026 08:35:25 | Jumpol Sudjitjul | 31-Jul-2026 |  | Sompop Singhatiraj | 04-Aug-2026 | 24-Jul-2026 11:36:27 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 24-Jul-2026 23:00:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 27-Jul-2026 15:30:07 | 27-Jul-2026 10:18:40 | 0 |  |  | Approver | Locate
AO-001221 | MM-ZTK-1F-ZWP23-STR-DWG-2938 | ZWP23 JACKET -GROUT, SKIRT SLEEVE VENT AND FLOODING DETAILS AT SKIRT PILE SLEEVE SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Jul-2026 16:51:53 | wisuda.c@jutal.com | 22-Jul-2026 08:35:30 | Jumpol Sudjitjul | 31-Jul-2026 |  | Sompop Singhatiraj | 04-Aug-2026 | 24-Jul-2026 11:38:15 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 24-Jul-2026 23:02:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 27-Jul-2026 15:30:27 | 27-Jul-2026 10:21:09 | 0 |  |  | Approver | Locate
AO-001221 | MM-ZTK-1F-ZWP23-STR-DWG-2939 | ZWP23 JACKET -GROUT, SKIRT SLEEVE VENT AND FLOODING DETAILS AT SKIRT PILE SLEEVE SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Jul-2026 16:52:23 | wisuda.c@jutal.com | 22-Jul-2026 08:35:29 | Jumpol Sudjitjul | 31-Jul-2026 |  | Sompop Singhatiraj | 04-Aug-2026 | 24-Jul-2026 11:38:24 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 24-Jul-2026 23:17:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 27-Jul-2026 15:29:38 | 27-Jul-2026 10:17:24 | 0 |  |  | Approver | Locate
AO-001221 | MM-ZTK-1F-ZWP23-STR-DWG-2940 | ZWP23 JACKET - BALLAST SYSTEM AND GROUTING LINE ROUTING AT EL(+) 8000 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Jul-2026 16:52:50 | wisuda.c@jutal.com | 22-Jul-2026 08:35:26 | Jumpol Sudjitjul | 31-Jul-2026 |  | Sompop Singhatiraj | 04-Aug-2026 | 24-Jul-2026 11:38:33 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 24-Jul-2026 23:16:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 27-Jul-2026 15:29:10 | 27-Jul-2026 10:14:47 | 0 |  |  | Approver | Locate
AO-001221 | MM-ZTK-1F-ZWP23-STR-DWG-2941 | ZWP23 JACKET - GROUT SYSTEM DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Jul-2026 16:53:19 | wisuda.c@jutal.com | 22-Jul-2026 08:35:26 | Jumpol Sudjitjul | 31-Jul-2026 |  | Sompop Singhatiraj | 04-Aug-2026 | 24-Jul-2026 11:39:42 | Pornlert Wanaphattharaphan | 05-Aug-2026 | 24-Jul-2026 23:14:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Aug-2026 | 27-Jul-2026 15:28:43 | 27-Jul-2026 10:11:04 | 0 |  |  | Approver | Locate
AO-001519 | MM-ZTK-1F-ZWP23-STR-DWG-2971 | ZWP23 JACKET - WELD PROFILE CONTROL SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 13-Aug-2026 17:02:23 | wisuda.c@jutal.com | 13-Aug-2026 17:11:56 | Jumpol Sudjitjul | 21-Aug-2026 | 14-Aug-2026 16:23:41 | Sompop Singhatiraj | 25-Aug-2026 | 20-Aug-2026 13:29:44 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 23-Aug-2026 17:30:41 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 18:07:20 | 24-Aug-2026 12:04:05 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP23-STR-DWG-2971 | ZWP23 JACKET - WELD PROFILE CONTROL SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 08:45:50 | wisuda.c@jutal.com | 14-Oct-2026 09:50:44 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 13:32:26 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:25:30 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:30:53 | 16-Oct-2026 09:43:40 | 0 |  |  | Approver | Locate
AO-001519 | MM-ZTK-1F-ZWP23-STR-DWG-2972 | ZWP23 JACKET - WELD PROFILE CONTROL SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 13-Aug-2026 17:02:56 | wisuda.c@jutal.com | 13-Aug-2026 17:11:48 | Jumpol Sudjitjul | 21-Aug-2026 | 14-Aug-2026 16:25:17 | Sompop Singhatiraj | 25-Aug-2026 | 20-Aug-2026 13:30:19 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 23-Aug-2026 17:31:31 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 17:59:23 | 24-Aug-2026 11:47:14 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP23-STR-DWG-2972 | ZWP23 JACKET - WELD PROFILE CONTROL SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 08:46:22 | wisuda.c@jutal.com | 14-Oct-2026 09:50:39 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 13:32:29 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:25:55 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:11:50 | 16-Oct-2026 09:39:08 | 0 |  |  | Approver | Locate
AO-001519 | MM-ZTK-1F-ZWP23-STR-DWG-2973 | ZWP23 JACKET - WELD PROFILE CONTROL SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 13-Aug-2026 17:03:25 | wisuda.c@jutal.com | 13-Aug-2026 17:11:52 | Jumpol Sudjitjul | 21-Aug-2026 | 14-Aug-2026 16:29:33 | Sompop Singhatiraj | 25-Aug-2026 | 20-Aug-2026 13:27:44 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 23-Aug-2026 17:30:13 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 18:06:51 | 24-Aug-2026 12:02:54 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP23-STR-DWG-2973 | ZWP23 JACKET - WELD PROFILE CONTROL SHEET 3 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 08:46:48 | wisuda.c@jutal.com | 14-Oct-2026 09:50:48 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 13:32:32 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:26:21 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:07:53 | 16-Oct-2026 09:37:56 | 0 |  |  | Approver | Locate
AO-001519 | MM-ZTK-1F-ZWP23-STR-DWG-2974 | ZWP23 JACKET - WELD PROFILE CONTROL SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 13-Aug-2026 17:03:53 | wisuda.c@jutal.com | 13-Aug-2026 17:11:49 | Jumpol Sudjitjul | 21-Aug-2026 | 14-Aug-2026 16:26:00 | Sompop Singhatiraj | 25-Aug-2026 | 20-Aug-2026 13:32:08 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 23-Aug-2026 17:32:11 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 18:06:15 | 24-Aug-2026 12:01:42 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP23-STR-DWG-2974 | ZWP23 JACKET - WELD PROFILE CONTROL SHEET 4 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 08:47:18 | wisuda.c@jutal.com | 14-Oct-2026 09:50:47 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 13:33:38 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:27:48 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:29:06 | 16-Oct-2026 09:41:23 | 0 |  |  | Approver | Locate
AO-001519 | MM-ZTK-1F-ZWP23-STR-DWG-2975 | ZWP23 JACKET - WELD PROFILE CONTROL SHEET 5 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 13-Aug-2026 17:04:23 | wisuda.c@jutal.com | 13-Aug-2026 17:11:53 | Jumpol Sudjitjul | 21-Aug-2026 | 14-Aug-2026 16:24:41 | Sompop Singhatiraj | 25-Aug-2026 | 20-Aug-2026 13:03:05 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 23-Aug-2026 17:20:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 18:05:44 | 24-Aug-2026 12:00:25 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP23-STR-DWG-2975 | ZWP23 JACKET - WELD PROFILE CONTROL SHEET 5 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 08:47:47 | wisuda.c@jutal.com | 14-Oct-2026 09:50:45 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 13:33:11 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:27:18 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:31:12 | 16-Oct-2026 09:09:19 | 0 |  |  | Approver | Locate
AO-001519 | MM-ZTK-1F-ZWP23-STR-DWG-2976 | ZWP23 JACKET - WELD PROFILE CONTROL SHEET 6 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 13-Aug-2026 17:04:54 | wisuda.c@jutal.com | 13-Aug-2026 17:11:52 | Jumpol Sudjitjul | 21-Aug-2026 | 14-Aug-2026 16:29:17 | Sompop Singhatiraj | 25-Aug-2026 | 20-Aug-2026 13:32:15 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 23-Aug-2026 17:31:50 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 18:05:02 | 24-Aug-2026 11:59:17 | 0 |  |  | Approver | Locate
AO-002503 | MM-ZTK-1F-ZWP23-STR-DWG-2976 | ZWP23 JACKET - WELD PROFILE CONTROL SHEET 6 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Oct-2026 08:48:15 | wisuda.c@jutal.com | 14-Oct-2026 09:50:45 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sompop Singhatiraj | 26-Oct-2026 | 15-Oct-2026 13:33:02 | Pornlert Wanaphattharaphan | 27-Oct-2026 | 15-Oct-2026 23:26:52 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 16-Oct-2026 15:21:31 | 16-Oct-2026 08:51:45 | 0 |  |  | Approver | Locate
AO-001165 | MM-ZTK-1F-ZWP23-STR-DWG-2984 | ZWP23 JACKET - PULLING LUG DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 10:37:44 | wisuda.c@jutal.com | 20-Jul-2026 15:36:57 | Jumpol Sudjitjul | 27-Jul-2026 |  | Sompop Singhatiraj | 31-Jul-2026 | 24-Jul-2026 11:32:35 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 24-Jul-2026 23:12:13 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 04-Aug-2026 | 27-Jul-2026 15:28:15 | 27-Jul-2026 09:59:05 | 0 |  |  | Approver | Locate
AO-002308 | MM-ZTK-1F-ZWP23-STR-DWG-2984 | ZWP23 JACKET - PULLING LUG DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 30-Sep-2026 09:36:39 | wisuda.c@jutal.com | 30-Sep-2026 16:08:42 | Jumpol Sudjitjul | 07-Oct-2026 |  | Sompop Singhatiraj | 09-Oct-2026 | 01-Oct-2026 18:04:01 | Pornlert Wanaphattharaphan | 12-Oct-2026 | 01-Oct-2026 22:44:40 | APPR | Approved | Jumpol Sudjitjul | 14-Oct-2026 | 02-Oct-2026 13:25:29 | 02-Oct-2026 07:19:53 | 0 |  |  | Approver | Locate
AO-001983 | MM-ZTK-1F-ZWP23-STR-DWG-2991 | ZWP23 JACKET - JACKET TRANSPORTATION ARRANGEMENT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP23 |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 10-Sep-2026 18:07:01 | wisuda.c@jutal.com | 10-Sep-2026 19:47:53 | Jumpol Sudjitjul | 18-Sep-2026 |  | Sompop Singhatiraj | 22-Sep-2026 | 18-Sep-2026 08:35:26 | Pornlert Wanaphattharaphan | 23-Sep-2026 | 19-Sep-2026 15:52:54 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 24-Sep-2026 | 20-Sep-2026 18:47:53 | 20-Sep-2026 12:31:25 | 0 |  |  | Approver | Locate
AO-000296 | MM-ZTK-1F-ZWP23-STR-MR-2001 | MATERIAL REǪUISITION FOR ZWP23 JACKET PRIMARY TUBULAR STEEL |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 04-May-2026 02:03:06 | wisuda.c@jutal.com | 04-May-2026 13:11:55 | Jumpol Sudjitjul | 11-May-2026 | 10-May-2026 08:27:36 | Sompop Singhatiraj | 13-May-2026 | 15-May-2026 16:01:59 | Pornlert Wanaphattharaphan | 14-May-2026 | 15-May-2026 23:33:47 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 15-May-2026 | 17-May-2026 10:04:00 | 17-May-2026 11:02:27 | 0 |  |  | Approver | Locate
AO-000317 | MM-ZTK-1F-ZWP23-STR-MR-2002 | MATERIAL REǪUISITION FOR ZWP23 JACKET PRIMARY STEEL (PLATE) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 06-May-2026 09:06:37 | wisuda.c@jutal.com | 06-May-2026 10:32:43 | Jumpol Sudjitjul | 13-May-2026 | 15-May-2026 07:42:53 | Sompop Singhatiraj | 15-May-2026 | 15-May-2026 16:48:53 | Pornlert Wanaphattharaphan | 18-May-2026 | 15-May-2026 23:25:28 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 19-May-2026 | 17-May-2026 10:05:33 | 17-May-2026 11:02:49 | 0 |  |  | Approver | Locate
AO-001194 | MM-ZTK-1F-ZWP23-STR-MTO-2001 | ZWP23 JACKET PRIMARY STEEL MTO REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 08:47:34 | wisuda.c@jutal.com | 20-Jul-2026 14:37:13 | Jumpol Sudjitjul | 27-Jul-2026 |  | Sompop Singhatiraj | 31-Jul-2026 | 11-Aug-2026 10:04:20 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 12-Aug-2026 00:26:36 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 04-Aug-2026 | 13-Aug-2026 13:06:49 | 13-Aug-2026 07:25:45 | 0 |  |  | Approver | Locate
AO-001192 | MM-ZTK-1F-ZWP23-STR-MTO-2002 | ZWP23 JACKET SECONDARY STEEL MTO REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | MTO | Material Take Off | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 08:48:02 | wisuda.c@jutal.com | 20-Jul-2026 14:38:03 | Jumpol Sudjitjul | 27-Jul-2026 |  | Sompop Singhatiraj | 31-Jul-2026 | 11-Aug-2026 10:06:36 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 12-Aug-2026 00:26:49 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 04-Aug-2026 | 13-Aug-2026 13:06:07 | 13-Aug-2026 07:24:24 | 0 |  |  | Approver | Locate
AO-000977 | MM-ZTK-1F-ZWP23-STR-TBE-1001 | TECHNICAL BID EVALUATION FOR ZWP23 JACKET PRIMARY HIGH-STRENGTH STEEL PLATE |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | TBE | Technical Bid Evaluation | 0 | Submitted | IFP | Issued for Purchase |  | 02-Jul-2026 17:56:00 | wisuda.c@jutal.com | 03-Jul-2026 13:57:15 | Jumpol Sudjitjul | 10-Jul-2026 |  | Sompop Singhatiraj | 14-Jul-2026 | 06-Jul-2026 16:00:50 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 07-Jul-2026 00:46:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 07-Jul-2026 08:21:47 | 07-Jul-2026 02:13:55 | 0 |  |  | Approver | Locate
AO-000136 | MM-ZTK-1F-ZWP23-STR-WCR-2001 | ZWP23 JACKET WEIGHT CONTROL REPORT |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | WCR | Weight Control Report | 0 | Submitted | IFR | Issued for Review |  | 14-Apr-2026 09:28:17 | zm169dc@jutal.com | 16-Apr-2026 12:48:03 | Jumpol Sudjitjul | 23-Apr-2026 |  | Sompop Singhatiraj | 27-Apr-2026 | 20-Apr-2026 16:31:47 | Pornlert Wanaphattharaphan | 28-Apr-2026 | 24-Apr-2026 00:10:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-Apr-2026 | 24-Apr-2026 09:39:31 | 24-Apr-2026 06:26:18 | 0 |  |  | Approver | Locate
AO-001090 | MM-ZTK-1F-ZWP23-STR-WCR-2001 | ZWP23 JACKET WEIGHT CONTROL REPORT |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | WCR | Weight Control Report | 0 | Submitted | IFA | Issued for Approval |  | 13-Jul-2026 08:31:32 | wisuda.c@jutal.com | 13-Jul-2026 09:09:30 | Jumpol Sudjitjul | 20-Jul-2026 |  | Sompop Singhatiraj | 22-Jul-2026 | 13-Jul-2026 13:49:05 | Pornlert Wanaphattharaphan | 23-Jul-2026 | 14-Jul-2026 23:33:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Jul-2026 | 15-Jul-2026 11:18:55 | 15-Jul-2026 05:17:35 | 0 |  |  | Approver | Locate
AO-001966 | MM-ZTK-1F-ZWP23-STR-WCR-2001 | ZWP23 JACKET WEIGHT CONTROL REPORT |  | C1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP23 |  |  | STR | Structural | WCR | Weight Control Report | 0 | Submitted | AFC | Approved for Construction |  | 10-Sep-2026 10:40:35 | wisuda.c@jutal.com | 10-Sep-2026 12:00:07 | Jumpol Sudjitjul | 17-Sep-2026 |  | Sompop Singhatiraj | 21-Sep-2026 | 21-Sep-2026 09:53:06 | Pornlert Wanaphattharaphan | 22-Sep-2026 | 22-Sep-2026 19:41:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Sep-2026 | 23-Sep-2026 13:31:30 | 23-Sep-2026 07:30:02 | 0 |  |  | Approver | Locate
AO-001904 | MM-ZTK-1F-ZWP8-INS-DTS-0001 | DATASHEET FOR ACTUATED ON-OFF VALVES (ZWP8) |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP08 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFR | Issued for Review |  | 07-Sep-2026 09:33:08 | wisuda.c@jutal.com | 08-Sep-2026 09:25:55 | Jumpol Sudjitjul | 15-Sep-2026 |  | Wichai Salee | 17-Sep-2026 | 14-Sep-2026 16:41:58 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 00:22:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:47:31 | 20-Sep-2026 12:30:07 | 0 |  |  | Approver | Locate
AO-002342 | MM-ZTK-1F-ZWP8-INS-DTS-0001 | DATASHEET FOR ACTUATED ON-OFF VALVES (ZWP8) |  | B1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP08 |  |  | INS | Instrumentation and Control | DTS | Data Sheet | 0 | Submitted | IFA | Issued for Approval |  | 02-Oct-2026 17:56:49 | wisuda.c@jutal.com | 02-Oct-2026 18:05:28 | Jumpol Sudjitjul | 12-Oct-2026 |  | Wichai Salee | 15-Oct-2026 | 14-Oct-2026 15:06:52 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 15-Oct-2026 22:55:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Oct-2026 | 16-Oct-2026 11:43:33 | 16-Oct-2026 04:58:15 | 0 |  |  | Approver | Locate
AO-001905 | MM-ZTK-1F-ZWP8-INS-MR-0001 | MATERIAL REQUISITION FOR ESDV MODIFICATION |  | A1 | Project Document | Engineering Document | Part B - Engineering Doc | ZWP08 |  |  | INS | Instrumentation and Control | MR | Material Requisition | 0 | Submitted | IFR | Issued for Review |  | 07-Sep-2026 09:33:36 | wisuda.c@jutal.com | 08-Sep-2026 09:23:36 | Jumpol Sudjitjul | 15-Sep-2026 | 09-Sep-2026 11:31:52 | Wichai Salee | 17-Sep-2026 | 15-Sep-2026 16:26:55 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 00:23:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:47:01 | 20-Sep-2026 12:28:55 | 0 |  |  | Approver | Locate
AO-000353 | MM-ZTK-1F-ZWPX-ELE-BLD-0001 | ELECTRICAL POWER & CONTROL SYSTEM BLOCK DIAGRAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | BLD | Block Diagram | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:12:26 | wisuda.c@jutal.com | 11-May-2026 11:32:42 | Jumpol Sudjitjul | 18-May-2026 |  | Wichai Salee | 20-May-2026 | 08-Jun-2026 16:20:27 | Pornlert Wanaphattharaphan | 21-May-2026 | 09-Jun-2026 00:50:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 09-Jun-2026 07:52:47 | 09-Jun-2026 01:11:13 | 0 |  |  | Approver | Locate
AO-001447 | MM-ZTK-1F-ZWPX-ELE-BLD-0001 | ELECTRICAL POWER & CONTROL SYSTEM BLOCK DIAGRAM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | BLD | Block Diagram | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 14:09:40 | wisuda.c@jutal.com | 07-Aug-2026 14:31:33 | Jumpol Sudjitjul | 17-Aug-2026 |  | Wichai Salee | 19-Aug-2026 | 17-Aug-2026 16:09:09 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:40:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 08:39:51 | 21-Aug-2026 01:52:17 | 0 |  |  | Approver | Locate
AO-001842 | MM-ZTK-1F-ZWPX-ELE-BLD-0001 | ELECTRICAL POWER & CONTROL SYSTEM BLOCK DIAGRAM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | BLD | Block Diagram | 0 | Submitted | AFC | Approved for Construction |  | 03-Sep-2026 15:18:47 | wisuda.c@jutal.com | 05-Sep-2026 19:35:55 | Jumpol Sudjitjul | 14-Sep-2026 |  | Wichai Salee | 16-Sep-2026 | 12-Sep-2026 20:40:18 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 13-Sep-2026 22:38:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 13-Sep-2026 23:15:04 | 13-Sep-2026 16:44:59 | 0 |  |  | Approver | Locate
AO-000402 | MM-ZTK-1F-ZWPX-ELE-BLD-0002 | ELECTRICAL OVERALL EARTHING AND BONDING BLOCK DIAGRAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | BLD | Block Diagram | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 10:51:14 | wisuda.c@jutal.com | 15-May-2026 18:14:27 | Jumpol Sudjitjul | 25-May-2026 |  | Wichai Salee | 27-May-2026 | 15-Jun-2026 09:37:06 | Pornlert Wanaphattharaphan | 28-May-2026 | 15-Jun-2026 22:50:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 16-Jun-2026 09:37:12 | 16-Jun-2026 03:42:04 | 0 |  |  | Approver | Locate
AO-001461 | MM-ZTK-1F-ZWPX-ELE-BLD-0002 | ELECTRICAL OVERALL EARTHING AND BONDING BLOCK DIAGRAM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | BLD | Block Diagram | 0 | Submitted | IFA | Issued for Approval |  | 07-Aug-2026 17:31:53 | wisuda.c@jutal.com | 07-Aug-2026 17:42:42 | Jumpol Sudjitjul | 18-Aug-2026 |  | Wichai Salee | 20-Aug-2026 | 17-Aug-2026 16:11:08 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:23:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 18:04:19 | 24-Aug-2026 11:57:51 | 0 |  |  | Approver | Locate
AO-001877 | MM-ZTK-1F-ZWPX-ELE-BLD-0002 | ELECTRICAL OVERALL EARTHING AND BONDING BLOCK DIAGRAM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | BLD | Block Diagram | 0 | Submitted | AFC | Approved for Construction |  | 04-Sep-2026 16:15:50 | wisuda.c@jutal.com | 05-Sep-2026 19:36:15 | Jumpol Sudjitjul | 14-Sep-2026 |  | Wichai Salee | 16-Sep-2026 | 12-Sep-2026 20:38:02 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 13-Sep-2026 22:37:23 | APPR | Approved | Jumpol Sudjitjul | 18-Sep-2026 | 13-Sep-2026 23:14:40 | 13-Sep-2026 17:25:22 | 0 |  |  | Approver | Locate
AO-001806 | MM-ZTK-1F-ZWPX-ELE-DWG-0001 | ELECTRICAL DRAWING INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 01-Sep-2026 10:14:43 | wisuda.c@jutal.com | 01-Sep-2026 15:42:01 | Neeranuch Nutong | 08-Sep-2026 |  | Wichai Salee | 10-Sep-2026 | 10-Sep-2026 13:42:34 | Pornlert Wanaphattharaphan | 11-Sep-2026 | 12-Sep-2026 15:30:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Sep-2026 | 13-Sep-2026 11:34:05 | 13-Sep-2026 05:39:45 | 0 |  |  | Approver | Locate
AO-002285 | MM-ZTK-1F-ZWPX-ELE-DWG-0001 | ELECTRICAL DRAWING INDEX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 28-Sep-2026 09:53:26 | wisuda.c@jutal.com | 28-Sep-2026 10:24:43 | Jumpol Sudjitjul | 05-Oct-2026 |  | Wichai Salee | 07-Oct-2026 | 01-Oct-2026 15:36:55 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 01-Oct-2026 23:15:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 02-Oct-2026 13:24:54 | 02-Oct-2026 07:02:58 | 0 |  |  | Approver | Locate
AO-000352 | MM-ZTK-1F-ZWPX-ELE-DWG-0002 | ELECTRICAL LEGENDS AND SYMBOL |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:57:08 | wisuda.c@jutal.com | 11-May-2026 11:37:08 | Jumpol Sudjitjul | 18-May-2026 |  | Wichai Salee | 20-May-2026 | 08-Jun-2026 16:29:26 | Pornlert Wanaphattharaphan | 21-May-2026 | 09-Jun-2026 00:55:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 09-Jun-2026 07:53:09 | 09-Jun-2026 01:31:27 | 0 |  |  | Approver | Locate
AO-002287 | MM-ZTK-1F-ZWPX-ELE-DWG-0002 | ELECTRICAL LEGENDS AND SYMBOL |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 28-Sep-2026 08:37:34 | wisuda.c@jutal.com | 28-Sep-2026 10:24:57 | Jumpol Sudjitjul | 05-Oct-2026 |  | Wichai Salee | 07-Oct-2026 | 01-Oct-2026 15:39:55 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 01-Oct-2026 23:15:21 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 02-Oct-2026 13:24:01 | 02-Oct-2026 07:01:33 | 0 |  |  | Approver | Locate
AO-000750 | MM-ZTK-1F-ZWPX-ELE-LAY-0001 | ELECTRICAL EQUIPMENT LOCATION PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 12-Jun-2026 08:41:13 | wisuda.c@jutal.com | 12-Jun-2026 14:45:23 | Jumpol Sudjitjul | 19-Jun-2026 |  | Wichai Salee | 23-Jun-2026 | 27-Jun-2026 23:17:45 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 28-Jun-2026 10:55:08 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 29-Jun-2026 20:46:45 | 29-Jun-2026 14:13:45 | 0 |  |  | Approver | Locate
AO-000598 | MM-ZTK-1F-ZWPX-ELE-LAY-0002 | E&I ROOM EQUIPMENT LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 25-May-2026 16:44:07 | wisuda.c@jutal.com | 25-May-2026 22:15:49 | Jumpol Sudjitjul | 04-Jun-2026 |  | Wichai Salee | 08-Jun-2026 | 19-Jun-2026 23:05:53 | Pornlert Wanaphattharaphan | 09-Jun-2026 | 19-Jun-2026 23:10:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jun-2026 | 21-Jun-2026 21:30:28 | 12-Jul-2026 10:37:39 | 0 |  |  | Approver | Locate
AO-001887 | MM-ZTK-1F-ZWPX-ELE-LAY-0002 | E&I ROOM EQUIPMENT LAYOUT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 04-Sep-2026 16:16:17 | wisuda.c@jutal.com | 05-Sep-2026 19:34:40 | Jumpol Sudjitjul | 14-Sep-2026 |  | Wichai Salee | 16-Sep-2026 | 12-Sep-2026 20:43:13 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 13-Sep-2026 22:40:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 18-Sep-2026 | 13-Sep-2026 23:14:13 | 13-Sep-2026 17:26:43 | 0 |  |  | Approver | Locate
AO-001172 | MM-ZTK-1F-ZWPX-ELE-LAY-0003 | ELECTRICAL MCT LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 10:39:39 | wisuda.c@jutal.com | 20-Jul-2026 15:44:34 | Jumpol Sudjitjul | 27-Jul-2026 |  | Wichai Salee | 31-Jul-2026 | 06-Aug-2026 23:06:00 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 07-Aug-2026 05:35:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 07-Aug-2026 08:42:03 | 07-Aug-2026 02:02:59 | 0 |  |  | Approver | Locate
AO-001625 | MM-ZTK-1F-ZWPX-ELE-LAY-0003 | ELECTRICAL MCT LAYOUT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 20-Aug-2026 14:24:18 | wisuda.c@jutal.com | 20-Aug-2026 14:45:25 | Jumpol Sudjitjul | 27-Aug-2026 |  | Wichai Salee | 31-Aug-2026 | 26-Aug-2026 14:51:55 | Pornlert Wanaphattharaphan | 01-Sep-2026 | 29-Aug-2026 23:33:05 | APPR | Approved | Jumpol Sudjitjul | 02-Sep-2026 | 30-Aug-2026 16:55:31 | 30-Aug-2026 10:53:55 | 0 |  |  | Approver | Locate
AO-001293 | MM-ZTK-1F-ZWPX-ELE-LAY-0004 | ELECTRICAL EARTHING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Jul-2026 09:38:22 | wisuda.c@jutal.com | 27-Jul-2026 15:55:55 | Jumpol Sudjitjul | 05-Aug-2026 |  | Wichai Salee | 07-Aug-2026 | 08-Aug-2026 18:46:35 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:50:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 13:05:37 | 13-Aug-2026 07:23:01 | 0 |  |  | Approver | Locate
AO-001348 | MM-ZTK-1F-ZWPX-ELE-LAY-0005 | ELECTRICAL CABLE TRAYS/LADDER LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 31-Jul-2026 09:31:59 | wisuda.c@jutal.com | 31-Jul-2026 09:36:50 | Jumpol Sudjitjul | 07-Aug-2026 |  | Wichai Salee | 11-Aug-2026 | 10-Aug-2026 22:13:11 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 16-Aug-2026 10:37:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Aug-2026 | 17-Aug-2026 14:15:09 | 17-Aug-2026 08:23:20 | 0 |  |  | Approver | Locate
AO-001173 | MM-ZTK-1F-ZWPX-ELE-LAY-0006 | ELECTRICAL CABLE ROUTING PLAN LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 10:40:07 | wisuda.c@jutal.com | 20-Jul-2026 15:44:51 | Jumpol Sudjitjul | 27-Jul-2026 |  | Wichai Salee | 31-Jul-2026 | 07-Aug-2026 13:43:34 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 07-Aug-2026 21:46:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 08-Aug-2026 10:30:05 | 08-Aug-2026 04:39:24 | 0 |  |  | Approver | Locate
AO-001177 | MM-ZTK-1F-ZWPX-ELE-LAY-0007 | ELECTRICAL LIGHTING LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 20-Jul-2026 10:40:33 | wisuda.c@jutal.com | 20-Jul-2026 15:45:06 | Jumpol Sudjitjul | 27-Jul-2026 |  | Wichai Salee | 31-Jul-2026 | 07-Aug-2026 13:45:08 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 07-Aug-2026 21:50:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 08-Aug-2026 10:24:41 | 08-Aug-2026 04:36:47 | 0 |  |  | Approver | Locate
AO-001612 | MM-ZTK-1F-ZWPX-ELE-LAY-0007 | ELECTRICAL LIGHTING LAYOUT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 19-Aug-2026 13:52:59 | wisuda.c@jutal.com | 19-Aug-2026 15:19:08 | Jumpol Sudjitjul | 26-Aug-2026 |  | Wichai Salee | 28-Aug-2026 | 26-Aug-2026 14:51:43 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 29-Aug-2026 23:22:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Sep-2026 | 30-Aug-2026 17:10:32 | 30-Aug-2026 11:36:57 | 0 |  |  | Approver | Locate
AO-000353 | MM-ZTK-1F-ZWPX-ELE-SLD-0001 | ELECTRICAL KEY SINGLE LINE DIAGRAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:12:51 | wisuda.c@jutal.com | 11-May-2026 11:33:58 | Jumpol Sudjitjul | 18-May-2026 |  | Wichai Salee | 20-May-2026 | 08-Jun-2026 16:21:30 | Pornlert Wanaphattharaphan | 21-May-2026 | 09-Jun-2026 00:52:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 09-Jun-2026 07:53:32 | 09-Jun-2026 01:12:27 | 0 |  |  | Approver | Locate
AO-001292 | MM-ZTK-1F-ZWPX-ELE-SLD-0001 | ELECTRICAL KEY SINGLE LINE DIAGRAM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:38:52 | wisuda.c@jutal.com | 27-Jul-2026 15:55:13 | Jumpol Sudjitjul | 05-Aug-2026 |  | Wichai Salee | 07-Aug-2026 | 07-Aug-2026 18:06:25 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 00:25:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 14:11:38 | 10-Aug-2026 07:48:47 | 0 |  |  | Approver | Locate
AO-002541 | MM-ZTK-1F-ZWPX-ELE-SLD-0001 | ELECTRICAL KEY SINGLE LINE DIAGRAM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | In Review | AFC | Approved for Construction |  | 16-Oct-2026 10:52:55 | wisuda.c@jutal.com | 16-Oct-2026 16:20:32 | Jumpol Sudjitjul | 26-Oct-2026 |  | Wichai Salee | 28-Oct-2026 |  | Pornlert Wanaphattharaphan | 29-Oct-2026 |  |  |  |  | 30-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000353 | MM-ZTK-1F-ZWPX-ELE-SLD-0002 | ELECTRICAL SINGLE LINE DIAGRAM DC DISTRIBUTION SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:57:36 | wisuda.c@jutal.com | 11-May-2026 11:34:14 | Jumpol Sudjitjul | 18-May-2026 |  | Wichai Salee | 20-May-2026 | 08-Jun-2026 16:22:24 | Pornlert Wanaphattharaphan | 21-May-2026 | 09-Jun-2026 00:53:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 09-Jun-2026 07:53:12 | 09-Jun-2026 01:32:44 | 0 |  |  | Approver | Locate
AO-001292 | MM-ZTK-1F-ZWPX-ELE-SLD-0002 | ELECTRICAL SINGLE LINE DIAGRAM DC DISTRIBUTION SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:39:17 | wisuda.c@jutal.com | 27-Jul-2026 15:55:26 | Jumpol Sudjitjul | 05-Aug-2026 |  | Wichai Salee | 07-Aug-2026 | 07-Aug-2026 18:07:51 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:47:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 13:00:06 | 13-Aug-2026 06:10:38 | 0 |  |  | Approver | Locate
AO-002541 | MM-ZTK-1F-ZWPX-ELE-SLD-0002 | ELECTRICAL SINGLE LINE DIAGRAM DC DISTRIBUTION SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | In Review | AFC | Approved for Construction |  | 16-Oct-2026 10:53:25 | wisuda.c@jutal.com | 16-Oct-2026 16:20:49 | Jumpol Sudjitjul | 26-Oct-2026 |  | Wichai Salee | 28-Oct-2026 |  | Pornlert Wanaphattharaphan | 29-Oct-2026 |  |  |  |  | 30-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000353 | MM-ZTK-1F-ZWPX-ELE-SLD-0003 | ELECTRICAL SINGLE LINE DIAGRAM AC DISTRIBUTION SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 08:58:02 | wisuda.c@jutal.com | 11-May-2026 11:34:32 | Jumpol Sudjitjul | 18-May-2026 |  | Wichai Salee | 20-May-2026 | 08-Jun-2026 16:23:11 | Pornlert Wanaphattharaphan | 21-May-2026 | 09-Jun-2026 00:54:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 09-Jun-2026 07:52:52 | 09-Jun-2026 01:30:12 | 0 |  |  | Approver | Locate
AO-001292 | MM-ZTK-1F-ZWPX-ELE-SLD-0003 | ELECTRICAL SINGLE LINE DIAGRAM AC DISTRIBUTION SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:39:42 | wisuda.c@jutal.com | 27-Jul-2026 15:55:41 | Jumpol Sudjitjul | 05-Aug-2026 |  | Wichai Salee | 07-Aug-2026 | 07-Aug-2026 18:08:23 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:47:42 | APPR | Approved | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 12:57:51 | 13-Aug-2026 06:09:15 | 0 |  |  | Approver | Locate
AO-002541 | MM-ZTK-1F-ZWPX-ELE-SLD-0003 | ELECTRICAL SINGLE LINE DIAGRAM AC DISTRIBUTION SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | SLD | Single Line Diagram | 0 | In Review | AFC | Approved for Construction |  | 16-Oct-2026 10:13:18 | wisuda.c@jutal.com | 16-Oct-2026 16:21:04 | Jumpol Sudjitjul | 26-Oct-2026 |  | Wichai Salee | 28-Oct-2026 |  | Pornlert Wanaphattharaphan | 29-Oct-2026 |  |  |  |  | 30-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001101 | MM-ZTK-1F-ZWPX-ELE-STD-0001 | ELECTRICAL TYPICAL INSTALLATION DETAILS POWER |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | STD | Standard | 0 | Submitted | IFR | Issued for Review |  | 14-Jul-2026 11:38:12 | wisuda.c@jutal.com | 14-Jul-2026 14:03:55 | Jumpol Sudjitjul | 21-Jul-2026 |  | Wichai Salee | 23-Jul-2026 | 24-Jul-2026 18:03:21 | Pornlert Wanaphattharaphan | 24-Jul-2026 | 26-Jul-2026 07:42:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Jul-2026 | 27-Jul-2026 15:30:24 | 27-Jul-2026 10:19:54 | 0 |  |  | Approver | Locate
AO-000974 | MM-ZTK-1F-ZWPX-ELE-STD-0002 | ELECTRICAL TYPICAL INSTALLATION DETAILS LIGHTING & SMALL POWER |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | STD | Standard | 0 | Submitted | IFR | Issued for Review |  | 02-Jul-2026 09:56:18 | wisuda.c@jutal.com | 02-Jul-2026 14:03:23 | Jumpol Sudjitjul | 09-Jul-2026 |  | Wichai Salee | 13-Jul-2026 | 15-Jul-2026 13:49:00 | Pornlert Wanaphattharaphan | 14-Jul-2026 | 16-Jul-2026 22:22:35 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jul-2026 | 17-Jul-2026 09:21:24 | 17-Jul-2026 03:38:49 | 0 |  |  | Approver | Locate
AO-001101 | MM-ZTK-1F-ZWPX-ELE-STD-0003 | ELECTRICAL TYPICAL INSTALLATION DETAILS EARTHING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | STD | Standard | 0 | Submitted | IFR | Issued for Review |  | 14-Jul-2026 11:38:50 | wisuda.c@jutal.com | 14-Jul-2026 14:04:22 | Jumpol Sudjitjul | 21-Jul-2026 |  | Wichai Salee | 23-Jul-2026 | 24-Jul-2026 18:19:29 | Pornlert Wanaphattharaphan | 24-Jul-2026 | 26-Jul-2026 07:42:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Jul-2026 | 27-Jul-2026 15:30:48 | 27-Jul-2026 10:22:26 | 0 |  |  | Approver | Locate
AO-000964 | MM-ZTK-1F-ZWPX-ELE-STD-0004 | ELECTRICAL TYPICAL INSTALLATION DETAILS CABLE LADDER/TRAY |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | STD | Standard | 0 | Submitted | IFR | Issued for Review |  | 01-Jul-2026 08:42:11 | wisuda.c@jutal.com | 01-Jul-2026 10:12:54 | Jumpol Sudjitjul | 08-Jul-2026 |  | Wichai Salee | 10-Jul-2026 | 15-Jul-2026 13:46:32 | Pornlert Wanaphattharaphan | 13-Jul-2026 | 16-Jul-2026 22:19:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Jul-2026 | 17-Jul-2026 09:21:02 | 17-Jul-2026 03:16:52 | 0 |  |  | Approver | Locate
AO-000965 | MM-ZTK-1F-ZWPX-ELE-STD-0005 | ELECTRICAL TYPICAL INSTALLATION DETAILS NAVIGATION AID, RED LANTERN, FLASHING BEACON, WARNING SIREN AND FOG HORN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | STD | Standard | 0 | Submitted | IFR | Issued for Review |  | 01-Jul-2026 08:42:47 | wisuda.c@jutal.com | 01-Jul-2026 10:13:12 | Jumpol Sudjitjul | 08-Jul-2026 |  | Wichai Salee | 10-Jul-2026 | 15-Jul-2026 13:47:28 | Pornlert Wanaphattharaphan | 13-Jul-2026 | 16-Jul-2026 22:20:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Jul-2026 | 17-Jul-2026 09:20:42 | 17-Jul-2026 02:23:50 | 0 |  |  | Approver | Locate
AO-001101 | MM-ZTK-1F-ZWPX-ELE-STD-0006 | ELECTRICAL TYPICAL INSTALLATION DETAILS SOLAR PANEL |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | STD | Standard | 0 | Submitted | IFR | Issued for Review |  | 14-Jul-2026 11:39:28 | wisuda.c@jutal.com | 14-Jul-2026 14:04:41 | Jumpol Sudjitjul | 21-Jul-2026 |  | Wichai Salee | 23-Jul-2026 | 24-Jul-2026 18:21:29 | Pornlert Wanaphattharaphan | 24-Jul-2026 | 26-Jul-2026 07:43:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Jul-2026 | 27-Jul-2026 15:31:09 | 27-Jul-2026 10:24:56 | 0 |  |  | Approver | Locate
AO-001655 | MM-ZTK-1F-ZWPX-ELE-WIR-0001 | ELECTRICAL WIRING INTERCONNECTION SOLAR POWER SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Aug-2026 18:43:43 | wisuda.c@jutal.com | 24-Aug-2026 18:39:13 | Jumpol Sudjitjul | 01-Sep-2026 |  | Wichai Salee | 03-Sep-2026 | 31-Aug-2026 15:48:56 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:47:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:11:15 | 07-Sep-2026 12:04:41 | 0 |  |  | Approver | Locate
AO-001655 | MM-ZTK-1F-ZWPX-ELE-WIR-0002 | ELECTRICAL WIRING INTERCONNECTION DC DISTRIBUTION BOARD |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Aug-2026 18:44:09 | wisuda.c@jutal.com | 24-Aug-2026 18:39:28 | Jumpol Sudjitjul | 01-Sep-2026 |  | Wichai Salee | 03-Sep-2026 | 31-Aug-2026 15:50:02 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:48:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:11:37 | 08-Sep-2026 04:50:05 | 0 |  |  | Approver | Locate
AO-001655 | MM-ZTK-1F-ZWPX-ELE-WIR-0003 | ELECTRICAL WIRING INTERCONNECTION NAVIGATION AID SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | ELE | Electrical | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Aug-2026 18:44:40 | wisuda.c@jutal.com | 24-Aug-2026 18:39:43 | Jumpol Sudjitjul | 01-Sep-2026 |  | Wichai Salee | 03-Sep-2026 | 31-Aug-2026 15:51:39 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:48:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:11:55 | 08-Sep-2026 04:51:11 | 0 |  |  | Approver | Locate
AO-000589 | MM-ZTK-1F-ZWPX-INS-BLD-0001 | INSTRUMENT BLOCK DIAGRAM SAFETY AND CONTROL SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | BLD | Block Diagram | 0 | Submitted | IFA | Issued for Review |  | 24-May-2026 15:29:14 | wisuda.c@jutal.com | 24-May-2026 20:48:26 | Jumpol Sudjitjul | 02-Jun-2026 |  | Wichai Salee | 05-Jun-2026 | 19-Jun-2026 23:24:21 | Pornlert Wanaphattharaphan | 08-Jun-2026 | 20-Jun-2026 08:39:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jun-2026 | 21-Jun-2026 21:29:50 | 10-Jul-2026 02:58:47 | 0 |  |  | Approver | Locate
AO-001174 | MM-ZTK-1F-ZWPX-INS-BLD-0001 | INSTRUMENT BLOCK DIAGRAM SAFETY AND CONTROL SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | BLD | Block Diagram | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 10:31:24 | wisuda.c@jutal.com | 20-Jul-2026 14:52:12 | Jumpol Sudjitjul | 27-Jul-2026 |  | Wichai Salee | 31-Jul-2026 | 06-Aug-2026 22:31:52 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 07-Aug-2026 05:34:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 07-Aug-2026 08:40:56 | 07-Aug-2026 02:01:32 | 0 |  |  | Approver | Locate
AO-001793 | MM-ZTK-1F-ZWPX-INS-BLD-0001 | INSTRUMENT BLOCK DIAGRAM SAFETY AND CONTROL SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | BLD | Block Diagram | 0 | Submitted | AFC | Approved for Construction |  | 31-Aug-2026 08:38:32 | wisuda.c@jutal.com | 31-Aug-2026 11:47:32 | Jumpol Sudjitjul | 07-Sep-2026 |  | Wichai Salee | 09-Sep-2026 | 09-Sep-2026 12:31:12 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 23:10:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 13-Sep-2026 11:34:29 | 13-Sep-2026 05:41:07 | 0 |  |  | Approver | Locate
AO-002178 | MM-ZTK-1F-ZWPX-INS-BLD-0001 | INSTRUMENT BLOCK DIAGRAM SAFETY AND CONTROL SYSTEM |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | BLD | Block Diagram | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 11:05:12 | wisuda.c@jutal.com | 21-Sep-2026 14:32:57 | Jumpol Sudjitjul | 28-Sep-2026 |  | Wichai Salee | 30-Sep-2026 | 28-Sep-2026 20:27:38 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 28-Sep-2026 22:52:07 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 29-Sep-2026 10:22:18 | 29-Sep-2026 03:50:37 | 0 |  |  | Approver | Locate
AO-000640 | MM-ZTK-1F-ZWPX-INS-BLD-0002 | INSTRUMENT CABLE BLOCK DIAGRAM PCS/SIS/FGS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | BLD | Block Diagram | 0 | Submitted | IFR | Issued for Review |  | 01-Jun-2026 10:03:11 | wisuda.c@jutal.com | 01-Jun-2026 12:34:39 | Jumpol Sudjitjul | 09-Jun-2026 |  | Wichai Salee | 11-Jun-2026 | 22-Jun-2026 18:25:17 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 22-Jun-2026 23:50:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 23-Jun-2026 09:25:03 | 23-Jun-2026 02:51:43 | 0 |  |  | Approver | Locate
AO-001021 | MM-ZTK-1F-ZWPX-INS-BLD-0002 | INSTRUMENT CABLE BLOCK DIAGRAM PCS/SIS/FGS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | BLD | Block Diagram | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 23:32:34 | wisuda.c@jutal.com | 04-Jul-2026 14:44:48 | Jumpol Sudjitjul | 10-Jul-2026 |  | Wichai Salee | 14-Jul-2026 | 22-Jul-2026 11:32:50 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 22-Jul-2026 22:51:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 23-Jul-2026 08:10:04 | 23-Jul-2026 01:17:36 | 0 |  |  | Approver | Locate
AO-002133 | MM-ZTK-1F-ZWPX-INS-BLD-0002 | INSTRUMENT CABLE BLOCK DIAGRAM PCS/SIS/FGS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | BLD | Block Diagram | 0 | Submitted | AFC | Approved for Construction |  | 17-Sep-2026 16:07:04 | wisuda.c@jutal.com | 17-Sep-2026 16:10:59 | Jumpol Sudjitjul | 24-Sep-2026 |  | Wichai Salee | 28-Sep-2026 | 26-Sep-2026 21:58:42 | Pornlert Wanaphattharaphan | 29-Sep-2026 | 28-Sep-2026 22:05:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 30-Sep-2026 | 29-Sep-2026 09:32:30 | 29-Sep-2026 03:03:11 | 0 |  |  | Approver | Locate
AO-000590 | MM-ZTK-1F-ZWPX-INS-BLD-0003 | OVERALL INSTRUMENT EARTHING DIAGRAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | BLD | Block Diagram | 0 | Submitted | IFR | Issued for Review |  | 24-May-2026 15:29:38 | wisuda.c@jutal.com | 24-May-2026 20:48:39 | Jumpol Sudjitjul | 02-Jun-2026 |  | Wichai Salee | 05-Jun-2026 | 19-Jun-2026 23:25:22 | Pornlert Wanaphattharaphan | 08-Jun-2026 | 22-Jun-2026 11:39:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jun-2026 | 22-Jun-2026 12:58:10 | 22-Jun-2026 06:53:51 | 0 |  |  | Approver | Locate
AO-001679 | MM-ZTK-1F-ZWPX-INS-BLD-0003 | OVERALL INSTRUMENT EARTHING DIAGRAM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | BLD | Block Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 09:42:50 | wisuda.c@jutal.com | 25-Aug-2026 08:55:37 | Jumpol Sudjitjul | 01-Sep-2026 |  | Wichai Salee | 03-Sep-2026 | 02-Sep-2026 10:44:56 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:46:45 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:12:13 | 07-Sep-2026 12:05:52 | 0 |  |  | Approver | Locate
AO-000765 | MM-ZTK-1F-ZWPX-INS-DWG-0001 | INSTRUMENT LEVEL SKETCHES DRAWING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 13-Jun-2026 08:39:53 | wisuda.c@jutal.com | 13-Jun-2026 09:13:34 | Jumpol Sudjitjul | 19-Jun-2026 |  | Wichai Salee | 23-Jun-2026 | 27-Jun-2026 23:19:04 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 28-Jun-2026 12:14:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 29-Jun-2026 20:49:35 | 29-Jun-2026 14:16:25 | 0 |  |  | Approver | Locate
AO-002343 | MM-ZTK-1F-ZWPX-INS-DWG-0001 | INSTRUMENT LEVEL SKETCHES DRAWING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | DWG | General Drawing | 0 | In Review | AFC | Approved for Construction |  | 02-Oct-2026 16:40:44 | wisuda.c@jutal.com | 02-Oct-2026 17:47:49 | Jumpol Sudjitjul | 12-Oct-2026 |  | Wichai Salee | 15-Oct-2026 |  | Pornlert Wanaphattharaphan | 16-Oct-2026 |  |  |  |  | 19-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000855 | MM-ZTK-1F-ZWPX-INS-ESD-0001 | CAUSE AND EFFECT DIAGRAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | ESD | Emergency Logic Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 22:36:12 | wisuda.c@jutal.com | 22-Jun-2026 13:48:46 | Jumpol Sudjitjul | 29-Jun-2026 |  | Wichai Salee | 01-Jul-2026 | 13-Jul-2026 11:59:21 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 13-Jul-2026 22:44:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 14-Jul-2026 08:48:18 | 14-Jul-2026 02:19:40 | 0 |  |  | Approver | Locate
AO-001562 | MM-ZTK-1F-ZWPX-INS-ESD-0001 | CAUSE AND EFFECT DIAGRAM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | ESD | Emergency Logic Diagram | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:18:44 | wisuda.c@jutal.com | 17-Aug-2026 16:01:54 | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 08:43:37 | Wichai Salee | 26-Aug-2026 | 31-Aug-2026 15:10:14 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 02-Sep-2026 23:16:42 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 03-Sep-2026 10:20:12 | 03-Sep-2026 04:02:30 | 0 |  |  | Approver | Locate
AO-002288 | MM-ZTK-1F-ZWPX-INS-ESD-0001 | CAUSE AND EFFECT DIAGRAM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | ESD | Emergency Logic Diagram | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 08:35:23 | wisuda.c@jutal.com | 28-Sep-2026 13:24:02 | Jumpol Sudjitjul | 05-Oct-2026 |  | Wichai Salee | 07-Oct-2026 | 02-Oct-2026 14:22:44 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 10-Oct-2026 01:21:36 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 10-Oct-2026 17:44:37 | 10-Oct-2026 11:18:49 | 0 |  |  | Approver | Locate
AO-000639 | MM-ZTK-1F-ZWPX-INS-LAY-0001 | INSTRUMENT LOCATION PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 01-Jun-2026 10:03:41 | wisuda.c@jutal.com | 01-Jun-2026 12:35:18 | Jumpol Sudjitjul | 09-Jun-2026 |  | Wichai Salee | 11-Jun-2026 | 22-Jun-2026 19:02:54 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 23-Jun-2026 00:37:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 23-Jun-2026 09:18:24 | 23-Jun-2026 02:50:22 | 0 |  |  | Approver | Locate
AO-002243 | MM-ZTK-1F-ZWPX-INS-LAY-0001 | INSTRUMENT LOCATION PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 10:52:21 | wisuda.c@jutal.com | 24-Sep-2026 13:52:13 | Jumpol Sudjitjul | 01-Oct-2026 |  | Wichai Salee | 05-Oct-2026 | 27-Sep-2026 14:19:45 | Pornlert Wanaphattharaphan | 06-Oct-2026 | 28-Sep-2026 22:56:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Oct-2026 | 29-Sep-2026 09:27:23 | 29-Sep-2026 03:00:43 | 0 |  |  | Approver | Locate
AO-000844 | MM-ZTK-1F-ZWPX-INS-LAY-0002 | FUSIBLE PLUG AND F&G EQUIPMENT LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 22:36:42 | wisuda.c@jutal.com | 22-Jun-2026 13:50:02 | Jumpol Sudjitjul | 29-Jun-2026 |  | Wichai Salee | 01-Jul-2026 | 07-Jul-2026 12:00:07 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 08-Jul-2026 00:28:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 08-Jul-2026 09:40:55 | 08-Jul-2026 03:17:01 | 0 |  |  | Approver | Locate
AO-001175 | MM-ZTK-1F-ZWPX-INS-LAY-0002 | FUSIBLE PLUG AND F&G EQUIPMENT LAYOUT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 20-Jul-2026 10:32:07 | wisuda.c@jutal.com | 20-Jul-2026 14:53:09 | Jumpol Sudjitjul | 27-Jul-2026 |  | Wichai Salee | 31-Jul-2026 | 06-Aug-2026 23:04:08 | Pornlert Wanaphattharaphan | 03-Aug-2026 | 07-Aug-2026 05:34:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Aug-2026 | 07-Aug-2026 08:40:30 | 07-Aug-2026 02:00:00 | 0 |  |  | Approver | Locate
AO-002178 | MM-ZTK-1F-ZWPX-INS-LAY-0002 | FUSIBLE PLUG AND F&G EQUIPMENT LAYOUT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 11:05:44 | wisuda.c@jutal.com | 21-Sep-2026 17:43:59 | Jumpol Sudjitjul | 29-Sep-2026 |  | Wichai Salee | 01-Oct-2026 | 28-Sep-2026 20:48:32 | Pornlert Wanaphattharaphan | 02-Oct-2026 | 28-Sep-2026 22:52:59 | APPR | Approved | Jumpol Sudjitjul | 05-Oct-2026 | 29-Sep-2026 09:23:57 | 29-Sep-2026 02:58:27 | 0 |  |  | Approver | Locate
AO-000768 | MM-ZTK-1F-ZWPX-INS-LAY-0003 | INSTRUMENT CABLE ROUTING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 13-Jun-2026 10:03:14 | wisuda.c@jutal.com | 14-Jun-2026 21:52:28 | Jumpol Sudjitjul | 22-Jun-2026 |  | Wichai Salee | 24-Jun-2026 | 03-Jul-2026 15:14:22 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 04-Jul-2026 15:57:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Jun-2026 | 05-Jul-2026 10:40:22 | 05-Jul-2026 04:06:33 | 0 |  |  | Approver | Locate
AO-002325 | MM-ZTK-1F-ZWPX-INS-LAY-0003 | INSTRUMENT CABLE ROUTING PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 01-Oct-2026 15:34:03 | wisuda.c@jutal.com | 01-Oct-2026 16:01:23 | Jumpol Sudjitjul | 08-Oct-2026 |  | Wichai Salee | 12-Oct-2026 | 06-Oct-2026 12:40:27 | Pornlert Wanaphattharaphan | 14-Oct-2026 | 10-Oct-2026 01:49:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Oct-2026 | 10-Oct-2026 17:39:52 | 10-Oct-2026 10:59:16 | 0 |  |  | Approver | Locate
AO-000766 | MM-ZTK-1F-ZWPX-INS-LAY-0004 | INSTRUMENT CABLE TRAY LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 13-Jun-2026 09:15:59 | wisuda.c@jutal.com | 13-Jun-2026 09:39:48 | Jumpol Sudjitjul | 19-Jun-2026 |  | Wichai Salee | 23-Jun-2026 | 27-Jun-2026 23:21:37 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 28-Jun-2026 12:25:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 29-Jun-2026 20:44:11 | 29-Jun-2026 14:24:09 | 0 |  |  | Approver | Locate
AO-002243 | MM-ZTK-1F-ZWPX-INS-LAY-0004 | INSTRUMENT CABLE TRAY LAYOUT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 10:52:51 | wisuda.c@jutal.com | 24-Sep-2026 13:52:26 | Jumpol Sudjitjul | 01-Oct-2026 |  | Wichai Salee | 05-Oct-2026 | 28-Sep-2026 20:48:49 | Pornlert Wanaphattharaphan | 06-Oct-2026 | 28-Sep-2026 22:58:36 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 29-Sep-2026 09:22:14 | 29-Sep-2026 02:28:32 | 0 |  |  | Approver | Locate
AO-000767 | MM-ZTK-1F-ZWPX-INS-LAY-0005 | INSTRUMENT TUBING TRAY LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 13-Jun-2026 09:16:28 | wisuda.c@jutal.com | 13-Jun-2026 09:40:01 | Jumpol Sudjitjul | 19-Jun-2026 |  | Wichai Salee | 23-Jun-2026 | 27-Jun-2026 23:23:25 | Pornlert Wanaphattharaphan | 24-Jun-2026 | 28-Jun-2026 12:49:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 25-Jun-2026 | 29-Jun-2026 20:42:02 | 29-Jun-2026 14:21:05 | 0 |  |  | Approver | Locate
AO-002243 | MM-ZTK-1F-ZWPX-INS-LAY-0005 | INSTRUMENT TUBING TRAY LAYOUT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 24-Sep-2026 10:53:32 | wisuda.c@jutal.com | 24-Sep-2026 13:52:42 | Jumpol Sudjitjul | 01-Oct-2026 |  | Wichai Salee | 05-Oct-2026 | 30-Sep-2026 08:20:57 | Pornlert Wanaphattharaphan | 06-Oct-2026 | 01-Oct-2026 21:34:51 | APPR | Approved | Jumpol Sudjitjul | 07-Oct-2026 | 02-Oct-2026 13:21:47 | 02-Oct-2026 07:00:13 | 0 |  |  | Approver | Locate
AO-000845 | MM-ZTK-1F-ZWPX-INS-LAY-0006 | INSTRUMENT MCT LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 22:37:05 | wisuda.c@jutal.com | 22-Jun-2026 13:51:10 | Jumpol Sudjitjul | 29-Jun-2026 |  | Wichai Salee | 01-Jul-2026 | 03-Jul-2026 15:29:34 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 04-Jul-2026 19:16:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 05-Jul-2026 10:39:40 | 05-Jul-2026 04:05:13 | 0 |  |  | Approver | Locate
AO-002178 | MM-ZTK-1F-ZWPX-INS-LAY-0006 | INSTRUMENT MCT LAYOUT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 09:26:07 | wisuda.c@jutal.com | 21-Sep-2026 10:13:26 | Jumpol Sudjitjul | 28-Sep-2026 |  | Wichai Salee | 30-Sep-2026 | 25-Sep-2026 22:21:28 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 26-Sep-2026 05:32:53 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 26-Sep-2026 16:19:17 | 26-Sep-2026 10:07:59 | 0 |  |  | Approver | Locate
AO-001522 | MM-ZTK-1F-ZWPX-INS-LIS-0020 | INSTRUMENT DRAWING INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 14-Aug-2026 11:31:14 | wisuda.c@jutal.com | 14-Aug-2026 12:44:27 | Jumpol Sudjitjul | 21-Aug-2026 |  | Wichai Salee | 25-Aug-2026 | 28-Aug-2026 16:00:57 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 29-Aug-2026 17:50:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Aug-2026 | 30-Aug-2026 17:11:35 | 30-Aug-2026 11:38:09 | 0 |  |  | Approver | Locate
AO-001483 | MM-ZTK-1F-ZWPX-INS-LPD-0001 | INSTRUMENT LOOP DIAGRAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | LPD | Loop Diagram | 0 | Submitted | IFR | Issued for Review |  | 10-Aug-2026 11:42:59 | wisuda.c@jutal.com | 10-Aug-2026 15:03:08 | Jumpol Sudjitjul | 18-Aug-2026 |  | Wichai Salee | 20-Aug-2026 | 31-Aug-2026 15:09:55 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 01-Sep-2026 23:29:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 02-Sep-2026 15:53:48 | 02-Sep-2026 11:04:02 | 0 |  |  | Approver | Locate
AO-002046 | MM-ZTK-1F-ZWPX-INS-LPD-0001 | INSTRUMENT LOOP DIAGRAM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | LPD | Loop Diagram | 0 | Submitted | IFA | Issued for Approval |  | 14-Sep-2026 09:28:01 | wisuda.c@jutal.com | 15-Sep-2026 15:18:17 | Jumpol Sudjitjul | 22-Sep-2026 |  | Wichai Salee | 24-Sep-2026 | 20-Sep-2026 17:58:14 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 26-Sep-2026 08:18:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 26-Sep-2026 16:19:42 | 28-Sep-2026 10:28:57 | 0 |  |  | Approver | Locate
AO-000734 | MM-ZTK-1F-ZWPX-INS-STD-0001 | INSTRUMENT MOUNTING DETAIL |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | STD | Standard | 0 | Submitted | IFR | Issued for Review |  | 10-Jun-2026 15:11:35 | wisuda.c@jutal.com | 10-Jun-2026 15:41:21 | Jumpol Sudjitjul | 17-Jun-2026 |  | Wichai Salee | 19-Jun-2026 | 24-Jun-2026 11:29:32 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 22:22:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 13:57:42 | 25-Jun-2026 08:12:10 | 0 |  |  | Approver | Locate
AO-002482 | MM-ZTK-1F-ZWPX-INS-STD-0001 | INSTRUMENT MOUNTING DETAIL |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | STD | Standard | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 11:44:09 | wisuda.c@jutal.com | 12-Oct-2026 13:33:36 | Jumpol Sudjitjul | 20-Oct-2026 |  | Wichai Salee | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001295 | MM-ZTK-1F-ZWPX-INS-STD-0002 | INSTRUMENT HOOK-UP DRAWING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | STD | Standard | 0 | Submitted | IFR | Issued for Review |  | 27-Jul-2026 09:19:04 | wisuda.c@jutal.com | 27-Jul-2026 15:59:44 | Jumpol Sudjitjul | 05-Aug-2026 |  | Wichai Salee | 07-Aug-2026 | 08-Aug-2026 18:47:50 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:50:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 13:05:05 | 13-Aug-2026 07:13:36 | 0 |  |  | Approver | Locate
AO-001795 | MM-ZTK-1F-ZWPX-INS-STD-0002 | INSTRUMENT HOOK-UP DRAWING |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | STD | Standard | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 08:39:11 | wisuda.c@jutal.com | 31-Aug-2026 11:47:04 | Jumpol Sudjitjul | 07-Sep-2026 |  | Wichai Salee | 09-Sep-2026 | 09-Sep-2026 12:30:17 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 23:10:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 13-Sep-2026 11:34:51 | 13-Sep-2026 05:42:29 | 0 |  |  | Approver | Locate
AO-002462 | MM-ZTK-1F-ZWPX-INS-STD-0002 | INSTRUMENT HOOK-UP DRAWING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | STD | Standard | 0 | In Review | AFC | Approved for Construction |  | 09-Oct-2026 14:42:13 | wisuda.c@jutal.com | 09-Oct-2026 15:19:33 | Jumpol Sudjitjul | 19-Oct-2026 |  | Wichai Salee | 21-Oct-2026 |  | Pornlert Wanaphattharaphan | 22-Oct-2026 |  |  |  |  | 26-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001345 | MM-ZTK-1F-ZWPX-INS-WIR-0001 | INSTRUMENT WIRING DIAGRAMS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 31-Jul-2026 09:29:03 | wisuda.c@jutal.com | 31-Jul-2026 09:34:48 | Jumpol Sudjitjul | 07-Aug-2026 |  | Wichai Salee | 11-Aug-2026 | 10-Aug-2026 21:46:12 | Pornlert Wanaphattharaphan | 13-Aug-2026 | 16-Aug-2026 10:37:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 14-Aug-2026 | 17-Aug-2026 14:16:10 | 17-Aug-2026 08:24:49 | 0 |  |  | Approver | Locate
AO-001794 | MM-ZTK-1F-ZWPX-INS-WIR-0001 | INSTRUMENT WIRING DIAGRAMS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 08:39:37 | wisuda.c@jutal.com | 31-Aug-2026 11:47:56 | Jumpol Sudjitjul | 07-Sep-2026 |  | Wichai Salee | 09-Sep-2026 | 09-Sep-2026 12:32:16 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 23:39:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 13-Sep-2026 11:36:52 | 13-Sep-2026 05:43:50 | 0 |  |  | Approver | Locate
AO-002353 | MM-ZTK-1F-ZWPX-INS-WIR-0001 | INSTRUMENT WIRING DIAGRAMS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | INS | Instrumentation and Control | WIR | Wiring Diagram | 0 | In Review | AFC | Approved for Construction |  | 05-Oct-2026 09:13:41 | wisuda.c@jutal.com | 05-Oct-2026 10:43:17 | Jumpol Sudjitjul | 12-Oct-2026 |  | Wichai Salee | 15-Oct-2026 |  | Pornlert Wanaphattharaphan | 16-Oct-2026 |  |  |  |  | 19-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-001878 | MM-ZTK-1F-ZWPX-PIP-ISO-0002 | PIPING ISOMETRIC DRAWINGS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PIP | Piping | ISO | Piping, Pipeline Isometric Drawing | 0 | Submitted | IFR | Issued for Review |  | 04-Sep-2026 16:14:55 | wisuda.c@jutal.com | 05-Sep-2026 19:39:01 | Jumpol Sudjitjul | 14-Sep-2026 |  | Aphisit Pinkaew | 16-Sep-2026 | 10-Sep-2026 09:49:40 | Pornlert Wanaphattharaphan | 17-Sep-2026 | 13-Sep-2026 17:12:44 | APPR | Approved | Jumpol Sudjitjul | 18-Sep-2026 | 13-Sep-2026 23:13:29 | 13-Sep-2026 17:21:46 | 0 |  |  | Approver | Locate
AO-000458 | MM-ZTK-1F-ZWPX-PIP-LAY-0001 | EQUIPMENT LAYOUT DRAWING INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 14:11:58 | wisuda.c@jutal.com | 18-May-2026 10:01:54 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 22:05:42 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 22:41:40 | APPR | Approved | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:41:52 | 07-Jun-2026 12:19:04 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWPX-PIP-LAY-0001 | EQUIPMENT LAYOUT DRAWING INDEX |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:43:14 | wisuda.c@jutal.com | 15-Sep-2026 11:44:13 | Jumpol Sudjitjul | 22-Sep-2026 | 22-Sep-2026 23:37:58 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 11:37:52 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 20:55:14 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 10:27:19 | 08-Oct-2026 04:46:06 | 0 |  |  | Approver | Locate
AO-000459 | MM-ZTK-1F-ZWPX-PIP-LAY-0002 | EQUIPMENT LAYOUT UPPER DECK PLAN T.O.S. EL(+) 24.500 M |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 14:12:24 | wisuda.c@jutal.com | 18-May-2026 10:03:04 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 22:07:17 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 22:51:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:42:43 | 07-Jun-2026 12:21:38 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWPX-PIP-LAY-0002 | EQUIPMENT LAYOUT UPPER DECK PLAN T.O.S. EL(+) 24.500 M |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:43:59 | wisuda.c@jutal.com | 15-Sep-2026 11:45:14 | Jumpol Sudjitjul | 22-Sep-2026 | 22-Sep-2026 23:37:16 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 21:00:16 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 22:59:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 10:27:58 | 08-Oct-2026 04:49:55 | 0 |  |  | Approver | Locate
AO-000460 | MM-ZTK-1F-ZWPX-PIP-LAY-0003 | EQUIPMENT LAYOUT MEZZANINE DECK PLAN T.O.S. EL.(+) 21.100 M. AND 21.300 M. |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 14:12:49 | wisuda.c@jutal.com | 18-May-2026 10:03:39 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 22:08:49 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 22:54:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:42:18 | 07-Jun-2026 12:20:25 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWPX-PIP-LAY-0003 | EQUIPMENT LAYOUT MEZZANINE DECK PLAN T.O.S. EL.(+) 21.100 M. AND 21.300 M. |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:44:36 | wisuda.c@jutal.com | 15-Sep-2026 11:45:55 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:35:41 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 21:09:50 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 23:00:07 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 10:28:35 | 08-Oct-2026 04:51:04 | 0 |  |  | Approver | Locate
AO-000461 | MM-ZTK-1F-ZWPX-PIP-LAY-0004 | EQUIPMENT LAYOUT LOWER DECK PLAN T.O.S. EL.(+) 18.300 M. |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 14:13:14 | wisuda.c@jutal.com | 18-May-2026 08:50:13 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 22:10:32 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 22:55:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:43:15 | 07-Jun-2026 12:22:52 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWPX-PIP-LAY-0004 | EQUIPMENT LAYOUT LOWER DECK PLAN T.O.S. EL.(+) 18.300 M. |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:45:07 | wisuda.c@jutal.com | 15-Sep-2026 11:46:13 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:35:35 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 21:13:47 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 23:00:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 10:29:05 | 08-Oct-2026 04:53:36 | 0 |  |  | Approver | Locate
AO-000462 | MM-ZTK-1F-ZWPX-PIP-LAY-0101 | EQUIPMENT LAYOUT FOR COILED TUBING UNIT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 14:13:38 | wisuda.c@jutal.com | 18-May-2026 08:49:54 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 22:12:01 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 22:58:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:43:41 | 07-Jun-2026 12:24:07 | 0 |  |  | Approver | Locate
AO-002059 | MM-ZTK-1F-ZWPX-PIP-LAY-0101-001 | EQUIPMENT LAYOUT FOR COILED TUBING UNIT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:28:27 | wisuda.c@jutal.com | 15-Sep-2026 11:11:22 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:24:58 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 20:28:21 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 22:48:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 10:28:48 | 08-Oct-2026 04:52:16 | 0 |  |  | Approver | Locate
AO-002060 | MM-ZTK-1F-ZWPX-PIP-LAY-0101-002 | EQUIPMENT LAYOUT FOR COILED TUBING UNIT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:28:58 | wisuda.c@jutal.com | 15-Sep-2026 11:11:19 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:25:01 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 20:31:37 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 22:48:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 10:27:52 | 08-Oct-2026 04:48:37 | 0 |  |  | Approver | Locate
AO-000463 | MM-ZTK-1F-ZWPX-PIP-LAY-0102 | EQUIPMENT LAYOUT FOR WELL CLEANUP UNIT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 14:14:02 | wisuda.c@jutal.com | 18-May-2026 08:49:32 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 22:13:50 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 23:00:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:44:03 | 07-Jun-2026 11:57:45 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWPX-PIP-LAY-0102 | EQUIPMENT LAYOUT FOR WELL CLEANUP UNIT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:45:37 | wisuda.c@jutal.com | 15-Sep-2026 11:11:19 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:35:30 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 20:34:54 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 22:49:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 10:26:57 | 08-Oct-2026 04:47:26 | 0 |  |  | Approver | Locate
AO-000465 | MM-ZTK-1F-ZWPX-PIP-LAY-0103-001 | EQUIPMENT LAYOUT FOR HYDRAULIC WORKOVER UNIT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 07:21:55 | wisuda.c@jutal.com | 18-May-2026 08:39:51 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 22:15:22 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 23:01:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:44:29 | 07-Jun-2026 12:02:57 | 0 |  |  | Approver | Locate
AO-002049 | MM-ZTK-1F-ZWPX-PIP-LAY-0103-001 | EQUIPMENT LAYOUT FOR HYDRAULIC WORKOVER UNIT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:29:26 | wisuda.c@jutal.com | 15-Sep-2026 11:11:21 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:22:31 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 20:37:05 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 22:50:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 10:26:20 | 08-Oct-2026 04:45:01 | 0 |  |  | Approver | Locate
AO-000466 | MM-ZTK-1F-ZWPX-PIP-LAY-0103-002 | EQUIPMENT LAYOUT FOR HYDRAULIC WORKOVER UNIT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 16-May-2026 07:22:20 | wisuda.c@jutal.com | 18-May-2026 08:39:27 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 22:17:09 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 23:02:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:44:54 | 07-Jun-2026 12:04:10 | 0 |  |  | Approver | Locate
AO-002050 | MM-ZTK-1F-ZWPX-PIP-LAY-0103-002 | EQUIPMENT LAYOUT FOR HYDRAULIC WORKOVER UNIT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:29:53 | wisuda.c@jutal.com | 15-Sep-2026 11:11:19 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:34:12 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 20:42:34 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 22:53:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 10:24:55 | 08-Oct-2026 04:43:47 | 0 |  |  | Approver | Locate
AO-000456 | MM-ZTK-1F-ZWPX-PIP-LAY-0103-003 | EQUIPMENT LAYOUT FOR HYDRAULIC WORKOVER UNIT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 18:51:28 | wisuda.c@jutal.com | 18-May-2026 08:38:55 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 22:18:49 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 23:03:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:45:16 | 07-Jun-2026 11:43:23 | 0 |  |  | Approver | Locate
AO-002052 | MM-ZTK-1F-ZWPX-PIP-LAY-0103-003 | EQUIPMENT LAYOUT FOR HYDRAULIC WORKOVER UNIT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:30:31 | wisuda.c@jutal.com | 15-Sep-2026 11:11:18 | Jumpol Sudjitjul | 22-Sep-2026 | 15-Sep-2026 22:23:49 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 20:45:44 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 22:55:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 10:23:49 | 08-Oct-2026 04:42:31 | 0 |  |  | Approver | Locate
AO-000455 | MM-ZTK-1F-ZWPX-PIP-LAY-0104 | EQUIPMENT LAYOUT FOR WELL UNLOADING UNIT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-May-2026 18:51:53 | wisuda.c@jutal.com | 18-May-2026 08:37:54 | Jumpol Sudjitjul | 25-May-2026 |  | Aphisit Pinkaew | 27-May-2026 | 02-Jun-2026 22:20:38 | Pornlert Wanaphattharaphan | 28-May-2026 | 05-Jun-2026 23:04:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 07-Jun-2026 17:45:39 | 07-Jun-2026 11:44:39 | 0 |  |  | Approver | Locate
AO-002045 | MM-ZTK-1F-ZWPX-PIP-LAY-0104 | EQUIPMENT LAYOUT FOR WELL UNLOADING UNIT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PIP | Piping | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 09:46:18 | wisuda.c@jutal.com | 15-Sep-2026 11:11:18 | Jumpol Sudjitjul | 22-Sep-2026 | 22-Sep-2026 23:37:44 | Aphisit Pinkaew | 24-Sep-2026 | 07-Oct-2026 20:52:18 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 07-Oct-2026 22:56:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 08-Oct-2026 10:19:10 | 08-Oct-2026 04:41:11 | 0 |  |  | Approver | Locate
AO-000725 | MM-ZTK-1F-ZWPX-PRO-ESD-0002 | ESD LOGIC DIAGRAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | ESD | Emergency Logic Diagram | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 17:23:45 | wisuda.c@jutal.com | 10-Jun-2026 08:38:04 | Jumpol Sudjitjul | 17-Jun-2026 |  | Chananun Rojanarungruengporn | 19-Jun-2026 | 22-Jun-2026 09:31:16 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 24-Jun-2026 22:22:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jun-2026 | 25-Jun-2026 13:58:22 | 25-Jun-2026 08:13:37 | 0 |  |  | Approver | Locate
AO-001441 | MM-ZTK-1F-ZWPX-PRO-ESD-0002 | ESD LOGIC DIAGRAM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | ESD | Emergency Logic Diagram | 0 | Submitted | AFC | Approved for Construction |  | 07-Aug-2026 10:09:40 | wisuda.c@jutal.com | 07-Aug-2026 10:19:14 | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 22:31:53 | Chananun Rojanarungruengporn | 19-Aug-2026 | 18-Aug-2026 09:01:03 | Pornlert Wanaphattharaphan | 20-Aug-2026 | 20-Aug-2026 23:41:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Aug-2026 | 21-Aug-2026 08:38:32 | 21-Aug-2026 01:55:49 | 0 |  |  | Approver | Locate
AO-000069 | MM-ZTK-1F-ZWPX-PRO-HMB-0001 | HEAT AND MATERIAL BALANCE |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | HMB | Heat And Material Balance | 0 | Submitted | IFR | Issued for Review |  | 02-Apr-2026 21:36:19 | zm169dc@jutal.com | 03-Apr-2026 07:01:27 | Jumpol Sudjitjul | 16-Apr-2026 |  | Chananun Rojanarungruengporn | 20-Apr-2026 | 09-Apr-2026 13:17:50 | Pornlert Wanaphattharaphan | 21-Apr-2026 | 20-Apr-2026 01:25:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Apr-2026 | 20-Apr-2026 08:12:27 | 20-Apr-2026 08:34:00 | 0 |  |  | Approver | Locate
AO-000411 | MM-ZTK-1F-ZWPX-PRO-HMB-0001 | HEAT AND MATERIAL BALANCE |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | HMB | Heat And Material Balance | 0 | Submitted | AFC | Approved for Construction | 06-May-2026 | 15-May-2026 15:31:57 | wisuda.c@jutal.com | 15-May-2026 18:11:38 | Jumpol Sudjitjul | 25-May-2026 |  | Chananun Rojanarungruengporn | 27-May-2026 | 26-May-2026 23:00:38 | Pornlert Wanaphattharaphan | 28-May-2026 | 10-Jun-2026 11:11:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-May-2026 | 10-Jun-2026 11:17:40 | 10-Jun-2026 11:31:09 | 0 |  |  | Approver | Locate
AO-000302 | MM-ZTK-1F-ZWPX-PRO-LIS-0001 | PROCESS LINE LIST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 05-May-2026 11:07:01 | wisuda.c@jutal.com | 05-May-2026 11:30:00 | Jumpol Sudjitjul | 12-May-2026 |  | Chananun Rojanarungruengporn | 14-May-2026 | 13-May-2026 13:44:46 | Pornlert Wanaphattharaphan | 15-May-2026 | 22-May-2026 01:31:48 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 18-May-2026 | 22-May-2026 10:09:58 | 22-May-2026 05:45:09 | 0 |  |  | Approver | Locate
AO-001082 | MM-ZTK-1F-ZWPX-PRO-LIS-0001 | PROCESS LINE LIST |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 12-Jul-2026 11:41:51 | wisuda.c@jutal.com | 12-Jul-2026 12:07:43 | Jumpol Sudjitjul | 17-Jul-2026 | 19-Jul-2026 23:58:13 | Chananun Rojanarungruengporn | 21-Jul-2026 | 20-Jul-2026 16:18:36 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 22-Jul-2026 23:05:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 23-Jul-2026 08:09:36 | 23-Jul-2026 01:23:28 | 0 |  |  | Approver | Locate
AO-002215 | MM-ZTK-1F-ZWPX-PRO-LIS-0001 | PROCESS LINE LIST |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | LIS | List, Index, Schedule, Listing | 0 | Submitted | AFC | Approved for Construction |  | 22-Sep-2026 18:02:06 | wisuda.c@jutal.com | 23-Sep-2026 13:52:56 | Jumpol Sudjitjul | 30-Sep-2026 | 01-Oct-2026 14:02:32 | Chananun Rojanarungruengporn | 02-Oct-2026 | 05-Oct-2026 07:50:40 | Pornlert Wanaphattharaphan | 05-Oct-2026 | 10-Oct-2026 00:16:59 | APPR | Approved | Jumpol Sudjitjul | 06-Oct-2026 | 10-Oct-2026 17:48:18 | 10-Oct-2026 11:42:50 | 0 |  |  | Approver | Locate
AO-000063 | MM-ZTK-1F-ZWPX-PRO-PFD-0001 | PROCESS FLOW DIAGRAM HYDROCARBON PRODUCTION SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PFD | Process Flow Diagram | 0 | Submitted | IFR | Issued for Review |  | 02-Apr-2026 21:36:41 | zm169dc@jutal.com | 03-Apr-2026 06:47:36 | Jumpol Sudjitjul | 16-Apr-2026 |  | Chananun Rojanarungruengporn | 20-Apr-2026 | 16-Apr-2026 09:10:52 | Pornlert Wanaphattharaphan | 21-Apr-2026 | 24-Apr-2026 00:04:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Apr-2026 | 24-Apr-2026 14:26:55 | 24-Apr-2026 14:48:48 | 0 |  |  | Approver | Locate
AO-000774 | MM-ZTK-1F-ZWPX-PRO-PFD-0001 | PROCESS FLOW DIAGRAM HYDROCARBON PRODUCTION SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PFD | Process Flow Diagram | 0 | Submitted | IFA | Issued for Approval |  | 14-Jun-2026 22:14:00 | wisuda.c@jutal.com | 15-Jun-2026 09:10:47 | Jumpol Sudjitjul | 22-Jun-2026 |  | Chananun Rojanarungruengporn | 24-Jun-2026 | 24-Jun-2026 13:55:08 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 24-Jun-2026 23:17:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Jun-2026 | 25-Jun-2026 14:01:56 | 25-Jun-2026 07:25:20 | 0 |  |  | Approver | Locate
AO-001521 | MM-ZTK-1F-ZWPX-PRO-PFD-0001 | PROCESS FLOW DIAGRAM HYDROCARBON PRODUCTION SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PFD | Process Flow Diagram | 0 | Submitted | AFC | Approved for Construction |  | 14-Aug-2026 11:59:36 | wisuda.c@jutal.com | 14-Aug-2026 12:43:17 | Jumpol Sudjitjul | 21-Aug-2026 |  | Chananun Rojanarungruengporn | 25-Aug-2026 | 20-Aug-2026 17:30:03 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 22-Aug-2026 13:11:45 | APPR | Approved | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 18:03:38 | 24-Aug-2026 11:37:45 | 0 |  |  | Approver | Locate
AO-000198 | MM-ZTK-1F-ZWPX-PRO-PID-0001 | P&ID PROCESS DRAWING INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:37:20 | wisuda.c@jutal.com | 22-Apr-2026 12:43:21 | Jumpol Sudjitjul | 29-Apr-2026 |  | Chananun Rojanarungruengporn | 05-May-2026 | 05-May-2026 17:09:52 | Pornlert Wanaphattharaphan | 06-May-2026 | 07-May-2026 18:26:11 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 08:26:23 | 08-May-2026 08:40:32 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWPX-PRO-PID-0001 | P&ID PROCESS DRAWING INDEX |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 16:55:53 | wisuda.c@jutal.com | 18-Jun-2026 17:36:11 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 30-Jun-2026 22:23:36 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 02-Jul-2026 23:54:43 | APPR | Approved | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 11:08:29 | 03-Jul-2026 04:18:50 | 0 |  |  | Approver | Locate
AO-001548 | MM-ZTK-1F-ZWPX-PRO-PID-0001 | P&ID PROCESS DRAWING INDEX |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 14:51:55 | wisuda.c@jutal.com | 17-Aug-2026 15:31:18 | Jumpol Sudjitjul | 24-Aug-2026 |  | Chananun Rojanarungruengporn | 26-Aug-2026 | 18-Aug-2026 08:32:08 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 22:58:10 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 18:03:03 | 24-Aug-2026 11:53:57 | 0 |  |  | Approver | Locate
AO-000198 | MM-ZTK-1F-ZWPX-PRO-PID-0002 | P&ID SYMBOLS AND LEGENDS EQUIPMENT SYMBOLS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:37:47 | wisuda.c@jutal.com | 22-Apr-2026 12:43:45 | Jumpol Sudjitjul | 29-Apr-2026 |  | Chananun Rojanarungruengporn | 05-May-2026 | 04-May-2026 15:10:41 | Pornlert Wanaphattharaphan | 06-May-2026 | 07-May-2026 16:16:10 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 07-May-2026 | 07-May-2026 16:17:55 | 07-May-2026 16:49:37 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWPX-PRO-PID-0002 | P&ID SYMBOLS AND LEGENDS EQUIPMENT SYMBOLS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 16:56:27 | wisuda.c@jutal.com | 18-Jun-2026 17:36:40 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 30-Jun-2026 23:43:45 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 02-Jul-2026 23:55:02 | APPR | Approved | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 11:07:39 | 03-Jul-2026 04:55:16 | 0 |  |  | Approver | Locate
AO-001548 | MM-ZTK-1F-ZWPX-PRO-PID-0002 | P&ID SYMBOLS AND LEGENDS EQUIPMENT SYMBOLS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 14:52:28 | wisuda.c@jutal.com | 17-Aug-2026 15:31:19 | Jumpol Sudjitjul | 24-Aug-2026 |  | Chananun Rojanarungruengporn | 26-Aug-2026 | 18-Aug-2026 08:31:13 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 22:57:30 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 18:02:30 | 24-Aug-2026 11:52:48 | 0 |  |  | Approver | Locate
AO-000198 | MM-ZTK-1F-ZWPX-PRO-PID-0003 | P&ID SYMBOLS AND LEGENDS PIPING SYMBOLS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:38:16 | wisuda.c@jutal.com | 22-Apr-2026 12:43:59 | Jumpol Sudjitjul | 29-Apr-2026 |  | Chananun Rojanarungruengporn | 05-May-2026 | 04-May-2026 15:12:20 | Pornlert Wanaphattharaphan | 06-May-2026 | 07-May-2026 16:17:14 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 07-May-2026 | 07-May-2026 16:18:52 | 07-May-2026 16:50:53 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWPX-PRO-PID-0003 | P&ID SYMBOLS AND LEGENDS PIPING SYMBOLS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 16:56:59 | wisuda.c@jutal.com | 18-Jun-2026 17:37:00 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 30-Jun-2026 23:43:57 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 02-Jul-2026 23:55:22 | APPR | Approved | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 11:07:03 | 03-Jul-2026 04:52:43 | 0 |  |  | Approver | Locate
AO-001548 | MM-ZTK-1F-ZWPX-PRO-PID-0003 | P&ID SYMBOLS AND LEGENDS PIPING SYMBOLS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 14:52:56 | wisuda.c@jutal.com | 17-Aug-2026 15:31:20 | Jumpol Sudjitjul | 24-Aug-2026 |  | Chananun Rojanarungruengporn | 26-Aug-2026 | 18-Aug-2026 08:29:37 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 22:56:23 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 18:01:58 | 24-Aug-2026 11:51:39 | 0 |  |  | Approver | Locate
AO-000198 | MM-ZTK-1F-ZWPX-PRO-PID-0004 | P&ID SYMBOLS AND LEGENDS INSTRUMENT SYMBOLS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:38:43 | wisuda.c@jutal.com | 22-Apr-2026 12:50:39 | Jumpol Sudjitjul | 29-Apr-2026 |  | Chananun Rojanarungruengporn | 05-May-2026 | 04-May-2026 15:12:52 | Pornlert Wanaphattharaphan | 06-May-2026 | 07-May-2026 16:25:32 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 07-May-2026 | 07-May-2026 16:27:54 | 07-May-2026 16:53:23 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWPX-PRO-PID-0004 | P&ID SYMBOLS AND LEGENDS INSTRUMENT SYMBOLS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 16:57:26 | wisuda.c@jutal.com | 18-Jun-2026 17:37:20 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 30-Jun-2026 23:44:11 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 02-Jul-2026 23:55:42 | APPR | Approved | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 11:05:41 | 03-Jul-2026 04:51:32 | 0 |  |  | Approver | Locate
AO-001548 | MM-ZTK-1F-ZWPX-PRO-PID-0004 | P&ID SYMBOLS AND LEGENDS INSTRUMENT SYMBOLS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 14:53:28 | wisuda.c@jutal.com | 17-Aug-2026 15:31:19 | Jumpol Sudjitjul | 24-Aug-2026 |  | Chananun Rojanarungruengporn | 26-Aug-2026 | 18-Aug-2026 08:39:26 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 22:59:45 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 18:01:28 | 24-Aug-2026 11:50:33 | 0 |  |  | Approver | Locate
AO-000198 | MM-ZTK-1F-ZWPX-PRO-PID-0005 | P&ID SYMBOLS AND LEGENDS ON/OF VALVE SYMBOLS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:39:11 | wisuda.c@jutal.com | 22-Apr-2026 12:51:05 | Jumpol Sudjitjul | 29-Apr-2026 |  | Chananun Rojanarungruengporn | 05-May-2026 | 05-May-2026 17:13:06 | Pornlert Wanaphattharaphan | 06-May-2026 | 07-May-2026 16:34:22 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 07-May-2026 | 07-May-2026 16:37:16 | 07-May-2026 16:57:53 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWPX-PRO-PID-0005 | P&ID SYMBOLS AND LEGENDS ON/OF VALVE SYMBOLS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 16:58:00 | wisuda.c@jutal.com | 18-Jun-2026 17:37:37 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 30-Jun-2026 23:44:25 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 02-Jul-2026 23:56:04 | APPR | Approved | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 11:00:19 | 03-Jul-2026 04:45:13 | 0 |  |  | Approver | Locate
AO-001548 | MM-ZTK-1F-ZWPX-PRO-PID-0005 | P&ID SYMBOLS AND LEGENDS ON/OF VALVE SYMBOLS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 14:53:59 | wisuda.c@jutal.com | 17-Aug-2026 15:31:20 | Jumpol Sudjitjul | 24-Aug-2026 |  | Chananun Rojanarungruengporn | 26-Aug-2026 | 18-Aug-2026 08:41:06 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:00:16 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 17:54:24 | 24-Aug-2026 11:43:49 | 0 |  |  | Approver | Locate
AO-000198 | MM-ZTK-1F-ZWPX-PRO-PID-0006 | P&ID SYMBOLS AND LEGENDS SAMPLING ARRANGEMENTS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:39:37 | wisuda.c@jutal.com | 22-Apr-2026 12:51:20 | Jumpol Sudjitjul | 29-Apr-2026 |  | Chananun Rojanarungruengporn | 05-May-2026 | 04-May-2026 15:13:13 | Pornlert Wanaphattharaphan | 06-May-2026 | 07-May-2026 16:26:04 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 07-May-2026 | 07-May-2026 16:29:47 | 07-May-2026 16:54:30 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWPX-PRO-PID-0006 | P&ID SYMBOLS AND LEGENDS SAMPLING ARRANGEMENTS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 16:58:40 | wisuda.c@jutal.com | 18-Jun-2026 17:37:46 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 30-Jun-2026 23:44:40 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 02-Jul-2026 23:56:26 | APPR | Approved | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 11:03:18 | 03-Jul-2026 04:50:20 | 0 |  |  | Approver | Locate
AO-001548 | MM-ZTK-1F-ZWPX-PRO-PID-0006 | P&ID SYMBOLS AND LEGENDS SAMPLING ARRANGEMENTS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 14:54:33 | wisuda.c@jutal.com | 17-Aug-2026 15:31:26 | Jumpol Sudjitjul | 24-Aug-2026 |  | Chananun Rojanarungruengporn | 26-Aug-2026 | 18-Aug-2026 09:26:11 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:01:10 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 18:00:50 | 24-Aug-2026 11:49:27 | 0 |  |  | Approver | Locate
AO-000198 | MM-ZTK-1F-ZWPX-PRO-PID-0007 | P&ID SYMBOLS AND LEGENDS INSTRUMENT CONNECTION AND ARRANGEMENTS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:40:02 | wisuda.c@jutal.com | 22-Apr-2026 12:51:34 | Jumpol Sudjitjul | 29-Apr-2026 |  | Chananun Rojanarungruengporn | 05-May-2026 | 04-May-2026 15:13:39 | Pornlert Wanaphattharaphan | 06-May-2026 | 07-May-2026 16:31:28 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 07-May-2026 | 07-May-2026 16:35:30 | 07-May-2026 16:55:40 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWPX-PRO-PID-0007 | P&ID SYMBOLS AND LEGENDS INSTRUMENT CONNECTION AND ARRANGEMENTS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 16:59:10 | wisuda.c@jutal.com | 18-Jun-2026 17:38:02 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 30-Jun-2026 23:46:34 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 02-Jul-2026 23:56:57 | APPR | Approved | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 11:01:51 | 03-Jul-2026 04:49:08 | 0 |  |  | Approver | Locate
AO-001548 | MM-ZTK-1F-ZWPX-PRO-PID-0007 | P&ID SYMBOLS AND LEGENDS INSTRUMENT CONNECTION AND ARRANGEMENTS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 14:55:01 | wisuda.c@jutal.com | 17-Aug-2026 15:31:19 | Jumpol Sudjitjul | 24-Aug-2026 |  | Chananun Rojanarungruengporn | 26-Aug-2026 | 20-Aug-2026 17:29:09 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:24:45 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 18:00:01 | 24-Aug-2026 11:48:21 | 0 |  |  | Approver | Locate
AO-000198 | MM-ZTK-1F-ZWPX-PRO-PID-0008 | P&ID SYMBOLS AND LEGENDS PSVS, CONTROL VALVES AND POSITIVE ISOLATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:40:26 | wisuda.c@jutal.com | 22-Apr-2026 12:58:53 | Jumpol Sudjitjul | 29-Apr-2026 |  | Chananun Rojanarungruengporn | 05-May-2026 | 04-May-2026 15:14:12 | Pornlert Wanaphattharaphan | 06-May-2026 | 07-May-2026 16:33:22 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 07-May-2026 | 07-May-2026 16:36:33 | 07-May-2026 16:56:47 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWPX-PRO-PID-0008 | P&ID SYMBOLS AND LEGENDS PSVS, CONTROL VALVES AND POSITIVE ISOLATION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 16:59:40 | wisuda.c@jutal.com | 18-Jun-2026 17:38:17 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 30-Jun-2026 23:47:31 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 02-Jul-2026 23:57:17 | APPR | Approved | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 11:01:00 | 03-Jul-2026 04:47:58 | 0 |  |  | Approver | Locate
AO-001548 | MM-ZTK-1F-ZWPX-PRO-PID-0008 | P&ID SYMBOLS AND LEGENDS PSVS, CONTROL VALVES AND POSITIVE ISOLATION |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 17-Aug-2026 14:55:30 | wisuda.c@jutal.com | 17-Aug-2026 15:31:24 | Jumpol Sudjitjul | 24-Aug-2026 |  | Chananun Rojanarungruengporn | 26-Aug-2026 | 20-Aug-2026 17:28:43 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:24:02 | APPR | Approved | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 17:59:26 | 24-Aug-2026 11:46:03 | 0 |  |  | Approver | Locate
AO-000198 | MM-ZTK-1F-ZWPX-PRO-PID-0009 | PIPING AND INSTRUMENTATION DIAGRAM TYPICAL WELLHEAD |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Issued for Review |  | 21-Apr-2026 16:41:00 | wisuda.c@jutal.com | 22-Apr-2026 12:59:11 | Jumpol Sudjitjul | 29-Apr-2026 |  | Chananun Rojanarungruengporn | 05-May-2026 | 05-May-2026 17:39:59 | Pornlert Wanaphattharaphan | 06-May-2026 | 07-May-2026 23:20:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 08:27:24 | 08-May-2026 01:41:43 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWPX-PRO-PID-0009 | PIPING AND INSTRUMENTATION DIAGRAM TYPICAL WELLHEAD |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Issued for Approval |  | 18-Jun-2026 17:00:07 | wisuda.c@jutal.com | 18-Jun-2026 17:38:37 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 30-Jun-2026 23:48:57 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 02-Jul-2026 23:57:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 11:00:24 | 03-Jul-2026 04:46:38 | 0 |  |  | Approver | Locate
AO-001668 | MM-ZTK-1F-ZWPX-PRO-PID-0009 | PIPING AND INSTRUMENTATION DIAGRAM TYPICAL WELLHEAD |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 10:06:59 | wisuda.c@jutal.com | 25-Aug-2026 09:45:59 | Jumpol Sudjitjul | 01-Sep-2026 |  | Chananun Rojanarungruengporn | 03-Sep-2026 | 02-Sep-2026 15:40:45 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:50:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:12:37 | 08-Sep-2026 04:40:16 | 0 |  |  | Approver | Locate
AO-002276 | MM-ZTK-1F-ZWPX-PRO-PID-0009 | PIPING AND INSTRUMENTATION DIAGRAM TYPICAL WELLHEAD |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 09:54:50 | wisuda.c@jutal.com | 28-Sep-2026 10:40:14 | Jumpol Sudjitjul | 05-Oct-2026 |  | Chananun Rojanarungruengporn | 07-Oct-2026 | 28-Sep-2026 16:52:16 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 28-Sep-2026 23:02:51 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 29-Sep-2026 09:20:06 | 29-Sep-2026 02:27:18 | 0 |  |  | Approver | Locate
AO-000198 | MM-ZTK-1F-ZWPX-PRO-PID-0010 | P&ID WELLHEAD CONTROL PANEL |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:41:28 | wisuda.c@jutal.com | 22-Apr-2026 12:59:29 | Jumpol Sudjitjul | 29-Apr-2026 |  | Chananun Rojanarungruengporn | 05-May-2026 | 05-May-2026 17:40:48 | Pornlert Wanaphattharaphan | 06-May-2026 | 07-May-2026 22:58:59 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 08:28:48 | 08-May-2026 08:44:23 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWPX-PRO-PID-0010 | P&ID WELLHEAD CONTROL PANEL |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 17:00:33 | wisuda.c@jutal.com | 18-Jun-2026 17:38:57 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 01-Jul-2026 23:01:17 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 03-Jul-2026 00:29:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 10:51:01 | 03-Jul-2026 04:35:33 | 0 |  |  | Approver | Locate
AO-001668 | MM-ZTK-1F-ZWPX-PRO-PID-0010 | P&ID WELLHEAD CONTROL PANEL |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 10:07:37 | wisuda.c@jutal.com | 25-Aug-2026 09:46:04 | Jumpol Sudjitjul | 01-Sep-2026 | 02-Sep-2026 23:45:57 | Chananun Rojanarungruengporn | 03-Sep-2026 | 03-Sep-2026 08:05:34 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:54:48 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:12:09 | 08-Sep-2026 04:41:22 | 0 |  |  | Approver | Locate
AO-000198 | MM-ZTK-1F-ZWPX-PRO-PID-0011 | P&ID PRODUCTION & TEST MANIFOLDS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:41:56 | wisuda.c@jutal.com | 22-Apr-2026 12:59:43 | Jumpol Sudjitjul | 29-Apr-2026 |  | Chananun Rojanarungruengporn | 05-May-2026 | 05-May-2026 13:49:00 | Pornlert Wanaphattharaphan | 06-May-2026 | 07-May-2026 21:24:33 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 08:29:52 | 08-May-2026 08:47:55 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWPX-PRO-PID-0011 | P&ID PRODUCTION & TEST MANIFOLDS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 17:01:06 | wisuda.c@jutal.com | 18-Jun-2026 17:46:52 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 01-Jul-2026 23:05:35 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 02-Jul-2026 23:54:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 10:58:16 | 03-Jul-2026 04:43:54 | 0 |  |  | Approver | Locate
AO-001668 | MM-ZTK-1F-ZWPX-PRO-PID-0011 | P&ID PRODUCTION & TEST MANIFOLDS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 10:08:15 | wisuda.c@jutal.com | 25-Aug-2026 09:45:58 | Jumpol Sudjitjul | 01-Sep-2026 | 02-Sep-2026 23:45:59 | Chananun Rojanarungruengporn | 03-Sep-2026 | 03-Sep-2026 08:05:02 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:54:28 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:11:43 | 08-Sep-2026 04:42:26 | 0 |  |  | Approver | Locate
AO-000198 | MM-ZTK-1F-ZWPX-PRO-PID-0012 | P&ID PIG LAUNCHER AND EXPORT LINE |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:42:26 | wisuda.c@jutal.com | 22-Apr-2026 13:02:04 | Jumpol Sudjitjul | 29-Apr-2026 |  | Chananun Rojanarungruengporn | 05-May-2026 | 05-May-2026 17:17:26 | Pornlert Wanaphattharaphan | 06-May-2026 | 07-May-2026 22:17:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 08:31:48 | 08-May-2026 09:15:04 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWPX-PRO-PID-0012 | P&ID PIG LAUNCHER AND EXPORT LINE |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 17:01:36 | wisuda.c@jutal.com | 18-Jun-2026 17:47:09 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 01-Jul-2026 23:09:10 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 02-Jul-2026 22:23:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 10:50:08 | 03-Jul-2026 04:31:11 | 0 |  |  | Approver | Locate
AO-001668 | MM-ZTK-1F-ZWPX-PRO-PID-0012 | P&ID PIG LAUNCHER AND EXPORT LINE |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 10:08:48 | wisuda.c@jutal.com | 25-Aug-2026 09:46:14 | Jumpol Sudjitjul | 01-Sep-2026 | 02-Sep-2026 23:46:56 | Chananun Rojanarungruengporn | 03-Sep-2026 | 03-Sep-2026 08:04:28 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:54:05 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:11:23 | 08-Sep-2026 04:43:32 | 0 |  |  | Approver | Locate
AO-000198 | MM-ZTK-1F-ZWPX-PRO-PID-0013 | P&ID TEST SEPARATOR |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:42:49 | wisuda.c@jutal.com | 22-Apr-2026 13:02:19 | Jumpol Sudjitjul | 29-Apr-2026 |  | Chananun Rojanarungruengporn | 05-May-2026 | 05-May-2026 13:58:35 | Pornlert Wanaphattharaphan | 06-May-2026 | 07-May-2026 21:45:38 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 08:34:47 | 08-May-2026 02:17:28 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWPX-PRO-PID-0013 | P&ID TEST SEPARATOR |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 17:02:09 | wisuda.c@jutal.com | 18-Jun-2026 17:47:34 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 30-Jun-2026 23:49:59 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 02-Jul-2026 23:58:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 10:51:41 | 03-Jul-2026 04:36:59 | 0 |  |  | Approver | Locate
AO-001668 | MM-ZTK-1F-ZWPX-PRO-PID-0013 | P&ID TEST SEPARATOR |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 10:09:17 | wisuda.c@jutal.com | 25-Aug-2026 09:46:07 | Jumpol Sudjitjul | 01-Sep-2026 | 02-Sep-2026 23:46:19 | Chananun Rojanarungruengporn | 03-Sep-2026 | 03-Sep-2026 08:03:40 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:53:18 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:11:01 | 08-Sep-2026 04:44:38 | 0 |  |  | Approver | Locate
AO-000198 | MM-ZTK-1F-ZWPX-PRO-PID-0014 | P&ID PIG RECEIVER |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:43:13 | wisuda.c@jutal.com | 22-Apr-2026 13:02:34 | Jumpol Sudjitjul | 29-Apr-2026 |  | Chananun Rojanarungruengporn | 05-May-2026 | 05-May-2026 17:22:20 | Pornlert Wanaphattharaphan | 06-May-2026 | 07-May-2026 22:30:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 08:36:07 | 08-May-2026 09:18:41 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWPX-PRO-PID-0014 | P&ID PIG RECEIVER |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 17:02:43 | wisuda.c@jutal.com | 18-Jun-2026 17:47:53 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 01-Jul-2026 00:11:02 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 03-Jul-2026 00:29:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 10:53:05 | 03-Jul-2026 04:39:44 | 0 |  |  | Approver | Locate
AO-001668 | MM-ZTK-1F-ZWPX-PRO-PID-0014 | P&ID PIG RECEIVER |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 10:09:50 | wisuda.c@jutal.com | 25-Aug-2026 09:46:04 | Jumpol Sudjitjul | 01-Sep-2026 | 02-Sep-2026 23:46:36 | Chananun Rojanarungruengporn | 03-Sep-2026 | 03-Sep-2026 08:02:57 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:51:59 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:10:42 | 08-Sep-2026 04:45:43 | 0 |  |  | Approver | Locate
AO-000198 | MM-ZTK-1F-ZWPX-PRO-PID-0015 | P&ID INDEX FOR WELLHEAD AND FLOWLINES |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:43:39 | wisuda.c@jutal.com | 22-Apr-2026 13:01:10 | Jumpol Sudjitjul | 29-Apr-2026 |  | Chananun Rojanarungruengporn | 05-May-2026 | 05-May-2026 17:23:00 | Pornlert Wanaphattharaphan | 06-May-2026 | 07-May-2026 22:30:48 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 08:37:26 | 08-May-2026 09:21:08 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWPX-PRO-PID-0015 | P&ID INDEX FOR WELLHEAD AND FLOWLINES |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 17:03:14 | wisuda.c@jutal.com | 18-Jun-2026 17:41:17 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 30-Jun-2026 23:50:42 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 02-Jul-2026 23:59:20 | APPR | Approved | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 10:49:23 | 03-Jul-2026 04:28:11 | 0 |  |  | Approver | Locate
AO-001668 | MM-ZTK-1F-ZWPX-PRO-PID-0015 | P&ID INDEX FOR WELLHEAD AND FLOWLINES |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 10:10:20 | wisuda.c@jutal.com | 25-Aug-2026 09:46:05 | Jumpol Sudjitjul | 01-Sep-2026 |  | Chananun Rojanarungruengporn | 03-Sep-2026 | 26-Aug-2026 16:53:46 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 31-Aug-2026 00:29:00 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 16:09:47 | 31-Aug-2026 10:06:32 | 0 |  |  | Approver | Locate
AO-002219 | MM-ZTK-1F-ZWPX-PRO-PID-0015 | P&ID INDEX FOR WELLHEAD AND FLOWLINES |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 23-Sep-2026 09:31:57 | wisuda.c@jutal.com | 23-Sep-2026 14:03:42 | Jumpol Sudjitjul | 30-Sep-2026 |  | Chananun Rojanarungruengporn | 02-Oct-2026 | 28-Sep-2026 16:49:50 | Pornlert Wanaphattharaphan | 05-Oct-2026 | 28-Sep-2026 22:53:56 | APPR | Approved | Jumpol Sudjitjul | 06-Oct-2026 | 29-Sep-2026 08:53:26 | 29-Sep-2026 02:24:48 | 0 |  |  | Approver | Locate
AO-000198 | MM-ZTK-1F-ZWPX-PRO-PID-0017 | P&ID INSTRUMENT GAS SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:44:05 | wisuda.c@jutal.com | 22-Apr-2026 13:00:50 | Jumpol Sudjitjul | 29-Apr-2026 |  | Chananun Rojanarungruengporn | 05-May-2026 | 05-May-2026 17:27:14 | Pornlert Wanaphattharaphan | 06-May-2026 | 07-May-2026 22:32:09 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 08:38:51 | 08-May-2026 02:23:27 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWPX-PRO-PID-0017 | P&ID INSTRUMENT GAS SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 17:03:43 | wisuda.c@jutal.com | 18-Jun-2026 17:41:43 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 30-Jun-2026 23:51:23 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 03-Jul-2026 00:00:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 10:55:22 | 03-Jul-2026 04:42:31 | 0 |  |  | Approver | Locate
AO-001724 | MM-ZTK-1F-ZWPX-PRO-PID-0017 | P&ID INSTRUMENT GAS SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 26-Aug-2026 18:39:15 | wisuda.c@jutal.com | 27-Aug-2026 08:53:52 | Jumpol Sudjitjul | 03-Sep-2026 | 03-Sep-2026 23:41:38 | Chananun Rojanarungruengporn | 07-Sep-2026 | 04-Sep-2026 14:03:10 | Pornlert Wanaphattharaphan | 08-Sep-2026 | 07-Sep-2026 01:11:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Sep-2026 | 07-Sep-2026 18:08:52 | 08-Sep-2026 03:40:56 | 0 |  |  | Approver | Locate
AO-000198 | MM-ZTK-1F-ZWPX-PRO-PID-0018 | P&ID CORROSION INHIBITOR INJECTION SYSTEM AND BIOCIDE INJECTION SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:44:30 | wisuda.c@jutal.com | 22-Apr-2026 13:00:33 | Jumpol Sudjitjul | 29-Apr-2026 |  | Chananun Rojanarungruengporn | 05-May-2026 | 05-May-2026 17:27:55 | Pornlert Wanaphattharaphan | 06-May-2026 | 07-May-2026 22:51:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 08:27:47 | 08-May-2026 08:43:02 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWPX-PRO-PID-0018 | P&ID CORROSION INHIBITOR INJECTION SYSTEM AND BIOCIDE INJECTION SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 17:04:11 | wisuda.c@jutal.com | 18-Jun-2026 17:41:58 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 01-Jul-2026 23:11:11 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 02-Jul-2026 22:21:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 10:54:32 | 03-Jul-2026 04:41:09 | 0 |  |  | Approver | Locate
AO-001668 | MM-ZTK-1F-ZWPX-PRO-PID-0018 | P&ID CORROSION INHIBITOR INJECTION SYSTEM AND BIOCIDE INJECTION SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 10:11:19 | wisuda.c@jutal.com | 25-Aug-2026 09:46:16 | Jumpol Sudjitjul | 01-Sep-2026 | 02-Sep-2026 23:46:15 | Chananun Rojanarungruengporn | 03-Sep-2026 | 03-Sep-2026 08:02:06 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:51:39 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:09:58 | 08-Sep-2026 04:46:50 | 0 |  |  | Approver | Locate
AO-000198 | MM-ZTK-1F-ZWPX-PRO-PID-0019 | P&ID POWER GENERATION SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:45:00 | wisuda.c@jutal.com | 22-Apr-2026 13:00:15 | Jumpol Sudjitjul | 29-Apr-2026 |  | Chananun Rojanarungruengporn | 05-May-2026 | 05-May-2026 17:34:07 | Pornlert Wanaphattharaphan | 06-May-2026 | 07-May-2026 23:13:42 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 08:38:44 | 08-May-2026 09:22:15 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWPX-PRO-PID-0019 | P&ID POWER GENERATION SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 17:04:37 | wisuda.c@jutal.com | 18-Jun-2026 17:42:14 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 30-Jun-2026 23:51:39 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 03-Jul-2026 00:01:32 | APPR | Approved | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 10:52:58 | 03-Jul-2026 04:38:19 | 0 |  |  | Approver | Locate
AO-001668 | MM-ZTK-1F-ZWPX-PRO-PID-0019 | P&ID POWER GENERATION SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 10:11:50 | wisuda.c@jutal.com | 25-Aug-2026 09:46:14 | Jumpol Sudjitjul | 01-Sep-2026 |  | Chananun Rojanarungruengporn | 03-Sep-2026 | 26-Aug-2026 16:51:40 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 31-Aug-2026 00:31:31 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 16:05:07 | 31-Aug-2026 10:02:36 | 0 |  |  | Approver | Locate
AO-000198 | MM-ZTK-1F-ZWPX-PRO-PID-0020 | P&ID CRANE AND UTILITY WATER SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:45:25 | wisuda.c@jutal.com | 22-Apr-2026 12:55:47 | Jumpol Sudjitjul | 29-Apr-2026 |  | Chananun Rojanarungruengporn | 05-May-2026 | 05-May-2026 17:33:16 | Pornlert Wanaphattharaphan | 06-May-2026 | 07-May-2026 23:27:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 08:29:43 | 08-May-2026 08:46:43 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWPX-PRO-PID-0020 | P&ID CRANE AND UTILITY WATER SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 17:05:04 | wisuda.c@jutal.com | 18-Jun-2026 17:42:34 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 30-Jun-2026 23:51:53 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 03-Jul-2026 00:02:15 | APPR | Approved | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 10:51:09 | 03-Jul-2026 04:34:00 | 0 |  |  | Approver | Locate
AO-001668 | MM-ZTK-1F-ZWPX-PRO-PID-0020 | P&ID CRANE AND UTILITY WATER SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 10:12:19 | wisuda.c@jutal.com | 25-Aug-2026 09:46:06 | Jumpol Sudjitjul | 01-Sep-2026 |  | Chananun Rojanarungruengporn | 03-Sep-2026 | 26-Aug-2026 16:48:35 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 31-Aug-2026 00:32:43 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 16:03:24 | 31-Aug-2026 10:00:25 | 0 |  |  | Approver | Locate
AO-000198 | MM-ZTK-1F-ZWPX-PRO-PID-0021 | P&ID HAZARDOUS OPEN DRAINS AND CLOSE DRAINS SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:45:50 | wisuda.c@jutal.com | 22-Apr-2026 12:55:33 | Jumpol Sudjitjul | 29-Apr-2026 |  | Chananun Rojanarungruengporn | 05-May-2026 | 05-May-2026 17:32:40 | Pornlert Wanaphattharaphan | 06-May-2026 | 07-May-2026 23:12:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 08:36:42 | 08-May-2026 02:19:55 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWPX-PRO-PID-0021 | P&ID HAZARDOUS OPEN DRAINS AND CLOSE DRAINS SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 17:05:31 | wisuda.c@jutal.com | 18-Jun-2026 17:44:52 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 30-Jun-2026 23:54:04 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 03-Jul-2026 00:16:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 10:50:34 | 03-Jul-2026 04:32:34 | 0 |  |  | Approver | Locate
AO-001668 | MM-ZTK-1F-ZWPX-PRO-PID-0021 | P&ID HAZARDOUS OPEN DRAINS AND CLOSE DRAINS SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 10:12:46 | wisuda.c@jutal.com | 25-Aug-2026 09:46:16 | Jumpol Sudjitjul | 01-Sep-2026 | 02-Sep-2026 23:45:37 | Chananun Rojanarungruengporn | 03-Sep-2026 | 03-Sep-2026 08:01:31 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 07-Sep-2026 00:51:19 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 07-Sep-2026 18:09:14 | 08-Sep-2026 07:47:26 | 0 |  |  | Approver | Locate
AO-000198 | MM-ZTK-1F-ZWPX-PRO-PID-0022 | P&ID NON-HAZARDOUS OPEN DRAINS SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:46:14 | wisuda.c@jutal.com | 22-Apr-2026 12:55:19 | Jumpol Sudjitjul | 29-Apr-2026 |  | Chananun Rojanarungruengporn | 05-May-2026 | 04-May-2026 15:15:33 | Pornlert Wanaphattharaphan | 06-May-2026 | 07-May-2026 21:12:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 08:34:44 | 08-May-2026 09:16:15 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWPX-PRO-PID-0022 | P&ID NON-HAZARDOUS OPEN DRAINS SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 17:05:59 | wisuda.c@jutal.com | 18-Jun-2026 17:45:12 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 30-Jun-2026 23:52:13 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 03-Jul-2026 00:13:35 | APPR | Approved | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 10:49:42 | 03-Jul-2026 04:29:39 | 0 |  |  | Approver | Locate
AO-001668 | MM-ZTK-1F-ZWPX-PRO-PID-0022 | P&ID NON-HAZARDOUS OPEN DRAINS SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 10:13:12 | wisuda.c@jutal.com | 25-Aug-2026 09:46:13 | Jumpol Sudjitjul | 01-Sep-2026 |  | Chananun Rojanarungruengporn | 03-Sep-2026 | 26-Aug-2026 16:46:40 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 31-Aug-2026 00:33:10 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 16:02:28 | 31-Aug-2026 09:45:00 | 0 |  |  | Approver | Locate
AO-000198 | MM-ZTK-1F-ZWPX-PRO-PID-0023 | P&ID VENT SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Apr-2026 16:46:38 | wisuda.c@jutal.com | 22-Apr-2026 12:55:05 | Jumpol Sudjitjul | 29-Apr-2026 |  | Chananun Rojanarungruengporn | 05-May-2026 | 05-May-2026 17:29:53 | Pornlert Wanaphattharaphan | 06-May-2026 | 07-May-2026 23:01:14 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 07-May-2026 | 08-May-2026 08:31:55 | 08-May-2026 09:13:49 | 0 |  |  | Approver | Locate
AO-000832 | MM-ZTK-1F-ZWPX-PRO-PID-0023 | P&ID VENT SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | IFA | Issued for Approval |  | 18-Jun-2026 17:06:25 | wisuda.c@jutal.com | 18-Jun-2026 17:45:29 | Jumpol Sudjitjul | 26-Jun-2026 |  | Chananun Rojanarungruengporn | 30-Jun-2026 | 30-Jun-2026 23:53:20 | Pornlert Wanaphattharaphan | 01-Jul-2026 | 03-Jul-2026 00:15:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jul-2026 | 03-Jul-2026 10:49:00 | 03-Jul-2026 04:26:46 | 0 |  |  | Approver | Locate
AO-001668 | MM-ZTK-1F-ZWPX-PRO-PID-0023 | P&ID VENT SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | PID | Piping and Instrumentation Diagram | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 10:13:39 | wisuda.c@jutal.com | 25-Aug-2026 09:46:12 | Jumpol Sudjitjul | 01-Sep-2026 |  | Chananun Rojanarungruengporn | 03-Sep-2026 | 26-Aug-2026 16:45:50 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 31-Aug-2026 00:33:39 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 31-Aug-2026 16:01:49 | 31-Aug-2026 09:43:54 | 0 |  |  | Approver | Locate
AO-000064 | MM-ZTK-1F-ZWPX-PRO-UFD-0001 | UTILITY FLOW DIAGRAM INSTRUMENT AND UTILITY GAS SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFR | Issued for Review |  | 02-Apr-2026 21:37:03 | zm169dc@jutal.com | 03-Apr-2026 06:45:54 | Jumpol Sudjitjul | 16-Apr-2026 |  | Chananun Rojanarungruengporn | 20-Apr-2026 | 16-Apr-2026 09:14:42 | Pornlert Wanaphattharaphan | 21-Apr-2026 | 20-Apr-2026 00:17:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Apr-2026 | 20-Apr-2026 08:13:44 | 20-Apr-2026 08:35:15 | 0 |  |  | Approver | Locate
AO-000775 | MM-ZTK-1F-ZWPX-PRO-UFD-0001 | UTILITY FLOW DIAGRAM INSTRUMENT AND UTILITY GAS SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFA | Issued for Approval |  | 14-Jun-2026 22:14:25 | wisuda.c@jutal.com | 15-Jun-2026 09:21:18 | Jumpol Sudjitjul | 22-Jun-2026 |  | Chananun Rojanarungruengporn | 24-Jun-2026 | 24-Jun-2026 16:49:41 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 24-Jun-2026 23:20:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Jun-2026 | 25-Jun-2026 14:05:11 | 25-Jun-2026 08:06:00 | 0 |  |  | Approver | Locate
AO-001521 | MM-ZTK-1F-ZWPX-PRO-UFD-0001 | UTILITY FLOW DIAGRAM INSTRUMENT AND UTILITY GAS SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | AFC | Approved for Construction |  | 14-Aug-2026 13:25:34 | wisuda.c@jutal.com | 14-Aug-2026 13:32:22 | Jumpol Sudjitjul | 21-Aug-2026 |  | Chananun Rojanarungruengporn | 25-Aug-2026 | 20-Aug-2026 17:28:08 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 22-Aug-2026 13:12:24 | APPR | Approved | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 17:58:50 | 24-Aug-2026 12:23:07 | 0 |  |  | Approver | Locate
AO-000065 | MM-ZTK-1F-ZWPX-PRO-UFD-0002 | UTILITY FLOW DIAGRAM VENT, OPEN DRAINS AND CLOSED DRAINS SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFR | Issued for Review |  | 02-Apr-2026 21:37:28 | zm169dc@jutal.com | 03-Apr-2026 06:44:12 | Jumpol Sudjitjul | 16-Apr-2026 |  | Chananun Rojanarungruengporn | 20-Apr-2026 | 16-Apr-2026 09:26:25 | Pornlert Wanaphattharaphan | 21-Apr-2026 | 20-Apr-2026 00:34:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Apr-2026 | 20-Apr-2026 08:18:11 | 20-Apr-2026 08:39:00 | 0 |  |  | Approver | Locate
AO-000776 | MM-ZTK-1F-ZWPX-PRO-UFD-0002 | UTILITY FLOW DIAGRAM VENT, OPEN DRAINS AND CLOSED DRAINS SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFA | Issued for Approval |  | 14-Jun-2026 22:14:49 | wisuda.c@jutal.com | 15-Jun-2026 09:21:50 | Jumpol Sudjitjul | 22-Jun-2026 |  | Chananun Rojanarungruengporn | 24-Jun-2026 | 24-Jun-2026 16:56:36 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 24-Jun-2026 23:21:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Jun-2026 | 25-Jun-2026 14:07:27 | 25-Jun-2026 08:08:50 | 0 |  |  | Approver | Locate
AO-001521 | MM-ZTK-1F-ZWPX-PRO-UFD-0002 | UTILITY FLOW DIAGRAM VENT, OPEN DRAINS AND CLOSED DRAINS SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | AFC | Approved for Construction |  | 14-Aug-2026 12:00:01 | wisuda.c@jutal.com | 14-Aug-2026 12:37:40 | Jumpol Sudjitjul | 21-Aug-2026 |  | Chananun Rojanarungruengporn | 25-Aug-2026 | 20-Aug-2026 17:26:59 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 23-Aug-2026 21:38:19 | APPR | Approved | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 17:57:30 | 24-Aug-2026 11:36:37 | 0 |  |  | Approver | Locate
AO-000066 | MM-ZTK-1F-ZWPX-PRO-UFD-0003 | UTILITY FLOW DIAGRAM CHEMICAL INJECTION SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFR | Issued for Review |  | 02-Apr-2026 21:37:56 | zm169dc@jutal.com | 03-Apr-2026 08:15:28 | Jumpol Sudjitjul | 16-Apr-2026 |  | Chananun Rojanarungruengporn | 20-Apr-2026 | 16-Apr-2026 10:46:00 | Pornlert Wanaphattharaphan | 21-Apr-2026 | 20-Apr-2026 00:50:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-Apr-2026 | 20-Apr-2026 08:16:58 | 20-Apr-2026 08:37:46 | 0 |  |  | Approver | Locate
AO-000777 | MM-ZTK-1F-ZWPX-PRO-UFD-0003 | UTILITY FLOW DIAGRAM CHEMICAL INJECTION SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFA | Issued for Approval |  | 14-Jun-2026 22:15:13 | wisuda.c@jutal.com | 15-Jun-2026 09:22:11 | Jumpol Sudjitjul | 22-Jun-2026 |  | Chananun Rojanarungruengporn | 24-Jun-2026 | 24-Jun-2026 16:50:53 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 24-Jun-2026 23:21:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Jun-2026 | 25-Jun-2026 14:08:25 | 25-Jun-2026 08:10:18 | 0 |  |  | Approver | Locate
AO-001521 | MM-ZTK-1F-ZWPX-PRO-UFD-0003 | UTILITY FLOW DIAGRAM CHEMICAL INJECTION SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | AFC | Approved for Construction |  | 14-Aug-2026 12:00:26 | wisuda.c@jutal.com | 14-Aug-2026 12:38:04 | Jumpol Sudjitjul | 21-Aug-2026 |  | Chananun Rojanarungruengporn | 25-Aug-2026 | 20-Aug-2026 17:25:37 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 23-Aug-2026 21:37:02 | APPR | Approved | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 17:56:52 | 24-Aug-2026 12:21:52 | 0 |  |  | Approver | Locate
AO-000067 | MM-ZTK-1F-ZWPX-PRO-UFD-0004 | UTILITY FLOW DIAGRAM DIESEL, UTILITY WATER AND POWER SYSTEM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFR | Issued for Review |  | 02-Apr-2026 21:38:22 | zm169dc@jutal.com | 03-Apr-2026 06:46:22 | Jumpol Sudjitjul | 16-Apr-2026 |  | Chananun Rojanarungruengporn | 20-Apr-2026 | 16-Apr-2026 11:13:03 | Pornlert Wanaphattharaphan | 21-Apr-2026 | 20-Apr-2026 00:56:10 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 22-Apr-2026 | 20-Apr-2026 08:16:01 | 20-Apr-2026 08:36:32 | 0 |  |  | Approver | Locate
AO-000778 | MM-ZTK-1F-ZWPX-PRO-UFD-0004 | UTILITY FLOW DIAGRAM DIESEL, UTILITY WATER AND POWER SYSTEM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | IFA | Issued for Approval |  | 14-Jun-2026 22:15:36 | wisuda.c@jutal.com | 15-Jun-2026 09:22:27 | Jumpol Sudjitjul | 22-Jun-2026 |  | Chananun Rojanarungruengporn | 24-Jun-2026 | 24-Jun-2026 16:48:10 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 24-Jun-2026 23:19:41 | APPR | Approved | Jumpol Sudjitjul | 26-Jun-2026 | 25-Jun-2026 14:05:34 | 25-Jun-2026 08:07:17 | 0 |  |  | Approver | Locate
AO-001521 | MM-ZTK-1F-ZWPX-PRO-UFD-0004 | UTILITY FLOW DIAGRAM DIESEL, UTILITY WATER AND POWER SYSTEM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | PRO | Process | UFD | Utility Flow Diagram | 0 | Submitted | AFC | Approved for Construction |  | 14-Aug-2026 11:31:42 | wisuda.c@jutal.com | 14-Aug-2026 12:38:19 | Jumpol Sudjitjul | 21-Aug-2026 |  | Chananun Rojanarungruengporn | 25-Aug-2026 | 20-Aug-2026 17:24:11 | Pornlert Wanaphattharaphan | 26-Aug-2026 | 23-Aug-2026 21:35:00 | APPR | Approved | Jumpol Sudjitjul | 27-Aug-2026 | 24-Aug-2026 17:56:19 | 24-Aug-2026 12:42:03 | 0 |  |  | Approver | Locate
AO-000545 | MM-ZTK-1F-ZWPX-SAF-DWG-0001 | HAZARDOUS AREA CLASSIFICATION DRAWING INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 13:36:13 | wisuda.c@jutal.com | 21-May-2026 14:19:44 | Jumpol Sudjitjul | 28-May-2026 | 05-Jun-2026 15:45:19 | Arnon Srisuwan | 02-Jun-2026 | 07-Jun-2026 20:33:34 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 10-Jun-2026 21:03:11 | APPR | Approved | Jumpol Sudjitjul | 05-Jun-2026 | 11-Jun-2026 13:29:54 | 11-Jun-2026 06:42:10 | 0 |  |  | Approver | Locate
AO-002283 | MM-ZTK-1F-ZWPX-SAF-DWG-0001 | HAZARDOUS AREA CLASSIFICATION DRAWING INDEX |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | SAF | Safety Engineering | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 09:43:39 | wisuda.c@jutal.com | 28-Sep-2026 10:02:48 | Jumpol Sudjitjul | 05-Oct-2026 | 04-Oct-2026 21:59:13 | Arnon Srisuwan | 07-Oct-2026 | 08-Oct-2026 11:31:13 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 10-Oct-2026 01:34:26 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 10-Oct-2026 17:47:54 | 10-Oct-2026 11:48:16 | 0 |  |  | Approver | Locate
AO-000517 | MM-ZTK-1F-ZWPX-SAF-LAY-0001 | ESCAPE ROUTES, FIRE FIGHTING, SAFETY EQUIPMENT AND SAFETY SIGN LAYOUT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 18:20:48 | wisuda.c@jutal.com | 19-May-2026 18:45:49 | Jumpol Sudjitjul | 27-May-2026 |  | Arnon Srisuwan | 29-May-2026 | 05-Jun-2026 11:00:02 | Pornlert Wanaphattharaphan | 02-Jun-2026 | 05-Jun-2026 23:09:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 04-Jun-2026 | 07-Jun-2026 17:46:03 | 07-Jun-2026 11:45:58 | 0 |  |  | Approver | Locate
AO-002457 | MM-ZTK-1F-ZWPX-SAF-LAY-0001 | ESCAPE ROUTES, FIRE FIGHTING, SAFETY EQUIPMENT AND SAFETY SIGN LAYOUT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | SAF | Safety Engineering | LAY | Layout Drawing | 0 | In Review | AFC | Approved for Construction |  | 09-Oct-2026 13:11:59 | wisuda.c@jutal.com | 09-Oct-2026 15:32:37 | Jumpol Sudjitjul | 19-Oct-2026 | 17-Oct-2026 17:15:05 | Arnon Srisuwan | 21-Oct-2026 |  | Pornlert Wanaphattharaphan | 22-Oct-2026 |  |  |  |  | 26-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000218 | MM-ZTK-1F-ZWPX-STR-DWG-0001 | TOPSIDE - GENERAL NOTES SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 12:29:07 | wisuda.c@jutal.com | 24-Apr-2026 13:43:38 | Jumpol Sudjitjul | 05-May-2026 |  | Sompop Singhatiraj | 07-May-2026 | 07-May-2026 14:44:36 | Pornlert Wanaphattharaphan | 08-May-2026 | 09-May-2026 00:18:33 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-May-2026 | 09-May-2026 08:20:39 | 09-May-2026 08:50:24 | 0 |  |  | Approver | Locate
AO-000781 | MM-ZTK-1F-ZWPX-STR-DWG-0001 | TOPSIDE - GENERAL NOTES SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Jun-2026 22:05:11 | wisuda.c@jutal.com | 15-Jun-2026 08:49:46 | Jumpol Sudjitjul | 22-Jun-2026 |  | Sompop Singhatiraj | 24-Jun-2026 | 15-Jun-2026 17:47:12 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 18-Jun-2026 12:55:31 | APPR | Approved | Jumpol Sudjitjul | 26-Jun-2026 | 18-Jun-2026 14:27:08 | 18-Jun-2026 08:06:21 | 0 |  |  | Approver | Locate
AO-000218 | MM-ZTK-1F-ZWPX-STR-DWG-0002 | TOPSIDE - GENERAL NOTES SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 12:29:30 | wisuda.c@jutal.com | 24-Apr-2026 13:44:02 | Jumpol Sudjitjul | 05-May-2026 | 27-Apr-2026 10:25:59 | Sompop Singhatiraj | 07-May-2026 | 08-May-2026 08:00:35 | Pornlert Wanaphattharaphan | 08-May-2026 | 09-May-2026 00:20:16 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-May-2026 | 09-May-2026 08:21:34 | 09-May-2026 08:51:33 | 0 |  |  | Approver | Locate
AO-000782 | MM-ZTK-1F-ZWPX-STR-DWG-0002 | TOPSIDE - GENERAL NOTES SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Jun-2026 22:05:36 | wisuda.c@jutal.com | 15-Jun-2026 08:50:16 | Jumpol Sudjitjul | 22-Jun-2026 |  | Sompop Singhatiraj | 24-Jun-2026 | 15-Jun-2026 17:49:54 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 18-Jun-2026 13:59:18 | APPR | Approved | Jumpol Sudjitjul | 26-Jun-2026 | 18-Jun-2026 14:27:38 | 18-Jun-2026 08:07:35 | 0 |  |  | Approver | Locate
AO-000864 | MM-ZTK-1F-ZWPX-STR-DWG-0002 | TOPSIDE - GENERAL NOTES SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 22-Jun-2026 13:16:51 | wisuda.c@jutal.com | 22-Jun-2026 14:41:20 | Jumpol Sudjitjul | 29-Jun-2026 |  | Sompop Singhatiraj | 01-Jul-2026 | 23-Jun-2026 06:56:35 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 23-Jun-2026 23:08:31 | APPR | Approved | Jumpol Sudjitjul | 03-Jul-2026 | 24-Jun-2026 13:54:33 | 24-Jun-2026 07:36:11 | 0 |  |  | Approver | Locate
AO-000218 | MM-ZTK-1F-ZWPX-STR-DWG-0011 | TOPSIDE - STANDARD DETAILS - DECK JOINTS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 12:29:53 | wisuda.c@jutal.com | 24-Apr-2026 13:44:19 | Jumpol Sudjitjul | 05-May-2026 | 27-Apr-2026 12:57:55 | Sompop Singhatiraj | 07-May-2026 | 08-May-2026 11:05:05 | Pornlert Wanaphattharaphan | 08-May-2026 | 09-May-2026 00:22:31 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-May-2026 | 09-May-2026 08:22:06 | 09-May-2026 09:16:21 | 0 |  |  | Approver | Locate
AO-000799 | MM-ZTK-1F-ZWPX-STR-DWG-0011 | TOPSIDE - STANDARD DETAILS - DECK JOINTS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 15-Jun-2026 12:06:34 | wisuda.c@jutal.com | 15-Jun-2026 16:43:16 | Jumpol Sudjitjul | 22-Jun-2026 |  | Sompop Singhatiraj | 24-Jun-2026 | 15-Jun-2026 17:52:02 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 18-Jun-2026 13:57:37 | APPR | Approved | Jumpol Sudjitjul | 26-Jun-2026 | 18-Jun-2026 14:28:19 | 18-Jun-2026 08:00:07 | 0 |  |  | Approver | Locate
AO-000218 | MM-ZTK-1F-ZWPX-STR-DWG-0012 | TOPSIDE - STANDARD DETAILS - DECK JOINTS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 12:30:18 | wisuda.c@jutal.com | 24-Apr-2026 13:44:34 | Jumpol Sudjitjul | 05-May-2026 | 27-Apr-2026 12:58:39 | Sompop Singhatiraj | 07-May-2026 | 08-May-2026 11:00:01 | Pornlert Wanaphattharaphan | 08-May-2026 | 09-May-2026 00:21:54 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-May-2026 | 09-May-2026 08:22:34 | 09-May-2026 02:17:31 | 0 |  |  | Approver | Locate
AO-001486 | MM-ZTK-1F-ZWPX-STR-DWG-0012 | TOPSIDE - STANDARD DETAILS - DECK JOINTS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Aug-2026 11:47:53 | wisuda.c@jutal.com | 10-Aug-2026 14:30:54 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 18-Aug-2026 09:36:34 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:24:52 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 17:55:46 | 24-Aug-2026 12:20:38 | 0 |  |  | Approver | Locate
AO-000218 | MM-ZTK-1F-ZWPX-STR-DWG-0013 | TOPSIDE - STANDARD DETAILS - DECK JOINTS - SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 12:30:48 | wisuda.c@jutal.com | 24-Apr-2026 13:52:09 | Jumpol Sudjitjul | 05-May-2026 | 27-Apr-2026 12:59:29 | Sompop Singhatiraj | 07-May-2026 | 11-May-2026 09:09:55 | Pornlert Wanaphattharaphan | 08-May-2026 | 11-May-2026 20:30:01 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 10:37:47 | 12-May-2026 11:26:24 | 0 |  |  | Approver | Locate
AO-000786 | MM-ZTK-1F-ZWPX-STR-DWG-0013 | TOPSIDE - STANDARD DETAILS - DECK JOINTS - SHEET 3 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Jun-2026 22:06:00 | wisuda.c@jutal.com | 15-Jun-2026 08:55:16 | Jumpol Sudjitjul | 22-Jun-2026 |  | Sompop Singhatiraj | 24-Jun-2026 | 15-Jun-2026 17:54:39 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 18-Jun-2026 13:53:30 | APPR | Approved | Jumpol Sudjitjul | 26-Jun-2026 | 18-Jun-2026 14:27:42 | 18-Jun-2026 08:08:46 | 0 |  |  | Approver | Locate
AO-000218 | MM-ZTK-1F-ZWPX-STR-DWG-0014 | TOPSIDE - STANDARD DETAILS - DECK JOINTS - SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 12:31:12 | wisuda.c@jutal.com | 24-Apr-2026 13:52:29 | Jumpol Sudjitjul | 05-May-2026 | 27-Apr-2026 13:00:40 | Sompop Singhatiraj | 07-May-2026 | 11-May-2026 09:12:51 | Pornlert Wanaphattharaphan | 08-May-2026 | 11-May-2026 20:31:03 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 10:38:09 | 12-May-2026 04:27:37 | 0 |  |  | Approver | Locate
AO-001486 | MM-ZTK-1F-ZWPX-STR-DWG-0014 | TOPSIDE - STANDARD DETAILS - DECK JOINTS - SHEET 4 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Aug-2026 11:48:28 | wisuda.c@jutal.com | 10-Aug-2026 14:30:52 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 18-Aug-2026 09:38:39 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:25:56 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 17:55:11 | 24-Aug-2026 12:19:28 | 0 |  |  | Approver | Locate
AO-000218 | MM-ZTK-1F-ZWPX-STR-DWG-0015 | TOPSIDE - STANDARD DETAILS - HANDRAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 12:31:38 | wisuda.c@jutal.com | 24-Apr-2026 13:52:53 | Jumpol Sudjitjul | 05-May-2026 | 27-Apr-2026 13:01:15 | Sompop Singhatiraj | 07-May-2026 | 11-May-2026 09:41:41 | Pornlert Wanaphattharaphan | 08-May-2026 | 11-May-2026 20:32:00 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 10:39:03 | 12-May-2026 11:46:14 | 0 |  |  | Approver | Locate
AO-000788 | MM-ZTK-1F-ZWPX-STR-DWG-0015 | TOPSIDE - STANDARD DETAILS - HANDRAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Jun-2026 22:06:23 | wisuda.c@jutal.com | 15-Jun-2026 08:55:17 | Jumpol Sudjitjul | 22-Jun-2026 |  | Sompop Singhatiraj | 24-Jun-2026 | 15-Jun-2026 17:58:04 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 18-Jun-2026 11:50:57 | APPR | Approved | Jumpol Sudjitjul | 26-Jun-2026 | 18-Jun-2026 11:54:14 | 18-Jun-2026 05:42:41 | 0 |  |  | Approver | Locate
AO-000218 | MM-ZTK-1F-ZWPX-STR-DWG-0016 | TOPSIDE - STANDARD DETAILS - HANDRAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 12:32:01 | wisuda.c@jutal.com | 24-Apr-2026 13:53:11 | Jumpol Sudjitjul | 05-May-2026 | 27-Apr-2026 13:01:42 | Sompop Singhatiraj | 07-May-2026 | 11-May-2026 09:55:39 | Pornlert Wanaphattharaphan | 08-May-2026 | 11-May-2026 20:34:30 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 10:39:36 | 12-May-2026 11:28:49 | 0 |  |  | Approver | Locate
AO-000789 | MM-ZTK-1F-ZWPX-STR-DWG-0016 | TOPSIDE - STANDARD DETAILS - HANDRAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Jun-2026 22:06:46 | wisuda.c@jutal.com | 15-Jun-2026 08:55:19 | Jumpol Sudjitjul | 22-Jun-2026 |  | Sompop Singhatiraj | 24-Jun-2026 | 15-Jun-2026 18:03:32 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 18-Jun-2026 11:50:13 | APPR | Approved | Jumpol Sudjitjul | 26-Jun-2026 | 18-Jun-2026 11:55:57 | 18-Jun-2026 05:43:52 | 0 |  |  | Approver | Locate
AO-000218 | MM-ZTK-1F-ZWPX-STR-DWG-0017 | TOPSIDE - STANDARD DETAILS - STAIRS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 12:32:25 | wisuda.c@jutal.com | 24-Apr-2026 13:56:06 | Jumpol Sudjitjul | 05-May-2026 | 27-Apr-2026 13:02:50 | Sompop Singhatiraj | 07-May-2026 | 11-May-2026 10:11:53 | Pornlert Wanaphattharaphan | 08-May-2026 | 11-May-2026 20:39:53 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 10:40:34 | 12-May-2026 04:30:03 | 0 |  |  | Approver | Locate
AO-001486 | MM-ZTK-1F-ZWPX-STR-DWG-0017 | TOPSIDE - STANDARD DETAILS - STAIRS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Aug-2026 11:48:55 | wisuda.c@jutal.com | 10-Aug-2026 14:30:50 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 18-Aug-2026 09:41:59 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:26:44 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 17:54:38 | 24-Aug-2026 12:18:23 | 0 |  |  | Approver | Locate
AO-000218 | MM-ZTK-1F-ZWPX-STR-DWG-0018 | TOPSIDE - STANDARD DETAILS - STAIRS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 12:32:47 | wisuda.c@jutal.com | 24-Apr-2026 13:55:37 | Jumpol Sudjitjul | 05-May-2026 | 27-Apr-2026 13:03:26 | Sompop Singhatiraj | 07-May-2026 | 11-May-2026 10:15:41 | Pornlert Wanaphattharaphan | 08-May-2026 | 11-May-2026 20:43:14 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 10:41:23 | 12-May-2026 04:45:09 | 0 |  |  | Approver | Locate
AO-000790 | MM-ZTK-1F-ZWPX-STR-DWG-0018 | TOPSIDE - STANDARD DETAILS - STAIRS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Jun-2026 22:07:10 | wisuda.c@jutal.com | 15-Jun-2026 08:55:23 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:49:41 | Sompop Singhatiraj | 24-Jun-2026 | 23-Jun-2026 08:00:52 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 23-Jun-2026 23:14:15 | APPR | Approved | Jumpol Sudjitjul | 26-Jun-2026 | 24-Jun-2026 14:25:43 | 24-Jun-2026 08:33:01 | 0 |  |  | Approver | Locate
AO-000218 | MM-ZTK-1F-ZWPX-STR-DWG-0019 | TOPSIDE - STANDARD DETAILS - LADDERS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 12:33:10 | wisuda.c@jutal.com | 24-Apr-2026 13:55:51 | Jumpol Sudjitjul | 05-May-2026 | 27-Apr-2026 13:03:47 | Sompop Singhatiraj | 07-May-2026 | 11-May-2026 10:39:45 | Pornlert Wanaphattharaphan | 08-May-2026 | 11-May-2026 20:44:40 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 10:42:29 | 12-May-2026 04:31:16 | 0 |  |  | Approver | Locate
AO-001486 | MM-ZTK-1F-ZWPX-STR-DWG-0019 | TOPSIDE - STANDARD DETAILS - LADDERS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Aug-2026 11:49:33 | wisuda.c@jutal.com | 10-Aug-2026 14:30:54 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 18-Aug-2026 09:41:39 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:26:19 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 17:48:10 | 24-Aug-2026 11:32:13 | 0 |  |  | Approver | Locate
AO-000218 | MM-ZTK-1F-ZWPX-STR-DWG-0020 | TOPSIDE - STANDARD DETAILS - LADDERS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 12:33:33 | wisuda.c@jutal.com | 24-Apr-2026 13:56:10 | Jumpol Sudjitjul | 05-May-2026 | 27-Apr-2026 13:04:15 | Sompop Singhatiraj | 07-May-2026 | 11-May-2026 10:55:53 | Pornlert Wanaphattharaphan | 08-May-2026 | 11-May-2026 20:45:41 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 10:43:06 | 12-May-2026 04:32:30 | 0 |  |  | Approver | Locate
AO-001486 | MM-ZTK-1F-ZWPX-STR-DWG-0020 | TOPSIDE - STANDARD DETAILS - LADDERS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Aug-2026 11:50:00 | wisuda.c@jutal.com | 10-Aug-2026 14:30:50 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 18-Aug-2026 09:37:55 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:25:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 17:54:04 | 24-Aug-2026 12:17:17 | 0 |  |  | Approver | Locate
AO-000218 | MM-ZTK-1F-ZWPX-STR-DWG-0021 | TOPSIDE - STANDARD DETAILS - LADDERS - SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 12:33:55 | wisuda.c@jutal.com | 24-Apr-2026 13:55:00 | Jumpol Sudjitjul | 05-May-2026 | 27-Apr-2026 13:04:38 | Sompop Singhatiraj | 07-May-2026 | 11-May-2026 11:05:43 | Pornlert Wanaphattharaphan | 08-May-2026 | 11-May-2026 20:46:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 10:43:30 | 12-May-2026 04:16:54 | 0 |  |  | Approver | Locate
AO-001486 | MM-ZTK-1F-ZWPX-STR-DWG-0021 | TOPSIDE - STANDARD DETAILS - LADDERS - SHEET 3 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Aug-2026 11:50:31 | wisuda.c@jutal.com | 10-Aug-2026 14:30:53 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 18-Aug-2026 09:45:12 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:27:19 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 17:53:32 | 24-Aug-2026 12:16:04 | 0 |  |  | Approver | Locate
AO-000218 | MM-ZTK-1F-ZWPX-STR-DWG-0022 | TOPSIDE - STANDARD DETAILS - PLATING AND GRATING - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 12:34:18 | wisuda.c@jutal.com | 24-Apr-2026 13:54:45 | Jumpol Sudjitjul | 05-May-2026 | 27-Apr-2026 13:06:05 | Sompop Singhatiraj | 07-May-2026 | 11-May-2026 11:29:23 | Pornlert Wanaphattharaphan | 08-May-2026 | 11-May-2026 20:47:27 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 10:39:25 | 12-May-2026 04:51:53 | 0 |  |  | Approver | Locate
AO-000791 | MM-ZTK-1F-ZWPX-STR-DWG-0022 | TOPSIDE - STANDARD DETAILS - PLATING AND GRATING - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Jun-2026 22:07:34 | wisuda.c@jutal.com | 15-Jun-2026 08:55:21 | Jumpol Sudjitjul | 22-Jun-2026 |  | Sompop Singhatiraj | 24-Jun-2026 | 15-Jun-2026 18:19:51 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 18-Jun-2026 11:49:36 | APPR | Approved | Jumpol Sudjitjul | 26-Jun-2026 | 18-Jun-2026 11:52:34 | 18-Jun-2026 05:41:32 | 0 |  |  | Approver | Locate
AO-000218 | MM-ZTK-1F-ZWPX-STR-DWG-0023 | TOPSIDE - STANDARD DETAILS - PLATING AND GRATING - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 12:34:42 | wisuda.c@jutal.com | 24-Apr-2026 13:54:32 | Jumpol Sudjitjul | 05-May-2026 | 27-Apr-2026 13:06:59 | Sompop Singhatiraj | 07-May-2026 | 11-May-2026 13:00:21 | Pornlert Wanaphattharaphan | 08-May-2026 | 11-May-2026 20:49:08 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 10:37:50 | 12-May-2026 04:15:40 | 0 |  |  | Approver | Locate
AO-000792 | MM-ZTK-1F-ZWPX-STR-DWG-0023 | TOPSIDE - STANDARD DETAILS - PLATING AND GRATING - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Jun-2026 22:07:58 | wisuda.c@jutal.com | 15-Jun-2026 08:55:25 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:48:38 | Sompop Singhatiraj | 24-Jun-2026 | 23-Jun-2026 07:29:41 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 23-Jun-2026 23:11:57 | APPR | Approved | Jumpol Sudjitjul | 26-Jun-2026 | 24-Jun-2026 14:26:09 | 24-Jun-2026 08:34:16 | 0 |  |  | Approver | Locate
AO-000218 | MM-ZTK-1F-ZWPX-STR-DWG-0024 | TOPSIDE - STANDARD DETAILS - DECK DRAINS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 12:35:05 | wisuda.c@jutal.com | 24-Apr-2026 13:54:17 | Jumpol Sudjitjul | 05-May-2026 | 27-Apr-2026 13:07:39 | Sompop Singhatiraj | 07-May-2026 | 11-May-2026 13:27:20 | Pornlert Wanaphattharaphan | 08-May-2026 | 11-May-2026 21:00:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 10:43:40 | 12-May-2026 04:14:22 | 0 |  |  | Approver | Locate
AO-001486 | MM-ZTK-1F-ZWPX-STR-DWG-0024 | TOPSIDE - STANDARD DETAILS - DECK DRAINS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:50:59 | wisuda.c@jutal.com | 10-Aug-2026 14:31:00 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 18-Aug-2026 10:11:45 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:27:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 17:52:54 | 24-Aug-2026 12:14:59 | 0 |  |  | Approver | Locate
AO-000218 | MM-ZTK-1F-ZWPX-STR-DWG-0025 | TOPSIDE - STANDARD DETAILS - DECK DRAINS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 12:35:28 | wisuda.c@jutal.com | 24-Apr-2026 13:51:13 | Jumpol Sudjitjul | 05-May-2026 | 27-Apr-2026 13:08:21 | Sompop Singhatiraj | 07-May-2026 | 11-May-2026 13:42:22 | Pornlert Wanaphattharaphan | 08-May-2026 | 11-May-2026 21:02:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 10:43:12 | 12-May-2026 04:13:08 | 0 |  |  | Approver | Locate
AO-001486 | MM-ZTK-1F-ZWPX-STR-DWG-0025 | TOPSIDE - STANDARD DETAILS - DECK DRAINS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:51:29 | wisuda.c@jutal.com | 10-Aug-2026 14:30:59 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 18-Aug-2026 10:17:48 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:28:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 17:52:09 | 24-Aug-2026 12:13:45 | 0 |  |  | Approver | Locate
AO-000218 | MM-ZTK-1F-ZWPX-STR-DWG-0026 | TOPSIDE - STANDARD DETAILS - WELD PROFILE - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 12:35:51 | wisuda.c@jutal.com | 24-Apr-2026 13:50:59 | Jumpol Sudjitjul | 05-May-2026 | 27-Apr-2026 13:08:58 | Sompop Singhatiraj | 07-May-2026 | 11-May-2026 13:45:45 | Pornlert Wanaphattharaphan | 08-May-2026 | 11-May-2026 21:04:44 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 10:41:06 | 12-May-2026 11:53:03 | 0 |  |  | Approver | Locate
AO-000793 | MM-ZTK-1F-ZWPX-STR-DWG-0026 | TOPSIDE - STANDARD DETAILS - WELD PROFILE - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Jun-2026 22:08:22 | wisuda.c@jutal.com | 15-Jun-2026 08:55:17 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:48:59 | Sompop Singhatiraj | 24-Jun-2026 | 23-Jun-2026 07:28:11 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 23-Jun-2026 23:10:28 | APPR | Approved | Jumpol Sudjitjul | 26-Jun-2026 | 24-Jun-2026 14:26:37 | 24-Jun-2026 08:35:28 | 0 |  |  | Approver | Locate
AO-000218 | MM-ZTK-1F-ZWPX-STR-DWG-0027 | TOPSIDE - STANDARD DETAILS - WELD PROFILE - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 12:36:14 | wisuda.c@jutal.com | 24-Apr-2026 13:50:43 | Jumpol Sudjitjul | 05-May-2026 | 27-Apr-2026 13:09:16 | Sompop Singhatiraj | 07-May-2026 | 11-May-2026 13:47:34 | Pornlert Wanaphattharaphan | 08-May-2026 | 11-May-2026 21:05:13 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 11-May-2026 | 12-May-2026 10:42:36 | 12-May-2026 11:54:08 | 0 |  |  | Approver | Locate
AO-000794 | MM-ZTK-1F-ZWPX-STR-DWG-0027 | TOPSIDE - STANDARD DETAILS - WELD PROFILE - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Jun-2026 22:08:49 | wisuda.c@jutal.com | 15-Jun-2026 08:55:22 | Jumpol Sudjitjul | 22-Jun-2026 | 18-Jun-2026 15:49:17 | Sompop Singhatiraj | 24-Jun-2026 | 23-Jun-2026 07:57:29 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 23-Jun-2026 23:12:58 | APPR | Approved | Jumpol Sudjitjul | 26-Jun-2026 | 24-Jun-2026 13:47:48 | 24-Jun-2026 07:33:49 | 0 |  |  | Approver | Locate
AO-000218 | MM-ZTK-1F-ZWPX-STR-DWG-0028 | TOPSIDE - STANDARD DETAILS - LOGO PAINTING |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Apr-2026 12:36:37 | wisuda.c@jutal.com | 24-Apr-2026 13:50:24 | Jumpol Sudjitjul | 05-May-2026 | 27-Apr-2026 13:10:01 | Sompop Singhatiraj | 07-May-2026 | 08-May-2026 10:51:25 | Pornlert Wanaphattharaphan | 08-May-2026 | 09-May-2026 00:20:50 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 11-May-2026 | 09-May-2026 08:23:04 | 09-May-2026 08:52:42 | 0 |  |  | Approver | Locate
AO-000795 | MM-ZTK-1F-ZWPX-STR-DWG-0028 | TOPSIDE - STANDARD DETAILS - LOGO PAINTING |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Jun-2026 22:09:12 | wisuda.c@jutal.com | 15-Jun-2026 08:55:21 | Jumpol Sudjitjul | 22-Jun-2026 |  | Sompop Singhatiraj | 24-Jun-2026 | 15-Jun-2026 18:07:42 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 18-Jun-2026 11:48:57 | APPR | Approved | Jumpol Sudjitjul | 26-Jun-2026 | 18-Jun-2026 11:50:08 | 18-Jun-2026 05:05:34 | 0 |  |  | Approver | Locate
AO-000653 | MM-ZTK-1F-ZWPX-STR-DWG-0051 | JACKET - GENERAL NOTES - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 02-Jun-2026 19:30:52 | wisuda.c@jutal.com | 03-Jun-2026 09:29:16 | Jumpol Sudjitjul | 10-Jun-2026 | 04-Jun-2026 08:12:50 | Sompop Singhatiraj | 12-Jun-2026 | 07-Jun-2026 12:43:36 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 21:24:19 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 16-Jun-2026 | 08-Jun-2026 08:59:02 | 08-Jun-2026 02:35:57 | 0 |  |  | Approver | Locate
AO-001510 | MM-ZTK-1F-ZWPX-STR-DWG-0051 | JACKET - GENERAL NOTES - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 11-Aug-2026 18:32:01 | wisuda.c@jutal.com | 13-Aug-2026 13:10:02 | Jumpol Sudjitjul | 20-Aug-2026 |  | Sompop Singhatiraj | 24-Aug-2026 | 20-Aug-2026 11:06:28 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 21-Aug-2026 20:07:41 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 24-Aug-2026 17:50:43 | 24-Aug-2026 11:02:12 | 0 |  |  | Approver | Locate
AO-000654 | MM-ZTK-1F-ZWPX-STR-DWG-0052 | JACKET - GENERAL NOTES - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 02-Jun-2026 19:31:22 | wisuda.c@jutal.com | 03-Jun-2026 09:29:31 | Jumpol Sudjitjul | 10-Jun-2026 | 04-Jun-2026 08:12:13 | Sompop Singhatiraj | 12-Jun-2026 | 07-Jun-2026 12:45:21 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 21:22:34 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 16-Jun-2026 | 08-Jun-2026 09:04:42 | 08-Jun-2026 02:43:48 | 0 |  |  | Approver | Locate
AO-001510 | MM-ZTK-1F-ZWPX-STR-DWG-0052 | JACKET - GENERAL NOTES - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 11-Aug-2026 18:32:29 | wisuda.c@jutal.com | 13-Aug-2026 13:10:30 | Jumpol Sudjitjul | 20-Aug-2026 |  | Sompop Singhatiraj | 24-Aug-2026 | 20-Aug-2026 11:07:38 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 21-Aug-2026 20:08:27 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 24-Aug-2026 17:49:46 | 24-Aug-2026 11:01:05 | 0 |  |  | Approver | Locate
AO-000655 | MM-ZTK-1F-ZWPX-STR-DWG-0061 | JACKET - STANDARD DETAILS WELD PROFILE - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 02-Jun-2026 19:31:46 | wisuda.c@jutal.com | 03-Jun-2026 09:29:46 | Jumpol Sudjitjul | 10-Jun-2026 | 04-Jun-2026 08:28:08 | Sompop Singhatiraj | 12-Jun-2026 | 07-Jun-2026 12:45:50 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 21:23:10 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 16-Jun-2026 | 08-Jun-2026 09:07:29 | 08-Jun-2026 02:48:56 | 0 |  |  | Approver | Locate
AO-001510 | MM-ZTK-1F-ZWPX-STR-DWG-0061 | JACKET - STANDARD DETAILS WELD PROFILE - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 11-Aug-2026 18:33:03 | wisuda.c@jutal.com | 13-Aug-2026 13:10:51 | Jumpol Sudjitjul | 20-Aug-2026 |  | Sompop Singhatiraj | 24-Aug-2026 | 20-Aug-2026 11:06:44 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 21-Aug-2026 20:08:03 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 24-Aug-2026 17:48:57 | 24-Aug-2026 10:59:52 | 0 |  |  | Approver | Locate
AO-000656 | MM-ZTK-1F-ZWPX-STR-DWG-0062 | JACKET - STANDARD DETAILS WELD PROFILE - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 02-Jun-2026 19:32:11 | wisuda.c@jutal.com | 03-Jun-2026 09:30:02 | Jumpol Sudjitjul | 10-Jun-2026 |  | Sompop Singhatiraj | 12-Jun-2026 | 07-Jun-2026 12:46:13 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 07-Jun-2026 21:21:54 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 16-Jun-2026 | 08-Jun-2026 09:09:03 | 08-Jun-2026 02:51:49 | 0 |  |  | Approver | Locate
AO-001510 | MM-ZTK-1F-ZWPX-STR-DWG-0062 | JACKET - STANDARD DETAILS WELD PROFILE - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 11-Aug-2026 18:33:33 | wisuda.c@jutal.com | 13-Aug-2026 13:11:10 | Jumpol Sudjitjul | 20-Aug-2026 |  | Sompop Singhatiraj | 24-Aug-2026 | 20-Aug-2026 11:07:49 | Pornlert Wanaphattharaphan | 25-Aug-2026 | 21-Aug-2026 20:09:00 | APPR | Approved | Jumpol Sudjitjul | 26-Aug-2026 | 24-Aug-2026 17:48:25 | 24-Aug-2026 10:58:44 | 0 |  |  | Approver | Locate
AO-001542 | MM-ZTK-1F-ZWPX-STR-DWG-1001 | TOPSIDES - DRAWING INDEX - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 17-Aug-2026 14:29:56 | wisuda.c@jutal.com | 17-Aug-2026 15:26:31 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 20-Aug-2026 08:43:54 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:11:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 17:47:23 | 24-Aug-2026 11:20:55 | 0 |  |  | Approver | Locate
AO-001542 | MM-ZTK-1F-ZWPX-STR-DWG-1002 | TOPSIDES - DRAWING INDEX - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 17-Aug-2026 14:30:29 | wisuda.c@jutal.com | 17-Aug-2026 15:26:54 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 20-Aug-2026 08:44:53 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:12:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 17:46:51 | 24-Aug-2026 11:19:39 | 0 |  |  | Approver | Locate
AO-001542 | MM-ZTK-1F-ZWPX-STR-DWG-1003 | TOPSIDES - DRAWING INDEX - SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 17-Aug-2026 14:30:59 | wisuda.c@jutal.com | 17-Aug-2026 15:27:20 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 20-Aug-2026 08:43:43 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 23-Aug-2026 23:11:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 24-Aug-2026 17:44:38 | 24-Aug-2026 11:17:24 | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1005 | TOPSIDE - DECK DESIGN LOADING DIAGRAMS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:14:59 | wisuda.c@jutal.com | 11-May-2026 13:12:46 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 12:54:09 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 12:36:12 | Pornlert Wanaphattharaphan | 21-May-2026 | 19-May-2026 00:33:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 19-May-2026 08:13:53 | 19-May-2026 01:35:19 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1005 | TOPSIDE - DECK DESIGN LOADING DIAGRAMS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:22:38 | wisuda.c@jutal.com | 27-Jul-2026 15:48:35 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 03-Aug-2026 11:26:18 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 05-Aug-2026 21:27:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 06-Aug-2026 09:36:38 | 06-Aug-2026 03:46:20 | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1100 | TOPSIDE - UPPER DECK PRIMARY STEEL - FRAMING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:15:22 | wisuda.c@jutal.com | 11-May-2026 13:13:11 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 12:55:41 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 16:45:40 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:17:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:12:33 | 22-May-2026 05:12:57 | 0 |  |  | Approver | Locate
AO-001285 | MM-ZTK-1F-ZWPX-STR-DWG-1100 | TOPSIDE - UPPER DECK PRIMARY STEEL - FRAMING PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 27-Jul-2026 09:23:07 | wisuda.c@jutal.com | 27-Jul-2026 15:48:36 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 03-Aug-2026 11:26:28 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 06:03:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 07-Aug-2026 08:39:16 | 07-Aug-2026 02:16:11 | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1101 | TOPSIDE - LOWER DECK PRIMARY STEEL - FRAMING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:15:44 | wisuda.c@jutal.com | 11-May-2026 13:13:26 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 12:56:58 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 16:45:55 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:17:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:13:40 | 22-May-2026 05:14:11 | 0 |  |  | Approver | Locate
AO-001286 | MM-ZTK-1F-ZWPX-STR-DWG-1101 | TOPSIDE - LOWER DECK PRIMARY STEEL - FRAMING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:23:32 | wisuda.c@jutal.com | 27-Jul-2026 15:48:36 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 03-Aug-2026 11:26:36 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 06:03:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 07-Aug-2026 08:37:30 | 07-Aug-2026 02:13:28 | 0 |  |  | Approver | Locate
AO-002053 | MM-ZTK-1F-ZWPX-STR-DWG-1101 | TOPSIDE - LOWER DECK PRIMARY STEEL - FRAMING PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:26:05 | wisuda.c@jutal.com | 15-Sep-2026 14:12:57 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 24-Sep-2026 13:56:05 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 26-Sep-2026 08:19:43 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 26-Sep-2026 16:20:45 | 26-Sep-2026 09:53:57 | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1102 | TOPSIDE - ELEVATION TRUSS ROW 'A' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:16:07 | wisuda.c@jutal.com | 11-May-2026 13:13:42 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 12:59:56 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 16:47:20 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:20:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:14:46 | 22-May-2026 05:15:20 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1102 | TOPSIDE - ELEVATION TRUSS ROW 'A' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:23:58 | wisuda.c@jutal.com | 27-Jul-2026 15:48:38 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 03-Aug-2026 11:28:06 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 22:03:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:29:35 | 08-Aug-2026 04:24:58 | 0 |  |  | Approver | Locate
AO-002362 | MM-ZTK-1F-ZWPX-STR-DWG-1102 | TOPSIDE - ELEVATION TRUSS ROW 'A' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 09:37:14 | wisuda.c@jutal.com | 05-Oct-2026 10:03:00 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 06-Oct-2026 12:32:28 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 22:48:06 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 11-Oct-2026 11:13:55 | 11-Oct-2026 04:32:23 | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1103 | TOPSIDE - ELEVATION TRUSS ROW 'B' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:16:48 | wisuda.c@jutal.com | 11-May-2026 13:13:44 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:01:14 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 16:47:07 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:18:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:17:32 | 22-May-2026 05:06:58 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1103 | TOPSIDE - ELEVATION TRUSS ROW 'B' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:24:26 | wisuda.c@jutal.com | 27-Jul-2026 15:48:38 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 03-Aug-2026 11:28:14 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 22:04:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:23:13 | 08-Aug-2026 04:21:17 | 0 |  |  | Approver | Locate
AO-002362 | MM-ZTK-1F-ZWPX-STR-DWG-1103 | TOPSIDE - ELEVATION TRUSS ROW 'B' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 09:37:40 | wisuda.c@jutal.com | 05-Oct-2026 10:03:01 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 06-Oct-2026 12:33:07 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 22:57:04 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 11-Oct-2026 11:13:21 | 11-Oct-2026 04:31:17 | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1104 | TOPSIDE - ELEVATION TRUSS ROW '1' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:17:17 | wisuda.c@jutal.com | 11-May-2026 13:14:01 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:02:35 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 16:49:23 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:24:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:18:34 | 22-May-2026 05:03:47 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1104 | TOPSIDE - ELEVATION TRUSS ROW '1' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:24:51 | wisuda.c@jutal.com | 27-Jul-2026 15:48:38 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 03-Aug-2026 11:28:21 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 22:54:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:30:45 | 08-Aug-2026 04:27:37 | 0 |  |  | Approver | Locate
AO-002053 | MM-ZTK-1F-ZWPX-STR-DWG-1104 | TOPSIDE - ELEVATION TRUSS ROW '1' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 20:04:34 | wisuda.c@jutal.com | 15-Sep-2026 14:13:02 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 24-Sep-2026 13:56:24 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 26-Sep-2026 08:20:12 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 26-Sep-2026 16:21:05 | 26-Sep-2026 10:05:34 | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1105 | TOPSIDE - ELEVATION TRUSS ROW '2' |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:17:41 | wisuda.c@jutal.com | 11-May-2026 13:14:14 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:03:54 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 16:49:12 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:21:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:21:27 | 22-May-2026 05:08:09 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1105 | TOPSIDE - ELEVATION TRUSS ROW '2' |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:25:17 | wisuda.c@jutal.com | 27-Jul-2026 15:48:38 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 03-Aug-2026 11:29:26 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 22:56:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:31:11 | 08-Aug-2026 04:28:53 | 0 |  |  | Approver | Locate
AO-002362 | MM-ZTK-1F-ZWPX-STR-DWG-1105 | TOPSIDE - ELEVATION TRUSS ROW '2' |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 05-Oct-2026 09:38:10 | wisuda.c@jutal.com | 05-Oct-2026 10:03:04 | Jumpol Sudjitjul | 12-Oct-2026 |  | Sompop Singhatiraj | 15-Oct-2026 | 06-Oct-2026 12:32:36 | Pornlert Wanaphattharaphan | 16-Oct-2026 | 10-Oct-2026 22:48:38 | APPR | Approved | Jumpol Sudjitjul | 19-Oct-2026 | 11-Oct-2026 11:12:48 | 11-Oct-2026 04:30:08 | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1106 | TOPSIDE - SECTIONS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:18:06 | wisuda.c@jutal.com | 11-May-2026 13:15:47 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:06:53 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 16:50:12 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:30:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:22:22 | 22-May-2026 05:11:46 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1106 | TOPSIDE - SECTIONS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:25:43 | wisuda.c@jutal.com | 27-Jul-2026 15:48:42 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 03-Aug-2026 13:01:17 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 22:59:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:31:33 | 08-Aug-2026 04:30:10 | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1118 | TOPSIDE - UPPER DECK JOINT DETAIL MARKING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:18:33 | wisuda.c@jutal.com | 11-May-2026 13:16:00 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:08:41 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 17:17:40 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:20:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:26:41 | 22-May-2026 05:09:21 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1118 | TOPSIDE - UPPER DECK JOINT DETAIL MARKING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:26:12 | wisuda.c@jutal.com | 27-Jul-2026 15:48:39 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 03-Aug-2026 14:47:01 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 22:59:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:32:20 | 08-Aug-2026 04:32:45 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1118 | TOPSIDE - UPPER DECK JOINT DETAIL MARKING PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 12-Oct-2026 11:52:53 | wisuda.c@jutal.com | 12-Oct-2026 13:17:06 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1119 | TOPSIDE - LOWER DECK JOINT DETAIL MARKING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:19:14 | wisuda.c@jutal.com | 11-May-2026 13:16:13 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:10:16 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 17:30:06 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:34:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:31:34 | 22-May-2026 05:25:14 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1119 | TOPSIDE - LOWER DECK JOINT DETAIL MARKING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:26:40 | wisuda.c@jutal.com | 27-Jul-2026 15:48:45 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 03-Aug-2026 14:49:16 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 23:00:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:22:36 | 08-Aug-2026 04:19:59 | 0 |  |  | Approver | Locate
AO-002053 | MM-ZTK-1F-ZWPX-STR-DWG-1119 | TOPSIDE - LOWER DECK JOINT DETAIL MARKING PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 20:05:02 | wisuda.c@jutal.com | 15-Sep-2026 14:12:59 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 24-Sep-2026 14:00:42 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 26-Sep-2026 08:22:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 26-Sep-2026 16:21:01 | 26-Sep-2026 10:06:50 | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1120 | TOPSIDE - MAIN JOINT DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:19:37 | wisuda.c@jutal.com | 11-May-2026 13:16:26 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:12:05 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 17:48:21 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:43:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:33:13 | 22-May-2026 05:26:30 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1120 | TOPSIDE - MAIN JOINT DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:27:07 | wisuda.c@jutal.com | 27-Jul-2026 15:51:18 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 04-Aug-2026 09:45:40 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 23:03:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:32:13 | 08-Aug-2026 04:31:26 | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1121 | TOPSIDE - MAIN JOINT DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:20:00 | wisuda.c@jutal.com | 11-May-2026 13:19:30 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:13:29 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 18:31:40 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:49:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:36:14 | 22-May-2026 05:29:00 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1121 | TOPSIDE - MAIN JOINT DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:27:32 | wisuda.c@jutal.com | 27-Jul-2026 15:51:21 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 04-Aug-2026 09:44:41 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 23:01:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:30:25 | 08-Aug-2026 04:26:17 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1121 | TOPSIDE - MAIN JOINT DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 12-Oct-2026 11:53:24 | wisuda.c@jutal.com | 12-Oct-2026 13:17:08 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1122 | TOPSIDE - MAIN JOINT DETAILS - SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:20:24 | wisuda.c@jutal.com | 11-May-2026 13:19:51 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:15:20 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 18:38:26 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:50:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:37:31 | 22-May-2026 05:57:52 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1122 | TOPSIDE - MAIN JOINT DETAILS - SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:28:01 | wisuda.c@jutal.com | 27-Jul-2026 15:51:28 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 04-Aug-2026 11:32:01 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 23:06:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:29:49 | 08-Aug-2026 04:07:10 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1122 | TOPSIDE - MAIN JOINT DETAILS - SHEET 3 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 12-Oct-2026 11:53:57 | wisuda.c@jutal.com | 12-Oct-2026 13:17:06 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1123 | TOPSIDE - MAIN JOINT DETAILS - SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:20:47 | wisuda.c@jutal.com | 11-May-2026 13:20:08 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:16:54 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 18:46:51 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:52:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:39:25 | 22-May-2026 06:01:58 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1123 | TOPSIDE - MAIN JOINT DETAILS - SHEET 4 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:28:41 | wisuda.c@jutal.com | 27-Jul-2026 15:51:17 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 04-Aug-2026 11:32:31 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 23:07:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:29:16 | 08-Aug-2026 04:05:51 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1123 | TOPSIDE - MAIN JOINT DETAILS - SHEET 4 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 12-Oct-2026 11:54:27 | wisuda.c@jutal.com | 12-Oct-2026 13:17:09 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1124 | TOPSIDE - MAIN JOINT DETAILS - SHEET 5 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:21:09 | wisuda.c@jutal.com | 11-May-2026 13:20:23 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:18:23 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 18:56:16 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:52:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:40:43 | 22-May-2026 05:52:10 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1124 | TOPSIDE - MAIN JOINT DETAILS - SHEET 5 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:29:14 | wisuda.c@jutal.com | 27-Jul-2026 15:51:27 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 04-Aug-2026 11:31:25 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 23:06:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:25:02 | 08-Aug-2026 04:00:30 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1124 | TOPSIDE - MAIN JOINT DETAILS - SHEET 5 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 12-Oct-2026 11:54:56 | wisuda.c@jutal.com | 12-Oct-2026 13:17:06 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1125 | TOPSIDE - MAIN JOINT DETAILS - SHEET 6 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:21:32 | wisuda.c@jutal.com | 11-May-2026 13:24:08 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:19:39 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 19:00:58 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:53:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:41:31 | 22-May-2026 06:05:14 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1125 | TOPSIDE - MAIN JOINT DETAILS - SHEET 6 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:29:44 | wisuda.c@jutal.com | 27-Jul-2026 15:51:27 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 04-Aug-2026 11:30:07 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 23:05:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:28:45 | 08-Aug-2026 04:04:33 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1125 | TOPSIDE - MAIN JOINT DETAILS - SHEET 6 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 12-Oct-2026 11:55:27 | wisuda.c@jutal.com | 12-Oct-2026 13:17:03 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1126 | TOPSIDE - MAIN JOINT DETAILS - SHEET 7 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:21:54 | wisuda.c@jutal.com | 11-May-2026 13:24:21 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:20:59 | Sompop Singhatiraj | 20-May-2026 | 19-May-2026 08:44:03 | Pornlert Wanaphattharaphan | 21-May-2026 | 22-May-2026 09:21:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 12:21:11 | 22-May-2026 15:56:00 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1126 | TOPSIDE - MAIN JOINT DETAILS - SHEET 7 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:30:15 | wisuda.c@jutal.com | 27-Jul-2026 15:51:25 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 05-Aug-2026 14:19:51 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 01:11:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 14:10:33 | 10-Aug-2026 07:47:24 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1126 | TOPSIDE - MAIN JOINT DETAILS - SHEET 7 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 12-Oct-2026 11:56:06 | wisuda.c@jutal.com | 12-Oct-2026 13:17:05 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1127 | TOPSIDE - MAIN JOINT DETAILS - SHEET 8 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:22:17 | wisuda.c@jutal.com | 11-May-2026 13:24:37 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:22:10 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 19:18:04 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:53:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:42:16 | 22-May-2026 06:01:30 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1127 | TOPSIDE - MAIN JOINT DETAILS - SHEET 8 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:30:46 | wisuda.c@jutal.com | 27-Jul-2026 15:51:23 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 05-Aug-2026 14:22:58 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 01:11:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 14:09:26 | 10-Aug-2026 07:45:59 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1127 | TOPSIDE - MAIN JOINT DETAILS - SHEET 8 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 12-Oct-2026 11:56:52 | wisuda.c@jutal.com | 12-Oct-2026 13:17:10 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1128 | TOPSIDE - MAIN JOINT DETAILS - SHEET 9 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:22:39 | wisuda.c@jutal.com | 11-May-2026 13:24:51 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:24:10 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 18:21:54 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:46:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:48:19 | 22-May-2026 05:56:42 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1128 | TOPSIDE - MAIN JOINT DETAILS - SHEET 9 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:31:16 | wisuda.c@jutal.com | 27-Jul-2026 15:51:26 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 05-Aug-2026 14:23:05 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 01:12:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 14:08:40 | 10-Aug-2026 07:44:37 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1128 | TOPSIDE - MAIN JOINT DETAILS - SHEET 9 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 12-Oct-2026 11:57:27 | wisuda.c@jutal.com | 12-Oct-2026 13:17:12 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1129 | TOPSIDE - MAIN JOINT DETAILS - SHEET 10 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:23:02 | wisuda.c@jutal.com | 11-May-2026 13:27:42 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:25:39 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 18:10:32 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:45:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:22:19 | 22-May-2026 05:48:48 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1129 | TOPSIDE - MAIN JOINT DETAILS - SHEET 10 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:31:44 | wisuda.c@jutal.com | 27-Jul-2026 15:51:32 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 05-Aug-2026 14:27:31 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 01:12:34 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 14:07:48 | 10-Aug-2026 07:43:15 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1129 | TOPSIDE - MAIN JOINT DETAILS - SHEET 10 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 12-Oct-2026 11:57:57 | wisuda.c@jutal.com | 12-Oct-2026 13:17:09 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1130 | TOPSIDE - MAIN JOINT DETAILS - SHEET 11 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:23:25 | wisuda.c@jutal.com | 11-May-2026 13:28:06 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:26:45 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 18:09:28 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:36:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:31:09 | 22-May-2026 05:46:20 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1130 | TOPSIDE - MAIN JOINT DETAILS - SHEET 11 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:32:17 | wisuda.c@jutal.com | 27-Jul-2026 15:51:28 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 04-Aug-2026 09:45:05 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 07-Aug-2026 23:02:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 08-Aug-2026 10:28:11 | 08-Aug-2026 04:01:49 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1130 | TOPSIDE - MAIN JOINT DETAILS - SHEET 11 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 12-Oct-2026 11:58:26 | wisuda.c@jutal.com | 12-Oct-2026 13:17:17 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1131 | TOPSIDE - MAIN JOINT DETAILS - SHEET 12 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:23:48 | wisuda.c@jutal.com | 11-May-2026 13:28:23 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:28:34 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 19:31:07 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:54:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:32:14 | 22-May-2026 06:02:03 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1131 | TOPSIDE - MAIN JOINT DETAILS - SHEET 12 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:32:48 | wisuda.c@jutal.com | 27-Jul-2026 15:51:29 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 05-Aug-2026 14:23:18 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 01:14:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 14:05:46 | 10-Aug-2026 07:41:54 | 0 |  |  | Approver | Locate
AO-002053 | MM-ZTK-1F-ZWPX-STR-DWG-1131 | TOPSIDE - MAIN JOINT DETAILS - SHEET 12 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 20:05:30 | wisuda.c@jutal.com | 15-Sep-2026 14:13:00 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 24-Sep-2026 13:57:24 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 26-Sep-2026 08:20:39 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 26-Sep-2026 16:20:36 | 26-Sep-2026 10:04:27 | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1132 | TOPSIDE - MAIN JOINT DETAILS - SHEET 13 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:24:12 | wisuda.c@jutal.com | 11-May-2026 13:21:42 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:29:40 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 20:09:06 | Pornlert Wanaphattharaphan | 21-May-2026 | 22-May-2026 00:08:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:49:07 | 22-May-2026 06:03:59 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1132 | TOPSIDE - MAIN JOINT DETAILS - SHEET 13 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:33:19 | wisuda.c@jutal.com | 27-Jul-2026 15:51:26 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 05-Aug-2026 16:15:05 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 01:16:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:50:49 | 10-Aug-2026 07:36:27 | 0 |  |  | Approver | Locate
AO-002053 | MM-ZTK-1F-ZWPX-STR-DWG-1132 | TOPSIDE - MAIN JOINT DETAILS - SHEET 13 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 20:05:56 | wisuda.c@jutal.com | 15-Sep-2026 14:13:02 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 24-Sep-2026 14:01:41 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 26-Sep-2026 08:23:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 26-Sep-2026 16:19:40 | 26-Sep-2026 10:03:18 | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1133 | TOPSIDE - MAIN JOINT DETAILS - SHEET 14 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:24:34 | wisuda.c@jutal.com | 11-May-2026 13:21:30 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:31:15 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 20:08:56 | Pornlert Wanaphattharaphan | 21-May-2026 | 22-May-2026 00:07:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:50:58 | 22-May-2026 05:54:20 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1133 | TOPSIDE - MAIN JOINT DETAILS - SHEET 14 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:33:54 | wisuda.c@jutal.com | 27-Jul-2026 15:51:32 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 05-Aug-2026 16:15:16 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 01:21:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 14:03:50 | 10-Aug-2026 07:40:29 | 0 |  |  | Approver | Locate
AO-002053 | MM-ZTK-1F-ZWPX-STR-DWG-1133 | TOPSIDE - MAIN JOINT DETAILS - SHEET 14 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 20:06:21 | wisuda.c@jutal.com | 15-Sep-2026 14:13:02 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 24-Sep-2026 14:01:32 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 26-Sep-2026 08:22:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 26-Sep-2026 16:19:10 | 26-Sep-2026 10:02:01 | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1134 | TOPSIDE - MAIN JOINT DETAILS - SHEET 15 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:24:57 | wisuda.c@jutal.com | 11-May-2026 13:21:17 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:32:53 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 20:07:20 | Pornlert Wanaphattharaphan | 21-May-2026 | 22-May-2026 00:00:37 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:51:56 | 22-May-2026 06:02:46 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1134 | TOPSIDE - MAIN JOINT DETAILS - SHEET 15 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:34:27 | wisuda.c@jutal.com | 27-Jul-2026 15:51:28 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 05-Aug-2026 16:18:50 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 01:13:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:53:28 | 10-Aug-2026 07:39:06 | 0 |  |  | Approver | Locate
AO-002053 | MM-ZTK-1F-ZWPX-STR-DWG-1134 | TOPSIDE - MAIN JOINT DETAILS - SHEET 15 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:26:35 | wisuda.c@jutal.com | 15-Sep-2026 14:12:59 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 24-Sep-2026 14:03:33 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 26-Sep-2026 08:26:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 26-Sep-2026 16:18:40 | 26-Sep-2026 09:52:51 | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1135 | TOPSIDE - MAIN JOINT DETAILS - SHEET 16 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:25:19 | wisuda.c@jutal.com | 11-May-2026 13:21:03 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:34:28 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 20:04:07 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:59:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:53:53 | 22-May-2026 06:00:15 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1135 | TOPSIDE - MAIN JOINT DETAILS - SHEET 16 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:34:55 | wisuda.c@jutal.com | 27-Jul-2026 15:51:26 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 05-Aug-2026 16:15:55 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 01:10:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:51:34 | 10-Aug-2026 07:37:45 | 0 |  |  | Approver | Locate
AO-002053 | MM-ZTK-1F-ZWPX-STR-DWG-1135 | TOPSIDE - MAIN JOINT DETAILS - SHEET 16 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 20:06:46 | wisuda.c@jutal.com | 15-Sep-2026 14:13:05 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 24-Sep-2026 14:03:24 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 26-Sep-2026 08:26:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 26-Sep-2026 16:18:13 | 26-Sep-2026 09:58:33 | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1136 | TOPSIDE - MAIN JOINT DETAILS - SHEET 17 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:25:42 | wisuda.c@jutal.com | 11-May-2026 13:18:17 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:36:02 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 19:52:33 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:58:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:36:20 | 22-May-2026 05:47:34 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1136 | TOPSIDE - MAIN JOINT DETAILS - SHEET 17 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:35:23 | wisuda.c@jutal.com | 27-Jul-2026 15:51:31 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 06-Aug-2026 15:05:49 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 01:10:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:49:52 | 10-Aug-2026 07:34:59 | 0 |  |  | Approver | Locate
AO-002053 | MM-ZTK-1F-ZWPX-STR-DWG-1136 | TOPSIDE - MAIN JOINT DETAILS - SHEET 17 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 20:07:12 | wisuda.c@jutal.com | 15-Sep-2026 14:13:06 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 24-Sep-2026 13:58:56 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 26-Sep-2026 08:21:09 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 26-Sep-2026 16:17:51 | 26-Sep-2026 09:57:18 | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1137 | TOPSIDE - MAIN JOINT DETAILS - SHEET 18 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:26:06 | wisuda.c@jutal.com | 11-May-2026 13:18:02 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:38:12 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 19:50:10 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:58:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:37:37 | 22-May-2026 05:51:00 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1137 | TOPSIDE - MAIN JOINT DETAILS - SHEET 18 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:35:50 | wisuda.c@jutal.com | 27-Jul-2026 15:51:35 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 06-Aug-2026 15:05:59 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 01:09:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:48:24 | 10-Aug-2026 07:33:36 | 0 |  |  | Approver | Locate
AO-002053 | MM-ZTK-1F-ZWPX-STR-DWG-1137 | TOPSIDE - MAIN JOINT DETAILS - SHEET 18 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 20:07:38 | wisuda.c@jutal.com | 15-Sep-2026 14:13:03 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 24-Sep-2026 14:36:35 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 26-Sep-2026 08:37:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 26-Sep-2026 16:17:24 | 26-Sep-2026 09:55:09 | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1138 | TOPSIDE - MAIN JOINT DETAILS - SHEET 19 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:26:29 | wisuda.c@jutal.com | 11-May-2026 13:17:42 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:39:29 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 19:35:35 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:56:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:56:38 | 22-May-2026 05:59:05 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1138 | TOPSIDE - MAIN JOINT DETAILS - SHEET 19 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:36:15 | wisuda.c@jutal.com | 27-Jul-2026 15:51:34 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 06-Aug-2026 15:06:09 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 01:08:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:46:59 | 10-Aug-2026 07:32:12 | 0 |  |  | Approver | Locate
AO-002053 | MM-ZTK-1F-ZWPX-STR-DWG-1138 | TOPSIDE - MAIN JOINT DETAILS - SHEET 19 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 19:27:15 | wisuda.c@jutal.com | 15-Sep-2026 14:13:07 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 24-Sep-2026 14:34:22 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 26-Sep-2026 08:36:44 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 26-Sep-2026 16:16:24 | 26-Sep-2026 09:51:38 | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1139 | TOPSIDE - MAIN JOINT DETAILS - SHEET 20 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 12:26:55 | wisuda.c@jutal.com | 11-May-2026 13:17:25 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:40:49 | Sompop Singhatiraj | 20-May-2026 | 18-May-2026 19:42:02 | Pornlert Wanaphattharaphan | 21-May-2026 | 21-May-2026 23:57:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 11:00:05 | 22-May-2026 05:55:33 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1139 | TOPSIDE - MAIN JOINT DETAILS - SHEET 20 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:36:41 | wisuda.c@jutal.com | 27-Jul-2026 15:51:31 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 06-Aug-2026 15:06:20 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 01:08:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:42:39 | 10-Aug-2026 07:29:24 | 0 |  |  | Approver | Locate
AO-002053 | MM-ZTK-1F-ZWPX-STR-DWG-1139 | TOPSIDE - MAIN JOINT DETAILS - SHEET 20 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 20:08:03 | wisuda.c@jutal.com | 15-Sep-2026 14:13:07 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 24-Sep-2026 14:37:49 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 26-Sep-2026 08:39:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 26-Sep-2026 16:13:21 | 26-Sep-2026 09:42:33 | 0 |  |  | Approver | Locate
AO-000365 | MM-ZTK-1F-ZWPX-STR-DWG-1140 | TOPSIDE - MAIN JOINT DETAILS - SHEET 21 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 11-May-2026 11:45:09 | wisuda.c@jutal.com | 11-May-2026 11:48:12 | Jumpol Sudjitjul | 18-May-2026 | 17-May-2026 13:42:08 | Sompop Singhatiraj | 20-May-2026 | 19-May-2026 19:15:25 | Pornlert Wanaphattharaphan | 21-May-2026 | 22-May-2026 00:15:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 22-May-2026 | 22-May-2026 10:39:17 | 22-May-2026 05:27:43 | 0 |  |  | Approver | Locate
AO-001284 | MM-ZTK-1F-ZWPX-STR-DWG-1140 | TOPSIDE - MAIN JOINT DETAILS - SHEET 21 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 09:37:11 | wisuda.c@jutal.com | 27-Jul-2026 15:51:35 | Jumpol Sudjitjul | 05-Aug-2026 |  | Sompop Singhatiraj | 07-Aug-2026 | 06-Aug-2026 15:06:30 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 10-Aug-2026 01:07:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 10-Aug-2026 13:35:03 | 10-Aug-2026 07:28:01 | 0 |  |  | Approver | Locate
AO-002053 | MM-ZTK-1F-ZWPX-STR-DWG-1140 | TOPSIDE - MAIN JOINT DETAILS - SHEET 21 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 14-Sep-2026 20:08:30 | wisuda.c@jutal.com | 15-Sep-2026 14:13:07 | Jumpol Sudjitjul | 22-Sep-2026 |  | Sompop Singhatiraj | 24-Sep-2026 | 25-Sep-2026 10:05:44 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 26-Sep-2026 05:58:15 | APPR | Approved | Jumpol Sudjitjul | 28-Sep-2026 | 26-Sep-2026 16:12:29 | 26-Sep-2026 09:41:19 | 0 |  |  | Approver | Locate
AO-001699 | MM-ZTK-1F-ZWPX-STR-DWG-1141 | TOPSIDE - MAIN JOINT DETAILS - SHEET 22 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 25-Aug-2026 11:01:41 | wisuda.c@jutal.com | 25-Aug-2026 13:01:58 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 09-Sep-2026 08:54:49 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 09-Sep-2026 22:55:34 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 07-Sep-2026 | 10-Sep-2026 09:10:21 | 10-Sep-2026 02:31:48 | 0 |  |  | Approver | Locate
AO-000618 | MM-ZTK-1F-ZWPX-STR-DWG-1200 | TOPSIDE - UPPER DECK SECONDARY STEEL - FRAMING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 17:26:51 | wisuda.c@jutal.com | 28-May-2026 18:06:39 | Jumpol Sudjitjul | 09-Jun-2026 |  | Sompop Singhatiraj | 11-Jun-2026 | 31-May-2026 16:42:23 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 31-May-2026 21:54:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 31-May-2026 22:07:07 | 31-May-2026 16:00:06 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1200 | TOPSIDE - UPPER DECK SECONDARY STEEL - FRAMING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 10:53:18 | wisuda.c@jutal.com | 24-Aug-2026 20:32:57 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 04-Sep-2026 13:30:45 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 05-Sep-2026 18:13:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 05-Sep-2026 18:33:51 | 05-Sep-2026 12:19:02 | 0 |  |  | Approver | Locate
AO-000618 | MM-ZTK-1F-ZWPX-STR-DWG-1201 | TOPSIDE - LOWER DECK SECONDARY STEEL - FRAMING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 17:27:19 | wisuda.c@jutal.com | 28-May-2026 18:06:16 | Jumpol Sudjitjul | 09-Jun-2026 |  | Sompop Singhatiraj | 11-Jun-2026 | 31-May-2026 16:41:20 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 31-May-2026 21:56:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 31-May-2026 22:07:34 | 31-May-2026 15:51:33 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1201 | TOPSIDE - LOWER DECK SECONDARY STEEL - FRAMING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:54:29 | wisuda.c@jutal.com | 24-Aug-2026 20:33:02 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 04-Sep-2026 13:32:33 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 05-Sep-2026 18:13:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 05-Sep-2026 18:34:53 | 05-Sep-2026 12:20:41 | 0 |  |  | Approver | Locate
AO-000506 | MM-ZTK-1F-ZWPX-STR-DWG-1211 | TOPSIDES - MEZZANINE DECK FRAMING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 11:07:00 | wisuda.c@jutal.com | 19-May-2026 13:00:00 | Jumpol Sudjitjul | 26-May-2026 |  | Sompop Singhatiraj | 28-May-2026 | 21-May-2026 15:04:30 | Pornlert Wanaphattharaphan | 29-May-2026 | 22-May-2026 00:39:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 22-May-2026 10:40:46 | 22-May-2026 05:33:59 | 0 |  |  | Approver | Locate
AO-001367 | MM-ZTK-1F-ZWPX-STR-DWG-1211 | TOPSIDES - MEZZANINE DECK FRAMING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Aug-2026 10:10:18 | wisuda.c@jutal.com | 03-Aug-2026 13:05:42 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 07-Aug-2026 15:27:19 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 10-Aug-2026 01:06:58 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 13:42:13 | 10-Aug-2026 08:23:42 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1211 | TOPSIDES - MEZZANINE DECK FRAMING PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 12-Oct-2026 11:58:57 | wisuda.c@jutal.com | 12-Oct-2026 13:24:17 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000506 | MM-ZTK-1F-ZWPX-STR-DWG-1212 | TOPSIDES - MEZZANINE DECK FRAMING SECTIONS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 11:07:32 | wisuda.c@jutal.com | 19-May-2026 12:59:59 | Jumpol Sudjitjul | 26-May-2026 |  | Sompop Singhatiraj | 28-May-2026 | 21-May-2026 15:04:44 | Pornlert Wanaphattharaphan | 29-May-2026 | 22-May-2026 00:43:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 22-May-2026 11:01:47 | 22-May-2026 05:24:03 | 0 |  |  | Approver | Locate
AO-001367 | MM-ZTK-1F-ZWPX-STR-DWG-1212 | TOPSIDES - MEZZANINE DECK FRAMING SECTIONS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Aug-2026 10:10:54 | wisuda.c@jutal.com | 03-Aug-2026 13:05:40 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 07-Aug-2026 15:25:43 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 10-Aug-2026 01:06:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 13:41:39 | 10-Aug-2026 08:22:16 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1212 | TOPSIDES - MEZZANINE DECK FRAMING SECTIONS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Oct-2026 11:59:29 | wisuda.c@jutal.com | 12-Oct-2026 13:24:24 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 | 14-Oct-2026 12:47:20 | Pornlert Wanaphattharaphan | 26-Oct-2026 | 15-Oct-2026 22:41:48 | APPR | Approved | Jumpol Sudjitjul | 27-Oct-2026 | 16-Oct-2026 15:30:47 | 16-Oct-2026 09:08:04 | 0 |  |  | Approver | Locate
AO-000506 | MM-ZTK-1F-ZWPX-STR-DWG-1213 | TOPSIDES - MEZZANINE DECK FRAMING SECTIONS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 11:08:08 | wisuda.c@jutal.com | 19-May-2026 13:00:00 | Jumpol Sudjitjul | 26-May-2026 |  | Sompop Singhatiraj | 28-May-2026 | 21-May-2026 15:06:08 | Pornlert Wanaphattharaphan | 29-May-2026 | 22-May-2026 00:45:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 22-May-2026 11:03:57 | 22-May-2026 05:19:49 | 0 |  |  | Approver | Locate
AO-001367 | MM-ZTK-1F-ZWPX-STR-DWG-1213 | TOPSIDES - MEZZANINE DECK FRAMING SECTIONS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Aug-2026 10:11:22 | wisuda.c@jutal.com | 03-Aug-2026 13:05:37 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 07-Aug-2026 15:25:54 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 10-Aug-2026 01:06:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 13:40:56 | 10-Aug-2026 08:20:52 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1213 | TOPSIDES - MEZZANINE DECK FRAMING SECTIONS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | In Review | IFA | Issued for Approval |  | 12-Oct-2026 12:00:01 | wisuda.c@jutal.com | 12-Oct-2026 13:24:24 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000506 | MM-ZTK-1F-ZWPX-STR-DWG-1214 | TOPSIDES - MEZZANINE DECK JOINT DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 11:08:39 | wisuda.c@jutal.com | 19-May-2026 12:59:58 | Jumpol Sudjitjul | 26-May-2026 |  | Sompop Singhatiraj | 28-May-2026 | 21-May-2026 15:05:58 | Pornlert Wanaphattharaphan | 29-May-2026 | 22-May-2026 00:44:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 22-May-2026 11:06:43 | 22-May-2026 05:16:35 | 0 |  |  | Approver | Locate
AO-001367 | MM-ZTK-1F-ZWPX-STR-DWG-1214 | TOPSIDES - MEZZANINE DECK JOINT DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Aug-2026 10:11:55 | wisuda.c@jutal.com | 03-Aug-2026 13:05:38 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 07-Aug-2026 15:26:02 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 10-Aug-2026 01:05:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 13:32:53 | 10-Aug-2026 08:19:32 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1214 | TOPSIDES - MEZZANINE DECK JOINT DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Oct-2026 12:00:31 | wisuda.c@jutal.com | 12-Oct-2026 13:24:23 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 | 14-Oct-2026 15:52:43 | Pornlert Wanaphattharaphan | 26-Oct-2026 | 15-Oct-2026 23:00:08 | APPR | Approved | Jumpol Sudjitjul | 27-Oct-2026 | 16-Oct-2026 15:12:39 | 16-Oct-2026 08:50:29 | 0 |  |  | Approver | Locate
AO-000506 | MM-ZTK-1F-ZWPX-STR-DWG-1215 | TOPSIDES - MEZZANINE DECK JOINT DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 11:09:18 | wisuda.c@jutal.com | 19-May-2026 13:00:06 | Jumpol Sudjitjul | 26-May-2026 |  | Sompop Singhatiraj | 28-May-2026 | 21-May-2026 15:07:19 | Pornlert Wanaphattharaphan | 29-May-2026 | 22-May-2026 00:46:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 22-May-2026 10:56:46 | 22-May-2026 05:31:33 | 0 |  |  | Approver | Locate
AO-001367 | MM-ZTK-1F-ZWPX-STR-DWG-1215 | TOPSIDES - MEZZANINE DECK JOINT DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Aug-2026 10:12:36 | wisuda.c@jutal.com | 03-Aug-2026 13:05:46 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 07-Aug-2026 15:26:12 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 10-Aug-2026 01:04:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 10:52:25 | 10-Aug-2026 05:01:49 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1215 | TOPSIDES - MEZZANINE DECK JOINT DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Oct-2026 12:01:01 | wisuda.c@jutal.com | 12-Oct-2026 13:24:24 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 | 14-Oct-2026 15:52:59 | Pornlert Wanaphattharaphan | 26-Oct-2026 | 15-Oct-2026 23:00:39 | APPR | Approved | Jumpol Sudjitjul | 27-Oct-2026 | 16-Oct-2026 15:29:09 | 16-Oct-2026 09:06:26 | 0 |  |  | Approver | Locate
AO-000506 | MM-ZTK-1F-ZWPX-STR-DWG-1216 | TOPSIDES - MEZZANINE DECK JOINT DETAILS - SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 11:09:59 | wisuda.c@jutal.com | 19-May-2026 13:00:03 | Jumpol Sudjitjul | 26-May-2026 |  | Sompop Singhatiraj | 28-May-2026 | 21-May-2026 15:07:29 | Pornlert Wanaphattharaphan | 29-May-2026 | 22-May-2026 00:47:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 22-May-2026 11:13:27 | 22-May-2026 05:32:45 | 0 |  |  | Approver | Locate
AO-001367 | MM-ZTK-1F-ZWPX-STR-DWG-1216 | TOPSIDES - MEZZANINE DECK JOINT DETAILS - SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Aug-2026 10:13:31 | wisuda.c@jutal.com | 03-Aug-2026 13:05:38 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 07-Aug-2026 15:26:19 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 10-Aug-2026 01:04:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 10:21:53 | 10-Aug-2026 04:44:11 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1216 | TOPSIDES - MEZZANINE DECK JOINT DETAILS - SHEET 3 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Oct-2026 12:01:29 | wisuda.c@jutal.com | 12-Oct-2026 13:24:25 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 | 14-Oct-2026 15:51:42 | Pornlert Wanaphattharaphan | 26-Oct-2026 | 15-Oct-2026 22:59:39 | APPR | Approved | Jumpol Sudjitjul | 27-Oct-2026 | 16-Oct-2026 15:28:40 | 16-Oct-2026 09:04:57 | 0 |  |  | Approver | Locate
AO-000506 | MM-ZTK-1F-ZWPX-STR-DWG-1221 | TOPSIDES - SUMP DECK - FRAMING PLAN AT TOS EL(+) 14700 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 11:10:33 | wisuda.c@jutal.com | 19-May-2026 13:02:54 | Jumpol Sudjitjul | 26-May-2026 |  | Sompop Singhatiraj | 28-May-2026 | 21-May-2026 15:08:49 | Pornlert Wanaphattharaphan | 29-May-2026 | 22-May-2026 00:54:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 22-May-2026 10:41:59 | 22-May-2026 05:30:13 | 0 |  |  | Approver | Locate
AO-001367 | MM-ZTK-1F-ZWPX-STR-DWG-1221 | TOPSIDES - SUMP DECK - FRAMING PLAN AT TOS EL(+) 14700 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Aug-2026 10:14:16 | wisuda.c@jutal.com | 03-Aug-2026 13:06:50 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 09-Aug-2026 10:43:17 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 10-Aug-2026 01:03:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 10:22:38 | 10-Aug-2026 04:45:44 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWPX-STR-DWG-1221 | TOPSIDES - SUMP DECK - FRAMING PLAN AT TOS EL(+) 14700 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 10:30:24 | wisuda.c@jutal.com | 28-Sep-2026 11:06:48 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 10:13:08 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 29-Sep-2026 23:58:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 15:43:57 | 30-Sep-2026 09:41:24 | 0 |  |  | Approver | Locate
AO-000506 | MM-ZTK-1F-ZWPX-STR-DWG-1222 | TOPSIDES - SUMP DECK SECTIONS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 10:08:45 | wisuda.c@jutal.com | 19-May-2026 13:02:58 | Jumpol Sudjitjul | 26-May-2026 |  | Sompop Singhatiraj | 28-May-2026 | 21-May-2026 15:08:57 | Pornlert Wanaphattharaphan | 29-May-2026 | 22-May-2026 00:56:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 22-May-2026 12:15:13 | 22-May-2026 15:51:06 | 0 |  |  | Approver | Locate
AO-001367 | MM-ZTK-1F-ZWPX-STR-DWG-1222 | TOPSIDES - SUMP DECK SECTIONS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Aug-2026 10:15:01 | wisuda.c@jutal.com | 03-Aug-2026 13:06:50 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 09-Aug-2026 10:46:22 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 10-Aug-2026 01:03:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 10:20:36 | 10-Aug-2026 04:42:33 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWPX-STR-DWG-1222 | TOPSIDES - SUMP DECK SECTIONS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 10:30:53 | wisuda.c@jutal.com | 28-Sep-2026 11:07:01 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 10:16:02 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:02:53 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 15:43:24 | 30-Sep-2026 09:39:05 | 0 |  |  | Approver | Locate
AO-000506 | MM-ZTK-1F-ZWPX-STR-DWG-1223 | TOPSIDES - SUMP DECK SECTIONS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 10:09:16 | wisuda.c@jutal.com | 19-May-2026 13:02:52 | Jumpol Sudjitjul | 26-May-2026 |  | Sompop Singhatiraj | 28-May-2026 | 21-May-2026 15:10:25 | Pornlert Wanaphattharaphan | 29-May-2026 | 22-May-2026 00:56:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 22-May-2026 10:58:42 | 22-May-2026 06:15:54 | 0 |  |  | Approver | Locate
AO-001367 | MM-ZTK-1F-ZWPX-STR-DWG-1223 | TOPSIDES - SUMP DECK SECTIONS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Aug-2026 10:16:02 | wisuda.c@jutal.com | 03-Aug-2026 13:06:51 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 16-Aug-2026 08:52:35 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 16-Aug-2026 23:20:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 17-Aug-2026 14:14:35 | 17-Aug-2026 08:57:41 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWPX-STR-DWG-1223 | TOPSIDES - SUMP DECK SECTIONS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 11:18:23 | wisuda.c@jutal.com | 28-Sep-2026 11:23:40 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 10:16:05 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:02:21 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 15:42:30 | 30-Sep-2026 09:25:01 | 0 |  |  | Approver | Locate
AO-000506 | MM-ZTK-1F-ZWPX-STR-DWG-1224 | TOPSIDES - SUMP DECK JOINT DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 10:09:58 | wisuda.c@jutal.com | 19-May-2026 13:02:53 | Jumpol Sudjitjul | 26-May-2026 |  | Sompop Singhatiraj | 28-May-2026 | 21-May-2026 15:10:35 | Pornlert Wanaphattharaphan | 29-May-2026 | 22-May-2026 00:57:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 22-May-2026 12:15:59 | 22-May-2026 15:52:19 | 0 |  |  | Approver | Locate
AO-001367 | MM-ZTK-1F-ZWPX-STR-DWG-1224 | TOPSIDES - SUMP DECK JOINT DETAILS SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Aug-2026 10:16:53 | wisuda.c@jutal.com | 03-Aug-2026 13:06:51 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 09-Aug-2026 10:44:57 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 10-Aug-2026 01:02:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 10:15:08 | 10-Aug-2026 04:41:03 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWPX-STR-DWG-1224 | TOPSIDES - SUMP DECK JOINT DETAILS SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 10:31:34 | wisuda.c@jutal.com | 28-Sep-2026 11:07:16 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 10:15:28 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:00:46 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 15:41:55 | 30-Sep-2026 09:36:42 | 0 |  |  | Approver | Locate
AO-000506 | MM-ZTK-1F-ZWPX-STR-DWG-1225 | TOPSIDES - SUMP DECK JOINT DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 10:10:34 | wisuda.c@jutal.com | 19-May-2026 13:02:55 | Jumpol Sudjitjul | 26-May-2026 |  | Sompop Singhatiraj | 28-May-2026 | 21-May-2026 15:11:50 | Pornlert Wanaphattharaphan | 29-May-2026 | 22-May-2026 00:58:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 22-May-2026 12:17:07 | 22-May-2026 15:53:32 | 0 |  |  | Approver | Locate
AO-001367 | MM-ZTK-1F-ZWPX-STR-DWG-1225 | TOPSIDES - SUMP DECK JOINT DETAILS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Aug-2026 10:17:25 | wisuda.c@jutal.com | 03-Aug-2026 13:06:52 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 09-Aug-2026 10:43:44 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 10-Aug-2026 01:02:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 10:14:12 | 10-Aug-2026 04:39:22 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWPX-STR-DWG-1225 | TOPSIDES - SUMP DECK JOINT DETAILS SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 10:32:02 | wisuda.c@jutal.com | 28-Sep-2026 11:07:28 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 10:15:38 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:01:12 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 15:41:22 | 30-Sep-2026 09:35:34 | 0 |  |  | Approver | Locate
AO-000506 | MM-ZTK-1F-ZWPX-STR-DWG-1226 | TOPSIDES - SUMP DECK JOINT DETAILS SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 19-May-2026 10:11:05 | wisuda.c@jutal.com | 19-May-2026 13:02:50 | Jumpol Sudjitjul | 26-May-2026 |  | Sompop Singhatiraj | 28-May-2026 | 21-May-2026 15:12:00 | Pornlert Wanaphattharaphan | 29-May-2026 | 22-May-2026 01:02:47 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Jun-2026 | 22-May-2026 12:18:19 | 22-May-2026 15:54:48 | 0 |  |  | Approver | Locate
AO-001367 | MM-ZTK-1F-ZWPX-STR-DWG-1226 | TOPSIDES - SUMP DECK JOINT DETAILS SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Aug-2026 10:17:55 | wisuda.c@jutal.com | 03-Aug-2026 13:06:53 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 07-Aug-2026 13:24:01 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 10-Aug-2026 01:01:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 10:13:22 | 10-Aug-2026 04:37:58 | 0 |  |  | Approver | Locate
AO-002300 | MM-ZTK-1F-ZWPX-STR-DWG-1226 | TOPSIDES - SUMP DECK JOINT DETAILS SHEET 3 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 09:51:00 | wisuda.c@jutal.com | 28-Sep-2026 10:07:51 | Jumpol Sudjitjul | 05-Oct-2026 |  | Sompop Singhatiraj | 07-Oct-2026 | 29-Sep-2026 10:15:43 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 30-Sep-2026 00:01:46 | APPR | Approved | Jumpol Sudjitjul | 09-Oct-2026 | 30-Sep-2026 15:40:57 | 30-Sep-2026 10:17:24 | 0 |  |  | Approver | Locate
AO-000937 | MM-ZTK-1F-ZWPX-STR-DWG-1231 | TOPSIDES - CASING SLOT ARRANGEMENT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 19:03:14 | wisuda.c@jutal.com | 27-Jun-2026 19:15:41 | Jumpol Sudjitjul | 06-Jul-2026 |  | Sompop Singhatiraj | 08-Jul-2026 | 28-Jun-2026 10:14:34 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 29-Jun-2026 01:33:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 29-Jun-2026 21:13:51 | 29-Jun-2026 14:58:03 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1231 | TOPSIDES - CASING SLOT ARRANGEMENT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 10:53:51 | wisuda.c@jutal.com | 24-Aug-2026 20:33:01 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 26-Aug-2026 14:21:32 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 18:29:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 21:24:58 | 30-Aug-2026 14:58:01 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1231 | TOPSIDES - CASING SLOT ARRANGEMENT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Oct-2026 12:01:59 | wisuda.c@jutal.com | 12-Oct-2026 13:24:25 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 | 14-Oct-2026 09:39:48 | Pornlert Wanaphattharaphan | 26-Oct-2026 | 15-Oct-2026 22:33:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Oct-2026 | 16-Oct-2026 15:27:46 | 16-Oct-2026 09:03:30 | 0 |  |  | Approver | Locate
AO-000937 | MM-ZTK-1F-ZWPX-STR-DWG-1232 | TOPSIDES - UNIHEAD SPACER ARRANGEMENT AND DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 19:04:07 | wisuda.c@jutal.com | 27-Jun-2026 19:14:27 | Jumpol Sudjitjul | 06-Jul-2026 |  | Sompop Singhatiraj | 08-Jul-2026 | 28-Jun-2026 10:16:18 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 29-Jun-2026 01:39:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 29-Jun-2026 21:11:06 | 29-Jun-2026 14:56:39 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1232 | TOPSIDES - UNIHEAD SPACER ARRANGEMENT AND DETAILS SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:54:59 | wisuda.c@jutal.com | 24-Aug-2026 20:32:58 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 26-Aug-2026 14:27:06 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 18:34:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 21:25:37 | 30-Aug-2026 14:54:25 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1232 | TOPSIDES - UNIHEAD SPACER ARRANGEMENT AND DETAILS SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Oct-2026 12:02:26 | wisuda.c@jutal.com | 12-Oct-2026 13:24:28 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 | 14-Oct-2026 09:41:37 | Pornlert Wanaphattharaphan | 26-Oct-2026 | 15-Oct-2026 22:34:09 | APPR | Approved | Jumpol Sudjitjul | 27-Oct-2026 | 16-Oct-2026 15:26:00 | 16-Oct-2026 09:02:10 | 0 |  |  | Approver | Locate
AO-000618 | MM-ZTK-1F-ZWPX-STR-DWG-1241 | TOPSIDE - VENT BOOM PLAN AND ELEVATION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 17:28:00 | wisuda.c@jutal.com | 28-May-2026 20:51:40 | Jumpol Sudjitjul | 09-Jun-2026 |  | Sompop Singhatiraj | 11-Jun-2026 | 29-May-2026 17:57:14 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 31-May-2026 21:24:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 31-May-2026 22:08:04 | 31-May-2026 15:52:48 | 0 |  |  | Approver | Locate
AO-001545 | MM-ZTK-1F-ZWPX-STR-DWG-1241 | TOPSIDE - VENT BOOM PLAN AND ELEVATION |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:31:37 | wisuda.c@jutal.com | 17-Aug-2026 15:23:28 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 24-Aug-2026 15:34:30 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 21:32:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 17:00:54 | 30-Aug-2026 11:04:38 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1241 | TOPSIDE - VENT BOOM PLAN AND ELEVATION |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Oct-2026 12:02:58 | wisuda.c@jutal.com | 12-Oct-2026 13:28:17 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 | 14-Oct-2026 12:21:56 | Pornlert Wanaphattharaphan | 26-Oct-2026 | 15-Oct-2026 22:40:33 | APPR | Approved | Jumpol Sudjitjul | 27-Oct-2026 | 16-Oct-2026 15:25:23 | 16-Oct-2026 09:26:59 | 0 |  |  | Approver | Locate
AO-000618 | MM-ZTK-1F-ZWPX-STR-DWG-1242 | TOPSIDE - VENT BOOM SECTIONS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 18:05:01 | wisuda.c@jutal.com | 28-May-2026 20:54:16 | Jumpol Sudjitjul | 09-Jun-2026 |  | Sompop Singhatiraj | 11-Jun-2026 | 29-May-2026 18:00:58 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 31-May-2026 21:34:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 31-May-2026 22:08:36 | 31-May-2026 15:54:07 | 0 |  |  | Approver | Locate
AO-001545 | MM-ZTK-1F-ZWPX-STR-DWG-1242 | TOPSIDE - VENT BOOM SECTIONS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:32:18 | wisuda.c@jutal.com | 17-Aug-2026 15:23:29 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 24-Aug-2026 15:34:19 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 21:31:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 17:04:37 | 30-Aug-2026 11:11:05 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1242 | TOPSIDE - VENT BOOM SECTIONS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Oct-2026 12:03:26 | wisuda.c@jutal.com | 12-Oct-2026 13:28:15 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 | 14-Oct-2026 12:21:42 | Pornlert Wanaphattharaphan | 26-Oct-2026 | 15-Oct-2026 22:39:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Oct-2026 | 16-Oct-2026 15:22:05 | 16-Oct-2026 08:53:08 | 0 |  |  | Approver | Locate
AO-000618 | MM-ZTK-1F-ZWPX-STR-DWG-1243 | TOPSIDE - VENT BOOM WALKWAY PLAN AND SECTIONS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 18:05:26 | wisuda.c@jutal.com | 28-May-2026 20:40:31 | Jumpol Sudjitjul | 09-Jun-2026 |  | Sompop Singhatiraj | 11-Jun-2026 | 29-May-2026 18:00:50 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 31-May-2026 21:29:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 31-May-2026 22:09:03 | 31-May-2026 15:55:23 | 0 |  |  | Approver | Locate
AO-001545 | MM-ZTK-1F-ZWPX-STR-DWG-1243 | TOPSIDE - VENT BOOM WALKWAY PLAN AND SECTIONS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:32:51 | wisuda.c@jutal.com | 17-Aug-2026 15:23:31 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 24-Aug-2026 15:36:01 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 21:33:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 17:05:23 | 30-Aug-2026 11:12:20 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1243 | TOPSIDE - VENT BOOM WALKWAY PLAN AND SECTIONS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Oct-2026 12:03:55 | wisuda.c@jutal.com | 12-Oct-2026 13:28:16 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 | 14-Oct-2026 12:20:31 | Pornlert Wanaphattharaphan | 26-Oct-2026 | 15-Oct-2026 22:39:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Oct-2026 | 16-Oct-2026 15:24:35 | 16-Oct-2026 08:58:15 | 0 |  |  | Approver | Locate
AO-000618 | MM-ZTK-1F-ZWPX-STR-DWG-1244 | TOPSIDE - VENT BOOM WALKWAY SECTIONS AND DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 17:28:35 | wisuda.c@jutal.com | 28-May-2026 20:40:48 | Jumpol Sudjitjul | 09-Jun-2026 |  | Sompop Singhatiraj | 11-Jun-2026 | 01-Jun-2026 14:38:54 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 02-Jun-2026 22:17:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 03-Jun-2026 09:13:48 | 03-Jun-2026 02:44:35 | 0 |  |  | Approver | Locate
AO-001545 | MM-ZTK-1F-ZWPX-STR-DWG-1244 | TOPSIDE - VENT BOOM WALKWAY SECTIONS AND DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:33:26 | wisuda.c@jutal.com | 17-Aug-2026 15:23:29 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 24-Aug-2026 15:35:52 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 21:32:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 17:02:42 | 30-Aug-2026 11:05:52 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1244 | TOPSIDE - VENT BOOM WALKWAY SECTIONS AND DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Oct-2026 12:04:21 | wisuda.c@jutal.com | 12-Oct-2026 13:28:26 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 | 14-Oct-2026 12:19:15 | Pornlert Wanaphattharaphan | 26-Oct-2026 | 15-Oct-2026 22:35:41 | APPR | Approved | Jumpol Sudjitjul | 27-Oct-2026 | 16-Oct-2026 15:23:41 | 16-Oct-2026 08:56:56 | 0 |  |  | Approver | Locate
AO-000618 | MM-ZTK-1F-ZWPX-STR-DWG-1245 | TOPSIDE - VENT BOOM WALKWAY SECTIONS AND DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 17:29:06 | wisuda.c@jutal.com | 28-May-2026 20:41:02 | Jumpol Sudjitjul | 09-Jun-2026 |  | Sompop Singhatiraj | 11-Jun-2026 | 29-May-2026 18:02:50 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 31-May-2026 21:39:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 31-May-2026 22:09:27 | 31-May-2026 15:58:49 | 0 |  |  | Approver | Locate
AO-001545 | MM-ZTK-1F-ZWPX-STR-DWG-1245 | TOPSIDE - VENT BOOM WALKWAY SECTIONS AND DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:34:00 | wisuda.c@jutal.com | 17-Aug-2026 15:23:33 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 24-Aug-2026 15:37:32 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 21:34:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 17:07:30 | 30-Aug-2026 11:13:35 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1245 | TOPSIDE - VENT BOOM WALKWAY SECTIONS AND DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Oct-2026 12:04:47 | wisuda.c@jutal.com | 12-Oct-2026 13:28:19 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 | 14-Oct-2026 12:19:25 | Pornlert Wanaphattharaphan | 26-Oct-2026 | 15-Oct-2026 22:36:27 | APPR | Approved | Jumpol Sudjitjul | 27-Oct-2026 | 16-Oct-2026 15:23:09 | 16-Oct-2026 08:55:41 | 0 |  |  | Approver | Locate
AO-000710 | MM-ZTK-1F-ZWPX-STR-DWG-1246 | TOPSIDES - SOLAR PANEL SUPPORT DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 09:24:17 | wisuda.c@jutal.com | 08-Jun-2026 16:34:54 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 12-Jun-2026 16:45:51 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 13-Jun-2026 00:50:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 13-Jun-2026 06:59:52 | 13-Jun-2026 00:27:35 | 0 |  |  | Approver | Locate
AO-001545 | MM-ZTK-1F-ZWPX-STR-DWG-1246 | TOPSIDES - SOLAR PANEL SUPPORT DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:34:39 | wisuda.c@jutal.com | 17-Aug-2026 15:23:36 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 24-Aug-2026 14:30:38 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 21:26:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 17:03:38 | 30-Aug-2026 11:07:06 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1246 | TOPSIDES - SOLAR PANEL SUPPORT DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Oct-2026 12:05:15 | wisuda.c@jutal.com | 12-Oct-2026 13:28:14 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 | 14-Oct-2026 10:14:58 | Pornlert Wanaphattharaphan | 26-Oct-2026 | 15-Oct-2026 22:34:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Oct-2026 | 16-Oct-2026 15:22:33 | 16-Oct-2026 08:54:29 | 0 |  |  | Approver | Locate
AO-000710 | MM-ZTK-1F-ZWPX-STR-DWG-1247 | TOPSIDES - SOLAR PANEL SECTIONS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 09:24:41 | wisuda.c@jutal.com | 08-Jun-2026 16:35:17 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 15-Jun-2026 14:16:42 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 18-Jun-2026 10:12:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 10:16:19 | 18-Jun-2026 03:43:49 | 0 |  |  | Approver | Locate
AO-001545 | MM-ZTK-1F-ZWPX-STR-DWG-1247 | TOPSIDES - SOLAR PANEL SECTIONS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:35:13 | wisuda.c@jutal.com | 17-Aug-2026 15:23:40 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 24-Aug-2026 14:31:54 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 21:30:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 17:08:47 | 30-Aug-2026 11:14:48 | 0 |  |  | Approver | Locate
AO-002475 | MM-ZTK-1F-ZWPX-STR-DWG-1247 | TOPSIDES - SOLAR PANEL SECTIONS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 12-Oct-2026 12:05:41 | wisuda.c@jutal.com | 12-Oct-2026 13:28:24 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 | 14-Oct-2026 10:15:47 | Pornlert Wanaphattharaphan | 26-Oct-2026 | 15-Oct-2026 22:35:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 27-Oct-2026 | 16-Oct-2026 11:49:33 | 16-Oct-2026 05:36:46 | 0 |  |  | Approver | Locate
AO-000937 | MM-ZTK-1F-ZWPX-STR-DWG-1300 | TOPSIDES - UPPER DECK FLOORING AND HANDRAIL - LAYOUT PLAN AT TOS EL(+) 24810 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 19:04:43 | wisuda.c@jutal.com | 27-Jun-2026 19:12:51 | Jumpol Sudjitjul | 06-Jul-2026 |  | Sompop Singhatiraj | 08-Jul-2026 | 28-Jun-2026 14:18:31 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 29-Jun-2026 01:55:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 29-Jun-2026 21:09:00 | 29-Jun-2026 14:55:16 | 0 |  |  | Approver | Locate
AO-001773 | MM-ZTK-1F-ZWPX-STR-DWG-1300 | TOPSIDES - UPPER DECK FLOORING AND HANDRAIL - LAYOUT PLAN AT TOS EL(+) 24810 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:34:57 | wisuda.c@jutal.com | 31-Aug-2026 11:08:04 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 09-Sep-2026 13:44:39 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 23:40:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 13-Sep-2026 11:37:16 | 13-Sep-2026 05:01:13 | 0 |  |  | Approver | Locate
AO-000937 | MM-ZTK-1F-ZWPX-STR-DWG-1301 | TOPSIDES - LOWER DECK FLOORING AND HANDRAIL - LAYOUT PLAN AT TOS EL(+) 18300 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 19:05:33 | wisuda.c@jutal.com | 27-Jun-2026 19:13:10 | Jumpol Sudjitjul | 06-Jul-2026 |  | Sompop Singhatiraj | 08-Jul-2026 | 28-Jun-2026 14:19:39 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 29-Jun-2026 01:56:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 29-Jun-2026 21:07:30 | 29-Jun-2026 14:35:41 | 0 |  |  | Approver | Locate
AO-001773 | MM-ZTK-1F-ZWPX-STR-DWG-1301 | TOPSIDES - LOWER DECK FLOORING AND HANDRAIL - LAYOUT PLAN AT TOS EL(+) 18300 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:35:23 | wisuda.c@jutal.com | 31-Aug-2026 11:08:04 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 09-Sep-2026 13:44:50 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 23:45:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 13-Sep-2026 11:35:28 | 13-Sep-2026 04:56:19 | 0 |  |  | Approver | Locate
AO-000937 | MM-ZTK-1F-ZWPX-STR-DWG-1302 | TOPSIDES - MEZZANINE DECK FLOORING AND HANDRAIL - LAYOUT PLAN AT TOS EL(+) 21100 & 21300 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 19:06:43 | wisuda.c@jutal.com | 27-Jun-2026 19:23:38 | Jumpol Sudjitjul | 06-Jul-2026 |  | Sompop Singhatiraj | 08-Jul-2026 | 28-Jun-2026 14:21:34 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 29-Jun-2026 01:58:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 29-Jun-2026 21:03:04 | 29-Jun-2026 14:32:55 | 0 |  |  | Approver | Locate
AO-001773 | MM-ZTK-1F-ZWPX-STR-DWG-1302 | TOPSIDES - MEZZANINE DECK FLOORING AND HANDRAIL - LAYOUT PLAN AT TOS EL(+) 21100 & 21300 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:36:01 | wisuda.c@jutal.com | 31-Aug-2026 11:08:15 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 10-Sep-2026 10:28:04 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 12-Sep-2026 11:43:06 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 13-Sep-2026 11:36:30 | 13-Sep-2026 04:57:31 | 0 |  |  | Approver | Locate
AO-000937 | MM-ZTK-1F-ZWPX-STR-DWG-1303 | TOPSIDES - SUMP DECK FLOORING AND HANDRAIL - LAYOUT PLAN AT TOS EL(+) 14700 & 8450 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 19:07:17 | wisuda.c@jutal.com | 27-Jun-2026 19:24:16 | Jumpol Sudjitjul | 06-Jul-2026 |  | Sompop Singhatiraj | 08-Jul-2026 | 28-Jun-2026 14:23:26 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 29-Jun-2026 01:59:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 29-Jun-2026 20:57:48 | 29-Jun-2026 14:31:31 | 0 |  |  | Approver | Locate
AO-001773 | MM-ZTK-1F-ZWPX-STR-DWG-1303 | TOPSIDES - SUMP DECK FLOORING AND HANDRAIL - LAYOUT PLAN AT TOS EL(+) 14700 & 8450 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:36:44 | wisuda.c@jutal.com | 31-Aug-2026 11:08:12 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 09-Sep-2026 13:44:58 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 23:46:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 13-Sep-2026 11:37:40 | 13-Sep-2026 05:03:44 | 0 |  |  | Approver | Locate
AO-000627 | MM-ZTK-1F-ZWPX-STR-DWG-1304 | TOPSIDES - FLOORING SECTION AND DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 18:10:40 | wisuda.c@jutal.com | 29-May-2026 18:58:04 | Jumpol Sudjitjul | 10-Jun-2026 |  | Sompop Singhatiraj | 12-Jun-2026 | 31-May-2026 15:27:21 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 31-May-2026 23:55:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 01-Jun-2026 09:22:48 | 01-Jun-2026 02:48:43 | 0 |  |  | Approver | Locate
AO-000618 | MM-ZTK-1F-ZWPX-STR-DWG-1311 | TOPSIDE - STAIR - LAYOUT AND DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 18:05:52 | wisuda.c@jutal.com | 28-May-2026 20:43:44 | Jumpol Sudjitjul | 09-Jun-2026 | 02-Jun-2026 16:26:36 | Sompop Singhatiraj | 11-Jun-2026 | 03-Jun-2026 19:29:57 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 06-Jun-2026 15:23:14 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:49:11 | 07-Jun-2026 11:52:24 | 0 |  |  | Approver | Locate
AO-001486 | MM-ZTK-1F-ZWPX-STR-DWG-1311 | TOPSIDE - STAIR - LAYOUT AND DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:51:59 | wisuda.c@jutal.com | 10-Aug-2026 14:32:40 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 18-Aug-2026 12:44:03 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:30:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 17:38:05 | 24-Aug-2026 11:29:56 | 0 |  |  | Approver | Locate
AO-000618 | MM-ZTK-1F-ZWPX-STR-DWG-1312 | TOPSIDE - STAIR - LAYOUT AND DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 17:29:41 | wisuda.c@jutal.com | 28-May-2026 20:44:11 | Jumpol Sudjitjul | 09-Jun-2026 | 02-Jun-2026 16:29:38 | Sompop Singhatiraj | 11-Jun-2026 | 03-Jun-2026 19:31:35 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 06-Jun-2026 15:30:25 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:48:30 | 07-Jun-2026 11:51:09 | 0 |  |  | Approver | Locate
AO-001486 | MM-ZTK-1F-ZWPX-STR-DWG-1312 | TOPSIDE - STAIR - LAYOUT AND DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:52:30 | wisuda.c@jutal.com | 10-Aug-2026 14:32:40 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 18-Aug-2026 12:45:07 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:30:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 17:36:37 | 24-Aug-2026 11:27:19 | 0 |  |  | Approver | Locate
AO-000618 | MM-ZTK-1F-ZWPX-STR-DWG-1313 | TOPSIDE - STAIR - LAYOUT AND DETAILS - SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 18:06:17 | wisuda.c@jutal.com | 28-May-2026 20:44:40 | Jumpol Sudjitjul | 09-Jun-2026 | 02-Jun-2026 16:31:14 | Sompop Singhatiraj | 11-Jun-2026 | 03-Jun-2026 19:31:43 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 06-Jun-2026 23:47:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 07-Jun-2026 17:47:47 | 07-Jun-2026 11:49:54 | 0 |  |  | Approver | Locate
AO-001486 | MM-ZTK-1F-ZWPX-STR-DWG-1313 | TOPSIDE - STAIR - LAYOUT AND DETAILS - SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:53:00 | wisuda.c@jutal.com | 10-Aug-2026 14:32:37 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 18-Aug-2026 12:45:14 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:31:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 17:35:24 | 24-Aug-2026 11:26:06 | 0 |  |  | Approver | Locate
AO-000618 | MM-ZTK-1F-ZWPX-STR-DWG-1314 | TOPSIDE - STAIR - LAYOUT AND DETAILS - SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 17:30:21 | wisuda.c@jutal.com | 28-May-2026 20:44:58 | Jumpol Sudjitjul | 09-Jun-2026 | 02-Jun-2026 16:34:13 | Sompop Singhatiraj | 11-Jun-2026 | 03-Jun-2026 19:34:06 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 21:26:49 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 15-Jun-2026 | 08-Jun-2026 09:13:27 | 08-Jun-2026 02:56:45 | 0 |  |  | Approver | Locate
AO-001486 | MM-ZTK-1F-ZWPX-STR-DWG-1314 | TOPSIDE - STAIR - LAYOUT AND DETAILS - SHEET 4 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Aug-2026 11:53:32 | wisuda.c@jutal.com | 10-Aug-2026 14:32:42 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 18-Aug-2026 12:47:51 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:31:36 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 17:34:45 | 24-Aug-2026 11:24:48 | 0 |  |  | Approver | Locate
AO-000618 | MM-ZTK-1F-ZWPX-STR-DWG-1315 | TOPSIDE - STAIR - LAYOUT AND DETAILS - SHEET 5 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 18:06:44 | wisuda.c@jutal.com | 28-May-2026 20:46:06 | Jumpol Sudjitjul | 09-Jun-2026 | 02-Jun-2026 16:35:17 | Sompop Singhatiraj | 11-Jun-2026 | 03-Jun-2026 19:33:58 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 21:45:30 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 08-Jun-2026 09:12:24 | 08-Jun-2026 02:55:33 | 0 |  |  | Approver | Locate
AO-001486 | MM-ZTK-1F-ZWPX-STR-DWG-1315 | TOPSIDE - STAIR - LAYOUT AND DETAILS - SHEET 5 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Aug-2026 11:54:01 | wisuda.c@jutal.com | 10-Aug-2026 14:32:52 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 18-Aug-2026 12:47:58 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:32:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 17:37:29 | 24-Aug-2026 11:28:38 | 0 |  |  | Approver | Locate
AO-000618 | MM-ZTK-1F-ZWPX-STR-DWG-1316 | TOPSIDE - STAIR - LAYOUT AND DETAILS - SHEET 6 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 18:07:11 | wisuda.c@jutal.com | 28-May-2026 20:46:40 | Jumpol Sudjitjul | 09-Jun-2026 | 02-Jun-2026 16:36:37 | Sompop Singhatiraj | 11-Jun-2026 | 03-Jun-2026 19:33:52 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 21:28:02 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 15-Jun-2026 | 08-Jun-2026 09:14:18 | 08-Jun-2026 03:04:48 | 0 |  |  | Approver | Locate
AO-001486 | MM-ZTK-1F-ZWPX-STR-DWG-1316 | TOPSIDE - STAIR - LAYOUT AND DETAILS - SHEET 6 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 10-Aug-2026 11:54:35 | wisuda.c@jutal.com | 10-Aug-2026 14:32:40 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 18-Aug-2026 12:48:32 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:32:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 17:34:07 | 24-Aug-2026 11:23:31 | 0 |  |  | Approver | Locate
AO-000618 | MM-ZTK-1F-ZWPX-STR-DWG-1317 | TOPSIDE - STAIR - LAYOUT AND DETAILS - SHEET 7 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 18:07:36 | wisuda.c@jutal.com | 28-May-2026 20:47:05 | Jumpol Sudjitjul | 09-Jun-2026 | 02-Jun-2026 16:45:14 | Sompop Singhatiraj | 11-Jun-2026 | 03-Jun-2026 19:35:46 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 21:35:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 08-Jun-2026 09:11:34 | 08-Jun-2026 02:54:20 | 0 |  |  | Approver | Locate
AO-001486 | MM-ZTK-1F-ZWPX-STR-DWG-1317 | TOPSIDE - STAIR - LAYOUT AND DETAILS - SHEET 7 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:55:07 | wisuda.c@jutal.com | 10-Aug-2026 14:32:42 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 18-Aug-2026 12:33:50 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:29:44 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 17:46:14 | 24-Aug-2026 11:31:04 | 0 |  |  | Approver | Locate
AO-000618 | MM-ZTK-1F-ZWPX-STR-DWG-1318 | TOPSIDE - STAIR - LAYOUT AND DETAILS - SHEET 8 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 17:30:55 | wisuda.c@jutal.com | 28-May-2026 20:47:20 | Jumpol Sudjitjul | 09-Jun-2026 | 02-Jun-2026 16:46:29 | Sompop Singhatiraj | 11-Jun-2026 | 03-Jun-2026 19:35:53 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 21:30:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 08-Jun-2026 09:14:56 | 08-Jun-2026 03:06:02 | 0 |  |  | Approver | Locate
AO-001486 | MM-ZTK-1F-ZWPX-STR-DWG-1318 | TOPSIDE - STAIR - LAYOUT AND DETAILS - SHEET 8 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:55:34 | wisuda.c@jutal.com | 10-Aug-2026 14:32:45 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 18-Aug-2026 12:52:01 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:32:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 15:01:46 | 24-Aug-2026 08:45:38 | 0 |  |  | Approver | Locate
AO-000618 | MM-ZTK-1F-ZWPX-STR-DWG-1319 | TOPSIDE - STAIR - LAYOUT AND DETAILS - SHEET 9 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 17:31:32 | wisuda.c@jutal.com | 28-May-2026 20:47:34 | Jumpol Sudjitjul | 09-Jun-2026 | 02-Jun-2026 16:47:59 | Sompop Singhatiraj | 11-Jun-2026 | 03-Jun-2026 19:36:02 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 07-Jun-2026 21:52:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 08-Jun-2026 09:09:54 | 08-Jun-2026 02:53:02 | 0 |  |  | Approver | Locate
AO-001486 | MM-ZTK-1F-ZWPX-STR-DWG-1319 | TOPSIDE - STAIR - LAYOUT AND DETAILS - SHEET 9 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:56:01 | wisuda.c@jutal.com | 10-Aug-2026 14:32:44 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 20-Aug-2026 07:34:54 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:48:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 14:58:59 | 24-Aug-2026 09:00:27 | 0 |  |  | Approver | Locate
AO-000937 | MM-ZTK-1F-ZWPX-STR-DWG-1320 | TOPSIDES - LADDER DETAILS - FROM JACKET ACCESS PLATFORM TO SUMP DECK |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 19:07:45 | wisuda.c@jutal.com | 27-Jun-2026 19:18:38 | Jumpol Sudjitjul | 06-Jul-2026 |  | Sompop Singhatiraj | 08-Jul-2026 | 28-Jun-2026 13:15:35 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 29-Jun-2026 01:53:55 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 29-Jun-2026 20:51:33 | 29-Jun-2026 14:30:07 | 0 |  |  | Approver | Locate
AO-001486 | MM-ZTK-1F-ZWPX-STR-DWG-1320 | TOPSIDES - LADDER DETAILS - FROM JACKET ACCESS PLATFORM TO SUMP DECK |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:56:30 | wisuda.c@jutal.com | 10-Aug-2026 14:34:03 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 18-Aug-2026 15:12:11 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:36:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 14:57:01 | 24-Aug-2026 08:59:11 | 0 |  |  | Approver | Locate
AO-000937 | MM-ZTK-1F-ZWPX-STR-DWG-1321 | TOPSIDES - LADDER DETAILS - FROM LOWER DECK TO SUMP DECK |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 19:08:16 | wisuda.c@jutal.com | 27-Jun-2026 19:19:09 | Jumpol Sudjitjul | 06-Jul-2026 |  | Sompop Singhatiraj | 08-Jul-2026 | 29-Jun-2026 07:43:51 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 02-Jul-2026 00:25:26 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 10-Jul-2026 | 02-Jul-2026 09:58:49 | 02-Jul-2026 03:42:29 | 0 |  |  | Approver | Locate
AO-001486 | MM-ZTK-1F-ZWPX-STR-DWG-1321 | TOPSIDES - LADDER DETAILS - FROM LOWER DECK TO SUMP DECK |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:56:59 | wisuda.c@jutal.com | 10-Aug-2026 14:34:30 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 18-Aug-2026 15:10:50 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:35:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 14:54:52 | 24-Aug-2026 08:57:51 | 0 |  |  | Approver | Locate
AO-000937 | MM-ZTK-1F-ZWPX-STR-DWG-1322 | TOPSIDES - LADDER DETAILS - FROM MEZZANINE DECK TO LOWER DECK SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 19:08:50 | wisuda.c@jutal.com | 27-Jun-2026 19:19:37 | Jumpol Sudjitjul | 06-Jul-2026 |  | Sompop Singhatiraj | 08-Jul-2026 | 28-Jun-2026 12:54:22 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 29-Jun-2026 01:48:32 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 29-Jun-2026 20:50:22 | 29-Jun-2026 14:28:42 | 0 |  |  | Approver | Locate
AO-001486 | MM-ZTK-1F-ZWPX-STR-DWG-1322 | TOPSIDES - LADDER DETAILS - FROM MEZZANINE DECK TO LOWER DECK SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:57:26 | wisuda.c@jutal.com | 10-Aug-2026 14:34:56 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 18-Aug-2026 15:12:18 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:38:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 14:53:25 | 24-Aug-2026 08:56:39 | 0 |  |  | Approver | Locate
AO-000937 | MM-ZTK-1F-ZWPX-STR-DWG-1323 | TOPSIDES - LADDER DETAILS - FROM MEZZANINE DECK TO LOWER DECK SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 19:09:15 | wisuda.c@jutal.com | 27-Jun-2026 19:20:05 | Jumpol Sudjitjul | 06-Jul-2026 |  | Sompop Singhatiraj | 08-Jul-2026 | 28-Jun-2026 12:56:54 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 29-Jun-2026 01:50:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 10-Jul-2026 | 29-Jun-2026 20:46:09 | 29-Jun-2026 14:25:35 | 0 |  |  | Approver | Locate
AO-001486 | MM-ZTK-1F-ZWPX-STR-DWG-1323 | TOPSIDES - LADDER DETAILS - FROM MEZZANINE DECK TO LOWER DECK SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 10-Aug-2026 11:57:53 | wisuda.c@jutal.com | 10-Aug-2026 14:35:24 | Jumpol Sudjitjul | 18-Aug-2026 |  | Sompop Singhatiraj | 20-Aug-2026 | 18-Aug-2026 15:12:27 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:38:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 14:51:31 | 24-Aug-2026 08:55:25 | 0 |  |  | Approver | Locate
AO-000619 | MM-ZTK-1F-ZWPX-STR-DWG-1351 | TOPSIDE - UPPER DECK DRAIN LAYOUT PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 17:32:05 | wisuda.c@jutal.com | 28-May-2026 20:55:59 | Jumpol Sudjitjul | 09-Jun-2026 |  | Sompop Singhatiraj | 11-Jun-2026 | 01-Jun-2026 15:28:59 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 02-Jun-2026 22:15:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 03-Jun-2026 09:14:20 | 03-Jun-2026 02:45:50 | 0 |  |  | Approver | Locate
AO-001545 | MM-ZTK-1F-ZWPX-STR-DWG-1351 | TOPSIDE - UPPER DECK DRAIN LAYOUT PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:35:56 | wisuda.c@jutal.com | 17-Aug-2026 15:25:04 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 24-Aug-2026 13:51:34 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 21:16:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 17:13:55 | 30-Aug-2026 11:18:39 | 0 |  |  | Approver | Locate
AO-000619 | MM-ZTK-1F-ZWPX-STR-DWG-1352 | TOPSIDE - LOWER DECK DRAIN LAYOUT PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 17:32:48 | wisuda.c@jutal.com | 28-May-2026 20:56:18 | Jumpol Sudjitjul | 09-Jun-2026 |  | Sompop Singhatiraj | 11-Jun-2026 | 01-Jun-2026 15:44:39 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 02-Jun-2026 22:13:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 03-Jun-2026 09:15:00 | 03-Jun-2026 02:47:05 | 0 |  |  | Approver | Locate
AO-001545 | MM-ZTK-1F-ZWPX-STR-DWG-1352 | TOPSIDE - LOWER DECK DRAIN LAYOUT PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:36:35 | wisuda.c@jutal.com | 17-Aug-2026 15:25:00 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 24-Aug-2026 13:49:12 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 21:14:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 17:13:32 | 30-Aug-2026 11:17:23 | 0 |  |  | Approver | Locate
AO-000619 | MM-ZTK-1F-ZWPX-STR-DWG-1400 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 17:33:16 | wisuda.c@jutal.com | 28-May-2026 20:48:18 | Jumpol Sudjitjul | 09-Jun-2026 |  | Sompop Singhatiraj | 11-Jun-2026 | 01-Jun-2026 18:02:46 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 02-Jun-2026 22:05:53 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 03-Jun-2026 09:15:26 | 03-Jun-2026 02:48:20 | 0 |  |  | Approver | Locate
AO-001773 | MM-ZTK-1F-ZWPX-STR-DWG-1400 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:37:43 | wisuda.c@jutal.com | 31-Aug-2026 11:08:13 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 09-Sep-2026 18:37:55 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 23:58:38 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 11-Sep-2026 | 13-Sep-2026 11:38:02 | 13-Sep-2026 05:06:14 | 0 |  |  | Approver | Locate
AO-000619 | MM-ZTK-1F-ZWPX-STR-DWG-1401 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 17:34:00 | wisuda.c@jutal.com | 28-May-2026 20:48:37 | Jumpol Sudjitjul | 09-Jun-2026 |  | Sompop Singhatiraj | 11-Jun-2026 | 01-Jun-2026 18:03:55 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 02-Jun-2026 22:00:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 03-Jun-2026 09:15:51 | 03-Jun-2026 02:49:36 | 0 |  |  | Approver | Locate
AO-001773 | MM-ZTK-1F-ZWPX-STR-DWG-1401 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:38:18 | wisuda.c@jutal.com | 31-Aug-2026 11:08:16 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 09-Sep-2026 18:39:41 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 12-Sep-2026 11:40:34 | APPR-C | Approved (Proceed to Rev.C) | Jumpol Sudjitjul | 11-Sep-2026 | 13-Sep-2026 11:39:17 | 13-Sep-2026 05:07:30 | 0 |  |  | Approver | Locate
AO-000619 | MM-ZTK-1F-ZWPX-STR-DWG-1402 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 17:34:29 | wisuda.c@jutal.com | 28-May-2026 20:48:52 | Jumpol Sudjitjul | 09-Jun-2026 |  | Sompop Singhatiraj | 11-Jun-2026 | 01-Jun-2026 18:04:54 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 02-Jun-2026 21:55:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 03-Jun-2026 09:16:27 | 03-Jun-2026 02:50:49 | 0 |  |  | Approver | Locate
AO-001773 | MM-ZTK-1F-ZWPX-STR-DWG-1402 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:38:52 | wisuda.c@jutal.com | 31-Aug-2026 11:08:18 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 09-Sep-2026 18:39:17 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 12-Sep-2026 11:38:57 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 13-Sep-2026 11:37:47 | 13-Sep-2026 05:04:59 | 0 |  |  | Approver | Locate
AO-000619 | MM-ZTK-1F-ZWPX-STR-DWG-1403 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 17:34:55 | wisuda.c@jutal.com | 28-May-2026 20:49:11 | Jumpol Sudjitjul | 09-Jun-2026 |  | Sompop Singhatiraj | 11-Jun-2026 | 01-Jun-2026 17:31:37 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 02-Jun-2026 21:49:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 03-Jun-2026 09:16:54 | 03-Jun-2026 02:52:03 | 0 |  |  | Approver | Locate
AO-001773 | MM-ZTK-1F-ZWPX-STR-DWG-1403 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 4 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:39:36 | wisuda.c@jutal.com | 31-Aug-2026 11:08:13 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 09-Sep-2026 18:39:49 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 12-Sep-2026 11:41:13 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 13-Sep-2026 11:37:24 | 13-Sep-2026 05:02:29 | 0 |  |  | Approver | Locate
AO-000619 | MM-ZTK-1F-ZWPX-STR-DWG-1404 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 5 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 17:35:26 | wisuda.c@jutal.com | 28-May-2026 20:50:09 | Jumpol Sudjitjul | 09-Jun-2026 |  | Sompop Singhatiraj | 11-Jun-2026 | 01-Jun-2026 17:20:25 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 02-Jun-2026 21:47:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 03-Jun-2026 09:17:28 | 03-Jun-2026 02:53:17 | 0 |  |  | Approver | Locate
AO-001773 | MM-ZTK-1F-ZWPX-STR-DWG-1404 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 5 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:40:05 | wisuda.c@jutal.com | 31-Aug-2026 11:08:26 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 09-Sep-2026 18:38:16 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 23:59:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 13-Sep-2026 11:36:57 | 13-Sep-2026 04:59:56 | 0 |  |  | Approver | Locate
AO-000619 | MM-ZTK-1F-ZWPX-STR-DWG-1405 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 6 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 17:36:06 | wisuda.c@jutal.com | 28-May-2026 20:50:23 | Jumpol Sudjitjul | 09-Jun-2026 |  | Sompop Singhatiraj | 11-Jun-2026 | 01-Jun-2026 17:08:21 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 02-Jun-2026 20:58:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 03-Jun-2026 09:17:57 | 03-Jun-2026 02:58:40 | 0 |  |  | Approver | Locate
AO-001773 | MM-ZTK-1F-ZWPX-STR-DWG-1405 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 6 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:40:38 | wisuda.c@jutal.com | 31-Aug-2026 11:08:25 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 10-Sep-2026 10:29:15 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 12-Sep-2026 11:47:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 13-Sep-2026 11:36:33 | 13-Sep-2026 04:58:43 | 0 |  |  | Approver | Locate
AO-000619 | MM-ZTK-1F-ZWPX-STR-DWG-1406 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 7 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 17:36:36 | wisuda.c@jutal.com | 28-May-2026 20:50:38 | Jumpol Sudjitjul | 09-Jun-2026 |  | Sompop Singhatiraj | 11-Jun-2026 | 01-Jun-2026 16:49:15 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 02-Jun-2026 20:57:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 03-Jun-2026 09:18:40 | 03-Jun-2026 02:59:52 | 0 |  |  | Approver | Locate
AO-001773 | MM-ZTK-1F-ZWPX-STR-DWG-1406 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 7 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:41:20 | wisuda.c@jutal.com | 31-Aug-2026 11:08:22 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 10-Sep-2026 10:32:37 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 12-Sep-2026 12:02:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 13-Sep-2026 11:35:33 | 13-Sep-2026 04:55:06 | 0 |  |  | Approver | Locate
AO-000619 | MM-ZTK-1F-ZWPX-STR-DWG-1407 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 8 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 28-May-2026 17:37:03 | wisuda.c@jutal.com | 28-May-2026 20:50:58 | Jumpol Sudjitjul | 09-Jun-2026 |  | Sompop Singhatiraj | 11-Jun-2026 | 01-Jun-2026 16:46:55 | Pornlert Wanaphattharaphan | 12-Jun-2026 | 02-Jun-2026 20:51:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 15-Jun-2026 | 03-Jun-2026 09:19:52 | 03-Jun-2026 03:01:09 | 0 |  |  | Approver | Locate
AO-001773 | MM-ZTK-1F-ZWPX-STR-DWG-1407 | TOPSIDE - DECK HATCH ARRANGEMENT AND DETAILS - SHEET 8 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:42:05 | wisuda.c@jutal.com | 31-Aug-2026 11:08:27 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 10-Sep-2026 10:30:39 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 12-Sep-2026 11:54:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 13-Sep-2026 11:35:06 | 13-Sep-2026 04:53:52 | 0 |  |  | Approver | Locate
AO-000710 | MM-ZTK-1F-ZWPX-STR-DWG-1500 | TOPSIDES - E&I ROOM PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 08:40:53 | wisuda.c@jutal.com | 08-Jun-2026 14:49:04 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 12-Jun-2026 17:53:03 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 13-Jun-2026 19:46:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 14-Jun-2026 21:43:52 | 14-Jun-2026 15:11:18 | 0 |  |  | Approver | Locate
AO-001545 | MM-ZTK-1F-ZWPX-STR-DWG-1500 | TOPSIDES - E&I ROOM PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:37:08 | wisuda.c@jutal.com | 17-Aug-2026 15:25:05 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 24-Aug-2026 13:21:52 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 27-Aug-2026 22:36:20 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 28-Aug-2026 11:10:21 | 28-Aug-2026 04:59:20 | 0 |  |  | Approver | Locate
AO-000710 | MM-ZTK-1F-ZWPX-STR-DWG-1501 | TOPSIDES - E&I ROOM ROOF PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 09:25:06 | wisuda.c@jutal.com | 08-Jun-2026 14:49:31 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 15-Jun-2026 14:15:38 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 18-Jun-2026 09:55:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 10:13:42 | 18-Jun-2026 03:42:30 | 0 |  |  | Approver | Locate
AO-001545 | MM-ZTK-1F-ZWPX-STR-DWG-1501 | TOPSIDES - E&I ROOM ROOF PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:37:45 | wisuda.c@jutal.com | 17-Aug-2026 15:25:07 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 24-Aug-2026 13:22:49 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 17:48:49 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 17:15:32 | 30-Aug-2026 11:19:54 | 0 |  |  | Approver | Locate
AO-000710 | MM-ZTK-1F-ZWPX-STR-DWG-1502 | TOPSIDES - E&I ROOM SECTIONS AND DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 08:41:19 | wisuda.c@jutal.com | 08-Jun-2026 14:49:47 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 12-Jun-2026 17:55:34 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 13-Jun-2026 20:10:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 14-Jun-2026 21:43:08 | 14-Jun-2026 15:10:04 | 0 |  |  | Approver | Locate
AO-001545 | MM-ZTK-1F-ZWPX-STR-DWG-1502 | TOPSIDES - E&I ROOM SECTIONS AND DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:38:15 | wisuda.c@jutal.com | 17-Aug-2026 15:25:07 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 24-Aug-2026 13:22:57 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 17:52:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 17:17:09 | 30-Aug-2026 11:22:28 | 0 |  |  | Approver | Locate
AO-000710 | MM-ZTK-1F-ZWPX-STR-DWG-1503 | TOPSIDES - E&I ROOM SECTIONS AND DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 09:25:32 | wisuda.c@jutal.com | 08-Jun-2026 14:50:01 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 12-Jun-2026 17:54:38 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 13-Jun-2026 19:55:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 14-Jun-2026 21:43:32 | 14-Jun-2026 14:59:43 | 0 |  |  | Approver | Locate
AO-001545 | MM-ZTK-1F-ZWPX-STR-DWG-1503 | TOPSIDES - E&I ROOM SECTIONS AND DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:38:44 | wisuda.c@jutal.com | 17-Aug-2026 15:25:01 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 24-Aug-2026 13:24:35 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 18:06:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 17:16:39 | 30-Aug-2026 11:21:12 | 0 |  |  | Approver | Locate
AO-000710 | MM-ZTK-1F-ZWPX-STR-DWG-1504 | TOPSIDES - E&I ROOM ELEVATIONS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 09:25:59 | wisuda.c@jutal.com | 08-Jun-2026 14:50:15 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 12-Jun-2026 17:56:32 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 13-Jun-2026 20:18:45 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 14-Jun-2026 21:42:21 | 14-Jun-2026 14:58:25 | 0 |  |  | Approver | Locate
AO-001545 | MM-ZTK-1F-ZWPX-STR-DWG-1504 | TOPSIDES - E&I ROOM ELEVATIONS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:39:14 | wisuda.c@jutal.com | 17-Aug-2026 15:25:02 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 24-Aug-2026 13:24:30 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 17:56:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 17:17:42 | 30-Aug-2026 11:23:43 | 0 |  |  | Approver | Locate
AO-000710 | MM-ZTK-1F-ZWPX-STR-DWG-1505 | TOPSIDES - WIND DRIVEN VENTILATION FANS FOR E&I ROOM LAYOUT AND MOUNTING DIAGRAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 08:41:44 | wisuda.c@jutal.com | 08-Jun-2026 16:36:56 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 12-Jun-2026 17:57:28 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 14-Jun-2026 00:24:18 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 14-Jun-2026 21:41:59 | 14-Jun-2026 15:08:47 | 0 |  |  | Approver | Locate
AO-001545 | MM-ZTK-1F-ZWPX-STR-DWG-1505 | TOPSIDES - WIND DRIVEN VENTILATION FANS FOR E&I ROOM LAYOUT AND MOUNTING DIAGRAM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:39:51 | wisuda.c@jutal.com | 17-Aug-2026 15:25:04 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 24-Aug-2026 13:24:42 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 20:54:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 17:18:10 | 30-Aug-2026 11:59:43 | 0 |  |  | Approver | Locate
AO-000796 | MM-ZTK-1F-ZWPX-STR-DWG-1506 | TOPSIDES - LADDER DETAILS FOR E&I ROOM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Jun-2026 22:09:38 | wisuda.c@jutal.com | 15-Jun-2026 08:54:46 | Jumpol Sudjitjul | 22-Jun-2026 |  | Sompop Singhatiraj | 24-Jun-2026 | 16-Jun-2026 10:07:31 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 18-Jun-2026 11:47:29 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Jun-2026 | 18-Jun-2026 11:56:34 | 18-Jun-2026 05:45:07 | 0 |  |  | Approver | Locate
AO-001545 | MM-ZTK-1F-ZWPX-STR-DWG-1506 | TOPSIDES - LADDER DETAILS FOR E&I ROOM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 14:40:26 | wisuda.c@jutal.com | 17-Aug-2026 15:25:11 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 24-Aug-2026 13:27:53 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 29-Aug-2026 21:05:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Aug-2026 | 30-Aug-2026 17:18:33 | 30-Aug-2026 12:00:57 | 0 |  |  | Approver | Locate
AO-000627 | MM-ZTK-1F-ZWPX-STR-DWG-1512 | TOPSIDES - CRANE BOOM REST - PLAN, SECTION AND DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 18:11:08 | wisuda.c@jutal.com | 29-May-2026 18:59:31 | Jumpol Sudjitjul | 10-Jun-2026 |  | Sompop Singhatiraj | 12-Jun-2026 | 31-May-2026 13:32:53 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 31-May-2026 22:03:01 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 31-May-2026 22:09:00 | 31-May-2026 15:47:48 | 0 |  |  | Approver | Locate
AO-001773 | MM-ZTK-1F-ZWPX-STR-DWG-1512 | TOPSIDES - CRANE BOOM REST - PLAN, SECTION AND DETAILS |  | B2 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 31-Aug-2026 09:42:45 | wisuda.c@jutal.com | 31-Aug-2026 11:08:24 | Jumpol Sudjitjul | 07-Sep-2026 |  | Sompop Singhatiraj | 09-Sep-2026 | 08-Sep-2026 13:36:37 | Pornlert Wanaphattharaphan | 10-Sep-2026 | 11-Sep-2026 22:47:17 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Sep-2026 | 13-Sep-2026 11:34:46 | 13-Sep-2026 04:52:37 | 0 |  |  | Approver | Locate
AO-000937 | MM-ZTK-1F-ZWPX-STR-DWG-1531 | TOPSIDES - CONDENSATE BURNER BOOM SUPPORT ARRANGEMENT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 19:09:49 | wisuda.c@jutal.com | 27-Jun-2026 19:19:51 | Jumpol Sudjitjul | 06-Jul-2026 |  | Sompop Singhatiraj | 08-Jul-2026 | 28-Jun-2026 11:53:06 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 29-Jun-2026 01:42:24 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 10-Jul-2026 | 29-Jun-2026 20:49:11 | 29-Jun-2026 14:27:05 | 0 |  |  | Approver | Locate
AO-000937 | MM-ZTK-1F-ZWPX-STR-DWG-1532 | TOPSIDES - CONDENSATE BURNER BOOM SUPPORT - DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 27-Jun-2026 19:10:16 | wisuda.c@jutal.com | 27-Jun-2026 19:20:08 | Jumpol Sudjitjul | 06-Jul-2026 |  | Sompop Singhatiraj | 08-Jul-2026 | 28-Jun-2026 11:54:36 | Pornlert Wanaphattharaphan | 09-Jul-2026 | 29-Jun-2026 01:42:47 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 10-Jul-2026 | 29-Jun-2026 20:43:06 | 29-Jun-2026 14:22:36 | 0 |  |  | Approver | Locate
AO-000710 | MM-ZTK-1F-ZWPX-STR-DWG-1611 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 09:26:25 | wisuda.c@jutal.com | 08-Jun-2026 15:38:03 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 17-Jun-2026 09:16:15 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 18-Jun-2026 11:25:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 11:40:00 | 18-Jun-2026 05:03:08 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1611 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 10:54:27 | wisuda.c@jutal.com | 24-Aug-2026 20:35:54 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 07-Sep-2026 09:38:50 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 08-Sep-2026 22:16:03 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 09-Sep-2026 11:09:22 | 09-Sep-2026 05:16:51 | 0 |  |  | Approver | Locate
AO-000710 | MM-ZTK-1F-ZWPX-STR-DWG-1612 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 09:26:49 | wisuda.c@jutal.com | 08-Jun-2026 15:38:04 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 17-Jun-2026 09:18:29 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 18-Jun-2026 11:25:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 11:41:06 | 18-Jun-2026 05:04:24 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1612 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:55:30 | wisuda.c@jutal.com | 24-Aug-2026 20:35:57 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 07-Sep-2026 09:39:11 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 08-Sep-2026 22:17:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 09-Sep-2026 11:08:57 | 09-Sep-2026 05:31:50 | 0 |  |  | Approver | Locate
AO-000710 | MM-ZTK-1F-ZWPX-STR-DWG-1613 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 08:42:11 | wisuda.c@jutal.com | 08-Jun-2026 15:38:03 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 17-Jun-2026 09:21:21 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 18-Jun-2026 11:22:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 11:43:37 | 18-Jun-2026 04:56:14 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1613 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 3 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 10:55:01 | wisuda.c@jutal.com | 24-Aug-2026 20:35:58 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 07-Sep-2026 09:39:24 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 08-Sep-2026 22:20:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 09-Sep-2026 10:37:01 | 09-Sep-2026 04:30:25 | 0 |  |  | Approver | Locate
AO-000710 | MM-ZTK-1F-ZWPX-STR-DWG-1614 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 08:42:35 | wisuda.c@jutal.com | 08-Jun-2026 15:38:05 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 17-Jun-2026 09:21:33 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 18-Jun-2026 11:21:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 11:46:25 | 18-Jun-2026 04:57:29 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1614 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 4 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:55:58 | wisuda.c@jutal.com | 24-Aug-2026 20:35:58 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 07-Sep-2026 09:39:42 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 08-Sep-2026 22:23:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 09-Sep-2026 11:10:21 | 09-Sep-2026 05:34:20 | 0 |  |  | Approver | Locate
AO-000710 | MM-ZTK-1F-ZWPX-STR-DWG-1615 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 5 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 08:43:01 | wisuda.c@jutal.com | 08-Jun-2026 15:38:06 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 17-Jun-2026 09:21:10 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 18-Jun-2026 11:20:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 11:49:07 | 18-Jun-2026 04:58:43 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1615 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 5 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:56:27 | wisuda.c@jutal.com | 24-Aug-2026 20:36:04 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 07-Sep-2026 10:15:49 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 08-Sep-2026 22:44:00 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 09-Sep-2026 11:11:27 | 09-Sep-2026 05:35:44 | 0 |  |  | Approver | Locate
AO-000710 | MM-ZTK-1F-ZWPX-STR-DWG-1616 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 6 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 09:27:14 | wisuda.c@jutal.com | 08-Jun-2026 15:38:07 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 17-Jun-2026 09:23:12 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 18-Jun-2026 11:20:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 11:57:29 | 18-Jun-2026 05:38:40 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1616 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 6 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 10:55:29 | wisuda.c@jutal.com | 24-Aug-2026 20:35:58 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 07-Sep-2026 10:09:35 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 08-Sep-2026 22:31:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 09-Sep-2026 10:33:50 | 09-Sep-2026 04:29:04 | 0 |  |  | Approver | Locate
AO-000710 | MM-ZTK-1F-ZWPX-STR-DWG-1617 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 7 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 08:43:27 | wisuda.c@jutal.com | 08-Jun-2026 15:44:08 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 17-Jun-2026 09:24:17 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 18-Jun-2026 11:15:19 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 11:18:31 | 18-Jun-2026 04:53:00 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1617 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 7 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 10:56:00 | wisuda.c@jutal.com | 24-Aug-2026 20:36:00 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 07-Sep-2026 10:15:22 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 08-Sep-2026 22:40:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 09-Sep-2026 10:33:21 | 09-Sep-2026 04:27:41 | 0 |  |  | Approver | Locate
AO-000710 | MM-ZTK-1F-ZWPX-STR-DWG-1618 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 8 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 08:43:52 | wisuda.c@jutal.com | 08-Jun-2026 15:43:53 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 17-Jun-2026 09:25:06 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 18-Jun-2026 10:21:02 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 10:26:06 | 18-Jun-2026 04:27:39 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1618 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 8 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:56:56 | wisuda.c@jutal.com | 24-Aug-2026 20:36:04 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 07-Sep-2026 10:14:32 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 08-Sep-2026 22:33:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 09-Sep-2026 10:32:39 | 09-Sep-2026 04:07:05 | 0 |  |  | Approver | Locate
AO-000710 | MM-ZTK-1F-ZWPX-STR-DWG-1619 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 9 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 08:44:15 | wisuda.c@jutal.com | 08-Jun-2026 15:43:34 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 17-Jun-2026 09:26:00 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 18-Jun-2026 10:20:15 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 10:26:26 | 18-Jun-2026 04:29:01 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1619 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 9 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:57:29 | wisuda.c@jutal.com | 24-Aug-2026 20:36:08 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 07-Sep-2026 10:24:47 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 08-Sep-2026 22:46:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 09-Sep-2026 10:31:47 | 09-Sep-2026 04:05:49 | 0 |  |  | Approver | Locate
AO-000710 | MM-ZTK-1F-ZWPX-STR-DWG-1620 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 10 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 08:44:44 | wisuda.c@jutal.com | 08-Jun-2026 15:43:12 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 17-Jun-2026 09:26:55 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 18-Jun-2026 10:19:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 10:26:51 | 18-Jun-2026 04:30:19 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1620 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 10 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:58:08 | wisuda.c@jutal.com | 24-Aug-2026 20:36:01 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 07-Sep-2026 10:25:24 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 08-Sep-2026 22:48:24 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 09-Sep-2026 11:12:30 | 09-Sep-2026 05:37:01 | 0 |  |  | Approver | Locate
AO-000780 | MM-ZTK-1F-ZWPX-STR-DWG-1621 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 11 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Jun-2026 22:10:02 | wisuda.c@jutal.com | 15-Jun-2026 08:57:10 | Jumpol Sudjitjul | 22-Jun-2026 |  | Sompop Singhatiraj | 24-Jun-2026 | 17-Jun-2026 09:30:05 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 18-Jun-2026 10:19:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Jun-2026 | 18-Jun-2026 10:27:17 | 18-Jun-2026 04:25:13 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1621 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 11 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:58:42 | wisuda.c@jutal.com | 24-Aug-2026 20:36:07 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 07-Sep-2026 10:25:32 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 08-Sep-2026 22:50:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 09-Sep-2026 10:31:16 | 09-Sep-2026 04:04:26 | 0 |  |  | Approver | Locate
AO-000710 | MM-ZTK-1F-ZWPX-STR-DWG-1622 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 12 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 08-Jun-2026 08:45:17 | wisuda.c@jutal.com | 08-Jun-2026 15:42:45 | Jumpol Sudjitjul | 15-Jun-2026 |  | Sompop Singhatiraj | 17-Jun-2026 | 17-Jun-2026 09:28:28 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 18-Jun-2026 10:18:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 18-Jun-2026 10:27:56 | 18-Jun-2026 04:31:35 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1622 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 12 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 10:56:32 | wisuda.c@jutal.com | 24-Aug-2026 20:36:07 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 09-Sep-2026 09:41:26 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 09-Sep-2026 22:53:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 10-Sep-2026 09:09:43 | 10-Sep-2026 02:44:02 | 0 |  |  | Approver | Locate
AO-000780 | MM-ZTK-1F-ZWPX-STR-DWG-1623 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 13 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Jun-2026 22:10:26 | wisuda.c@jutal.com | 15-Jun-2026 08:57:28 | Jumpol Sudjitjul | 22-Jun-2026 |  | Sompop Singhatiraj | 24-Jun-2026 | 17-Jun-2026 09:31:57 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 18-Jun-2026 10:17:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Jun-2026 | 18-Jun-2026 10:28:17 | 18-Jun-2026 04:32:50 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1623 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 13 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 09:59:10 | wisuda.c@jutal.com | 24-Aug-2026 20:36:02 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 07-Sep-2026 10:26:51 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 08-Sep-2026 22:54:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 09-Sep-2026 10:30:00 | 09-Sep-2026 04:03:00 | 0 |  |  | Approver | Locate
AO-000780 | MM-ZTK-1F-ZWPX-STR-DWG-1624 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 14 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Jun-2026 22:10:49 | wisuda.c@jutal.com | 15-Jun-2026 08:57:50 | Jumpol Sudjitjul | 22-Jun-2026 |  | Sompop Singhatiraj | 24-Jun-2026 | 17-Jun-2026 09:32:02 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 18-Jun-2026 10:16:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Jun-2026 | 18-Jun-2026 10:28:39 | 18-Jun-2026 04:34:08 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1624 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 14 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 10:57:01 | wisuda.c@jutal.com | 24-Aug-2026 20:36:03 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 07-Sep-2026 10:25:46 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 08-Sep-2026 22:51:04 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 09-Sep-2026 10:29:31 | 09-Sep-2026 04:23:52 | 0 |  |  | Approver | Locate
AO-001662 | MM-ZTK-1F-ZWPX-STR-DWG-1625 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT DETAILS - SHEET 15 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 10:57:28 | wisuda.c@jutal.com | 24-Aug-2026 20:36:12 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 25-Aug-2026 09:53:36 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 15:35:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 17:19:04 | 30-Aug-2026 11:44:21 | 0 |  |  | Approver | Locate
AO-001662 | MM-ZTK-1F-ZWPX-STR-DWG-1626 | TOPSIDES - STEP LAYOUT AND SECTION |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-Aug-2026 09:59:44 | wisuda.c@jutal.com | 24-Aug-2026 20:35:40 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 25-Aug-2026 09:21:14 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 12:31:32 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 17:18:51 | 30-Aug-2026 12:02:10 | 0 |  |  | Approver | Locate
AO-002483 | MM-ZTK-1F-ZWPX-STR-DWG-1627 | TOPSIDES - REMOVABLE PADEYE COLUMN PLAN, SECTION AND DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 12-Oct-2026 12:06:10 | wisuda.c@jutal.com | 12-Oct-2026 13:31:33 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 | 14-Oct-2026 08:20:02 | Pornlert Wanaphattharaphan | 26-Oct-2026 | 15-Oct-2026 22:25:17 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 27-Oct-2026 | 16-Oct-2026 11:42:22 | 16-Oct-2026 04:56:56 | 0 |  |  | Approver | Locate
AO-002484 | MM-ZTK-1F-ZWPX-STR-DWG-1628 | TOPSIDES - TYPICAL EQUIPMENT SUPPORT IN E&I ROOM SECTIONS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 12-Oct-2026 12:06:43 | wisuda.c@jutal.com | 12-Oct-2026 13:31:50 | Jumpol Sudjitjul | 20-Oct-2026 |  | Sompop Singhatiraj | 22-Oct-2026 | 14-Oct-2026 07:51:48 | Pornlert Wanaphattharaphan | 26-Oct-2026 | 15-Oct-2026 22:24:41 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 27-Oct-2026 | 16-Oct-2026 11:41:32 | 16-Oct-2026 04:55:42 | 0 |  |  | Approver | Locate
AO-001389 | MM-ZTK-1F-ZWPX-STR-DWG-1641 | TOPSIDES - SAFETY SIGNS SUPPORT DETAILS SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 11:28:50 | wisuda.c@jutal.com | 03-Aug-2026 13:10:02 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 09-Aug-2026 12:09:56 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 10-Aug-2026 01:01:11 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 10:10:22 | 10-Aug-2026 03:24:52 | 0 |  |  | Approver | Locate
AO-001389 | MM-ZTK-1F-ZWPX-STR-DWG-1642 | TOPSIDES - SAFETY SIGNS SUPPORT DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 11:29:21 | wisuda.c@jutal.com | 03-Aug-2026 13:10:26 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 09-Aug-2026 12:12:30 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 10-Aug-2026 01:00:42 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 10:11:30 | 10-Aug-2026 03:26:14 | 0 |  |  | Approver | Locate
AO-001389 | MM-ZTK-1F-ZWPX-STR-DWG-1644 | TOPSIDES - MEZZANINE DECK FLOORING LAYOUT FOR SAFETY SIGN SUPPORT AT TOG EL(+) 21138 & 21338 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 11:29:49 | wisuda.c@jutal.com | 03-Aug-2026 13:13:00 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 09-Aug-2026 12:12:23 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 10-Aug-2026 01:00:14 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 10:08:22 | 10-Aug-2026 03:21:25 | 0 |  |  | Approver | Locate
AO-001389 | MM-ZTK-1F-ZWPX-STR-DWG-1645 | TOPSIDES - LOWER DECK FLOORING LAYOUT FOR SAFETY SIGN SUPPORT AT TOPL EL(+) 18310 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 10:57:31 | wisuda.c@jutal.com | 03-Aug-2026 13:13:19 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 09-Aug-2026 12:13:54 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 10-Aug-2026 00:59:51 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 10:07:36 | 10-Aug-2026 03:20:04 | 0 |  |  | Approver | Locate
AO-001389 | MM-ZTK-1F-ZWPX-STR-DWG-1646 | TOPSIDES - SUMP DECK FLOORING LAYOUT FOR SAFETY SIGN SUPPORT AT TOG EL(+) 14738 & 8488 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 03-Aug-2026 10:57:55 | wisuda.c@jutal.com | 03-Aug-2026 13:13:39 | Jumpol Sudjitjul | 10-Aug-2026 |  | Sompop Singhatiraj | 13-Aug-2026 | 09-Aug-2026 12:14:03 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 10-Aug-2026 00:59:28 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 17-Aug-2026 | 10-Aug-2026 10:06:28 | 10-Aug-2026 03:18:44 | 0 |  |  | Approver | Locate
AO-000780 | MM-ZTK-1F-ZWPX-STR-DWG-1711 | TOPSIDES - AMENITIES CUBICLE PLAN AND SECTIONS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Jun-2026 22:11:13 | wisuda.c@jutal.com | 15-Jun-2026 08:59:29 | Jumpol Sudjitjul | 22-Jun-2026 |  | Sompop Singhatiraj | 24-Jun-2026 | 17-Jun-2026 16:41:34 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 18-Jun-2026 10:16:33 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Jun-2026 | 18-Jun-2026 10:29:21 | 18-Jun-2026 04:39:13 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1711 | TOPSIDES - AMENITIES CUBICLE PLAN AND SECTIONS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 10:57:54 | wisuda.c@jutal.com | 24-Aug-2026 20:35:39 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 25-Aug-2026 11:59:15 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 16:39:54 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 17:16:12 | 30-Aug-2026 11:43:12 | 0 |  |  | Approver | Locate
AO-000780 | MM-ZTK-1F-ZWPX-STR-DWG-1712 | TOPSIDES - AMENITIES CUBICLE SECTIONS AND DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Jun-2026 22:11:37 | wisuda.c@jutal.com | 15-Jun-2026 08:59:47 | Jumpol Sudjitjul | 22-Jun-2026 |  | Sompop Singhatiraj | 24-Jun-2026 | 17-Jun-2026 16:44:08 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 18-Jun-2026 10:16:14 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 26-Jun-2026 | 18-Jun-2026 10:30:09 | 18-Jun-2026 04:41:44 | 0 |  |  | Approver | Locate
AO-001664 | MM-ZTK-1F-ZWPX-STR-DWG-1712 | TOPSIDES - AMENITIES CUBICLE SECTIONS AND DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 10:00:13 | wisuda.c@jutal.com | 24-Aug-2026 20:35:36 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 25-Aug-2026 11:56:44 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 16:29:19 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 17:11:31 | 30-Aug-2026 11:58:29 | 0 |  |  | Approver | Locate
AO-000780 | MM-ZTK-1F-ZWPX-STR-DWG-1713 | TOPSIDES - PLATFORM NAME PLATE/IDENTIFICATION PANEL |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Jun-2026 22:12:01 | wisuda.c@jutal.com | 15-Jun-2026 09:02:06 | Jumpol Sudjitjul | 22-Jun-2026 |  | Sompop Singhatiraj | 24-Jun-2026 | 17-Jun-2026 16:44:34 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 18-Jun-2026 10:15:58 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 26-Jun-2026 | 18-Jun-2026 10:30:22 | 18-Jun-2026 04:43:01 | 0 |  |  | Approver | Locate
AO-001664 | MM-ZTK-1F-ZWPX-STR-DWG-1713 | TOPSIDES - PLATFORM NAME PLATE/IDENTIFICATION PANEL |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 10:58:25 | wisuda.c@jutal.com | 24-Aug-2026 20:35:39 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 25-Aug-2026 11:13:35 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 16:26:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 17:15:11 | 30-Aug-2026 11:41:56 | 0 |  |  | Approver | Locate
AO-000627 | MM-ZTK-1F-ZWPX-STR-DWG-1714 | TOPSIDES - SWING ROPES AND DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 18:11:35 | wisuda.c@jutal.com | 29-May-2026 18:56:08 | Jumpol Sudjitjul | 10-Jun-2026 |  | Sompop Singhatiraj | 12-Jun-2026 | 31-May-2026 14:30:53 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 31-May-2026 22:29:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 31-May-2026 22:31:22 | 31-May-2026 15:50:19 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1714 | TOPSIDES - SWING ROPES AND DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 10:58:52 | wisuda.c@jutal.com | 24-Aug-2026 20:35:38 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 25-Aug-2026 12:37:14 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 17:11:48 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 17:13:18 | 30-Aug-2026 11:40:37 | 0 |  |  | Approver | Locate
AO-000627 | MM-ZTK-1F-ZWPX-STR-DWG-1715 | TOPSIDES - SWING ROPES AND DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 18:11:59 | wisuda.c@jutal.com | 29-May-2026 18:56:34 | Jumpol Sudjitjul | 10-Jun-2026 |  | Sompop Singhatiraj | 12-Jun-2026 | 31-May-2026 14:32:44 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 31-May-2026 22:22:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 31-May-2026 22:30:16 | 31-May-2026 15:49:03 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1715 | TOPSIDES - SWING ROPES AND DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 10:59:20 | wisuda.c@jutal.com | 24-Aug-2026 20:35:35 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 25-Aug-2026 12:35:36 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 16:50:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 17:12:26 | 30-Aug-2026 11:39:23 | 0 |  |  | Approver | Locate
AO-001542 | MM-ZTK-1F-ZWPX-STR-DWG-1716 | TOPSIDES - LIFE RAFT AND DESCENDING DEVICES SUPPORTING DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 17-Aug-2026 14:41:02 | wisuda.c@jutal.com | 17-Aug-2026 15:28:11 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 24-Aug-2026 07:54:11 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 27-Aug-2026 22:28:18 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 28-Aug-2026 | 28-Aug-2026 11:11:36 | 28-Aug-2026 04:47:43 | 0 |  |  | Approver | Locate
AO-001542 | MM-ZTK-1F-ZWPX-STR-DWG-1717 | TOPSIDES - LIFE RAFT AND DESCENDING DEVICES SECTION AND DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 17-Aug-2026 14:41:32 | wisuda.c@jutal.com | 17-Aug-2026 15:28:53 | Jumpol Sudjitjul | 24-Aug-2026 |  | Sompop Singhatiraj | 26-Aug-2026 | 24-Aug-2026 07:30:52 | Pornlert Wanaphattharaphan | 27-Aug-2026 | 27-Aug-2026 22:27:32 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 28-Aug-2026 | 28-Aug-2026 11:12:26 | 28-Aug-2026 04:48:59 | 0 |  |  | Approver | Locate
AO-000780 | MM-ZTK-1F-ZWPX-STR-DWG-1722 | TOPSIDES - SECURITY GATE PLAN AND DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Jun-2026 22:12:25 | wisuda.c@jutal.com | 15-Jun-2026 09:03:41 | Jumpol Sudjitjul | 22-Jun-2026 |  | Sompop Singhatiraj | 24-Jun-2026 | 17-Jun-2026 16:44:53 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 18-Jun-2026 10:15:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Jun-2026 | 18-Jun-2026 10:30:00 | 18-Jun-2026 04:40:30 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1722 | TOPSIDES - SECURITY GATE PLAN AND DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 10:59:52 | wisuda.c@jutal.com | 24-Aug-2026 20:35:33 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 25-Aug-2026 13:54:36 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 17:22:22 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 21:26:17 | 30-Aug-2026 14:59:17 | 0 |  |  | Approver | Locate
AO-000780 | MM-ZTK-1F-ZWPX-STR-DWG-1723 | TOPSIDES - SECURITY GATE PLAN AND DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Jun-2026 22:12:48 | wisuda.c@jutal.com | 15-Jun-2026 09:04:07 | Jumpol Sudjitjul | 22-Jun-2026 |  | Sompop Singhatiraj | 24-Jun-2026 | 17-Jun-2026 16:47:02 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 18-Jun-2026 10:15:25 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 26-Jun-2026 | 18-Jun-2026 10:29:28 | 18-Jun-2026 04:37:56 | 0 |  |  | Approver | Locate
AO-001664 | MM-ZTK-1F-ZWPX-STR-DWG-1723 | TOPSIDES - SECURITY GATE PLAN AND DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 24-Aug-2026 11:00:21 | wisuda.c@jutal.com | 24-Aug-2026 20:35:38 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 25-Aug-2026 10:09:32 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 00:17:46 | APPR | Approved | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 17:10:28 | 30-Aug-2026 11:35:38 | 0 |  |  | Approver | Locate
AO-000627 | MM-ZTK-1F-ZWPX-STR-DWG-1801 | TOPSIDES - GENERAL MUD WALL - FRAMING PLAN & DETAILS AT LOWER DECK TOPL EL(+) 18308 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 18:12:22 | wisuda.c@jutal.com | 29-May-2026 18:53:12 | Jumpol Sudjitjul | 10-Jun-2026 |  | Sompop Singhatiraj | 12-Jun-2026 | 31-May-2026 14:59:09 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 31-May-2026 23:41:44 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 01-Jun-2026 09:23:11 | 01-Jun-2026 02:52:11 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1801 | TOPSIDES - GENERAL MUD WALL - FRAMING PLAN & DETAILS AT LOWER DECK TOPL EL(+) 18308 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 11:00:56 | wisuda.c@jutal.com | 24-Aug-2026 20:35:31 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 26-Aug-2026 09:21:20 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 18:09:16 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 21:26:46 | 30-Aug-2026 15:00:31 | 0 |  |  | Approver | Locate
AO-000627 | MM-ZTK-1F-ZWPX-STR-DWG-1802 | TOPSIDES - GENERAL MUD WALL - SECTIONS AND DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 18:12:47 | wisuda.c@jutal.com | 29-May-2026 18:53:40 | Jumpol Sudjitjul | 10-Jun-2026 |  | Sompop Singhatiraj | 12-Jun-2026 | 31-May-2026 14:57:36 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 31-May-2026 23:32:27 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 01-Jun-2026 09:23:33 | 01-Jun-2026 02:53:26 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1802 | TOPSIDES - GENERAL MUD WALL - SECTIONS AND DETAILS - SHEET 1 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 11:01:25 | wisuda.c@jutal.com | 24-Aug-2026 20:35:31 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 26-Aug-2026 09:23:56 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 18:12:42 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 21:27:09 | 30-Aug-2026 15:01:47 | 0 |  |  | Approver | Locate
AO-000627 | MM-ZTK-1F-ZWPX-STR-DWG-1803 | TOPSIDES - GENERAL MUD WALL - SECTIONS AND DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 18:13:12 | wisuda.c@jutal.com | 29-May-2026 18:53:56 | Jumpol Sudjitjul | 10-Jun-2026 |  | Sompop Singhatiraj | 12-Jun-2026 | 31-May-2026 14:56:02 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 31-May-2026 23:18:59 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 01-Jun-2026 09:23:39 | 01-Jun-2026 02:54:40 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1803 | TOPSIDES - GENERAL MUD WALL - SECTIONS AND DETAILS - SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Latest | IFA | Issued for Approval |  | 24-Aug-2026 11:01:54 | wisuda.c@jutal.com | 24-Aug-2026 20:35:28 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 26-Aug-2026 09:24:08 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 18:13:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 21:27:30 |  | 0 |  |  | Approver | Locate
AO-000627 | MM-ZTK-1F-ZWPX-STR-DWG-1804 | TOPSIDES - GENERAL MUD WALL - CANVAS PLAN AT LOWER DECK TOS EL(+) 18300 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 29-May-2026 18:13:37 | wisuda.c@jutal.com | 29-May-2026 18:54:11 | Jumpol Sudjitjul | 10-Jun-2026 |  | Sompop Singhatiraj | 12-Jun-2026 | 31-May-2026 14:54:44 | Pornlert Wanaphattharaphan | 15-Jun-2026 | 31-May-2026 22:41:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jun-2026 | 01-Jun-2026 09:21:27 | 01-Jun-2026 02:47:25 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1804 | TOPSIDES - GENERAL MUD WALL - CANVAS PLAN AT LOWER DECK TOS EL(+) 18300 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 10:00:42 | wisuda.c@jutal.com | 24-Aug-2026 20:35:30 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 26-Aug-2026 09:22:37 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 18:09:38 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 21:28:08 | 31-Aug-2026 04:37:07 | 0 |  |  | Approver | Locate
AO-000780 | MM-ZTK-1F-ZWPX-STR-DWG-1901 | TOPSIDES - LIFTING ARRANGEMENT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Jun-2026 22:13:11 | wisuda.c@jutal.com | 15-Jun-2026 09:05:02 | Jumpol Sudjitjul | 22-Jun-2026 |  | Sompop Singhatiraj | 24-Jun-2026 | 17-Jun-2026 16:46:34 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 18-Jun-2026 10:15:09 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Jun-2026 | 18-Jun-2026 10:29:01 | 18-Jun-2026 04:36:39 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1901 | TOPSIDES - LIFTING ARRANGEMENT |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 11:02:26 | wisuda.c@jutal.com | 24-Aug-2026 20:35:33 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 26-Aug-2026 13:24:31 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 18:20:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 21:28:16 | 30-Aug-2026 15:03:04 | 0 |  |  | Approver | Locate
AO-000780 | MM-ZTK-1F-ZWPX-STR-DWG-1902 | TOPSIDES - LIFTING PADEYE DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 14-Jun-2026 22:13:36 | wisuda.c@jutal.com | 15-Jun-2026 09:05:19 | Jumpol Sudjitjul | 22-Jun-2026 |  | Sompop Singhatiraj | 24-Jun-2026 | 17-Jun-2026 16:50:35 | Pornlert Wanaphattharaphan | 25-Jun-2026 | 18-Jun-2026 10:14:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 26-Jun-2026 | 18-Jun-2026 10:28:35 | 18-Jun-2026 04:35:23 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1902 | TOPSIDES - LIFTING PADEYE DETAILS |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 11:02:52 | wisuda.c@jutal.com | 24-Aug-2026 20:35:33 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 26-Aug-2026 13:26:04 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 18:24:10 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 21:27:44 | 01-Sep-2026 08:15:46 | 0 |  |  | Approver | Locate
AO-000807 | MM-ZTK-1F-ZWPX-STR-DWG-1903 | TOPSIDE - LIFTING PADEYE DETAILS SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 15-Jun-2026 22:49:46 | wisuda.c@jutal.com | 16-Jun-2026 10:51:04 | Jumpol Sudjitjul | 23-Jun-2026 |  | Sompop Singhatiraj | 25-Jun-2026 | 18-Jun-2026 07:22:36 | Pornlert Wanaphattharaphan | 26-Jun-2026 | 18-Jun-2026 10:14:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 29-Jun-2026 | 18-Jun-2026 10:18:32 | 18-Jun-2026 03:57:38 | 0 |  |  | Approver | Locate
AO-001665 | MM-ZTK-1F-ZWPX-STR-DWG-1903 | TOPSIDE - LIFTING PADEYE DETAILS SHEET 2 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 24-Aug-2026 11:03:18 | wisuda.c@jutal.com | 24-Aug-2026 20:35:29 | Jumpol Sudjitjul | 01-Sep-2026 |  | Sompop Singhatiraj | 03-Sep-2026 | 26-Aug-2026 13:27:18 | Pornlert Wanaphattharaphan | 04-Sep-2026 | 30-Aug-2026 18:24:41 | AWC | Approved with Comment | Jumpol Sudjitjul | 07-Sep-2026 | 30-Aug-2026 21:27:23 | 31-Aug-2026 04:46:18 | 0 |  |  | Approver | Locate
AO-000720 | MM-ZTK-1F-ZWPX-STR-DWG-2221 | JACKET - JACKET ACCESS LAYOUT AND DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 17:22:14 | wisuda.c@jutal.com | 10-Jun-2026 08:22:45 | Jumpol Sudjitjul | 17-Jun-2026 |  | Sompop Singhatiraj | 19-Jun-2026 | 12-Jun-2026 15:05:38 | Pornlert Wanaphattharaphan | 22-Jun-2026 | 14-Jun-2026 01:04:56 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 23-Jun-2026 | 14-Jun-2026 21:41:37 | 14-Jun-2026 14:57:09 | 0 |  |  | Approver | Locate
AO-001607 | MM-ZTK-1F-ZWPX-STR-DWG-2221 | JACKET - JACKET ACCESS LAYOUT AND DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 09:59:02 | wisuda.c@jutal.com | 19-Aug-2026 10:47:57 | Jumpol Sudjitjul | 26-Aug-2026 |  | Sompop Singhatiraj | 28-Aug-2026 | 20-Aug-2026 14:19:16 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 23-Aug-2026 23:37:59 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 24-Aug-2026 14:48:25 | 24-Aug-2026 08:44:22 | 0 |  |  | Approver | Locate
AO-000721 | MM-ZTK-1F-ZWPX-STR-DWG-2222 | JACKET - JACKET ACCESS LAYOUT AND DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 15:27:52 | wisuda.c@jutal.com | 09-Jun-2026 15:39:48 | Jumpol Sudjitjul | 16-Jun-2026 |  | Sompop Singhatiraj | 18-Jun-2026 | 12-Jun-2026 14:49:58 | Pornlert Wanaphattharaphan | 19-Jun-2026 | 14-Jun-2026 01:10:35 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 22-Jun-2026 | 14-Jun-2026 21:41:13 | 14-Jun-2026 15:07:30 | 0 |  |  | Approver | Locate
AO-001607 | MM-ZTK-1F-ZWPX-STR-DWG-2222 | JACKET - JACKET ACCESS LAYOUT AND DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 09:59:33 | wisuda.c@jutal.com | 19-Aug-2026 10:47:56 | Jumpol Sudjitjul | 26-Aug-2026 |  | Sompop Singhatiraj | 28-Aug-2026 | 20-Aug-2026 14:11:36 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 23-Aug-2026 23:36:26 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 24-Aug-2026 14:47:31 | 24-Aug-2026 08:43:15 | 0 |  |  | Approver | Locate
AO-000722 | MM-ZTK-1F-ZWPX-STR-DWG-2223 | JACKET - JACKET ACCESS LAYOUT AND DETAILS - SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 15:28:25 | wisuda.c@jutal.com | 09-Jun-2026 15:40:12 | Jumpol Sudjitjul | 16-Jun-2026 |  | Sompop Singhatiraj | 18-Jun-2026 | 12-Jun-2026 14:55:27 | Pornlert Wanaphattharaphan | 19-Jun-2026 | 14-Jun-2026 01:09:30 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 22-Jun-2026 | 14-Jun-2026 21:40:50 | 14-Jun-2026 15:06:13 | 0 |  |  | Approver | Locate
AO-001607 | MM-ZTK-1F-ZWPX-STR-DWG-2223 | JACKET - JACKET ACCESS LAYOUT AND DETAILS - SHEET 3 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 10:00:14 | wisuda.c@jutal.com | 19-Aug-2026 10:48:00 | Jumpol Sudjitjul | 26-Aug-2026 |  | Sompop Singhatiraj | 28-Aug-2026 | 20-Aug-2026 14:17:02 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 23-Aug-2026 23:37:14 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 24-Aug-2026 14:46:43 | 24-Aug-2026 08:42:07 | 0 |  |  | Approver | Locate
AO-000723 | MM-ZTK-1F-ZWPX-STR-DWG-2224 | JACKET - JACKET WALKWAY STAIR NO 8 LANDING PLANS, SECTION & DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 15:29:00 | wisuda.c@jutal.com | 09-Jun-2026 15:40:29 | Jumpol Sudjitjul | 16-Jun-2026 |  | Sompop Singhatiraj | 18-Jun-2026 | 12-Jun-2026 14:56:53 | Pornlert Wanaphattharaphan | 19-Jun-2026 | 14-Jun-2026 01:07:52 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 22-Jun-2026 | 14-Jun-2026 21:40:26 | 14-Jun-2026 15:04:59 | 0 |  |  | Approver | Locate
AO-001607 | MM-ZTK-1F-ZWPX-STR-DWG-2224 | JACKET - JACKET WALKWAY STAIR NO 8 LANDING PLANS, SECTION & DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 10:00:47 | wisuda.c@jutal.com | 19-Aug-2026 10:48:03 | Jumpol Sudjitjul | 26-Aug-2026 |  | Sompop Singhatiraj | 28-Aug-2026 | 20-Aug-2026 14:24:04 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 23-Aug-2026 23:39:27 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 24-Aug-2026 14:45:50 | 24-Aug-2026 08:40:58 | 0 |  |  | Approver | Locate
AO-000724 | MM-ZTK-1F-ZWPX-STR-DWG-2225 | JACKET - STAIR NO 9 PLANS, SECTIONS & DETAILS |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 09-Jun-2026 15:29:25 | wisuda.c@jutal.com | 09-Jun-2026 15:40:47 | Jumpol Sudjitjul | 16-Jun-2026 |  | Sompop Singhatiraj | 18-Jun-2026 | 12-Jun-2026 14:58:18 | Pornlert Wanaphattharaphan | 19-Jun-2026 | 14-Jun-2026 01:06:27 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 22-Jun-2026 | 14-Jun-2026 21:40:02 | 14-Jun-2026 15:03:43 | 0 |  |  | Approver | Locate
AO-001607 | MM-ZTK-1F-ZWPX-STR-DWG-2225 | JACKET - STAIR NO 9 PLANS, SECTIONS & DETAILS |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 10:01:32 | wisuda.c@jutal.com | 19-Aug-2026 10:47:57 | Jumpol Sudjitjul | 26-Aug-2026 |  | Sompop Singhatiraj | 28-Aug-2026 | 20-Aug-2026 14:23:58 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 23-Aug-2026 23:38:50 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 24-Aug-2026 14:44:21 | 24-Aug-2026 08:53:21 | 0 |  |  | Approver | Locate
AO-000541 | MM-ZTK-1F-ZWPX-STR-DWG-2231 | JACKET - BOATLANDING ARRANGEMENT |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 13:32:33 | wisuda.c@jutal.com | 21-May-2026 14:16:26 | Jumpol Sudjitjul | 28-May-2026 |  | Sompop Singhatiraj | 02-Jun-2026 | 21-May-2026 18:25:14 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 22-May-2026 01:08:38 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 05-Jun-2026 | 22-May-2026 12:18:48 | 22-May-2026 15:45:23 | 0 |  |  | Approver | Locate
AO-001607 | MM-ZTK-1F-ZWPX-STR-DWG-2231 | JACKET - BOATLANDING ARRANGEMENT |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 10:02:15 | wisuda.c@jutal.com | 19-Aug-2026 10:47:58 | Jumpol Sudjitjul | 26-Aug-2026 |  | Sompop Singhatiraj | 28-Aug-2026 | 20-Aug-2026 16:03:17 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 23-Aug-2026 23:39:51 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 24-Aug-2026 14:40:43 | 24-Aug-2026 08:52:13 | 0 |  |  | Approver | Locate
AO-000541 | MM-ZTK-1F-ZWPX-STR-DWG-2232 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 1 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 13:33:00 | wisuda.c@jutal.com | 21-May-2026 14:16:26 | Jumpol Sudjitjul | 28-May-2026 |  | Sompop Singhatiraj | 02-Jun-2026 | 21-May-2026 18:25:24 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 22-May-2026 01:09:23 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 05-Jun-2026 | 22-May-2026 12:22:19 | 22-May-2026 15:46:36 | 0 |  |  | Approver | Locate
AO-001607 | MM-ZTK-1F-ZWPX-STR-DWG-2232 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 1 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 10:02:52 | wisuda.c@jutal.com | 19-Aug-2026 10:48:02 | Jumpol Sudjitjul | 26-Aug-2026 |  | Sompop Singhatiraj | 28-Aug-2026 | 20-Aug-2026 16:10:30 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 23-Aug-2026 23:40:19 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 24-Aug-2026 14:39:29 | 24-Aug-2026 08:51:06 | 0 |  |  | Approver | Locate
AO-000541 | MM-ZTK-1F-ZWPX-STR-DWG-2233 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 2 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 13:33:25 | wisuda.c@jutal.com | 21-May-2026 14:16:26 | Jumpol Sudjitjul | 28-May-2026 |  | Sompop Singhatiraj | 02-Jun-2026 | 21-May-2026 18:25:36 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 22-May-2026 01:09:55 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 05-Jun-2026 | 22-May-2026 12:23:33 | 22-May-2026 15:47:49 | 0 |  |  | Approver | Locate
AO-001607 | MM-ZTK-1F-ZWPX-STR-DWG-2233 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 2 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 10:03:24 | wisuda.c@jutal.com | 19-Aug-2026 10:48:08 | Jumpol Sudjitjul | 26-Aug-2026 |  | Sompop Singhatiraj | 28-Aug-2026 | 20-Aug-2026 16:22:08 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 23-Aug-2026 23:42:37 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 24-Aug-2026 14:28:40 | 24-Aug-2026 08:26:56 | 0 |  |  | Approver | Locate
AO-000541 | MM-ZTK-1F-ZWPX-STR-DWG-2234 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 3 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 13:33:49 | wisuda.c@jutal.com | 21-May-2026 14:16:32 | Jumpol Sudjitjul | 28-May-2026 |  | Sompop Singhatiraj | 02-Jun-2026 | 21-May-2026 18:26:50 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 22-May-2026 01:11:27 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 05-Jun-2026 | 22-May-2026 12:18:26 | 22-May-2026 15:44:11 | 0 |  |  | Approver | Locate
AO-001607 | MM-ZTK-1F-ZWPX-STR-DWG-2234 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 3 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 10:03:54 | wisuda.c@jutal.com | 19-Aug-2026 10:48:02 | Jumpol Sudjitjul | 26-Aug-2026 |  | Sompop Singhatiraj | 28-Aug-2026 | 20-Aug-2026 16:20:02 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 23-Aug-2026 23:42:12 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 24-Aug-2026 14:27:14 | 24-Aug-2026 08:25:48 | 0 |  |  | Approver | Locate
AO-000541 | MM-ZTK-1F-ZWPX-STR-DWG-2235 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 4 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 13:34:15 | wisuda.c@jutal.com | 21-May-2026 14:16:27 | Jumpol Sudjitjul | 28-May-2026 |  | Sompop Singhatiraj | 02-Jun-2026 | 21-May-2026 18:26:58 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 22-May-2026 01:12:18 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 05-Jun-2026 | 22-May-2026 12:16:47 | 22-May-2026 15:42:57 | 0 |  |  | Approver | Locate
AO-001607 | MM-ZTK-1F-ZWPX-STR-DWG-2235 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 4 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 10:04:27 | wisuda.c@jutal.com | 19-Aug-2026 10:48:03 | Jumpol Sudjitjul | 26-Aug-2026 |  | Sompop Singhatiraj | 28-Aug-2026 | 20-Aug-2026 16:18:52 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 23-Aug-2026 23:41:50 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 24-Aug-2026 14:25:38 | 24-Aug-2026 08:24:35 | 0 |  |  | Approver | Locate
AO-000541 | MM-ZTK-1F-ZWPX-STR-DWG-2236 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 5 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 13:34:40 | wisuda.c@jutal.com | 21-May-2026 14:16:27 | Jumpol Sudjitjul | 28-May-2026 |  | Sompop Singhatiraj | 02-Jun-2026 | 21-May-2026 18:27:06 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 22-May-2026 01:12:43 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 05-Jun-2026 | 22-May-2026 12:15:26 | 22-May-2026 15:41:44 | 0 |  |  | Approver | Locate
AO-001607 | MM-ZTK-1F-ZWPX-STR-DWG-2236 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 5 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 10:05:11 | wisuda.c@jutal.com | 19-Aug-2026 10:48:11 | Jumpol Sudjitjul | 26-Aug-2026 |  | Sompop Singhatiraj | 28-Aug-2026 | 20-Aug-2026 16:16:51 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 23-Aug-2026 23:41:27 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 24-Aug-2026 14:24:43 | 24-Aug-2026 08:23:25 | 0 |  |  | Approver | Locate
AO-000541 | MM-ZTK-1F-ZWPX-STR-DWG-2237 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 6 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 13:35:06 | wisuda.c@jutal.com | 21-May-2026 14:16:31 | Jumpol Sudjitjul | 28-May-2026 |  | Sompop Singhatiraj | 02-Jun-2026 | 21-May-2026 18:28:05 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 22-May-2026 01:13:46 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 05-Jun-2026 | 22-May-2026 11:01:44 | 22-May-2026 06:14:37 | 0 |  |  | Approver | Locate
AO-001607 | MM-ZTK-1F-ZWPX-STR-DWG-2237 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 6 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 10:06:03 | wisuda.c@jutal.com | 19-Aug-2026 10:48:03 | Jumpol Sudjitjul | 26-Aug-2026 |  | Sompop Singhatiraj | 28-Aug-2026 | 20-Aug-2026 16:14:27 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 23-Aug-2026 23:41:08 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 24-Aug-2026 14:22:20 | 24-Aug-2026 08:22:14 | 0 |  |  | Approver | Locate
AO-000541 | MM-ZTK-1F-ZWPX-STR-DWG-2238 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 7 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 21-May-2026 13:35:32 | wisuda.c@jutal.com | 21-May-2026 14:16:31 | Jumpol Sudjitjul | 28-May-2026 |  | Sompop Singhatiraj | 02-Jun-2026 | 21-May-2026 18:28:17 | Pornlert Wanaphattharaphan | 04-Jun-2026 | 22-May-2026 01:17:09 | AWC-C | Approved with Comment (Proceed to Rev.C) | Jumpol Sudjitjul | 05-Jun-2026 | 22-May-2026 11:00:00 | 22-May-2026 06:13:22 | 0 |  |  | Approver | Locate
AO-001607 | MM-ZTK-1F-ZWPX-STR-DWG-2238 | JACKET - BOATLANDING SECTIONS & DETAILS - SHEET 7 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | STR | Structural | DWG | General Drawing | 0 | Submitted | AFC | Approved for Construction |  | 19-Aug-2026 10:06:43 | wisuda.c@jutal.com | 19-Aug-2026 10:48:02 | Jumpol Sudjitjul | 26-Aug-2026 |  | Sompop Singhatiraj | 28-Aug-2026 | 20-Aug-2026 16:13:19 | Pornlert Wanaphattharaphan | 31-Aug-2026 | 23-Aug-2026 23:40:39 | APPR | Approved | Jumpol Sudjitjul | 01-Sep-2026 | 24-Aug-2026 14:20:38 | 24-Aug-2026 08:21:00 | 0 |  |  | Approver | Locate
AO-000852 | MM-ZTK-1F-ZWPX-TEL-BLD-0001 | TELECOMMUNICATION BLOCK DIAGRAM FOR ZWP20/21/22/23 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | TEL | Telecommunication | BLD | Block Diagram | 0 | Revised | AFC | Issued for Review |  | 21-Jun-2026 22:42:11 | wisuda.c@jutal.com | 24-Apr-2026 15:42:36 | Jumpol Sudjitjul |  |  | Wichai Salee |  | 21-May-2026 23:40:22 | Pornlert Wanaphattharaphan |  | 22-May-2026 09:44:42 |  |  | Jumpol Sudjitjul |  | 22-May-2026 12:20:33 |  | 0 |  |  | Approver | Locate
AO-000861 | MM-ZTK-1F-ZWPX-TEL-BLD-0001 | TELECOMMUNICATION BLOCK DIAGRAM FOR ZWP20/21/22/23 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | TEL | Telecommunication | BLD | Block Diagram | 0 | Submitted | AFC | Issued for Approval |  |  | wisuda.c@jutal.com | 22-Jun-2026 14:06:35 | Jumpol Sudjitjul | 29-Jun-2026 |  | Wichai Salee | 01-Jul-2026 | 13-Jul-2026 12:29:16 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 13-Jul-2026 22:49:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Jul-2026 | 14-Jul-2026 08:47:28 | 14-Jul-2026 02:31:28 | 0 |  |  | Approver | Locate
AO-001732 | MM-ZTK-1F-ZWPX-TEL-BLD-0001 | TELECOMMUNICATION BLOCK DIAGRAM FOR ZWP20/21/22/23 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | TEL | Telecommunication | BLD | Block Diagram | 0 | Submitted | AFC | Approved for Construction |  | 26-Aug-2026 19:21:47 | wisuda.c@jutal.com | 27-Aug-2026 11:28:01 | Jumpol Sudjitjul | 03-Sep-2026 |  | Wichai Salee | 07-Sep-2026 | 08-Sep-2026 12:44:45 | Pornlert Wanaphattharaphan | 08-Sep-2026 | 08-Sep-2026 23:22:52 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Sep-2026 | 09-Sep-2026 10:29:06 | 09-Sep-2026 04:01:41 | 0 |  |  | Approver | Locate
AO-002181 | MM-ZTK-1F-ZWPX-TEL-BLD-0001 | TELECOMMUNICATION BLOCK DIAGRAM FOR ZWP20/21/22/23 |  | C2 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | TEL | Telecommunication | BLD | Block Diagram | 0 | Submitted | AFC | Approved for Construction |  | 21-Sep-2026 11:13:06 | wisuda.c@jutal.com | 21-Sep-2026 14:14:01 | Jumpol Sudjitjul | 28-Sep-2026 |  | Wichai Salee | 30-Sep-2026 | 28-Sep-2026 20:15:45 | Pornlert Wanaphattharaphan | 01-Oct-2026 | 28-Sep-2026 22:51:00 | APPR | Approved | Jumpol Sudjitjul | 02-Oct-2026 | 29-Sep-2026 09:17:23 | 29-Sep-2026 02:26:08 | 0 |  |  | Approver | Locate
AO-000584 | MM-ZTK-1F-ZWPX-TEL-LAY-0001 | TELECOMMUNICATION EQUIPMENT LAYOUT COVER SHEET FOR ZWP20/21/22/23 |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | TEL | Telecommunication | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 24-May-2026 15:30:32 | wisuda.c@jutal.com | 24-May-2026 20:50:56 | Jumpol Sudjitjul | 02-Jun-2026 |  | Wichai Salee | 05-Jun-2026 | 19-Jun-2026 23:07:04 | Pornlert Wanaphattharaphan | 08-Jun-2026 | 22-Jun-2026 11:43:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Jun-2026 | 22-Jun-2026 12:57:36 | 22-Jun-2026 06:48:32 | 0 |  |  | Approver | Locate
AO-001020 | MM-ZTK-1F-ZWPX-TEL-LAY-0001 | TELECOMMUNICATION EQUIPMENT LAYOUT COVER SHEET FOR ZWP20/21/22/23 |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | TEL | Telecommunication | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 03-Jul-2026 23:38:29 | wisuda.c@jutal.com | 04-Jul-2026 14:31:50 | Jumpol Sudjitjul | 10-Jul-2026 |  | Wichai Salee | 14-Jul-2026 | 22-Jul-2026 11:31:09 | Pornlert Wanaphattharaphan | 15-Jul-2026 | 22-Jul-2026 22:50:21 | AWC | Approved with Comment | Jumpol Sudjitjul | 16-Jul-2026 | 23-Jul-2026 08:09:13 | 23-Jul-2026 01:22:04 | 0 |  |  | Approver | Locate
AO-001917 | MM-ZTK-1F-ZWPX-TEL-LAY-0001 | TELECOMMUNICATION EQUIPMENT LAYOUT COVER SHEET FOR ZWP20/21/22/23 |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | TEL | Telecommunication | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 07-Sep-2026 17:59:46 | wisuda.c@jutal.com | 08-Sep-2026 09:43:24 | Jumpol Sudjitjul | 15-Sep-2026 |  | Wichai Salee | 17-Sep-2026 | 14-Sep-2026 11:30:47 | Pornlert Wanaphattharaphan | 18-Sep-2026 | 19-Sep-2026 00:20:43 | AWC | Approved with Comment | Jumpol Sudjitjul | 21-Sep-2026 | 20-Sep-2026 18:46:27 | 20-Sep-2026 12:50:32 | 0 |  |  | Approver | Locate
AO-000693 | MM-ZTK-1F-ZWPX-TEL-LAY-0002 | TELECOMMUNICATION CABLE ROUTING PLAN |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | TEL | Telecommunication | LAY | Layout Drawing | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 21:01:06 | wisuda.c@jutal.com | 07-Jun-2026 18:14:06 | Jumpol Sudjitjul | 15-Jun-2026 |  | Wichai Salee | 17-Jun-2026 | 24-Jun-2026 10:06:50 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 24-Jun-2026 20:11:07 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 25-Jun-2026 13:58:42 | 25-Jun-2026 07:23:44 | 0 |  |  | Approver | Locate
AO-001300 | MM-ZTK-1F-ZWPX-TEL-LAY-0002 | TELECOMMUNICATION CABLE ROUTING PLAN |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | TEL | Telecommunication | LAY | Layout Drawing | 0 | Submitted | IFA | Issued for Approval |  | 27-Jul-2026 08:48:36 | wisuda.c@jutal.com | 27-Jul-2026 16:05:57 | Jumpol Sudjitjul | 05-Aug-2026 |  | Wichai Salee | 07-Aug-2026 | 08-Aug-2026 18:49:14 | Pornlert Wanaphattharaphan | 10-Aug-2026 | 12-Aug-2026 00:51:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 11-Aug-2026 | 13-Aug-2026 13:04:44 | 13-Aug-2026 07:10:55 | 0 |  |  | Approver | Locate
AO-002292 | MM-ZTK-1F-ZWPX-TEL-LAY-0002 | TELECOMMUNICATION CABLE ROUTING PLAN |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | TEL | Telecommunication | LAY | Layout Drawing | 0 | Submitted | AFC | Approved for Construction |  | 28-Sep-2026 08:39:24 | wisuda.c@jutal.com | 28-Sep-2026 13:25:46 | Jumpol Sudjitjul | 05-Oct-2026 |  | Wichai Salee | 07-Oct-2026 | 01-Oct-2026 15:50:12 | Pornlert Wanaphattharaphan | 08-Oct-2026 | 01-Oct-2026 23:14:40 | AWC | Approved with Comment | Jumpol Sudjitjul | 09-Oct-2026 | 02-Oct-2026 13:21:18 | 02-Oct-2026 07:17:15 | 0 |  |  | Approver | Locate
AO-000821 | MM-ZTK-1F-ZWPX-TEL-LIS-0002 | TELECOMMUNICATION DRAWING INDEX |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | TEL | Telecommunication | LIS | List, Index, Schedule, Listing | 0 | Submitted | IFR | Issued for Review |  | 17-Jun-2026 21:58:38 | wisuda.c@jutal.com | 18-Jun-2026 09:56:23 | Jumpol Sudjitjul | 25-Jun-2026 |  | Wichai Salee | 29-Jun-2026 | 02-Jul-2026 17:23:45 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 02-Jul-2026 22:06:56 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 03-Jul-2026 10:36:49 | 03-Jul-2026 04:22:08 | 0 |  |  | Approver | Locate
AO-000690 | MM-ZTK-1F-ZWPX-TEL-SCH-0001 | TELECOMMUNICATION SCHEMATIC DIAGRAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | TEL | Telecommunication | SCH | Schematic | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 21:01:46 | wisuda.c@jutal.com | 07-Jun-2026 18:15:10 | Jumpol Sudjitjul | 15-Jun-2026 |  | Wichai Salee | 17-Jun-2026 | 24-Jun-2026 10:08:51 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 24-Jun-2026 20:36:28 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 25-Jun-2026 13:57:37 | 25-Jun-2026 07:21:53 | 0 |  |  | Approver | Locate
AO-001077 | MM-ZTK-1F-ZWPX-TEL-SCH-0001 | TELECOMMUNICATION SCHEMATIC DIAGRAM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | TEL | Telecommunication | SCH | Schematic | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:39:59 | wisuda.c@jutal.com | 12-Jul-2026 12:05:42 | Jumpol Sudjitjul | 17-Jul-2026 |  | Wichai Salee | 21-Jul-2026 | 23-Jul-2026 20:10:09 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 26-Jul-2026 01:46:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 27-Jul-2026 15:31:19 | 27-Jul-2026 10:26:13 | 0 |  |  | Approver | Locate
AO-002333 | MM-ZTK-1F-ZWPX-TEL-SCH-0001 | TELECOMMUNICATION SCHEMATIC DIAGRAM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | TEL | Telecommunication | SCH | Schematic | 0 | In Review | AFC | Approved for Construction |  | 02-Oct-2026 08:40:25 | wisuda.c@jutal.com | 02-Oct-2026 17:50:58 | Jumpol Sudjitjul | 12-Oct-2026 |  | Wichai Salee | 15-Oct-2026 |  | Pornlert Wanaphattharaphan | 16-Oct-2026 |  |  |  |  | 19-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000819 | MM-ZTK-1F-ZWPX-TEL-STD-0001 | TELECOMMUNICATION INSTALLATION AND MOUNTING DETAIL |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | TEL | Telecommunication | STD | Standard | 0 | Submitted | IFR | Issued for Review |  | 17-Jun-2026 21:59:03 | wisuda.c@jutal.com | 18-Jun-2026 09:58:20 | Jumpol Sudjitjul | 25-Jun-2026 |  | Wichai Salee | 29-Jun-2026 | 02-Jul-2026 17:17:44 | Pornlert Wanaphattharaphan | 30-Jun-2026 | 02-Jul-2026 22:09:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 01-Jul-2026 | 03-Jul-2026 10:19:40 | 03-Jul-2026 04:20:23 | 0 |  |  | Approver | Locate
AO-001384 | MM-ZTK-1F-ZWPX-TEL-STD-0001 | TELECOMMUNICATION INSTALLATION AND MOUNTING DETAIL |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | TEL | Telecommunication | STD | Standard | 0 | Submitted | IFA | Issued for Approval |  | 03-Aug-2026 11:31:21 | wisuda.c@jutal.com | 03-Aug-2026 14:15:40 | Jumpol Sudjitjul | 10-Aug-2026 |  | Wichai Salee | 13-Aug-2026 | 10-Aug-2026 10:11:11 | Pornlert Wanaphattharaphan | 14-Aug-2026 | 13-Aug-2026 00:03:01 | NA | Not Approved | Jumpol Sudjitjul | 17-Aug-2026 | 13-Aug-2026 13:04:11 | 13-Aug-2026 06:20:52 | 0 |  |  | Approver | Locate
AO-002041 | MM-ZTK-1F-ZWPX-TEL-STD-0001 | TELECOMMUNICATION INSTALLATION AND MOUNTING DETAIL |  | B2 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | TEL | Telecommunication | STD | Standard | 0 | Submitted | IFA | Issued for Approval |  | 14-Sep-2026 09:53:51 | wisuda.c@jutal.com | 15-Sep-2026 15:06:57 | Jumpol Sudjitjul | 22-Sep-2026 |  | Wichai Salee | 24-Sep-2026 | 17-Sep-2026 16:08:12 | Pornlert Wanaphattharaphan | 25-Sep-2026 | 19-Sep-2026 20:26:50 | AWC | Approved with Comment | Jumpol Sudjitjul | 28-Sep-2026 | 20-Sep-2026 18:45:54 | 20-Sep-2026 12:32:42 | 0 |  |  | Approver | Locate
AO-002481 | MM-ZTK-1F-ZWPX-TEL-STD-0001 | TELECOMMUNICATION INSTALLATION AND MOUNTING DETAIL |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | TEL | Telecommunication | STD | Standard | 0 | In Review | AFC | Approved for Construction |  | 12-Oct-2026 12:09:13 | wisuda.c@jutal.com | 12-Oct-2026 13:42:40 | Jumpol Sudjitjul | 20-Oct-2026 |  | Wichai Salee | 22-Oct-2026 |  | Pornlert Wanaphattharaphan | 26-Oct-2026 |  |  |  |  | 27-Oct-2026 |  |  | 0 |  |  | Approver | Locate
AO-000694 | MM-ZTK-1F-ZWPX-TEL-WIR-0001 | TELECOMMUNICATION SYSTEM WIRING DIAGRAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | TEL | Telecommunication | WIR | Wiring Diagram | 0 | Submitted | IFR | Issued for Review |  | 05-Jun-2026 21:02:36 | wisuda.c@jutal.com | 07-Jun-2026 18:16:47 | Jumpol Sudjitjul | 15-Jun-2026 |  | Wichai Salee | 17-Jun-2026 | 24-Jun-2026 10:13:00 | Pornlert Wanaphattharaphan | 18-Jun-2026 | 24-Jun-2026 20:41:46 | AWC | Approved with Comment | Jumpol Sudjitjul | 19-Jun-2026 | 25-Jun-2026 13:56:48 | 25-Jun-2026 07:19:30 | 0 |  |  | Approver | Locate
AO-001078 | MM-ZTK-1F-ZWPX-TEL-WIR-0001 | TELECOMMUNICATION SYSTEM WIRING DIAGRAM |  | B1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWPX |  |  | TEL | Telecommunication | WIR | Wiring Diagram | 0 | Submitted | IFA | Issued for Approval |  | 12-Jul-2026 11:40:25 | wisuda.c@jutal.com | 12-Jul-2026 12:06:09 | Jumpol Sudjitjul | 17-Jul-2026 |  | Wichai Salee | 21-Jul-2026 | 24-Jul-2026 11:45:34 | Pornlert Wanaphattharaphan | 22-Jul-2026 | 26-Jul-2026 02:32:11 | AWC | Approved with Comment | Jumpol Sudjitjul | 23-Jul-2026 | 27-Jul-2026 15:30:51 | 27-Jul-2026 10:23:43 | 0 |  |  | Approver | Locate
| MM-ZTK-1F-ZWPX-TNI-BLD-8001 | DESIGN BASIS FOR PLATFORMS TRANSPORTATION AND INSTALLATION ENGINEERING |  | A1 | Project Document | Engineering Document | Part F - Transportation & Installation | ZWPX |  |  | TNI | Transportation and Installation | BLD | Block Diagram | 0 | Submitted | IFR | Issued for Review |  | 16-Jul-2026 14:05:01 | [16 empty] | 14-Jul-2026 07:04:52 | 0 |  |  | Approver | Locate
AO-001134 | MM-ZTK-1F-ZWPX-TNI-BOD-8001 | DESIGN BASIS FOR PLATFORMS TRANSPORTATION AND INSTALLATION ENGINEERING |  | A1 | Project Document | Engineering Document | Part F - Transportation & Installation | ZWPX |  |  | TNI | Transportation and Installation | BOD | Basis of Design | 0 | Submitted | IFR | Issued for Review |  | 16-Jul-2026 18:01:25 | kjb@coes.cn | 16-Jul-2026 20:54:09 | Jumpol Sudjitjul | 24-Jul-2026 | 23-Jul-2026 11:09:05 | Sukit Nualchanchai | 30-Jul-2026 | 27-Jul-2026 09:46:09 | Pornlert Wanaphattharaphan | 31-Jul-2026 | 29-Jul-2026 00:38:39 | AWC | Approved with Comment | Jumpol Sudjitjul | 03-Aug-2026 | 30-Jul-2026 09:40:09 | 30-Jul-2026 03:48:20 | 0 |  |  | Approver | Locate
AO-001573 | MM-ZTK-1F-ZWPX-TNI-BOD-8001 | DESIGN BASIS FOR PLATFORMS TRANSPORTATION AND INSTALLATION ENGINEERING |  | B1 | Project Document | Engineering Document | Part F - Transportation & Installation | ZWPX |  |  | TNI | Transportation and Installation | BOD | Basis of Design | 0 | Submitted | IFA | Issued for Approval |  | 17-Aug-2026 17:17:34 | kjb@coes.cn | 18-Aug-2026 08:44:21 | Jumpol Sudjitjul | 25-Aug-2026 | 27-Aug-2026 12:08:05 | Sukit Nualchanchai | 27-Aug-2026 | 07-Sep-2026 11:42:56 | Prin Jitatisil | 28-Aug-2026 | 09-Sep-2026 21:51:23 | AWC | Approved with Comment | Jumpol Sudjitjul | 31-Aug-2026 | 10-Sep-2026 09:09:09 | 10-Sep-2026 02:39:59 | 0 |  |  | Approver | Locate
AO-002220 | MM-ZTK-1F-ZWPX-TNI-BOD-8001 | DESIGN BASIS FOR PLATFORMS TRANSPORTATION AND INSTALLATION ENGINEERING |  | C1 | Project Document | Engineering Document | Part F - Transportation & Installation | ZWPX |  |  | TNI | Transportation and Installation | BOD | Basis of Design | 0 | Submitted | AFC | Approved for Construction |  | 23-Sep-2026 09:30:46 | kjb@coes.cn | 23-Sep-2026 14:03:54 | Jumpol Sudjitjul | 30-Sep-2026 |  | Sukit Nualchanchai | 02-Oct-2026 | 13-Oct-2026 12:21:37 | Prin Jitatisil | 05-Oct-2026 | 14-Oct-2026 09:55:22 | APPR | Approved | Jumpol Sudjitjul | 06-Oct-2026 | 14-Oct-2026 16:41:10 | 14-Oct-2026 10:02:26 | 0 |  |  | Approver | Locate
AO-002222 | MM-ZTK-1F-ZWPX-TNI-CAL-8004 | GENERIC BOATLANDING LIFTING ANALYSIS (RIGGING DESIGN) |  | A1 | Project Document | Engineering Document | Part F - Transportation & Installation | ZWPX |  |  | TNI | Transportation and Installation | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 23-Sep-2026 10:38:24 | kjb@coes.cn | 23-Sep-2026 14:01:43 | Jumpol Sudjitjul | 30-Sep-2026 | 23-Sep-2026 15:13:31 | Sukit Nualchanchai | 02-Oct-2026 | 06-Oct-2026 13:28:47 | Prin Jitatisil | 05-Oct-2026 | 06-Oct-2026 15:23:05 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Oct-2026 | 06-Oct-2026 15:46:28 | 06-Oct-2026 09:01:06 | 0 |  |  | Approver | Locate
AO-002149 | MM-ZTK-1F-ZWPX-TNI-CAL-8005 | DERRICK CRANE BARGE DP CAPACITY ANALYSIS (HXKP 01) |  | A1 | Project Document | Engineering Document | Part F - Transportation & Installation | ZWPX |  |  | TNI | Transportation and Installation | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFR | Issued for Review |  | 18-Sep-2026 15:12:55 | kjb@coes.cn | 18-Sep-2026 17:52:05 | Jumpol Sudjitjul | 28-Sep-2026 | 18-Sep-2026 21:46:13 | Sukit Nualchanchai | 30-Sep-2026 | 06-Oct-2026 14:15:20 | Prin Jitatisil | 01-Oct-2026 | 06-Oct-2026 15:23:26 | AWC | Approved with Comment | Jumpol Sudjitjul | 02-Oct-2026 | 06-Oct-2026 15:47:48 | 06-Oct-2026 08:58:35 | 0 |  |  | Approver | Locate
AO-002514 | MM-ZTK-1F-ZWPX-TNI-CAL-8005 | DERRICK CRANE BARGE DP CAPACITY ANALYSIS (HXKP 01) |  | B1 | Project Document | Engineering Document | Part F - Transportation & Installation | ZWPX |  |  | TNI | Transportation and Installation | CAL | Calculation Note, Calculation Report | 0 | Submitted | IFA | Issued for Approval |  | 14-Oct-2026 12:30:01 | kjb@coes.cn | 14-Oct-2026 13:24:58 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sukit Nualchanchai | 26-Oct-2026 | 15-Oct-2026 16:45:34 | Prin Jitatisil | 27-Oct-2026 | 15-Oct-2026 16:56:22 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 15-Oct-2026 17:00:00 | 15-Oct-2026 10:50:38 | 0 |  |  | Approver | Locate
AO-002226 | MM-ZTK-1F-ZWPX-TNI-DWG-8004 | GENERIC BOATLANDING RIGGING DETAILS |  | A1 | Project Document | Engineering Document | Part F - Transportation & Installation | ZWPX |  |  | TNI | Transportation and Installation | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 23-Sep-2026 10:38:55 | kjb@coes.cn | 23-Sep-2026 13:59:46 | Jumpol Sudjitjul | 30-Sep-2026 | 23-Sep-2026 15:08:17 | Sukit Nualchanchai | 02-Oct-2026 | 06-Oct-2026 09:32:15 | Prin Jitatisil | 05-Oct-2026 | 06-Oct-2026 11:33:31 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Oct-2026 | 06-Oct-2026 14:08:23 | 06-Oct-2026 07:49:44 | 0 |  |  | Approver | Locate
AO-002516 | MM-ZTK-1F-ZWPX-TNI-DWG-8004 | GENERIC BOATLANDING RIGGING DETAILS |  | B1 | Project Document | Engineering Document | Part F - Transportation & Installation | ZWPX |  |  | TNI | Transportation and Installation | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 14-Oct-2026 13:51:12 | kjb@coes.cn | 14-Oct-2026 13:58:12 | Jumpol Sudjitjul | 21-Oct-2026 |  | Sukit Nualchanchai | 26-Oct-2026 | 15-Oct-2026 16:54:37 | Prin Jitatisil | 27-Oct-2026 | 15-Oct-2026 16:56:48 | APPR | Approved | Jumpol Sudjitjul | 28-Oct-2026 | 15-Oct-2026 17:01:19 | 15-Oct-2026 10:38:48 | 0 |  |  | Approver | Locate
AO-002224 | MM-ZTK-1F-ZWPX-TNI-DWG-8005 | GENERIC BOATLANDING RIGGING LAYDOWN |  | A1 | Project Document | Engineering Document | Part F - Transportation & Installation | ZWPX |  |  | TNI | Transportation and Installation | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 23-Sep-2026 10:39:20 | kjb@coes.cn | 23-Sep-2026 14:00:08 | Jumpol Sudjitjul | 30-Sep-2026 | 23-Sep-2026 15:07:12 | Sukit Nualchanchai | 02-Oct-2026 | 06-Oct-2026 09:44:38 | Prin Jitatisil | 05-Oct-2026 | 06-Oct-2026 11:33:51 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Oct-2026 | 06-Oct-2026 14:09:03 | 06-Oct-2026 07:50:59 | 0 |  |  | Approver | Locate
AO-002517 | MM-ZTK-1F-ZWPX-TNI-DWG-8005 | GENERIC BOATLANDING RIGGING LAYDOWN |  | B1 | Project Document | Engineering Document | Part F - Transportation & Installation | ZWPX |  |  | TNI | Transportation and Installation | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 14-Oct-2026 15:11:15 | kjb@coes.cn | 15-Oct-2026 08:43:13 | Jumpol Sudjitjul | 22-Oct-2026 |  | Sukit Nualchanchai | 27-Oct-2026 | 15-Oct-2026 16:57:11 | Prin Jitatisil | 28-Oct-2026 | 15-Oct-2026 17:08:21 | APPR | Approved | Jumpol Sudjitjul | 29-Oct-2026 | 16-Oct-2026 11:40:16 | 16-Oct-2026 04:54:29 | 0 |  |  | Approver | Locate
AO-002223 | MM-ZTK-1F-ZWPX-TNI-DWG-8006 | GENERIC TOPSIDE TUGGER LINES CONNECTION DETAILS |  | A1 | Project Document | Engineering Document | Part F - Transportation & Installation | ZWPX |  |  | TNI | Transportation and Installation | DWG | General Drawing | 0 | Submitted | IFR | Issued for Review |  | 23-Sep-2026 10:39:48 | kjb@coes.cn | 23-Sep-2026 14:02:34 | Jumpol Sudjitjul | 30-Sep-2026 | 23-Sep-2026 15:06:27 | Sukit Nualchanchai | 02-Oct-2026 | 06-Oct-2026 09:57:36 | Prin Jitatisil | 05-Oct-2026 | 06-Oct-2026 11:34:12 | AWC | Approved with Comment | Jumpol Sudjitjul | 06-Oct-2026 | 06-Oct-2026 14:09:50 | 06-Oct-2026 07:45:20 | 0 |  |  | Approver | Locate
AO-002519 | MM-ZTK-1F-ZWPX-TNI-DWG-8006 | GENERIC TOPSIDE TUGGER LINES CONNECTION DETAILS |  | B1 | Project Document | Engineering Document | Part F - Transportation & Installation | ZWPX |  |  | TNI | Transportation and Installation | DWG | General Drawing | 0 | Submitted | IFA | Issued for Approval |  | 14-Oct-2026 15:11:55 | kjb@coes.cn | 15-Oct-2026 08:44:07 | Jumpol Sudjitjul | 22-Oct-2026 |  | Sukit Nualchanchai | 27-Oct-2026 | 15-Oct-2026 16:58:31 | Prin Jitatisil | 28-Oct-2026 | 15-Oct-2026 17:08:05 | APPR | Approved | Jumpol Sudjitjul | 29-Oct-2026 | 16-Oct-2026 11:38:53 | 16-Oct-2026 04:53:20 | 0 |  |  | Approver | Locate
AO-000846 | MM-ZTK-MOD-19005-ZPQ-PRO-ESD-0001_A | ZPQM ESD LOGIC DIAGRAM |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZPQ |  |  | PRO | Process | ESD | Emergency Logic Diagram | 0 | Submitted | IFR | Issued for Review |  | 21-Jun-2026 22:45:55 | wisuda.c@jutal.com | 22-Jun-2026 14:20:50 | Jumpol Sudjitjul | 29-Jun-2026 |  | Chananun Rojanarungruengporn | 01-Jul-2026 | 05-Jul-2026 17:27:05 | Pornlert Wanaphattharaphan | 02-Jul-2026 | 07-Jul-2026 00:50:22 | APPR | Approved | Jumpol Sudjitjul | 03-Jul-2026 | 07-Jul-2026 08:23:07 | 07-Jul-2026 01:59:38 | 0 |  |  | Approver | Locate
AO-001480 | MM-ZTK-MOD-19005-ZPQ-PRO-ESD-0001_A | ZPQM ESD LOGIC DIAGRAM |  | C1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZPQ |  |  | PRO | Process | ESD | Emergency Logic Diagram | 0 | Submitted | AFC | Approved for Construction |  | 10-Aug-2026 12:02:53 | wisuda.c@jutal.com | 10-Aug-2026 15:15:26 | Jumpol Sudjitjul | 18-Aug-2026 | 18-Aug-2026 23:56:40 | Chananun Rojanarungruengporn | 20-Aug-2026 | 19-Aug-2026 09:27:37 | Pornlert Wanaphattharaphan | 21-Aug-2026 | 21-Aug-2026 19:39:02 | APPR | Approved | Jumpol Sudjitjul | 24-Aug-2026 | 24-Aug-2026 14:18:45 | 24-Aug-2026 08:06:02 | 0 |  |  | Approver | Locate
AO-001670 | ZTK-1C-WP8-INS-LIS-0002_A | WP8 INSTRUMENT I/O LIST |  | A1 | Project Document | Engineering Document | Part C - Engineering Dwg | ZWP08 |  |  | INS | Instrumentation and Control | LIS | List, Index, Schedule, Listing | 0 | Latest | IFR | Issued for Review |  | 24-Aug-2026 09:43:27 | wisuda.c@jutal.com | 25-Aug-2026 08:32:53 | Jumpol Sudjitjul | 01-Sep-2026 |  | Wichai Salee | 03-Sep-2026 |  | Pornlert Wanaphattharaphan | 04-Sep-2026 |  |  |  |  | 07-Sep-2026 |  |  | 0 |  |  | Approver | Locate